## Sheet1
1 | Identification and location of shallow services | Measure depth of cover to utility services | Trained contractor staff | Two measures per service (each side of the road) | Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap | Mandatory HOLD POINT Designer Signoff Required | Marked up sheet | Site Engineer | Designer Signoff | 1 - Identification and location of shallow services | VERIFICATION ACTIVITY: Measure depth of cover to utility services | METHODS OR REFERENCE: Trained contractor staff | FREQUENCY: Two measures per service (each side of the road) | ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Marked up sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | 1 - Identification and location of shallow services
2 | Milling / Cut to Waste Type O = 210mm Type C = 305mm Type W = 500mm | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm to design level | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Site Engineer | Designer Signoff | [9 empty] | VERIFICATION ACTIVITY: Measure depth of cover to utility services
3 | Existing subgrade / subbase | No unacceptable subgrade materials after excavation | Visual Inspection | Sitewide | Free of detritius and loose material | Inprocess Inspection | Photos | Site Engineer | Designer Signoff | [9 empty] | METHODS OR REFERENCE: Trained contractor staff
4 | Type O = Contingency weak / soft spot | Benkelman Beam Test | BB Test on exisitng Subbase | 10m interval alternative wheelpath | If BB Deflection >2.1mm and CHAR(LESS)3.5mm, Mill Further 70mm CHAR(AMP) replace with AC20 asphalt If BB Deflection > 3.5mm - Designer to review and advise | Mandatory HOLD POINT Designer Signoff Required | BB test results | Site Engineer | Designer Signoff | [9 empty] | FREQUENCY: Two measures per service (each side of the road)
5 | Type C CHAR(AMP) W = Contingency weak / soft spot | Scalar Testing | Scalar Testing on existing subgrade/subbase | 5m grid | Ensure exposed subgrade CBR ≥ 2. If CBR between 2 and 1 undercut 300mm and replace with woodhill sand wrapped in bidim A29 geotextile If CBR CHAR(LESS) 1 - designer to review and advise | Mandatory HOLD POINT Designer Signoff Required | BB test results | Site Engineer | Designer Signoff | [9 empty] | ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap
6 | All Areas Contingency Weak / Soft Spot | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm No trafficking of the excavated subgrade | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Site Engineer | Designer Signoff | [9 empty] | TYPE: Mandatory HOLD POINT Designer Signoff Required
7 | Existing subgrade / subbase | No unacceptable subgrade materials after excavation | Visual Inspection | NA | Free of detritius and loose material | Inprocess Inspection | Photos | Site Engineer | Designer Signoff | [9 empty] | RECORDS (Responsibility): Marked up sheet
8 | AT AP65 = Pavement Type W | No non-compliant results | Material test results | Once | Compliance with TNZ B/2 | Mandatory HOLD POINT Designer Signoff Required | Testing Results | Site Engineer | - | [9 empty] | ONSITE RESPONSIBILITY: Site Engineer
9 | AT AP65 = Pavement Type W | Compaction Testing | Clegg Testing | 5m grids | CIV > 35. to be compacted in 150mm layers | Mandatory HOLD POINT Designer Signoff Required | Testing Results | Site Engineer | Designer Signoff | [9 empty] | CONTRACT MANAGER SIGNOFF: Designer Signoff
10 | AT AP65 = Pavement Type W | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm No trafficking of the excavated subgrade | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Site Engineer | Designer Signoff
11 | AT AP65 = Pavement Type W | Surface finish | Visual Inspection | All area | Free of detritius and loose material | Mandatory HOLD POINT Designer Signoff Required | Photos | Site Engineer | -
12 | Concrete Subbase = Pavement Type W CHAR(AMP) C | Strength and slump | Concrete dockets CHAR(AMP) Lab Testing | each pour | Strength = 20MPa Slump = 130mm pump mix Pump mix being used hence cannot specify slump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface | Inprocess Inspection | Concrete Dockets Slump Testing Report Cylinder Testing Report | Site Engineer | -
13 | Concrete Subbase = Pavement Type W CHAR(AMP) C | Levels / thickness | Dip from stringline or survey as-built to top of subbase (Surveyor to provide set-out information prior to concrete pour) | 10m each lane | +0 / -20mm Target thickness = 150mm | Mandatory HOLD POINT Designer Signoff Required | Stringline Sheet | Site Engineer | Designer Signoff
14 | Concrete Subbase = Pavement Type W CHAR(AMP) C | Rough trowel or Broom surface finish | Visual Inspection | All area | Rough surface verified over 100% of surface area | Inprocess Inspection | Production Recurs | Site Engineer | -
15 | Type W CHAR(AMP) Type C | Blinding/CAT60 | Visual Inspection | each lot | ON CONCRETE SUBBASE Hand spray heavy tack coat emulsion (residual bitumen 1L/m2) Blinding sufficient to protect emsulsion from construction movement | Inprocess Testing | Photos | Site Engineer | -
16 | Type O = Contingency weak / soft spot | Grade 4 Membrane | Visual Inspection | each lot | ON EXISTING PAVEMENT Hand spray Heavy tack coat emulsion (residual bitumen 1L/m2) Grade 4 chip | Inprocess Testing | Photos | Site Engineer | -
17 | Hatelit XP Grid | Photos | Visual Inspection | each lot | Type W CHAR(AMP)C = required over concrete subbase Extend 500mm into existing pavement (with CHAR(LESS)20mm asphalt blinding) Extend 1m into Type O | Inprocess Testing | Photos | Site Engineer | -
17 | AC14HF CHAR(AMP) AC20 | Mix Design | Sign-off by Designer | Prior to starting | Sign-off by Designer | Mandatory HOLD POINT Designer Signoff Required | Mix Design Report | Site Engineer | Designer Signoff
18 | AC14HF CHAR(AMP) AC20 | Check weather reports | Check weather reports | Daily | No fog, rain or wet surface. Base temp ≥ 7o C | Inprocess Testing | AC check sheet | Site Engineer | -
19 | AC14HF CHAR(AMP) AC20 | Ensure previous layer is broomed clean | Visual | Prior to starting | Free of detritius and loose material | Inprocess Testing | AC check sheet | Site Engineer | -
20 | AC14HF CHAR(AMP) AC20 | Production tests | Grading, binder content, max density, temp | As per M/10 | NZTA M/10 | Inprocess Testing | Lab test | Site Engineer | -
21 | AC14HF CHAR(AMP) AC20 | Surface finish inspection | Visual inspection by the Engineer | Each lot | Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing | Inspection sheet | Site Engineer | -
22 | AC14HF CHAR(AMP) AC20 | Density testing | NDM | Every 10m each lane staggerd | Air voids to meet NZTA M/10:2020 | Inprocess Testing | Inspection sheet | Site Engineer | Auckland Transport Signoff
23 | AC14HF (Type O) | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | Thickness no less than 55mm Height discrepancy +/- 5mm | Inprocess Testing | Survey As-built / Stringline sheet | Site Engineer | -
24 | AC20 (All three types) | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | Thickness no less than 100mm Height discrepancy +/- 10mm | Inprocess Testing | Survey As-built / Stringline sheet | Site Engineer | -
25 | AC14HF CHAR(AMP) AC20 | Density testing | Cores air voids | Location to be jointly agreed with the Engineer on-site and be outside of wheelpath | Air voids to meet NZTA M/10:2020 Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot. 3 joint cores where possible/practicable | Mandatory HOLD POINT Auckland Transport Signoff Required | RFI response | Site Engineer | Auckland Transport Signoff
26 | AC14HF CHAR(AMP) AC20 | Thickness | Cores depth | Location to be jointly agreed with the Engineer on-site and be outside of wheelpath | Target thickness 155mm (no less than 155mm thickness for AC14HF and AC20 combined) Target thickness 100mm (no less than 100mm thickness for AC20) | Mandatory HOLD POINT Auckland Transport Signoff Required | Core test report | Site Engineer | Auckland Transport Signoff
27 | Shape of road | 3m straight edge | NZTA M/10 spec | At joints and any other areas of concern | Irregularities CHAR(LESS) 5mm under straight edge | Inprocess Inspection | Check sheet | Site Engineer | -
28 | Temperature Limitations | Temperature | Contract Spec / M10 Spec | Every Site | Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degree | Inprocess Inspection | Asphalt QA | Site Engineer | -
29 | Surface Preparation | Visual | NZTA M/10 spec | Every Site | Swept clean; all necessary measures to prevent ponding prior to any surfacing | Inprocess Inspection | Visual | Site Engineer | -
30 | Asphalt Production Tests for AC14 | Production Tests | Grading, binder content, max density, temp | As per M/10 | NZTA M/10 | Laboratory Testing | IANZ Lab | Site Engineer | -
31 | AC14 - Layer thickness - 55mm compacted depth | Insitu | Contract Spec / NZTA M10 Spec | Continuous | 55 mm minimum and 60 mm maximum compacted depth Final asphalt level to be 5mm proud of lip of channel | Mandatory HOLD POINT Auckland Transport Signoff Required | Asphalt QA | Site Engineer | Auckland Transport Signoff
32 | AC14 | Density testing | NDM | Every 10m each lane staggerd | NZTA M/10 | Mandatory HOLD POINT Auckland Transport Signoff Required | RFI response | Site Engineer | Auckland Transport Signoff
33 | Reinstatement of Linemarking and RRPM's CHAR(AMP) Apply Joint sealing | Visual | Visual inspection | Every site | Visual inspection | Inprocess Inspection | Photos | Site Engineer | -
33 | As-built information | Documentation | As-built drawings and ramm sheets completed | - | As-built records | Inprocess Inspection | - | Site Engineer | Auckland Transport Signoff
33 | RAMM DATA | Documentation | RAMM Sheet | - | RAMM Sheet | Inprocess Inspection | - | Site Engineer | Auckland Transport Signoff