## Sheet1
1 | Drawings supplied most current IFC Retrieved from InEight | ENG | Visual | Reviewed drawing register | Reviewed drawing register | Prior to works | HP | W | 1 - Drawings supplied most current IFC Retrieved from InEight | Responsibility - ENG | Method - Visual | Conformance Criteria - Reviewed drawing register | Specification Clause - Reviewed drawing register | Frequency - Prior to works | Verification: THIESS (Initial) - HP | Verification: Client (Initial) - W | 1 - Drawings supplied most current IFC Retrieved from InEight
2 | Management Plans submitted and approved as per PMP | ENG | Visual | Approved Package MP’s | Approved Package MP’s | Prior to works | HP | W | 2 - Management Plans submitted and approved as per PMP | Responsibility - ENG | Method - Visual | Conformance Criteria - Approved Package MP’s | Specification Clause - Approved Package MP’s | Frequency - Prior to works | Verification: THIESS (Initial) - HP | Verification: Client (Initial) - W | Responsibility - ENG
3 | Inspection Test Plan (ITP) submitted and approved | ENG | Visual | Approved ITP revision | Approved ITP revision | Prior to works | HP | W | 3 - Inspection Test Plan (ITP) submitted and approved | Responsibility - ENG | Method - Visual | Conformance Criteria - Approved ITP revision | Specification Clause - Approved ITP revision | Frequency - Prior to works | Verification: THIESS (Initial) - HP | Verification: Client (Initial) - W | Method - Visual
4 | Lot Register/ WBS submitted and approved | ENG | Visual | Approved WBS | Approved WBS | Prior to works | WP | W | 4 - Lot Register/ WBS submitted and approved | Responsibility - ENG | Method - Visual | Conformance Criteria - Approved WBS | Specification Clause - Approved WBS | Frequency - Prior to works | Verification: THIESS (Initial) - WP | Verification: Client (Initial) - W | Conformance Criteria - Reviewed drawing register
5 | Check existing services and dial before you dig | ENV/ENG | Visual | Approved erosion and sediment control plan | EVAMP001-EVA- EN-PLA-0001 | Prior to works | HP | HP | 5 - Check existing services and dial before you dig | Responsibility - ENV/ENG | Method - Visual | Conformance Criteria - Approved erosion and sediment control plan | Specification Clause - EVAMP001-EVA- EN-PLA-0001 | Frequency - Prior to works | Verification: THIESS (Initial) - HP | Verification: Client (Initial) - HP | Specification Clause - Reviewed drawing register
6 | Underlying lot CHAR(AMP) ITP signed off and conforming | ENG | Visual | Topsoil stripping ITP signed off | Approved QMP | Prior to works | HP | W | 6 - Underlying lot CHAR(AMP) ITP signed off and conforming | Responsibility - ENG | Method - Visual | Conformance Criteria - Topsoil stripping ITP signed off | Specification Clause - Approved QMP | Frequency - Prior to works | Verification: THIESS (Initial) - HP | Verification: Client (Initial) - W | Frequency - Prior to works
7 | Removal and replacement of unsuitable material | SV | Visual | Determination of unsuitable material by the Level 1 GITA or Principal is required prior to the removal of any unsuitable material. Unsuitable material shall be disposed as directed by the company or in areas specified in the annexure. | EVAMP001-THS- CV-SPE-0001 | As required | HP | W | 7 - Removal and replacement of unsuitable material | Responsibility - SV | Method - Visual | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Principal is required prior to the removal of any unsuitable material. Unsuitable material shall be disposed as directed by the company or in areas specified in the annexure. | Specification Clause - EVAMP001-THS- CV-SPE-0001 | Frequency - As required | Verification: THIESS (Initial) - HP | Verification: Client (Initial) - W | Verification: THIESS (Initial) - HP
8 | Subgrade preparation – 200mm depth | SV | Visual | Area to be ripped and conditioned to suit a minimum CBR value of 10. | C10 and C14 107501-EB- 00000-27280-001 Rev A EVAMP001-THS- CV-SPE-0001 clause 4.16 | As required | HP | HP | 8 - Subgrade preparation – 200mm depth | Responsibility - SV | Method - Visual | Conformance Criteria - Area to be ripped and conditioned to suit a minimum CBR value of 10. | Specification Clause - C10 and C14 107501-EB- 00000-27280-001 Rev A EVAMP001-THS- CV-SPE-0001 clause 4.16 | Frequency - As required | Verification: THIESS (Initial) - HP | Verification: Client (Initial) - HP | Verification: Client (Initial) - W
9 | Proof-roll subgrade surface prior to placement of embankment fill | SV | Field Test | All subgrades and foundations shall be proof rolled under a standard 8 tonne axle load to confirm that, in the principal’s opinion, deflections are negligible. | EVAMP001-THS- CV-SPE-0001 clause 4.16 | As required | HP | W | 9 - Proof-roll subgrade surface prior to placement of embankment fill | Responsibility - SV | Method - Field Test | Conformance Criteria - All subgrades and foundations shall be proof rolled under a standard 8 tonne axle load to confirm that, in the principal’s opinion, deflections are negligible. | Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16 | Frequency - As required | Verification: THIESS (Initial) - HP | Verification: Client (Initial) - W | 2 - Management Plans submitted and approved as per PMP
10 | Surface level check/ and survey pick-up | Surv | Survey/ Field test | Surface level as per Table 10 C15 DXF file submitted to Company | EVAMP001-THS- CV-SPE-0001 clause 4.16 | As required | HP | HP | 10 - Surface level check/ and survey pick-up | Responsibility - Surv | Method - Survey/ Field test | Conformance Criteria - Surface level as per Table 10 C15 DXF file submitted to Company | Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16 | Frequency - As required | Verification: THIESS (Initial) - HP | Verification: Client (Initial) - HP | Responsibility - ENG
11 | Works completed and update ITP/ Lot Register/ MDR and close out of GDP | ENG | Visual | GDP permits closed. ITP closed. Approved MDR | - EVAMP001- EVA-EN-PLA- 0001 - EVA PMP | As required | HP | HP | 11 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Responsibility - ENG | Method - Visual | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR | Specification Clause - - EVAMP001- EVA-EN-PLA- 0001 - EVA PMP | Frequency - As required | Verification: THIESS (Initial) - HP | Verification: Client (Initial) - HP | Method - Visual
Conformance Criteria - Approved Package MP’s
Specification Clause - Approved Package MP’s
Frequency - Prior to works
Verification: THIESS (Initial) - HP
Verification: Client (Initial) - W
3 - Inspection Test Plan (ITP) submitted and approved
Responsibility - ENG
Method - Visual
Conformance Criteria - Approved ITP revision
Specification Clause - Approved ITP revision
Frequency - Prior to works
Verification: THIESS (Initial) - HP
Verification: Client (Initial) - W
4 - Lot Register/ WBS submitted and approved
Responsibility - ENG
Method - Visual
Conformance Criteria - Approved WBS
Specification Clause - Approved WBS
Frequency - Prior to works
Verification: THIESS (Initial) - WP
Verification: Client (Initial) - W
5 - Check existing services and dial before you dig
Responsibility - ENV/ENG
Method - Visual
Conformance Criteria - Approved erosion and sediment control plan
Specification Clause - EVAMP001-EVA- EN-PLA-0001
Frequency - Prior to works
Verification: THIESS (Initial) - HP
Verification: Client (Initial) - HP
6 - Underlying lot CHAR(AMP) ITP signed off and conforming
Responsibility - ENG
Method - Visual
Conformance Criteria - Topsoil stripping ITP signed off
Specification Clause - Approved QMP
Frequency - Prior to works
Verification: THIESS (Initial) - HP
Verification: Client (Initial) - W
7 - Removal and replacement of unsuitable material
Responsibility - SV
Method - Visual
Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Principal is required prior to the removal of any unsuitable material. Unsuitable material shall be disposed as directed by the company or in areas specified in the annexure.
Specification Clause - EVAMP001-THS- CV-SPE-0001
Frequency - As required
Verification: THIESS (Initial) - HP
Verification: Client (Initial) - W
8 - Subgrade preparation – 200mm depth
Responsibility - SV
Method - Visual
Conformance Criteria - Area to be ripped and conditioned to suit a minimum CBR value of 10.
Specification Clause - C10 and C14 107501-EB- 00000-27280-001 Rev A EVAMP001-THS- CV-SPE-0001 clause 4.16
Frequency - As required
Verification: THIESS (Initial) - HP
Verification: Client (Initial) - HP
9 - Proof-roll subgrade surface prior to placement of embankment fill
Responsibility - SV
Method - Field Test
Conformance Criteria - All subgrades and foundations shall be proof rolled under a standard 8 tonne axle load to confirm that, in the principal’s opinion, deflections are negligible.
Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16
Frequency - As required
Verification: THIESS (Initial) - HP
Verification: Client (Initial) - W
10 - Surface level check/ and survey pick-up
Responsibility - Surv
Method - Survey/ Field test
Conformance Criteria - Surface level as per Table 10 C15 DXF file submitted to Company
Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16
Frequency - As required
Verification: THIESS (Initial) - HP
Verification: Client (Initial) - HP
11 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
Responsibility - ENG
Method - Visual
Conformance Criteria - GDP permits closed. ITP closed. Approved MDR
Specification Clause - - EVAMP001- EVA-EN-PLA- 0001 - EVA PMP
Frequency - As required
Verification: THIESS (Initial) - HP
Verification: Client (Initial) - HP