## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Anchoring ITP |  |  |  |  | Yes | Anchoring ITP | 15eecff3-804b-4448-b3d3-d1222c6dfb42
checkpoint-status |  |  | checkpoint | Attach any relevant photos and documents
text | 028f0315-74ab-5e73-a1fb-c08d51035f83 |  | textbox | Row
text | 97045238-baad-5c1b-a67d-7422f4a62d10 |  | textbox | Anchor No
text | be690863-9e7d-5333-863e-137118c3d567 |  | textbox | Anchor Type
text | 6768772d-e176-557f-a7e0-a60d95c4e39b |  | textbox | Anchor Angle
text | 60848a84-582c-55b8-a9a9-fce7105aa2b0 |  | textbox | Anchor Borehole Dia
text | ac6991ef-4f44-526f-80a5-5731e4c07f7f |  | textbox | Anchor Size
text | 3f6b5f47-6c3f-526b-9e9a-c7c0602e3896 |  | textbox | No of Strands
text | db577cf1-84d9-5f1e-bbcc-949cf8e6d8de |  | textbox | Entry Level (RL)
text | 73e0f5ed-1488-5690-878d-3dd407cd96fb |  | textbox | Bond Length
text | 40ee1ebd-9d82-5798-b6c3-4eae2112da48 |  | textbox | Free Length
text | a33c20b7-1d7b-5d3d-b7c3-f611e24649c6 |  | textbox | Total Drill Length
text | 3e88ccc5-fa81-5161-8e53-a80c5fd8ad5d |  | textbox | Drill Date
text | 19eefdf4-5cf5-5a09-bb1a-ac475b5c1647 |  | textbox | Grout Date
text | d1f402e8-8203-5f30-bf6c-58aaf31429af |  | textbox | Grout Type
text | 3071cbeb-f427-5cb8-b7b5-099b41c87280 |  | textbox | Stress Date
checklist-sectioned |  |  | checklist | Anchoring Works |  |  |  |  | Yes | Anchoring Works | 27f2a3f9-1a6e-47ea-8911-9e936a68f047
checkpoint-group |  |  | section | Prior to Start
checkpoint-status |  |  | checkpoint | Drawings
boolean | bbb4d808-8157-5970-be19-a44f4348b17c |  | tickbox | Drawing name
checkpoint-status |  |  | checkpoint | Anchor Supply (1)
holdpoint |  |  | signoff | Mill certificate
checkpoint-status |  |  | checkpoint | Anchor Supply (2)
holdpoint |  |  | signoff | Test Certificate
checkpoint-status |  |  | checkpoint | Anchor Supply (3)
holdpoint |  |  | signoff | Batch number Noted
checkpoint-status |  |  | checkpoint | Anchor Survey Set out
boolean | ee8d00dd-3aa1-59a5-9a65-006be8d323d6 |  | tickbox | Anchor points to be marked by surveyor and confirmed with DELTA
boolean | e111b108-dbf3-5efa-95da-2218eebd967f |  | tickbox | Surveyor Records
checkpoint-group |  |  | section | Anchor Works
checkpoint-status |  |  | checkpoint | Anchor Strand Centralisers
boolean | eb9afceb-bb5c-5238-a71e-72c6178b975f |  | tickbox | Batch number Noted
checkpoint-status |  |  | checkpoint | Excavation & Preparation of Anchor Wall face / batter
boolean | 3525d650-79df-5caa-8305-f5ba775a0aaa |  | tickbox | As per drawings & site inspection from DELTA
checkpoint-status |  |  | checkpoint | Anchor Drilling
boolean | 1d2849ee-60cd-55e6-a05b-116255644551 |  | tickbox | Hole to be drilled to specification
holdpoint |  |  | signoff | On Record as per Drilling and Installation docket
checkpoint-status |  |  | checkpoint | Grout Equipment
boolean | 5818d1d7-6c6e-5128-b12a-3a6425e7f59a |  | tickbox | Grout pump to be actuated by a piston of screw pump
checkpoint-status |  |  | checkpoint | Grout supply
boolean | b295208e-faa7-56d9-b14a-3d4a67bd10d4 |  | tickbox | Water & Cement grout mix as per design
boolean | 80d994eb-0bd3-5c91-98ee-381b31488fc3 |  | tickbox | TDS, PDS, Batch number
checkpoint-status |  |  | checkpoint | Grout batching
boolean | d4134bc6-b205-5e1f-8143-eea52ada33ec |  | tickbox | Batch by dry weight measure water by calibrated flow meter, continuous agitating after mixing use recirculation system inject within 30 mins of batching
checkpoint-status |  |  | checkpoint | Grout Testing
holdpoint |  |  | signoff | Field testing of grout for Compressive Strength, Per batch, 3 tests
checkpoint-status |  |  | checkpoint | Installation & Grouting of Rock Bolt/Anchors/Soil Nails
boolean | 29b4ea2e-282a-5084-b9b4-0d583568c49d |  | tickbox | Place anchor in prepared clean hole, fill hole from the bottom using grout tube allow grout to flow until pure grout comes out top of hole
boolean | deddaf65-a931-535f-80eb-0d7dfee6f4db |  | tickbox | TDS, PDS, batch number, Mill certificates, Test Certificates
checkpoint-status |  |  | checkpoint | Anchor Stressing
boolean | 673756fa-d07e-5a19-91ac-9d6e96972727 |  | tickbox | AS per drawings & specification
boolean | 760be2c2-f31c-5ace-820e-785c73dfe266 |  | tickbox | Drilling and installation docket for Anchors done on a daily basis
holdpoint |  |  | signoff | Stressing records captured per AGT records