## Reinforced Slope
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | H1501A - Tukipo Stream Bridge |  | CPS Approver | Quality Approver | CPS Eng. | Sujathan k
|  |  |  | Procedure: | Reinforced Slope (Rock Bolts, Soil Nails) |  | Name / Signature | Name / Signature | Site Engineer | Wellerson De Souza
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng. | Dharminder Singh
Lot No: |  |  |  | Corresponding Work Instruction: |  | TREC Construction Approval - Tukipo Stream Bridge .docx |  | Compliance with Work Instructions and Specifications
Detailed Location: Tukipo Stream Bridge-SH50-RS 79-RP 4.1
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Others Initials (Grey if not required) | Date(s)
1 | Dimensions and Set-out | H | Once on site the Contractor shall confirm the condition and dimensions of the structure. | Prior to commencement | Visual Inspection | The CPS Engineer shall be informed immediately if any conflicts in dimensions are encountered. | Photos | Site Engineer | CPS Engineer
2 | Erosion and Sediment Control | W | ESC measures shall be designed and maintained by the contractor during the period of the works | Prior to commencement | Visual Inspection | Ensure no surface runoff flows over temporary excavations | Photos | Site Engineer
3 | Clearing & Earthworks | W | Before setout of the reinforced slope method the bank along the full length of the abutment shall be trimmed/excavated to remove all loose material. | Prior to commencement | Visual Inspection | Keep excavation to a minimum | Photos | Site Engineer
4 | Clearing & Earthworks | H | Founding materials shall be inspected and verified by a geotechnical Engineer on site | Prior to commencement | Visual Inspection | Any soft or unsuitable soil shall be excavated and replaced with lean concrete (minimum compression strength of 10MPa at 28 days) | Email | Site Engineer | CPS Engineer
5 | Clearing & Earthworks | H | Contractor shall submit their construction methodology for the trial anchors to the CPS Engineer at least 3 days prior to anchor installation. | Prior to commencement | Submission |  | Methodology | Site Engineer | CPS Engineer
6 | Reinforcement Compliance | W | All reinforcement shall meet design specifications | Prior to commencement | Document Review | Grade 500E and shall comply with AS/NZS 4671 | Delivery Docket | Site Engineer
7 | Anchor Ties Compliance | W | All steel solid bar anchor ties are to meet design specifications. Alternative anchor systems will be considered provided they achieve the intent of these works | Prior to commencement | Document Review | 20mm diameter grade 500E Reidbar or similar approved, and hot dip galvanised in accordance with AS/NZS 4680:2006. Damaged bars are to be rejected. | Delivery Docket | Site Engineer
8 | Bearing Plate Compliance | W | Bearing plate steel, coupling hex nuts and other accessories must meet design specifications. | Prior to commencement | Document Review | Bearing plate steel: Minimum yield strength of 250MPa, min 200x200x12mm. All galvanised to HDG600 | Delivery Docket | Site Engineer
9 | Concrete Compliance | W | All concrete to meet design specifications | Prior to commencement | Document Review | Workmanship in accordance with NZS 3109 and meets minimum 28-day compressive strength of 30 MPa | Delivery Docket | Site Engineer
10 | Grout Testing | H | Contractor should employ an IANZ accredited laboratory to perform one compressive strength test for every anchor at 1,7, and 28 days in accordance with NZS 3112.4. Test results shall be supplied to the CPS Engineer within 24 hours of testing. | Prior to commencement | Testing | Anchor grout shall be Sika grout 212 or similar as approved by the Engineer and is required to achieve minimum characteristic strength of 20MPa at 7 days and 30MPa at 28 days. | Lab test results to CONQA Procore | Site Engineer | CPS Engineer
11 | Anchor testing | H | Three sacrificial soil nail tests are required by the Engineer. Location will be agreed on site with CPS Engineer. Testing may only commence once the grout has reached 30MPa as confirmed by grout cylinder testing. | Prior to commencement | Testing | Grout test results to be provided to the CPS Engineer prior to nail testing. Test equipment certificates and calibration certificates submitted to CPS Engineer prior to testing. Sacrificial test anchors and production anchors shall comply with Section 3.4 Table 1. Test results shall be provided to the CPS Engineer for approval within 24 hours of testing | Lab test results to CONQA Procore | Site Engineer | CPS Engineer
12 | Anchor testing | H | Three production anchors shall be proof tested in a location agreed with the CPS Engineer. All remaining production anchors shall be acceptance tested. | Prior to commencement | Testing | Testing done in accordance with Section 3.5, test results provided to the CPS Engineer for approval within 24 hours of testing. Rejection of anchors in accordance with Section 3.6 | Test results to CONQA Procore | Site Engineer | CPS Engineer
13 | Anchor Installation | W | Anchors shall be installed in accordance with the lines, lengths and levels shown in drawings. | During Construction | Measure | Bonded length of anchors is minimum 4m. Upper row installed at 10 degrees downward from horizontal. Lower row installed at 35 degrees downward from horizontal. Anchor drilling, hole cleaning, anchor installation and grouting shall be completed within 24 hours of commencement. No holes are to be left open overnight. | Photos identifying anchors and installed locations | Site Engineer
14 | Anchor Installation | W | The contractor shall keep a record for each individual ground anchor and submit these to the CPS Engineer | During Construction | Submission | Record must include: -Type of drill bit -Drilling rate -Grout pressure -Grout volumes -Ground conditions encountered -Unforeseen conditions -Prestressing steel manufacturer's mill test reports for the solid bars incorporated in the installation | Subcontractor QA Records | Site Engineer
15 | Anchor Installation | W | Install grout | During Construction | Visual Inspection | The entire length of the nail should be grouted without voids, intrusion of soil, or gaps in the grouted column. Grouted columns are not to be leaded for at least 72 hours after grouting. | Photos | Site Engineer
16 | Anchor Installation | W | Install bearing plates and washers/nuts | During Construction | Visual Inspection | Bearing plates (anchor heads) are required to be buried within the mass of the skirt concrete block. Tie rod nuts are to be snug tightened only to remove any slack. | Photos | Site Engineer
17 | Reinforced Steel | H | Reinforcement shall be installed in accordance with Section 3.8. | During Construction | Visual Inspection |  | Photos | Site Engineer | CPS Engineer
18 | Drainage Installation | H | Sub horizontal filter wrapped slotted pipes to be installed as shown on design plan. Outlet pipes shall be installed along the front face of the concrete block to form weepholes as per construction drawings. | During Construction | Visual Inspection | Drains shall be installed in 65mm diameter drilled holes at 10 degrees upward from horizontal. | Photos, Subcontractor QA Records | Site Engineer | CPS Engineer
19 | Drainage Installation | H | When completed the subdrains shall be inspected by a geotechnical Engineer on site | During Construction | Visual Inspection |  | Email | Site Engineer | CPS Engineer
20 | Concrete | W | Ensure any cavities and surface is clean prior to application of concrete | During Construction | Visual Inspection |  | Photos | Site Engineer
21 | Concrete | W | Apply concrete in specified locations | During Construction | Visual Inspection |  | Photos | Site Engineer
22 | Concrete | W | All concrete shall be properly cured for a period of seven days or until specified strength is obtained. | After Construction | Visual Inspection |  |  | Site Engineer
23 | Concrete | H | Once the concrete block has been completed, the CPS Engineer must be offered the opportunity to inspect the completed works. | After Construction | Visual Inspection |  | Email | Site Engineer | CPS Engineer
24 | Bank Reshaping | W | After completion of the works, the existing banks shall be shaped to match with the new bank. | After Construction | Visual Inspection |  | Photos | Site Engineer
25 | Topsoiling and Grassing | W | All areas disturbed by the works shall be topsoiled and grassed except as noted. | After Construction | Visual Inspection | Topsoil shall be spread at a nominal thickness of 100mm, but no less than 50mm and no more than 120mm. Batters steeper than 2:1 are not to be topsoiled. Topsoil is to be tamped down to a firm state (minor indentation when stepped on). | Photos | Site Engineer
26 | Topsoiling and Grassing | W | Grassing of topsoiled areas shall be a to a mix agreed with the CPS Engineer on site. | After Construction | Visual Inspection | Contractor shall apply 50 grams per square metre of superphosphate. No seed is to be sown until preparation work has been approved by the Engineer. The grass seed mixture shall be sown at a rate of 25 grams per square metre bare seed weight. | Photos | Site Engineer
27 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register, Subcontractor QA Records | Site Engineer
28 | As-built | H | Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red line mark up drawings to be included in QA file | During and at completion of work. | Survey / Drawings |  | Survey receipts, As-built plans | Site Engineer | CPS Engineer
29 | Completion Sign Off From Fields Below | H | Below sign-offs to be Captured in CONQA / Procore |  |  |  | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date: