## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - H1501A - Tupiko Stream Bridge - Reinforced Slope (Rock Bolts, Soil Nails) | itp |  |  |  |  | ITP - H1501A - Tupiko Stream Bridge - Reinforced Slope (Rock Bolts, Soil Nails) | 2973051b-ac2f-47a6-b7ed-f70f24c0cc9f
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Dimensions and Set-out
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Once on site the Contractor shall confirm the condition and dimensions of the structure.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - The CPS Engineer shall be informed immediately if any conflicts in dimensions are encountered.
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Erosion and Sediment Control
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - ESC measures shall be designed and maintained by the contractor during the period of the works
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure no surface runoff flows over temporary excavations
label | Records - Photos
checkpoint | 3 - Clearing & Earthworks
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Before setout of the reinforced slope method the bank along the full length of the abutment shall be trimmed/excavated to remove all loose material.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Keep excavation to a minimum
label | Records - Photos
checkpoint | 4 - Clearing & Earthworks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Founding materials shall be inspected and verified by a geotechnical Engineer on site
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Any soft or unsuitable soil shall be excavated and replaced with lean concrete (minimum compression strength of 10MPa at 28 days)
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Clearing & Earthworks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Contractor shall submit their construction methodology for the trial anchors to the CPS Engineer at least 3 days prior to anchor installation.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Methodology
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Reinforcement Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All reinforcement shall meet design specifications
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Grade 500E and shall comply with AS/NZS 4671
label | Records - Delivery Docket
checkpoint | 7 - Anchor Ties Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All steel solid bar anchor ties are to meet design specifications. Alternative anchor systems will be considered provided they achieve the intent of these works
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - 20mm diameter grade 500E Reidbar or similar approved, and hot dip galvanised in accordance with AS/NZS 4680:2006. Damaged bars are to be rejected.
label | Records - Delivery Docket
checkpoint | 8 - Bearing Plate Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Bearing plate steel, coupling hex nuts and other accessories must meet design specifications.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Bearing plate steel: Minimum yield strength of 250MPa, min 200x200x12mm. All galvanised to HDG600
label | Records - Delivery Docket
checkpoint | 9 - Concrete Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All concrete to meet design specifications
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Workmanship in accordance with NZS 3109 and meets minimum 28-day compressive strength of 30 Mpa
label | Records - Delivery Docket
checkpoint | 10 - Grout Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Contractor should employ an IANZ accredited laboratory to perform one compressive strength test for every anchor at 1,7, and 28 days in accordance with NZS 3112.4. Test results shall be supplied to the CPS Engineer within 24 hours of testing.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Anchor grout shall be Sika grout 212 or similar as approved by the Engineer and is required to achieve minimum characteristic strength of 20MPa at 7 days and 30MPa at 28 days.
label | Records - Lab test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Anchor testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Three sacrificial soil nail tests are required by the Engineer. Location will be agreed on site with CPS Engineer. Testing may only commence once the grout has reached 30MPa as confirmed by grout cylinder testing.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Grout test results to be provided to the CPS Engineer prior to nail testing.
label | ○ Test equipment certificates and calibration certificates submitted to CPS Engineer prior to testing.
label | ○ Sacrificial test anchors and production anchors shall comply with Section 3.4 Table 1.
label | ○ Test results shall be provided to the CPS Engineer for approval within 24 hours of testing
label | Records - Lab test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Anchor testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Three production anchors shall be proof tested in a location agreed with the CPS Engineer. All remaining production anchors shall be acceptance tested.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Testing done in accordance with Section 3.5, test results provided to the CPS Engineer for approval within 24 hours of testing. Rejection of anchors in accordance with Section 3.6
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Anchor Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Anchors shall be installed in accordance with the lines, lengths and levels shown in drawings.
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Bonded length of anchors is minimum 4m. Upper row installed at 10 degrees downward from horizontal. Lower row installed at 35 degrees downward from horizontal.
label | ○ Anchor drilling, hole cleaning, anchor installation and grouting shall be completed within 24 hours of commencement. No holes are to be left open overnight.
label | Records - Photos identifying anchors and installed locations
checkpoint | 14 - Anchor Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The contractor shall keep a record for each individual ground anchor and submit these to the CPS Engineer
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Record must include:
label | – Type of drill bit
label | – Drilling rate
label | – Grout pressure
label | – Grout volumes
label | – Ground conditions encountered
label | – Unforeseen conditions
label | – Prestressing steel manufacturer's mill test reports for the solid bars incorporated in the installation
label | Records - Subcontractor QA Records
checkpoint | 15 - Anchor Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install grout
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - The entire length of the nail should be grouted without voids, intrusion of soil, or gaps in the grouted column. Grouted columns are not to be leaded for at least 72 hours after grouting.
label | Records - Photos
checkpoint | 16 - Anchor Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install bearing plates and washers/nuts
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Bearing plates (anchor heads) are required to be buried within the mass of the skirt concrete block.
label | ○ Tie rod nuts are to be snug tightened only to remove any slack.
label | Records - Photos
checkpoint | 17 - Reinforced Steel
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Reinforcement shall be installed in accordance with Section 3.8.
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - Drainage Installation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Sub horizontal filter wrapped slotted pipes to be installed as shown on design plan. Outlet pipes shall be installed along the front face of the concrete block to form weepholes as per construction drawings.
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Drains shall be installed in 65mm diameter drilled holes at 10 degrees upward from horizontal.
label | Records - Photos, Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - Drainage Installation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - When completed the subdrains shall be inspected by a geotechnical Engineer on site
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - Concrete
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure any cavities and surface is clean prior to application of concrete
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 21 - Concrete
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply concrete in specified locations
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 22 - Concrete
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All concrete shall be properly cured for a period of seven days or until specified strength is obtained.
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records -
checkpoint | 23 - Concrete
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Once the concrete block has been completed, the CPS Engineer must be offered the opportunity to inspect the completed works.
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 24 - Bank Reshaping
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - After completion of the works, the existing banks shall be shaped to match with the new bank.
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 25 - Topsoiling and Grassing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All areas disturbed by the works shall be topsoiled and grassed except as noted.
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Topsoil shall be spread at a nominal thickness of 100mm, but no less than 50mm and no more than 120mm. Batters steeper than 2:1 are not to be topsoiled. Topsoil is to be tamped down to a firm state (minor indentation when stepped on).
label | Records - Photos
checkpoint | 26 - Topsoiling and Grassing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Grassing of topsoiled areas shall be a to a mix agreed with the CPS Engineer on site.
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Contractor shall apply 50 grams per square metre of superphosphate.
label | ○ No seed is to be sown until preparation work has been approved by the Engineer.
label | ○ The grass seed mixture shall be sown at a rate of 25 grams per square metre bare seed weight.
label | Records - Photos
checkpoint | 27 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register, Subcontractor QA Records
checkpoint | 28 - As-built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red line mark up drawings to be included in QA file
label | Frequency - During and at completion of work.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Records - Survey receipts, As-built plans
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 29 - Completion Sign Off From Fields Below
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Below sign-offs to be Captured in CONQA / Procore
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT