## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Steel & Shotcrete ITP |  |  |  |  | Yes | Steel & Shotcrete ITP | 759afd48-3b62-4c85-88e0-156751e4a9a6
checkpoint-group |  |  | section | Prior to Start
checkpoint-status |  |  | checkpoint | Approval of shotcrete mix design
boolean | a5919698-efa3-564f-bc3e-28363519585c |  | tickbox | Mix design sent and approved
checkpoint-status |  |  | checkpoint | Locate washout area
checkpoint-status |  |  | checkpoint | Provision of Certificates and test results
boolean | dac338b4-ff0f-51cc-97b9-1bab9a14e3fe |  | tickbox | Documents provided and attached
checkpoint-group |  |  | section | Shotcrete Preparation
checkpoint-status |  |  | checkpoint | Surface check
boolean | 8e596ead-44e3-52e8-9bd5-dc3cf6e9e123 |  | tickbox | Surface checks of formwork and column dimensions - as per design drawings
checkpoint-status |  |  | checkpoint | Place reinforcement as per design drawings on Column Encasement
boolean | 6d33180f-38bb-5b2a-90c7-1b6950fa62b5 |  | tickbox | Required mesh secured with pins as per structural drawings
checkpoint-status |  |  | checkpoint | Inspection of shotcrete wall and/or Column
boolean | 5200ce2e-339a-523e-8185-a898f932c7f4 |  | tickbox | Visual inspection to verify Mesh/Steel is as per structural drawings
checkpoint-status |  |  | checkpoint | Testing of shotcrete
boolean | 30128269-ed8a-5ff9-9835-9d7ff0a944c2 |  | tickbox | Onsite slump and visual testing by qualified concrete tester (4 Cylinders required for testing)
checkpoint-status |  |  | checkpoint | Placement of shotcrete
boolean | a6af3f3d-9e53-5451-a952-a0a3e0841f6d |  | tickbox | Place shotcrete no less than the minimum thickness and cover as per structural drawings
boolean | 0ee4d3ac-000c-5f51-b87d-cba31169a513 |  | tickbox | Design Strength of Concrete as noted on the structural drawing
checkpoint-status |  |  | checkpoint | Finish of shotcrete
boolean | a4eea958-c225-56d6-b4df-6d5b23032b52 |  | tickbox | Sponge Finish c/w expansion and construction joints as per structural drawings