## Sheet1
4.1 | Proof Roll | Each Lot | Following completion of the curing period, detailed trim and survey conformance, the Principle’s Representative will be invited to a proof roll (24 hours notice). Proof roll will be accepted if no rutting greater than 25mm is observed. Proof roll will involve using a heavy vibrating roller (in static mode) Proof rolling of the subgrade will be approval to place Sub-basecourse or Basecourse. If rain falls on subgrade prior to placing next layer, a further inspection will be required. | Cl3.12 Cl4.6 | Verify | This signed ITP | HP WP HP HP | Project/Site Engineer Principle’s Representative | 4.1 - Proof Roll | Frequency - Each Lot | Acceptance Criteria - Following completion of the curing period, detailed trim and survey conformance, the Principle’s Representative will be invited to a proof roll (24 hours notice). Proof roll will be accepted if no rutting greater than 25mm is observed. Proof roll will involve using a heavy vibrating roller (in static mode) Proof rolling of the subgrade will be approval to place Sub-basecourse or Basecourse. If rain falls on subgrade prior to placing next layer, a further inspection will be required. | Reference Documents - Cl3.12 Cl4.6 | Inspection/Test Method - Verify | Record of conformity - This signed ITP | HP WP HP HP | Responsibility - Project/Site Engineer Principle’s Representative | Date Completed: | 4.1 - Proof Roll
4.2 | Surface Smoothness | Each Lot every 10m | Long straight edge surface not to deviate by more than 12mm over a 3.5m long straight edge, following subgrade treatment | Cl3.16 | Verify | This signed ITP Results Attached | TP | Project/Site Engineer | 4.2 - Surface Smoothness | Frequency - Each Lot every 10m | Acceptance Criteria - Long straight edge surface not to deviate by more than 12mm over a 3.5m long straight edge, following subgrade treatment | Reference Documents - Cl3.16 | Inspection/Test Method - Verify | Record of conformity - This signed ITP Results Attached | TP | Responsibility - Project/Site Engineer | Date Completed: | Frequency - Each Lot
4.3 | Strength Testing (CBR) | Each Lot – Once per 1500m2 | To exceed 20% CBR after 7 days. | Cl3.16 | Verify | This signed ITP Results Attached | TP | Project/Site Engineer | 4.3 - Strength Testing (CBR) | Frequency - Each Lot – Once per 1500m2 | Acceptance Criteria - To exceed 20% CBR after 7 days. | Reference Documents - Cl3.16 | Inspection/Test Method - Verify | Record of conformity - This signed ITP Results Attached | TP | Responsibility - Project/Site Engineer | Date Completed: | Acceptance Criteria - Following completion of the curing period, detailed trim and survey conformance, the Principle’s Representative will be invited to a proof roll (24 hours notice). Proof roll will be accepted if no rutting greater than 25mm is observed. Proof roll will involve using a heavy vibrating roller (in static mode) Proof rolling of the subgrade will be approval to place Sub-basecourse or Basecourse. If rain falls on subgrade prior to placing next layer, a further inspection will be required.
4.4 | Field Dry Density | Each Lot – Once per 500m2 | Maximum Dry Density used is lime stabilised subgrade 100% using standard compaction. | Cl3.11 Cl3.16 | Verify | This signed ITP Results Attached | TP | Project/Site Engineer | 4.4 - Field Dry Density | Frequency - Each Lot – Once per 500m2 | Acceptance Criteria - Maximum Dry Density used is lime stabilised subgrade 100% using standard compaction. | Reference Documents - Cl3.11 Cl3.16 | Inspection/Test Method - Verify | Record of conformity - This signed ITP Results Attached | TP | Responsibility - Project/Site Engineer | Date Completed: | Reference Documents - Cl3.12 Cl4.6
4.5 | Surface Level | Each Lot | Stabilised and compacted subgrade surface layer to comply within -25mm to +0mm from specified levels. | Cl3.16 | Verify Report | This signed ITP Results Attached | SCP | Project/Site Engineer | 4.5 - Surface Level | Frequency - Each Lot | Acceptance Criteria - Stabilised and compacted subgrade surface layer to comply within -25mm to +0mm from specified levels. | Reference Documents - Cl3.16 | Inspection/Test Method - Verify Report | Record of conformity - This signed ITP Results Attached | SCP | Responsibility - Project/Site Engineer | Date Completed: | Inspection/Test Method - Verify
Record of conformity - This signed ITP
HP WP HP HP
Responsibility - Project/Site Engineer Principle’s Representative
Date Completed:
4.2 - Surface Smoothness
Frequency - Each Lot every 10m
Acceptance Criteria - Long straight edge surface not to deviate by more than 12mm over a 3.5m long straight edge, following subgrade treatment
Reference Documents - Cl3.16
Inspection/Test Method - Verify
Record of conformity - This signed ITP Results Attached
TP
Responsibility - Project/Site Engineer
Date Completed:
4.3 - Strength Testing (CBR)
Frequency - Each Lot – Once per 1500m2
Acceptance Criteria - To exceed 20% CBR after 7 days.
Reference Documents - Cl3.16
Inspection/Test Method - Verify
Record of conformity - This signed ITP Results Attached
TP
Responsibility - Project/Site Engineer
Date Completed:
4.4 - Field Dry Density
Frequency - Each Lot – Once per 500m2
Acceptance Criteria - Maximum Dry Density used is lime stabilised subgrade 100% using standard compaction.
Reference Documents - Cl3.11 Cl3.16
Inspection/Test Method - Verify
Record of conformity - This signed ITP Results Attached
TP
Responsibility - Project/Site Engineer
Date Completed:
4.5 - Surface Level
Frequency - Each Lot
Acceptance Criteria - Stabilised and compacted subgrade surface layer to comply within -25mm to +0mm from specified levels.
Reference Documents - Cl3.16
Inspection/Test Method - Verify Report
Record of conformity - This signed ITP Results Attached
SCP
Responsibility - Project/Site Engineer
Date Completed: