## Table 1
|  | SURFACING RENEWALS INSPECTION AND TEST PLAN – Asphalt Paving | [6 empty] | Doc No: | 670584 ITP v1.1
|  | Site Name: | Wreys Bush 3 | [5 empty] | Version: | 1.1 | Pages:
|  | Location: | SH 96 RS 066 RP 10760 to 10840 | [5 empty] | Prepared: | Tom Richmond | Date: | 2023-11-28
[9 empty] | Approved: | Quinn Stewart | Date:
Item Number | ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQ. | ACCEPTANCE CRITERIA |  | INSPECTORATE W/H |  |  | Responsible Person | RECORDS / REMARKS
[8 empty] | W=WITNESS, H =HOLD |  |  |  | incl NCR ref
[7 empty] | Type | Assessor | Description |  |  | Sign & date if appropriate
1 | Preliminary and General
1.1 | Construction Programme Completion |  | Confirmation | Best Practice Contract Specific MMP | Before work commences | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date. | W |  |  |  | Renewals Manager
1.2 | Approved RQP |  | Confirmation | Contract Specification | Before work commences | Principal Acceptance according to guidelines in appendix 6.3 | H |  | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve |  | Renewals Manager
1.3 | Traffic Management | TMP | Visual check | CoPTTM | Before traffic management set up | TMP checked and approved Plans approved Current EED (if applicable) | H |  | Hold point - No traffic management is to be set up until TMP has been checked and approved |  | Paving Supervisor
1.4 | Mix Design Verification for all mixes Check Laydown Trials are complete and compliant |  | Confirmation | NZTA M/10, P/11, P23 | Before planning commences | Mix Design compliant, current and relevant. Batching plant production capability is confirmed | H |  | Hold point - No planning of on-site works shall commenced until the mix design is verified. |  | Paving Supervisor
1.5 | Notification of intention to start work |  | Notification |  | Before work commences | Letter drop to local residents. Greater consultation where required | H |  | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. |  | Paving Supervisor
1.6 | Works Extents |  | Confirmation | Site Visit | Before work commences | Renewals Manager and/or Client to agree extents of project | H |  | Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA |  | Paving Supervisor
1.7 | Pavement Marking Records |  | Measurment Data | Site Measure or Video Viewer | Before work commences | Measure existing markings to aid reinstatement | H |  | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. |  | Paving Supervisor
2 | Milling and Preparation
2.1 | Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H |  | Hold point - No excavation/milling is to be commenced until services are located and accounted for |  | Paving Supervisor
2.2 | Stormwater Management |  | Visual check | On Site | Before work commences | Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering | H |  | Hold point - No work to be commenced until protections in place |  | Paving Supervisor
2.3 | Traffic Management | Setup | Visual check | Traffic Management Plan | Before work commences each day | Traffic management complies with TMP | H |  | Hold point - No physical works are to be commenced until necessary traffic management is in place |  | Site Foreperson
2.4 | Milling Depths |  | Measurement | On Site | Measure each side of milling machine cut | Every 10m. Depth matches target | H |  | Milling String Sheets or photos of depths taken and uploaded to CONQA |  | Site Foreperson / QA
2.5 | Service Covers Preparation |  | Visual | On site measurements & photos | All Covers | Hand excavation around ironwork and adjustment to desired level (if required) | H |  |  |  | Site Foreperson
2.6 | Additional Surfacing Preparation - Side Roads - Accesses - Driveways - Dish Channels - High Shoulders |  | Visual Check | Per Design | Before Membraning and Paving | Have all areas of additional surfacing on the design been prepared, membraned and marked for paving? | H |  | Hold Point – All areas planned for AC are prepared ready for surfacing layer |  | Site Foreperson
2.7 | Milling Surface inspection / walkover |  | Visual Check, proof roll with loaded truck to check deflections | On site measurements & photos | Prior to surfacing | Renewals Manager and NZTA invited to inspect milled surface and agree if any additional overmilling is required | H |  | Hold point - Inspection and agreement by NZTA |  | Paving Supervisor / Paving Manager
2.8 | Over-Milling |  | Measurement | On site measurements & photos | Prior to pre-level | Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill. | H |  |  |  | Paving Supervisor
2.9 | Pre-Level |  | Measurement | On site measurements & photos | Prior to surfacing | Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents | H |  | Hold point - Inspection and agreement by NZTA |  | Paving Supervisor / Paving Manager
3 | Paving Structural
3.1 | Production Properties | PSD (Particle Size Distribution) | Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing | ASTM C136-06 / C 117-14 | 1 per 200t or maximum of 3 per production lot | Job Mix Formula and NZTA M/10 Table 5.3 tolerances | W |  | IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance |  | Paving Supervisor
|  | Binder Content | Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method | B19 Issue 6 - 2009
|  | Maximum Specific Gravity | Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures | ASTM D2041/D2041M - 2011 |  | Per Mix design
3.2 | Preparation |  | Visual | NZTA M/10 | Prior to Shift | Paving plan to be completed for every shift, with dimensions | W |  | Paving Plan and Crew Briefing Plan completed prior |  | Paving Supervisor
3.3 | Joins |  | Visual | NZTA M/10 | Prior to Shift | Joins are outside of trafficked wheel paths where possible. | W |  |  |  | Paving Supervisor
3.4 | Mix Inconsistency and Deficiency |  | Visual | NZTA M/10 | Continuous | Visually check asphalt surface during paving for areas of segregation | H |  |  |  | Site Foreperson
3.5 | Load Locate |  | Measurement |  | Every Load | Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | W |  | Per standard practice |  | Quality Assurance Engineer
3.6 | Laying Temperature |  | Confirmation | NZTA M/10 | Every Load | Arrival temperature 150°C (±10°) checked for every load | H |  | Hold point - Reject mix for non- compliant temperatures. |  | Quality Assurance Engineer
3.7 | Compaction |  | NDM Testing | NZTA M/10 | Minimum: 1 Test per 300m² within Mat. 1 Test per 100m of joint. | Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2 | H |  | Hold Point - No Wearing course paved until any non-compliance is sorted. PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks. |  | Quality Assurance Engineer
4 | Paving Wearing Course
4.1 | Production Properties | PSD (Particle Size Distribution) | Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing | ASTM C136-06 / C 117-14 | 1 per 200t or maximum of 3 per production lot | Job Mix Formula and NZTA M/10 Table 5.3 tolerances | W |  | IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance |  | Paving Supervisor
|  | Binder Content | Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method | B19 Issue 6 - 2009
|  | Maximum Specific Gravity | Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures | ASTM D2041/D2041M - 2011 |  | Per Mix design
4.2 | Preparation |  | Visual | NZTA M/10 | Prior to Shift | Paving plan to be completed for every shift, with dimensions | W |  | Paving Plan and Crew Briefing Plan completed prior |  | Paving Supervisor
4.3 | Joins |  | Visual | NZTA M/10 | Prior to Shift | Joins are outside of trafficked wheel paths where possible. | W |  |  |  | Paving Supervisor
4.4 | Membrane Sealing |  | Visual | NZTA M/10 | Prior to Paving | Membrane seal meets design and extent. Sealing Docket record kept | H |  | Hold Point - No paving until Membrane Done. Ensure correct application of chip & emulsion |  | Paving Supervisor
4.5 | Mix Inconsistency and Deficiency |  | Visual | NZTA M/10 | Continuous | Visually check asphalt surface during paving for areas of segregation | H |  |  |  | Site Foreperson
4.6 | Load Locate |  | Measurement |  | Every Load | Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Ground Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | W |  | Per standard practice |  | Quality Assurance Technician.
4.7 | Laying Temperature |  | Confirmation | NZTA M/10 | Every Load | Based on Mix design | H |  | Hold point - Reject mix for non- compliant temperatures. |  | Quality Assurance Technician
4.8 | Compaction |  | PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing. | NZTA M/10 | As per Agreed on Contract. | Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2 | W |  | PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks. |  | Quality Assurance Technician / Paving Manager
4.9 | Roughness |  | Visual | On Site | Post Construction | Agreement with WK as per M10 | H |  | Site walkover with client to determine ability to comply with straight edge measurement outlined in M10 |  | Paving Supervisor
5 | Site Reinstatement / Clearance
5.1 | Shoulder Reinstatement (where no K&C) |  | Measurement/Visua l | On Site | All low shoulder created by paving edge | Shoulders reinstated to between 1:4 and 1:6 | H |  | Low shoulder created by rural paving is corrected using AP20/40 or DG Mix. Not relevant in kerb and channel scenario. Hold Point - Site TTM/TSL should not be removed until these hazards possible are attended to. |  | Paving Supervisor
5.2 | Post-seal Area Check |  | Measurement | On Site tape- measure | After Surfacing | Check sealed area meets design | W |  | Notify Renewals Engineer or Renewals Manager |  | Paving Supervisor
5.3 | Service Covers |  | Measurement/Visua l | On Site | After Surfacing | All service covers are checked and adjusted (if necessary) to finished level (+10mm, -0mm) | W |  |  |  | Paving Supervisor
5.4 | Joint Sealing |  | Visual | On Site | After Surfacing | Check cold joints are bandage sealed | W |  |  |  | Paving Supervisor
5.5 | Road Marking |  | MOTSAM | Visual inspection | All markings | Replaced in same position, or per design | H |  | Hold point – Site TTM cannot be removed until markings reinstated |  | Paving Supervisor
5.6 | Other Traffic Services | Marker pegs/ Signs/Markings/RRP Ms Replaced | TNZ C/20: 2003 | Visual inspection | All signs/markers | Replaced in same position, height etc | H |  | Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated |  | Paving Supervisor
5.7 | Stormwater Management Controls removed |  | Visual check |  | All installed measures | Installed controls are removed | H |  |  |  | Paving Supervisor
5.8 | Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W |  |  |  | Paving Supervisor
5.9 | Site left clean & tidy |  | Visual check |  | After vacating site |  Stockpiles removed | W |  | Invite NZTA to carry out joint site inspection to inspect site. |  | Paving Supervisor
 Plant removed
 Litter cleared from site
6 | As Built Records
6.1 | Collect asset data |  | SHDOM (SM050) |  | During construction | All relevant as built information collected. | W |  |  |  | Paving Supervisor
6.2 | Enter asset data into RAMM and/or register(s) |  | SHDOM (SM050) | RAMM | At completion of work. | All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file. | W |  | Data entered by 20th of follow month after month of completion |  | Asset Information Manager
6.3 | Construction Completion Report |  | Confirmation | Contract Specification | At completion of work. | Checked and approved | W |  | Completed within two months after Paving Wearing Course |  | Renewals Engineer/ Renewals Manager
Quality Assurance Close Out by:
Date:
(name)
(signature)
This record to contract file.