## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SNOC ITP Earnslaw St - 670581 ITP v1.1 | itp |  |  |  |  | SNOC ITP Earnslaw St - 670581 ITP v1.1
section | Preliminary and General
checkpoint | 1.1 - Construction Programme Completion
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - Best Practice Contract Specific MMP
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Renewals Manager
checkpoint | 1.2 - Approved RQP
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - Contract Specification
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. NZTA to approve
label | RESPONSIBLE PERSON - Renewals Manager
holdpoint | HOLD POINT
checkpoint | 1.3 - Traffic Management - TMP
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - CoPTTM
label | FREQ. - Before traffic management set up
label | ACCEPTANCE CRITERIA - TMP checked and approved Plans approved, Current EED (if applicable)
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 1.4 - Mix Design Verification for all mixes Check Laydown Trials are complete and compliant
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - NZTA M/10, P/11, P23
label | FREQ. - Before planning commences
label | ACCEPTANCE CRITERIA - Mix Design compliant, current and relevant. Batching plant production capability is confirmed
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - No planning of on-site works shall commenced until the mix design is verified.
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 1.5 - Notification of intention to start work
label | VERIFICATION ACTIVITY - Notification
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Letter drop to local residents. Greater consultation where required
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 1.6 - Works Extents
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - Site Visit
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Renewals Manager and/or Client to agree extents of project
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - Walk over site with Renewals Engineer and/or Renewals Manager and/or NZTA
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 1.7 - Pavement Marking Records
label | VERIFICATION ACTIVITY - Measurment Data
label | METHODS OR REFERENCE - Site Measure or Video Viewer
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Measure existing markings to aid reinstatement
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
section | Milling and Preparation
checkpoint | 2.1 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | VERIFICATION ACTIVITY - Visual plan, BeforeUDig Cable locate (electronic or pothole for line & depth)
label | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Zero service strikes
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - No excavation/milling is to be commenced until services are located and accounted for
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 2.2 - Stormwater Management
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - On Site
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Mudtanks bunded or filtered to prevent mix from dropping in or runoff entering
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - No work to be commenced until protections in place
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 2.3 - Traffic Management - Setup
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Traffic Management Plan
label | FREQ. - Before work commences each day
label | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
checkpoint | 2.4 - Milling Depths
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - On Site
label | FREQ. - Measure each side of milling machine cut
label | ACCEPTANCE CRITERIA - Every 10m. Depth matches target
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Milling String Sheets or photos of depths taken and uploaded to CONQA
label | RESPONSIBLE PERSON - Site Foreperson / QA
holdpoint | HOLD POINT
checkpoint | 2.5 - Service Covers Preparation
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - On site measurements & photos
label | FREQ. - All Covers
label | ACCEPTANCE CRITERIA - Hand excavation around ironwork and adjustment to desired level (if required)
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
checkpoint | 2.6 - Additional Surfacing Preparation
label | – Side Roads
label | – Accesses
label | – Driveways
label | – Dish Channels
label | – High Shoulders
label | VERIFICATION ACTIVITY - Visual Check
label | METHODS OR REFERENCE - Per Design
label | FREQ. - Before Membraning and Paving
label | ACCEPTANCE CRITERIA - Have all areas of additional surfacing on the design been prepared, membraned and marked for paving?
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold Point – All areas planned for AC are prepared ready for surfacing layer
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
checkpoint | 2.7 - Milling Surface inspection / walkover
label | VERIFICATION ACTIVITY - Visual Check, proof roll with loaded truck to check deflections
label | METHODS OR REFERENCE - On site measurements & photos
label | FREQ. - Prior to surfacing
label | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree if any additional overmilling is required
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint | HOLD POINT
checkpoint | 2.8 - Over-Milling
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - On site measurements & photos
label | FREQ. - Prior to pre-level
label | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 2.9 - Pre-Level
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - On site measurements & photos
label | FREQ. - Prior to surfacing
label | ACCEPTANCE CRITERIA - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - Inspection and agreement by NZTA
label | RESPONSIBLE PERSON - Paving Supervisor / Paving Manager
holdpoint | HOLD POINT
checkpoint | 2.10 - Membrane Sealing
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - On Site
label | FREQ. - Prior to surfacing
label | ACCEPTANCE CRITERIA - Membrane seal meets design and extent. Sealing Docket record kept
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
section | Paving Structural
checkpoint | 3.1 - Production Properties - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 3.1 - Production Properties - Binder Content
label | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 3.1 - Production Properties - Maximum Specific Gravity
label | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Per Mix design
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 3.2 - Preparation
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - Prior to Shift
label | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 3.3 - Joins
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - Prior to Shift
label | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 3.4 - Mix Inconsistency and Deficiency
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - Continuous
label | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
checkpoint | 3.5 - Load Locate
label | VERIFICATION ACTIVITY - Measurement
label | FREQ. - Every Load
label | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | – Truck ID/Rego/Driver
label | – Depart Plant Time
label | – Arrive Site Time
label | – AC Temp on Arrival
label | – Ground Temp on Arrival
label | – Tonnage
label | – Run Width
label | – Estimated Run Length
label | – Calculated Area
label | – Calculated Average Depth
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Per standard practice
label | RESPONSIBLE PERSON - Quality Assurance Engineer
checkpoint | 3.6 - Laying Temperature
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - Every Load
label | ACCEPTANCE CRITERIA - Arrival temperature 150°C (±10°) checked for every load
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - Reject mix for non- compliant temperatures.
label | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint | HOLD POINT
checkpoint | 3.7 - Compaction
label | VERIFICATION ACTIVITY - NDM Testing
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - Minimum:
label | ○ 1 Test per 300m² within Mat.
label | ○ 1 Test per 100m of joint.
label | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold Point - No Wearing course paved until any non-compliance is sorted. PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | RESPONSIBLE PERSON - Quality Assurance Engineer
holdpoint | HOLD POINT
checkpoint | 3.8 - Roughness
label | VERIFICATION ACTIVITY - N/A
label | METHODS OR REFERENCE - N/A
label | FREQ. - N/A
label | ACCEPTANCE CRITERIA - N/A
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
section | Paving Wearing Course
checkpoint | 4.1 - Production Properties - PSD (Particle Size Distribution)
label | VERIFICATION ACTIVITY - Sieve analysis of fine and coarse aggregates and material finer than 75µm by washing
label | METHODS OR REFERENCE - ASTM C136-06 / C 117-14
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 4.1 - Production Properties - Binder Content
label | VERIFICATION ACTIVITY - Quantitiive Extraction of Bitumen from Bituminous Paving Mixtures by Bowl Centrifuge Method
label | METHODS OR REFERENCE - B19 Issue 6 - 2009
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Job Mix Formula and NZTA M/10 Table 5.3 tolerances
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 4.1 - Production Properties - Maximum Specific Gravity
label | VERIFICATION ACTIVITY - Theoretical Maximum Specific Gravity & Density of Bituminous Paving Mixtures
label | METHODS OR REFERENCE - ASTM D2041/D2041M - 2011
label | FREQ. - 1 per 200t or maximum of 3 per production lot
label | ACCEPTANCE CRITERIA - Per Mix design
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - IANZ Lab Reports. Becomes a Hold Point for future paving if there is non- comformance
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 4.2 - Preparation
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - NZTA M/10
label | ACCEPTANCE CRITERIA - Paving plan to be completed for every shift, with dimensions
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Paving Plan and Crew Briefing Plan completed prior
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 4.3 - Joins
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - Prior to Shift
label | ACCEPTANCE CRITERIA - Joins are outside of trafficked wheel paths where possible.
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 4.4 - Membrane Sealing
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - Prior to Paving
label | ACCEPTANCE CRITERIA - application rate as per TAC design
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold Point - No paving until Membrane Done. Ensure correct application of chip & emulsion
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 4.5 - Mix Inconsistency and Deficiency
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - Continuous
label | ACCEPTANCE CRITERIA - Visually check asphalt surface during paving for areas of segregation
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Site Foreperson
holdpoint | HOLD POINT
checkpoint | 4.6 - Load Locate
label | VERIFICATION ACTIVITY - Measurement
label | FREQ. - Every Load
label | ACCEPTANCE CRITERIA - Each load can be indentified to a location using a diagram. Record includes:
label | – Truck ID/Rego/Driver
label | – Depart Plant Time
label | – Arrive Site Time
label | – AC Temp on Arrival
label | – Ground Temp on Arrival
label | – Tonnage
label | – Run Width
label | – Estimated Run Length
label | – Calculated Area
label | – Calculated Average Depth
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Per standard practice
label | RESPONSIBLE PERSON - Quality Assurance Technician.
checkpoint | 4.7 - Laying Temperature
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - Every Load
label | ACCEPTANCE CRITERIA - Based on Mix design
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point - Reject mix for non- compliant temperatures.
label | RESPONSIBLE PERSON - Quality Assurance Technician
holdpoint | HOLD POINT
checkpoint | 4.8 - Compaction
label | VERIFICATION ACTIVITY - PQI Non-Nuclear Gauge/Cores. Or Non Distrctive Method Testing.
label | METHODS OR REFERENCE - NZTA M/10
label | FREQ. - As per Agreed on Contract.
label | ACCEPTANCE CRITERIA - Mat: Air voids JMF +3,-2 Join: Air voids JMF +5,-2
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - PQI / Core recorded with RP, lane, offset, date, air voids. Core results received within 2 weeks.
label | RESPONSIBLE PERSON - Quality Assurance Technician / Paving Manager
section | Site Reinstatement / Clearance
checkpoint | 5.1 - Post-seal Area Check
label | VERIFICATION ACTIVITY - Measurement
label | METHODS OR REFERENCE - On Site tape- measure
label | FREQ. - After Surfacing
label | ACCEPTANCE CRITERIA - Check sealed area meets design
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Notify Renewals Engineer or Renewals Manager
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 5.2 - Service Covers
label | VERIFICATION ACTIVITY - Measurement/Visual
label | METHODS OR REFERENCE - On Site
label | FREQ. - After Surfacing
label | ACCEPTANCE CRITERIA - All service covers are checked and adjusted (if necessary) to finished level (+10mm, -0mm)
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 5.3 - Joint Sealing
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - On Site
label | FREQ. - After Surfacing
label | ACCEPTANCE CRITERIA - Check cold joints are bandage sealed
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 5.4 - Road Marking
label | VERIFICATION ACTIVITY - MOTSAM
label | METHODS OR REFERENCE - Visual inspection
label | FREQ. - All markings
label | ACCEPTANCE CRITERIA - Replaced in same position, or per design
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until markings reinstated
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 5.5 - Other Traffic Services - Marker pegs/ Signs/Markings/RRP Ms Replaced
label | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | METHODS OR REFERENCE - Visual inspection
label | FREQ. - All signs/markers
label | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | INSPECTORATE W/H: Type - H
label | INSPECTORATE W/H: Description - Hold point – Site TTM cannot be removed until marker pegs, signs, markings and RRPMs reinstated
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 5.6 - Stormwater Management Controls removed
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - All installed measures
label | ACCEPTANCE CRITERIA - Installed controls are removed
label | INSPECTORATE W/H: Type - H
label | RESPONSIBLE PERSON - Paving Supervisor
holdpoint | HOLD POINT
checkpoint | 5.7 - Traffic Management Removed
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - When safe, after all physical works completed
label | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 5.8 - Site left clean & tidy
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - After vacating site
label | ACCEPTANCE CRITERIA - Stockpiles removed, Plant removed, Litter cleared from site
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Invite NZTA to carry out joint site inspection to inspect site.
label | RESPONSIBLE PERSON - Paving Supervisor
section | As Built Records
checkpoint | 6.1 - Collect asset data
label | VERIFICATION ACTIVITY - SHDOM (SM050)
label | FREQ. - During construction
label | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | INSPECTORATE W/H: Type - W
label | RESPONSIBLE PERSON - Paving Supervisor
checkpoint | 6.2 - Enter asset data into RAMM and/or register(s)
label | VERIFICATION ACTIVITY - SHDOM (SM050)
label | METHODS OR REFERENCE - RAMM
label | FREQ. - At completion of work.
label | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Data entered by 20th of follow month after month of completion
label | RESPONSIBLE PERSON - Asset Information Manager
checkpoint | 6.3 - Construction Completion Report
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - Contract Specification
label | FREQ. - At completion of work.
label | ACCEPTANCE CRITERIA - Checked and approved
label | INSPECTORATE W/H: Type - W
label | INSPECTORATE W/H: Description - Completed within two months after Paving Wearing Course
label | RESPONSIBLE PERSON - Renewals Engineer/ Renewals Manager
checkpoint | Quality Assurance Close Out by:
textbox | (name):
date | Date:
label | This record to contract file.
holdpoint | (signature)