## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 004 - Earthworks Cut |  |  |  |  | Yes | ITP-004 - Earthworks Cut | 46bb3171-5048-4e01-ba74-7b262ae04ed8
section | 1.0 Pre-Construction
checkpoint | 1.01 - Approved CWP
label | Method/Description - Document Review
label | Test frequency - Prior to personal starting
label | Constructor - H
label | Verifying Records - signed off CWP
checkpoint | 1.02 - IFC issued
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Constructor - H
label | Verifying Records - IFC drawings or written approval from PAB
checkpoint | 1.03 - Approved SCWMP
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Constructor - H
label | Verifying Records - Approved SCWMP
section | 2.0 During Construction
checkpoint | 2.01 - Set out extents
label | Method/Description - Survey/visual
label | Test frequency - Prior to Commencement
label | Constructor - H
label | Verifying Records - Earthworks Cut Checklist dsr reports
checkpoint | 2.02 - Verify Machine Control
label | Method/Description - Survey/visual
label | Test frequency - Daily
label | Constructor - W
label | Verifying Records - Plant Pre Starts
checkpoint | 2.03 - Assess Crest detail
label | Method/Description - Hand augers/ slope assess
label | Test frequency - Prior to Excavation
label | Constructor - H
label | Designer - H
label | Verifying Records - Earthworks Cut Checklist dsr reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04.01 - Install crest detail: Soil Nailing
label | Method/Description - Visual Inspection
label | Test frequency - Prior to cutting rock slope
label | Constructor - H
label | Designer - H
label | Verifying Records - Sub Contractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04.02 - Install crest detail: Erosion Matting
label | Method/Description - Visual Inspection
label | Test frequency - Prior to cutting rock slope
label | Constructor - H
label | Designer - W
label | Verifying Records - Sub Contractor QA Records
checkpoint | 2.05 - Cut Face inspection: Cut Face inspection
label | Method/Description - Survey check by construction team, visual inspection by designer.
label | Test frequency - 100m2 or maximum 5m vertical cut
label | Constructor - H
label | Verifying Records - Earthworks Cut Checklist, Survey record, As-built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.06 - Cut Face inspection: Cut face material verification - Geo mapping
label | Method/Description - Geo inspection and face mapping
label | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
label | Constructor - H
label | Designer - H
label | Verifying Records - Earthworks Cut Checklist dsr reports, And face map from geotechnical engineer/geologist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Install Rock Drape: Set out drape anchorages
label | Method/Description - Geo walk over
label | Test frequency - Prior to drilling
label | Constructor - H
label | Designer - H
label | Verifying Records - Sub Contractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.08 - Install Rock Drape: Install anchors
label | Method/Description - Drill and grout records. Stressing records.
label | Test frequency - During construction and at end
label | Constructor - H
label | Designer - H
label | Verifying Records - Sub Contractor QA Records. Calibration certificates for stressing equipment.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.09 - Install Rock Drape: Install Drapes
label | Method/Description - Visual inspection
label | Test frequency - During construction and at end
label | Constructor - H
label | Designer - H
label | Verifying Records - Sub Contractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Install Rock Bolts
label | Method/Description - Drill and grout records. Stressing records.
label | Test frequency - During construction and at end
label | Constructor - H
label | Designer - H
label | Verifying Records - Sub Contractor QA Records. Calibration certificates for stressing equipment.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Catch Ditch Inspection
label | Method/Description - Visual inspection
label | Test frequency - During construction and at end
label | Constructor - W
label | Designer - H
label | Verifying Records - EarthworksCut Checklist
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Post Construction
checkpoint | 3.01 - Rock Fall Test
label | Method/Description - Visual inspection
label | Test frequency - After catch ditch is formed at each rock cutting site
label | Constructor - H
label | Designer - H
label | Verifying Records - Designer assessment Memo
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.02 - Survey As-builts
label | Method/Description - Survey As-built
label | Test frequency - During construction and at end
label | Constructor - H
label | Verifying Records - Digital file
checkpoint | 3.03 - Monitoring Data
label | Method/Description - Visual inspection and review of monitoring data review.
label | Test frequency - End of construction
label | Constructor - H
label | Designer - H
label | Verifying Records - Digital file
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.04 - Red Line Mark Ups
label | Method/Description - Red Pen Mark up
label | Test frequency - End of construction
label | Constructor - H
label | Designer - W
label | Verifying Records - Red Pen mark ups
section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
holdpoint | SIGNATURE
checklist | ITP - 011 - Fill 15 | itp |  |  |  | Yes | ITP-011 - Fill 15 | 56cfed4c-fc80-4fa7-9f5f-38e8f24799d6
section | 1.1.0 Pre-construction Approvals
checkpoint | 1.1.1 - Construction Environmental Management Plan
label | Method/Description - Document Review
label | Test frequency - Prior to work starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CEMP
checkpoint | 1.1.2 - Construction Work Plan
label | Method/Description - Document Review
label | Test frequency - Prior to personal starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.1.3 - IANZ accredited testing organisation
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - IFC's specification
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - IFC drawings
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.6 - Approved earthworks model
label | Method/Description - Document Review
label | Test frequency - Every new Earthworks Model and prior to work commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - ?
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.7 - Approval of stockpile location
label | Method/Description - Document Review & Approval
label | Test frequency - Prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - ?
holdpoint | AUTHORITY HOLDPOINT
section | 1.2.0 Material Compliance
checkpoint | 1.2.1 - Structural fill
label | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
label | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
label | • Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8
label | Test frequency - 1 test per 20,000m³
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Buttress Fill
label | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
label | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
label | Test frequency - 1 test per 20,000m3
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.3 - GAP 65
label | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.3
label | • NZS 4402 Supplement No 1:1998 - Test 3.8.1 Determination of the particle size distribution Standard method by wet sieving
label | • Large shear box (min 3 normal stresses) - BS 1377 Part 7: 1990. Methods of tests for Soils for civil engineering purposes – Part 7 : Shear strength tests (total stress).Test 5 – Determination of shear strength by direct shear (large shear box apparatus)
label | Test frequency - Determination of the dry density/water content - 3 tests per source.
label | • PSD - 3 no. tests per source + 1 test per 2,000m3.
label | • Permeability, Large shear box (min 3 normal stresses) - 3 no. tests per source
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.4 - GAP 65
label | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
label | Test frequency - 3 no. tests per source and 1 test per 2000m3
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.5 - Cement stabilised structural fill
label | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
label | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
label | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
label | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
label | • Atterberg limit - 1 test per source and 1 test per 500 m3
label | • UCS - 3 no. tests per source at adopted cement ratio.
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.6 - MSE Fill
label | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
label | Test frequency - 3 no. tests per source and 1 test per 2500m3
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.8 - Cement stabilised GAP 65
label | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
label | • NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving
label | • NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer
label | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
label | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
label | • PSD - 3 no. tests per source + 1 test per 2,000 m3
label | • UCS - 3 no. tests per source at adopted cement ratio.
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.9 - Cement stabilised structural fill
label | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
label | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
label | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
label | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
label | • Atterberg limit - 1 test per source and 1 test per 500 m3
label | • UCS - 3 no. tests per source at adopted cement ratio.
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
section | 1.3.0 Geosynthetics, geogrid and basal reinforcement - Pre-construction
checkpoint | 1.3.1 - Product name Name and address of producer/supplier Manufacturer’s compliance certificate
label | Method/Description - Document Review
label | Test frequency - Check each lot (1 roll)
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
checkpoint | 1.3.2 - Tensile strength (machine direction) - geogrid and basal reinforcement
label | Method/Description - Document Review
label | Test frequency - 1 test per production batch
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
checkpoint | 1.3.3 - Visual inspection - separation geotextiles, basal reinforcement
label | Method/Description - To inspect geotextile and basal reinforement is the proper type and no tears, rips or other signs of deterioration.
label | Test frequency - Check each lot (1 roll)
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Approval checklist
checkpoint | 1.3.4 - Visual inspection - geogrids
label | Method/Description - To inspect geogrid is the proper type and no tears, rips or other signs of deterioration.
label | Test frequency - Check each lot (1 roll)
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Approval checklist
section | 1.4.0 Monitoring - Pre-construction
checkpoint | 1.4.1 - Monitoring prior to preload
label | Method/Description - Baseline readings
label | Test frequency - Settlement marker, extensometer, profilometer, and lateral deformation markers - 1 month before construction start. 2 consistent readings (24 hrs apart) post installation and one immediately prior to filling Vibrating wire piezometer - 1 month
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary - confirming baseline readings satisfactory
holdpoint | AUTHORITY HOLDPOINT
section | 2.1.0 Pre-filling
checkpoint | 2.1.1 - Set out extents of fill and check against design
label | Method/Description - Survey/visual
label | Test frequency - Prior to Commencement
label | Contractor - W
checkpoint | 2.1.2 - Vegetation Clearance
label | Method/Description - Survey/visual
label | Test frequency - Fill area foot print
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet Designer site report (where advise given)
checkpoint | 2.1.4 - Designer witness of in-situ subgrade prior to filling
label | Method/Description - Visual inspection
label | Test frequency - Prior to Filling
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.5 - General Undercuts
label | Method/Description - Visual inspection
label | Test frequency - Prior to Filling
label | Contractor - I
label | Designer - I
label | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
checkpoint | 2.1.6 - Required undercuts for basal reinforcement installation
label | Method/Description - Visual inspection
label | Test frequency - Prior to Filling
label | Contractor - H
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.7 - Basal reinforcement installation
label | Method/Description - Visual inspection of directional placement, panel length, laps, and damage
label | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
label | Contractor - H
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.8 - Drainage blanket installation
label | Method/Description - Visual inspection
label | Test frequency - Prior to filling, and every 100m2 of geotextile installed.
label | Contractor - H
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.9 - Construction of wick drains
label | Method/Description - Visual inspection and subcontractor record review
label | Test frequency - During wick drain construction
label | Contractor - I
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Wick drain check list
checkpoint | 2.1.10 - Sub soil drainage
label | Method/Description - Inspection
label | Test frequency - During subsoil construction
label | Contractor - I
label | Designer - I
label | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
checkpoint | 2.1.11 - Monitoring Equipment
label | Method/Description - Survey/ data logging
label | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
label | Contractor - W
label | Verifying Records Checklists, Test and Supplier Certificates - Drill logs
section | 2.2.0 Fill Construction
checkpoint | 2.2.1 - Filling operations
label | Method/Description - Visual inspection
label | Test frequency - Daily
label | Contractor - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.2 - Filling operations
label | Method/Description - Survey/visual
label | Test frequency - Daily
label | Contractor - W
label | Verifying Records Checklists, Test and Supplier Certificates - test report
checkpoint | 2.2.3 - Insitu fill testing
label | Method/Description - Plateau Test
label | Test frequency - Structural Fill - 1 test per material type per earthworks zone,
label | • Buttress Fill - 1 test per material type per earthworks zone
label | • GAP65 - 1 test per material type per structure / location
label | • Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.4 - Insitu fill testing
label | Method/Description - In situ moisture content and density
label | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length (approx 1 per 3000 m3) ; 1 test per lift per 50m length for top 1m of fill to subgrade level
label | • Buttress fill - 1 test per 200m length, approx 1 per 6000 m3
label | • GAP65 - 4 tests per lift per structure
label | • Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
label | • Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
label | Contractor - W
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.5 - Insitu fill testing
label | Method/Description - Undrained shear Strength
label | Test frequency - Structural fill - 1 test per layer per 1000m2
label | • Buttress Fill - 1 Test per layer per 2000m2
label | • Cement Stabilised Structural Fill - 1 test per layer per 500m2
label | Contractor - W
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.6 - Pavement Subgrade Fill Testing
label | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
label | Test frequency - Surcharged Fills - 1 test at subgrade formation level per 50m length, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth
label | Contractor - W
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.7 - Pavement Subgrade Fill Testing
label | Method/Description - Scala Penetrometer Surcharged Fills
label | Test frequency - 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width
label | Contractor - W
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.8 - Pavement Subgrade Fill Testing
label | Method/Description - Benkelman beam and FWD Testing
label | Test frequency - Surcharged Fills - At subgrade formation level 10m interval in each wheel path
label | • Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
label | Contractor - W
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.9 - Pavement Subgrade Fill Testing
label | Method/Description - Laboratory Soaked CBR
label | Test frequency - Surcharged Fills and Cut Fill Transitions - 1 Test per 5000m2 at subgrade formation level
label | Contractor - W
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.10 - Confirm testing requirements are meet for insitu fill
label | Method/Description - Summarise, interpret and review test records
label | Test frequency - Every test result
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Review of testing records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.11 - Failed test result and remedial approval
label | Method/Description - Review and approval of remedial action
label | Test frequency - Every failed test and prior to remedial works
label | Contractor - H
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.12 - Insitu Fill Testing
label | Method/Description - Undrained shear Strength
label | Test frequency - Structural fill - 1 test per layer per 1000m2
label | • Buttress Fill - 1 Test per layer per 2000m2
label | • Cement Stabilised Structural Fill - 1 test per layer per 500m2
label | Contractor - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
section | 2.3.0 Preload/Surcharge (for embankments requiring preload)
checkpoint | 2.3.1 - Visual inspection for rate of filling
label | Method/Description - Inspection of fill height, rate of filling of 200mm/day (1m per week)
label | Test frequency - To be monitored daily
label | Contractor - H
label | Designer - W
checkpoint | 2.3.2 - After 1m of fill placement. Await approval from Designer before placing more fill.
label | Method/Description - Review data and TARP levels before releasing HOLD.
label | Test frequency - Before releasing hold periods and allowing filling to continue.
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.3 - Removal of preload/surcharge
label | Method/Description - Assessment of monitoring and instrumentation data
label | Test frequency - After completion of proposed hold period
label | Contractor - H
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
section | 2.4.0 Monitoring
checkpoint | 2.4.1 - During earth filling/preloading/surcharging
label | Method/Description - Monitoring during earth filling/preloading/surcharging
label | Test frequency - Plate settlement marker, extensometer, profilometer, water standpipe, and lateral deformation marker- twice weekly Vibrating wire piezometer - hourly reading via data logger, twice weekly download
label | Contractor - W
checkpoint | 2.4.2 - During preload or surcharge hold period
label | Method/Description - Monitoring during preloading or surcharge hold period
label | Test frequency - Plate settlement marker, extensometer and profilometer, and lateral deformation marker - twice weekly for the first month then weekly. Vibrating wire piezometer - hourly reading via data logger, twice weekly download
label | Contractor - W
checkpoint | 2.4.3 - At surcharge removal or hold period release
label | Method/Description - Monitoring at surcharge removal or hold period release
label | Test frequency - Plate settlement marker, extensometer and profilometer, lateral deformation marker, and vibrating wire piezometer - one reading 24 hours prior and one reading 24 hours following.
label | Contractor - W
section | 2.5.0 Monitoring reports
checkpoint | 2.5.1 - Preliminary inspection/monitoring report
label | Method/Description - Summary of site inspection / observation / measurement
label | Test frequency - Within one working day of site inspection/observation/measurement
label | Contractor - W
checkpoint | 2.5.2 - Inspection/ monitoring report
label | Report - Full and certified results
label | Frequency/timing - Within five working days of reading the particular instrument
label | Owner - Construction Team and Geotechnical Technician
label | Distribution - Geotechnical Engineer, Geotechnical Lead
checkpoint | 2.5.3 - Pre surcharge removal report
label | Report - Comparison between monitored results and baseline design predictions in both table and graphical format. Provide approval to remove surcharge.
label | Frequency/timing - Prior to surcharge removal at each fill
label | Owner - Geotechnical Engineer (with Geotechnical Lead approval)
label | Distribution - Design Manager, Construction Manager
section | 3.0 Post Construction
checkpoint | 3.2 - Survey As-builts
label | Test frequency - During construction and at end
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - CAD files
checkpoint | 3.3 - As-builts
label | Method/Description - Mark up of construction drawings to reflect completed works
label | Test frequency - End of Construction or after completion of preload/surcharge works
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
holdpoint | SIGNATURE
checklist | ITP - 012 - Concrete Culvert | itp |  |  |  | Yes | ITP-012 - Concrete Culvert | 4f45d31a-7812-407a-96f9-09c844036807
section | 1.1.0 Pre-construction approvals
checkpoint | 1.1.1 - Construction Environmental Management Plan
label | Method/Description - Document Review
label | Test frequency - Prior to work starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed CEMP
checkpoint | 1.1.2 - Construction Work Plan
label | Method/Description - Document Review
label | Test frequency - Prior to work starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.1.3 - IANZ accredited testing organisation
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - IFC's specification
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC specifications or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - IFC drawings
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.6 - Approved Drainage Strings
label | Method/Description - Document Review
label | Test frequency - Every new Drainage Line and prior to work commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC Cover Form
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.7 - Approval of stockpile location
label | Method/Description - Document Review & Approval
label | Test frequency - Prior to works commencing
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Written approval from DSR
section | 1.2.0 Material compliance
checkpoint | 1.2.1 - Materials - pipes and fittings
label | Method/Description - Confirm pipe diameter, class and jointing type as shown on the drawings and that pipes are in correct and good condition.
label | Test frequency - Each delivery to site
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check Sheet
checkpoint | 1.2.2 - Materials – pipes and pre-cast units (wingwalls)
label | Method/Description - Specification compliance – manufacturer’s certificate to TNZ F/3 for pipe and pre-cast units
label | Test frequency - Each delivery to site
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Compliance Cettifcates
checkpoint | 1.2.3 - Materials – Grading for Bedding, Haunch and Sides Zones AP20
label | Method/Description - NZS 4407 Test 3.8.1 (or similar approved) Determination of the particle size distribution Standard method by wet sieving
label | Test frequency - 2 per 400m3, 3 per 400-1500m3, 4 per 1500-4000m3 and for over 4000m3, 1 additional test per 1000 m3
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.4 - Materials – Testing for Bedding, Haunch and Sides Zones AP20
label | Method/Description - Determination of the linear shrinkage NZS 4402.2.6, Determination of the Weathering Index NZS 4407.3.11, Determination of the Crushing Resistance NZS 4407.3.10
label | Test frequency - 2 per source then 1 per 1000 m3
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.5 - Materials – Compaction Curves Bedding, Haunch and Sides Zones AP20
label | Method/Description - Establish a relationship between MDD and DI (density index) to determine the target MDD (NZS 4402.4.2.1 for the minimum dry density and NZS4402.4.2.2 for the maximum dry density).
label | Test frequency - 3 no. tests per source with minimum 5 points
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.6 - Materials - Grading GAP 65
label | Method/Description - NZS 4407 Test 3.8.1 (or similar approved) Determination of the particle size distribution Standard method by wet sieving
label | Test frequency - 2 per 400m3, 3 per 400-1500m3, 4 per 1500-4000m3 and for over 4000m3, 1 additional test per 1000 m3
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Reports
checkpoint | 1.2.7 - Materials - Testing GAP 65
label | Method/Description - Determination of the Weathering Index NZS 4407.3.11, Determination of the Crushing Resistance NZS 4407.3.10
label | Test frequency - 2 per source then 1 per 1000 m3
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Reports
checkpoint | 1.2.8 - Materials – Compaction Curves GAP 65
label | Method/Description - Establish the optimum moisture content and minimum and maximum dry density. NZS4402 Supplement No 1:1988 - Test 4.1.1 or similar approved
label | Test frequency - 3 no. tests per source with minimum 5 points
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.9 - Materials - Structural Fill and for Overlay Zones
label | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2, Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4, Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8
label | Test frequency - 1 test per 20,000m3
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.10 - Material - Rip Rap - Grading
label | Method/Description - NZS 4407 Test 3.8.1 (or similar approved) Determination of the particle size distribution Standard method by wet sieving
label | Test frequency - 1 per source then 1 per 500 m3
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.11 - Material - Rip Rap
label | Method/Description - Determination of: Weathering Index Coarse Aggregate dry density NZS4407.3.11, Crushing Resistance of Coarse Aggregate NZS4407.3.10, Solid Density of Aggregate NZS4407.3.7.1 & 2, Point Load Strength ASTM D5731, UCS Rock AS4133.4.2.2
label | Test frequency - 1 per source then 1 per 1000 m3
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
section | 1.3.0 Geosynthetics
checkpoint | 1.3.3 - Visual inspection - geotextiles
label | Method/Description - To inspect geotextile and is the proper type and no tears, rips or other signs of deterioration.
label | Test frequency - Check each lot (1 roll)
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checklist
checkpoint | 1.3.4 - Geotextiles
label | Method/Description - Specification compliance – manufacturer’s certificate to TNZ F/7 2003
label | Test frequency - Check each lot (1 roll)
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Manufactures Certifcate
section | 2.1.0 Trench Excavation
checkpoint | 2.1.1 - Trench Subgrade
label | Method/Description - Testing trench foundation material to assess is undercut is required. Scala penetrometer test as per NZS4402.6.5.2 for non-cohesive materials. The CBR value of the subgrade soils shall also be measured using the in-situ CBR test in accordance with NZS4402 Test 6.1.3.
label | Test frequency - 2 nos. scala penetrometer tests / 5m of trench, 1 per ancillary structure
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 2.1.2 - Trench Benching
label | Method/Description - 1.5m benches to be constructed strating from rock (pap) top
label | Test frequency - Daily
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check List
section | 2.2.0 Pipe Bedding and Construction
checkpoint | 2.2.1 - Construction of embedment, bed, haunch and side zones using AP20
label | Method/Description - Nuclear Densometer Direct Mode NZS 4407 4.2.1 or Nuclear Densometer Backscatter Mode NZS 4407 4.3.1
label | Test frequency - 2no NDM test "sets" per 10 m max centres tests on combined lifts upto 300mm lift and minimum of test at the bottom layer, middle of pipe and top of pipe
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 2.2.2 - Construction of Overlay Zone
label | Method/Description - Nuclear Densometer Direct Mode NZS 4407 4.2.1 or Nuclear Densometer Backscatter Mode NZS 4407 4.3.1. Undrained shear Strength
label | Test frequency - 1no NDM and 1no Shear Vane Test per 20m max canters at 300mm lifts
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 2.2.3 - Construction of pipe
label | Method/Description - Visual test prior to backfill above the side zones – line and level, correct installation, and joints are all sealed.
label | Test frequency - Review every 10m and witness every 25m
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.4 - Construction of Wingwalls
label | Method/Description - Foundation and bedding testing as per pipes, using AP65 as opposed to AP20. Visual inspection of joints between pipe and wingwall
label | Test frequency - Each Wingwall
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Test report, Onsite Checksheet
checkpoint | 2.2.5 - Construction of Antiseep Collars
label | Method/Description - Antiseep collars to be embeded 200mm horizontaly into side of trench and 400mm below base of trench. To be located every second pipe joint. Concrete strength >=25MPa
label | Test frequency - Each Anti Seep Collar
label | Contractor - W
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - DSR Inspection (Pre-Pour), Pre-Pour Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.6 - Construction of Cut Off Toes
label | Method/Description - Cut off Toe to be embeded 1m (or note 4) from top of wingwall base, to be consructed as per IFC Drawings
label | Test frequency - Each Cut Off Toe
label | Contractor - W
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Pre-Pour Checksheet, Detail Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.7 - Construction of Inlet/Outlet Channels
label | Method/Description - DSR to inpect geotextiles before rip - rap is laid. Max drop heights to be adhered to when placing rip-rap
label | Test frequency - Each Channels
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Geotextile Installation Check Sheet
checkpoint | 2.2.8 - Fish Passage
label | Method/Description - 25% embedment depth with meandering low flow path from voild filled riprap. Spat ropes for CU-17
label | Test frequency - Review every 10m and witness every 25m
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checksheet
checkpoint | 2.2.9 - Construction of Safety Rail
label | Method/Description - Constructed as per IFC Drawings
label | Test frequency - Each Fence
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checksheet
section | 3.0 Post Construction
checkpoint | 3.1 - Survey/as-builts
label | Method/Description - As built survey of coordinates and invert levels, structures, and pipe ends
label | Test frequency - Every 25m
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - As-Built
checkpoint | 3.2 - Post Construction CCTV inspection
label | Method/Description - Check conformance with the specification and assess the asset condition post construction
label | Test frequency - To be completed following pipe construction but prior to spat rope installation
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - CCTV log Report as per the standard
section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
holdpoint | SIGNATURE
checklist | ITP - 009 - Geotechnical Equipment Installation |  |  |  |  | Yes | ITP-009 - Geotechnical Equipment Installation | deba3ec5-36d6-489e-888b-4d2fe8dcd74b
section | 1.0 Pre-Construction
checkpoint | 1.01 - Construction Environmental Management Plan
label | Method/Description - Document Review
label | Test frequency - Prior to personnel starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.02 - Construction Work Plan
label | Method/Description - Document Review
label | Test frequency - Prior to work starting
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.03 - IFC's specification
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
checkpoint | 1.04 - IFC drawings
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
checkpoint | 1.05 - Approved setout locations of instrumentations
label | Method/Description - Designer Confirmation
label | Test frequency - Once for every fill site prior to work commencing
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Written Confirmation from Designeer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.06 - Method Statements Approval
label | Method/Description - Document Review
label | Test frequency - Prior to installation of instrumentation
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Method Statement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.07 - Calibration of Read Out Equipment
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Calibration Certificate
section | 2.0 Material Compliance
checkpoint | 2.01 - Vibrating Wire Piezometer manufacturer specification
label | Method/Description - Document Review
label | Test frequency - Once
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Vibrating Wire Piezometer calibration
label | Method/Description - Document review of manufacturer's calibration certificate of piezometer
label | Test frequency - Delivery and acceptance of piezometer material; prior to installation
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Extensometer manufacturer specification
label | Method/Description - Document Review
label | Test frequency - Once
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Inclinometer manufacturer specification
label | Method/Description - Document Review
label | Test frequency - Once
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Inclinometer casing material
label | Method/Description - Inspection of Inclinometer Casing Materials
label | Test frequency - After Delivery and acceptance of Inclinometer Casing Materials; Prior to Installation.
label | Contractor - I - Installer Engineer W - Site Engineer
label | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
checkpoint | 2.06 - Inclinometer grouting materials
label | Method/Description - Review & approval of approved grout mix
label | Test frequency - Prior to Equipment Installation
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Inclinometer materials
label | Method/Description - Inspection of Inclinometer Measuring Equipment
label | Test frequency - After Delivery and acceptance of Inclinometer Measuring Equipment; Prior to Installation.
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 2.08 - Rod and Plate Settlement Markers
label | Method/Description - Inspection of Settlement Plate Materials
label | Test frequency - After Delivery and acceptance of Settlement Plate Materials; Prior to Installation.
label | Contractor - I
label | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
checkpoint | 2.09 - Surface settlement marker material
label | Method/Description - Inspection of Surface Settlement Marker Materials
label | Test frequency - After Delivery and acceptance of Settlement Marker Materials; Prior to Installation.
label | Contractor - W - Site Engineer
checkpoint | 2.1 - Surface monitoring marker material
label | Method/Description - Inspection of Surface Monitoring Marker Materials
label | Test frequency - After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation.
label | Contractor - W - Site Engineer
checkpoint | 2.11 - Lateral deformation marker material
label | Method/Description - Inspection of Lateral Deformation Marker Materials
label | Test frequency - After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation.
label | Contractor - W - Site Engineer
checkpoint | 2.12 - Profilometer material
label | Method/Description - Inspection of Profilometer Tubing & Backfill Materials
label | Test frequency - After Delivery and acceptance of Profilometer Tubing & Backfill Materials; Prior to Installation.
label | Contractor - I - Installer Engineer W - Site Engineer
label | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
section | 3.1.0 Vibrating Wire Piezometer Installation
checkpoint | 3.1.1 - Piezometer location per construction drawings
label | Method/Description - Inspection of borehole location
label | Test frequency - Before borehole drilling
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.1.2 - Borehole Drilling
label | Method/Description - Inspection of borehole
label | Test frequency - After borehole drilling
label | Contractor - I - Installer Engineer W - Site Engineer
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
checkpoint | 3.1.3 - Depth of piezometers
label | Method/Description - Review & approval of depths of piezometer based on the results of the core logging
label | Test frequency - After borehole drilling
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.4 - Core materials
label | Method/Description - Inspection of all retaining cores
label | Test frequency - After borehole installation
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.1.5 - Heavy duty connecting cable placement
label | Method/Description - Inspection of completed heavy duty connecting cable placement
label | Test frequency - After placement of heavy duty connecting cable
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.1.6 - Splicing of heavy duty connecting cable
label | Method/Description - Review & approval regarding acceptance of cable splicing
label | Test frequency - Prior to splicing of heavy duty connecting cable
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.7 - Readout unit/data logger placement
label | Method/Description - Inspection of completed readout unit/data logger placement
label | Test frequency - After placement of readout unit/data logger
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.1.8 - Ground surface finish of installed piezometer
label | Method/Description - Inspection After completion of the installation process of Piezometer
label | Test frequency - After completion of the installation process of Piezometer
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.1.9 - Ground surface finish of installed connecting cables
label | Method/Description - Inspection After completion of the installation process of Piezometer
label | Test frequency - After completion of the installation process of Piezometer
label | Contractor - I - Installer Engineer W - Site Engineer
label | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
section | 3.2.0 Inclinometer Installation
checkpoint | 3.2.1 - Inclinometer location per construction drawings
label | Method/Description - Inspection of Inclinometer Placement
label | Test frequency - After Placement of Inclinometer
label | Contractor - I - Installer Engineer W - Site Engineer
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Borehole drilling
label | Method/Description - Inspection of Borehole Installation
label | Test frequency - After Borehole drilling
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.2.3 - Depth of inclinometer
label | Method/Description - Review & Approval regarding depth of Inclinometer based on the results of the core logging
label | Test frequency - During Borehole drilling
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - Core materials
label | Method/Description - Inspection of all retained cores
label | Test frequency - After Borehole drilling
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.2.5 - Grouting installation
label | Method/Description - Inspection of Grouting Installation
label | Test frequency - After Grouting Installation
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.2.6 - Ground surface finish of installed inclinometer
label | Method/Description - Inspection After completion of the installation process of Inclinometer
label | Test frequency - After completion of the installation process of Inclinometer
label | Contractor - I - Installer Engineer W - Site Engineer
section | 3.3.0 Profilometer Installation
checkpoint | 3.3.1 - Profilometer tubing levels and location per construction drawings
label | Method/Description - Inspection of profilometer tubing Placement
label | Test frequency - After placement of the profilometer tubing
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.3.2 - Profilometer installation
label | Method/Description - Inspection of profilometer tubing Placement
label | Test frequency - After placement of the profilometer tubing
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.3.3 - Ground surface finish of installed profilometer
label | Method/Description - Inspection after completion of the installation process of profilometer
label | Test frequency - After completion of the installation process of profilometer
label | Contractor - I - Installer Engineer W - Site Engineer
section | 3.4.0 Rod and Plate Settlement Plate Installation
checkpoint | 3.4.1 - Settlement plate installation
label | Method/Description - Inspection of Settlement Plate Placement
label | Test frequency - Before placement of the Settlement Plate
label | Contractor - W - Site Engineer
checkpoint | 3.4.2 - Ground surface finish of installed settlement plate
label | Method/Description - Inspection After completion of the installation process of Settlement Plate
label | Test frequency - After completion of the installation process of Settlement Plate
label | Contractor - W - Site Engineer
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.5.0 Surface Settlement Marker Installation
checkpoint | 3.5.1 - Ground surface finish of installed surface settlement marker
label | Method/Description - Inspection After completion of the installation process of Surface Settlement Marker
label | Test frequency - After completion of the installation process of Settlement Marker
label | Contractor - W - Site Engineer
section | 3.6.0 Surface Monitoring Marker Installation
checkpoint | 3.6.1 - Ground surface finish of installed surface monitoring marker
label | Method/Description - Inspection After completion of the installation process of Surface Monitoring Marker
label | Test frequency - After completion of the installation process of Surface Monitoring Marker
label | Contractor - W - Site Engineer
section | 3.7.0 Lateral Deformation Marker Installation
checkpoint | 3.7.1 - Ground surface finish of installed lateral deformation marker
label | Method/Description - Inspection After completion of the installation process of Lateral Deformation Marker
label | Test frequency - After completion of the installation process of Surface Monitoring Marker
label | Contractor - W - Site Engineer
section | 3.8.0 UAV Survey/Face Scan
checkpoint | 3.8.1 - Ground surveys using unmanned aerial vehicles (UAVs)
label | Method/Description - Survey
label | Test frequency - 1. Prior to any ground disturbance; 2. Upon completion of vegetation and topsoil strip; 3. Regular intervals as fill embankments are raised (maximum of 5m fill placed between surveys) and cuttings are formed (maximum 10m depth increments between surveys); 4. Upon reaching final surcharge heights for preload embankments and final embankment heights where no surcharge is required, and full cut depths; 5. Monthly intervals during the earthworks operations and at the end/commencement of each earthworks season; 6. Following removal of surcharge and final embankment profiles have been formed; 7. Immediately prior to pavement construction; 8. At completion of pavement construction; 9. Practical Completion; 10. Every 3 months during Defects Liability Period; 11. End of Defects Liability Period. Face scans of rock cuttings shall be completed as each cutting is advanced in increments of 10m and at maximum three monthly intervals thereafter during the earthworks season and at commencement and end of each earthworks season. Scans shall have an accuracy of ±100mm and repeat surveys shall be able to compared to previous surveys to assess potential surface movements between surveys using 3D Reshaper software or similar.
label | Contractor - W - Site Engineer
section | 3.9.0 Extensometer Installation
checkpoint | 3.9.1 - Extensometer location per construction drawings
label | Method/Description - Inspection of extensometer Placement
label | Test frequency - After Placement of extensometer
label | Contractor - I - Installer Engineer W - Site Engineer
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9.2 - Borehole Drilling
label | Method/Description - Inspection of Borehole Installation
label | Test frequency - After Borehole drilling
label | Contractor - I - Installer Engineer W - Site Engineer
checkpoint | 3.9.3 - Extensometer tubes
label | Method/Description - Inspection of Grouting Installation
label | Test frequency - After Grouting Installation
label | Contractor - W - Site Engineer
checkpoint | 3.9.4 - Spider magnets
label | Method/Description - Review & Approval regarding depth of based on the results of the core logging
label | Test frequency - During Borehole drilling
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9.5 - Reading and recording settlement
label | Method/Description - Inspection after completion of the installation process
label | Test frequency - After completion of the installation process
label | Contractor - W - Site Engineer
section | 3.10.0 Reflected Survey Marker Installation
checkpoint | 3.10.1 - Reflective survey target marker installation
label | Method/Description - Inspection of Reflective Survey Target Marker Placement
label | Test frequency - Before placement of the Reflective Survey Target Marker
label | Contractor - W - Site Engineer
checkpoint | 3.6.1 - Reflective survey target marker installation completion
label | Method/Description - Inspection After completion of the installationof Reflective Survey Target Marker
label | Test frequency - After completion of the installation process of Reflective Survey Target Market
label | Contractor - W - Site Engineer
section | 4.0 Completion of Instrumentation Installation
checkpoint | 4.01 - Vibrating Wire Piezometer completion of placement
label | Method/Description - Document Review submitted through Hold Point
label | Test frequency - After Piezometer Completion of Placement
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Inclinometer Completion of Placement
label | Method/Description - Document Review submitted through Hold Point
label | Test frequency - After Inclinometer Completion of Placement
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Profilometer Completion of Placement
label | Method/Description - Document Review submitted through Hold Point in Aconex
label | Test frequency - After Profilometer Completion of Placement
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04 - Instrument has been received and approved by the Designer
label | Method/Description - Document Review submitted through Hold Point in Aconex
label | Test frequency - After Completion of Instrumentation Installation
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.05 - If an instrument is blocked, obstructed or damaged
label | Method/Description - Inspection and Document Review
label | Test frequency - After completion of the remedials work on the instrument
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
section | 5.0 Monitoring
checkpoint | 5.01 - Base Line Readings
label | Method/Description - Survey
label | Test frequency - Per individual piece of equipment refer to ITPs for embankment/earthworks and cut slopes
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
holdpoint | AUTHORITY HOLDPOINT
section | 6.0 Verification Testing
checkpoint | 6.01 - Cone Penetration Tests with Measurement of Porewater Pressure (Piezocone) on embankments constructed on soft ground.
label | Method/Description - Document Review
label | Test frequency - Following surcharge removal or as directed by the Geotechnical Designer
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.02 - Geonor Shear Vane Test in Borehole
label | Method/Description - Document Review
label | Test frequency - Following surcharge removal or as directed by the Geotechnical Designer
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
holdpoint | AUTHORITY HOLDPOINT
section | 7.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
holdpoint | SIGNATURE