## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-000 - Client Pre-Construction Checklist Rev1 | itp |  |  |  |  | ITP-000 - Client Pre-Construction Checklist Rev1
section | Pre - Construction Works
checkpoint | 1.1 Asphalt - submission of asphalt mix design
label | FREQUENCY: Prior to commencing asphalt
label | ACCEPTANCE CRITERIA: Ensure the mix design/s have been registered and are approved by Superintendent prior to laying mix.
label | REFERENCE DOCUMENTS: VicRoads Spec.Cl.407.09. RAP DoT letter from production plant
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from the RAP DoT Letter.
label | RECORD OF CONFORMITY: Superintendent approval via hold point release
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 Concrete - submission & approval of concrete mix design prior to commencement of project
label | FREQUENCY: Prior to first concrete pour
label | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour. Mix shall contain minimum 460 kg/m3 cement content. Special 50 mPa mix is to be VS502B25MET1 with a suitably flowable design slump agreed prior to construction.
label | REFERENCE DOCUMENTS: CE-019-ST- 0033 VicRoads Spec.Cl. 503.04
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from supplier
label | RECORD OF CONFORMITY: Superintendent approval via hold point release
label | HP
label | RESPONSIBILITY: FH Engineer / Superintendent
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 Welders qualifications, competencies & work methodology
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Weld methodology to be submitted prior to commencement of works. Welders shall be trained and compliant in Australian aluminothermic welding competencies as outlined below;
label | – TLIW2012 Grind Rails
label | – TLIW3015 Weld Rails using Aluminothermic welding process
label | – TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
label | REFERENCE DOCUMENTS: CE-019-ST- 0033 Appendix C
label | INSPECTION/TEST METHOD: Welding methodology
label | RECORD OF CONFORMITY: Superintendent approval via hold point release
label | HP
label | RESPONSIBILITY: FH Engineer / Superintendent
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: