## Sheet1
Enviro Hydrostatic 1
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Suppoting documentations - e.g location, CIDD alerts etc.
SECTION | BATCH DETAIL NUMBER OF PRODUCTS
Checkpoint | Enviro Hydrostatic 1
Label | Records - Photograph
Label | surveillance point
SECTION | PRE COMMENCEMENT
Checkpoint | Sample Submissions
Label | Submit samples for approval as per Specific Material Requirements.
Label | Record Submissions
Checkpoint | First Of Type Inspection
Label | First of type of inspection conducted by builder prior to commencment of works taking place.
Label | Record Submissions
Checkpoint | Material Management & Storage - Envirosystems TDS
Label | Store materials in a dry, clean place away from direct sunlight as per TDS
Label | Records - Photograph
Label | Witness Point
Checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
Label | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per TDS prior to application
Label | Records - Photograph
Label | Witness Point
Checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3 and AS 4654.2
Label | Builder to confirm compliant falls; minimum 1-100 falls
Label | Hold Point
SECTION | FIRST BASE COAT - EACH LOCATION
Checkpoint | Surface Priming
Label | Ensure surface is damped with water prior to membraning with Hydrostatic
Checkpoint | Weather/RH - Enviro Hydrostatic Product TDS
Label | Apply within 5-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
Label | surveillance point
Checkpoint | Product Mixing - Enviro Hydrostatic Product TDS
Label | • Pour water and Hydrostatic powder in a bucket and mix with a mechanical mixer at low speed (less than 400 RPM) for 5 minutes until smooth and uniform. Avoid lumps in membrane
Label | Witness Point
Checkpoint | Application- Enviro Hydrostatic Product TDS
Label | • Hydrostatic one to be applied by roller vertically on substrate and terminating min 150mm with brush.
Label | Minimum application requirements set forth relevant Australian Standards to be followed
Label | Allow membrane to cure before overcoating.
Label | Records - Photograph
Label | Witness Point
SECTION | SECOND BASE COAT - EACH LOCATION
Checkpoint | Weather/RH - Enviro Hydrostatic Product TDS
Label | Apply within 5-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
Label | surveillance point
Checkpoint | Product Mixing - Enviro Hydrostatic Product TDS
Label | • Pour water and Hydrostatic powder in a bucket and mix with a mechanical mixer at low speed (less than 400 RPM) for 5 minutes until smooth and uniform. Avoid lumps in membrane
Label | Witness Point
Checkpoint | Application- Enviro Hydrostatic Product TDS
Label | • Hydrostatic one to be applied by roller vertically on substrate and terminating min 150mm with brush.
Label | Minimum application requirements set forth relevant Australian Standards to be followed
Label | Records - Photograph
Label | Witness Point
Section | QA TESTING - EACH LOCATION
Checkpoint | Inspection
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
Label | Records - Photograph
Label | Witness point
Checkpoint | Thickness Testing - Delfasco Positector
Label | Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.( 1 test per 10m2)
Label | Records - Photograph
Label | Hold Point
SECTION | SIGN OFFS
Checkpoint | Polyseal ITP acceptance Sign off
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman ITP accceptance Sign off
SIGNOFF | Site Engineer/foreman inspection sign off