## Dermafil (Concrete Lid)
type | name | values | prefix | postfix | usage count
checklist-flat | Torch-On Installation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate Acceptance (as per manufacturer's technical data sheet and method statement)
button | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below | Yes,No
button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
button | Substrate free from pooling or ponding water | Yes,No
button | Moisture content is 4% or less (Moisture gauge photo attached below) | Yes,No
button | Adequate fall in substrate | Yes,No
checkpoint | Priming
label | Record batch numbers
button | Dermaprimer installed to manufacturer's specification - photos attached below | Yes,No
button | Primer given adequate time to cure as per manufacturers specification | Yes,No
button | Area completed and suitable for membrane application - photos attached below | Yes,No
checkpoint | Dermafil Installation
label | Record batch numbers
button | Substrate clear of dust, debris and contaminants - photos attached below | Yes,No
button | Installation of base layer membrane (min. 100mm overlaps) - photos attached below | Yes,No
button | Termination pressure bar installed where required - photos attached below | Yes,No
checkpoint | ILD Testing
button | ILD test requested | Yes,No
button | ILD test performed | Yes,No
text | Any rectifications performed
button | ILD test report issued | Yes,No
checkpoint | Protection
button | Casali Protector installed - photos attached below | Yes,No
checkpoint | Area completed to manufacturer's specification - photos attached below
label | Attach Client Signature Below

## Eradix (Backfilled Downturns)
type | name | values | prefix | postfix | usage count
checklist-flat | SEMZ - Mobilisation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
Checkpoint | Traffic Management to facilitate crane lift of all fall protection and material to roof.
Checkpoint | Material and fall protection craned to roof
Checkpoint | Material and fall protection spread around roof as per loading plan.
Checkpoint | Fall protection installed
Checkpoint | 6m3 bin available for early demolition
Checkpoint | All allocated labour inducted
type | name | values | prefix | postfix | usage count
checklist-flat | SEMZ - Main Floor Preparation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Decommission Redundant Walkways
button | Dismantle and dispose of nominated existing walkways. | Yes,No
checkpoint | Decommission and Repair GPO's
button | GPO's deommissioned by qualified Electrician | Yes,No
button | Cut down, fill void and patch decommissioned GPO's. | Yes,No
checkpoint | Patch and Repair Existing Membrane Defects
label | Cut out any defective patches
button | Primed to manufacturer's specification (Record Batch of Primer) | Yes,No
button | Patch with 100mm extension on all sides installed (Record Batch of Sheet | Yes,No
button | Area completed and suitable for membrane application - photos attached below | Yes,No
checkpoint | Pressure Wash
checkpoint | Vent Pipes
label | Cut out 1m2 around vent pipe.
button | Primed to manufacturer's specification (Record Batch of Primer) | Yes,No
button | Patch with 2 x 1m2 extension of base sheet on all sides installed (Record Batch of Sheet) - photos attached below | Yes,No
button | Patch with 2 x 1m2 extension of cap sheet on all sides installed (Record Batch of Sheet) - photos attached below | Yes,No
type | name | values | prefix | postfix | usage count
checklist-flat | SEMZ - Perimeter Detail Installation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Remove perimeter flashing and set aside for reinstatement
checkpoint | Removal of 1m perimeter
button | Removal of pressure bar and upturn | Yes,No
button | Cut out and removal of 1m wide cap sheet at perimeter | Yes,No
checkpoint | Grinding Substrate
button | Substrate to be assessed for latent conditions | Yes,No
button | Grind substrate to acceptable condition for membrane installation | Yes,No
checkpoint | Substrate Acceptance (as per manufacturer's technical data sheet and method statement)
button | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below | Yes,No
button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
button | Moisture content is 4% or less (Moisture gauge photo attached below) | Yes,No
checkpoint | Priming | Yes,No
button | Primed to manufacturer's specification (Record Batch of Primer) | Yes,No
checkpoint | Base and Cap Sheet Installation
button | Install 2 x 1m wide base sheet to perimeter and upturn (Record Batch of Sheet) - photos attached below | Yes,No
button | Install with 2 x 1m wide base sheet to perimeter and upturn (Record Batch of Sheet) - photos attached below | Yes,No
checkpoint | Termination Pressure Bar
button | Supply and install termination pressure bar - photos attached below | Yes,No
checkpoint | Reinstatement of Flashing
type | name | values | prefix | postfix | usage count
checklist-flat | SEMZ - Main Floor Installation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Installation of ILD Mesh
button | Supply and install ILD mesh to existing membrane prior to cap sheet installation. | Yes,No
checkpoint | Priming | Yes,No
button | Primed to manufacturer's specification (Record Batch of Primer) | Yes,No
checkpoint | Cap Sheet Installation
button | Pressure wash of substrate | Yes,No
button | Install 1 layer of cap sheet to main floor area (Record Batch of Sheet) - photos attached below | Yes,No
checkpoint | ILD Testing
button | ILD test requested | Yes,No
button | ILD test performed | Yes,No
text | Any rectifications performed
button | ILD test report issued | Yes,No
checkpoint | Area completed to manufacturer's specification - photos attached below
label | Attach Client Signature Below
type | name | values | prefix | postfix | usage count
checklist-flat | SEMZ - Perimeter Caulking
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Perimeter CaulkIng Preparation
button | Cut out existing caulk | Yes,No
button | Primed to manufacturer's specification (Record Batch of Primer) | Yes,No
button | Polyurethane caulk installed to manufacturer's specification (Record Batch of Primer) | Yes,No
type | name | values | prefix | postfix | usage count
checklist-flat | SEMZ - Demobilisation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | Enter SOW description
Checkpoint | Remaining Material and Rubbish Packaged and Ready for Removal
Checkpoint | Fall protection removed and packaged rady for removal
Checkpoint | Traffic Management to facilitate crane lift of all fall protection and remaining debris from roof.
Checkpoint | Material and fall protection craned from roof and removed by contractors
Checkpoint | 6m3 bin removed