## Digout
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Sealed Pavement Repair - Digout |  |  | DN-GD-GP030/Digout Log/ Excavation Log/Scala Log |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) |  |  | Ground Distrubance Permit |  |  |  | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Preparation |  | Sub Supervisor/Downer Engineer | GAP=DEPTH/1.5 | Atleast 1 check/patch | DN-GD-GP030/Ground Distrubance Permit | NO | W(10%) | R | H |  |  | W & I | Supplier
2 | Excavation |  | Sub Supervisor/Downer Engineer | The bottom of the digout should match slope of the pavement surface | Atleast 1 check/patch | DN-GD-GP030 | YES | W(10%) | R | H
3 | Checking the base (Scala Test) |  | Sub Supervisor/Downer Engineer | Base is strong enough to safely carry the load | Atleast 1 check/patch | DN-GD-GP030/Scala Log | YES | W | W(10%) | H
4 | Filter Fabric |  | Sub Supervisor/Downer Engineer | Lay the fabric when Subgrade reached | Atleast 1 check/patch | DN-GD-GP030 | YES | W(10%) | R | H
5 | Subsoil Drainage |  | Sub Supervisor/Downer Engineer | Refer GP089 | Atleast 1 check/patch | DN-GD-GP030 | YES | W(10%) | R | H
6 | Backfill and Compact (Clegg Hammer Reading) |  | Sub Supervisor/Downer Engineer | Atleast 35 CIV | After every 1m | DN-GD-GP030/Clegg Log | YES | W | W(10%) | H
7 | Final shape and Trim |  | Sub Supervisor/Downer Engineer | Shape and trim the repair to prsent a tidy apperance | Atleast 1 check/patch | DN-GD-GP030 | NO | W(10%) | R | H
8 | Surfacing |  | Sub Supervisor/Downer Engineer | Chip Seal refer GP047/Premix refer GP041 | Atleast 1 check/patch | DN-GD-GP030 | YES | W(10%) | R | H
9 | Test and Check |  | Sub Supervisor/Downer Engineer | No more than 6mm depression with 2 meter straight edge | Atleast 1 check/patch | DN-GD-GP030 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 04/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Stabi
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Sealed Pavement Repair - Insitu Stabilisation |  |  | DN-GD-GP031/Insitu Stabi. Log/ Excavation Log/Scala Log |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) |  |  | Ground Distrubance Permit |  |  |  | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Site Preparation |  | Sub Sup/Downer Eng | Avoid Seal Joint within the wheel path | Atleast 1 check/patch | DN-GD-GP031/Ground Distrubance Permit | NO | W(10%) | R | H |  |  | W & I | Supplier
2 | Asphalt Pavement |  | Sub Sup/Downer Eng | If greater than 50mm deep, remove asphalt from site and dipose of properly | Atleast 1 check/patch | DN-GD-GP031 | NO | R | R | H
3 | Depressions |  | Sub Sup/Downer Eng | Compact lightly (2 passes) | Atleast 1 check/patch | DN-GD-GP031 | NO | R | R | H
4 | Cement Application Quantity |  | Sub Sup/Downer Eng | As per specification | Atleast 1 check/patch | DN-GD-GP031 | YES | W(10%) | R | H
5 | Spread Cement |  | Sub Sup/Downer Eng | Too much or too little could cause failure | Atleast 1 check/patch | DN-GD-GP031 | NO | W(10%) | R | H
6 | Roatry Hoeing |  | Sub Sup/Downer Eng | Start from the edge of the patch and hoe the entire area at design depth | Atleast 1 check/patch | DN-GD-GP031 | NO | W(10%) | R | H
7 | Make Edge as Straight as possible |  | Sub Sup/Downer Eng | Aim to have material with a max. size 40mm | Atleast 1 check/patch | DN-GD-GP031 | NO | W(10%) | R | H
8 | Water Application |  | Sub Sup/Downer Eng | Add enough water to make the material sticky | Atleast 1 check/patch | DN-GD-GP031 | NO | W(10%) | R | H
9 | Initial Compaction |  | Sub Sup/Downer Eng | High Amplitude 5 passes Low Amplitude 3 passes No Vibration 1 pass | Atleast 1 check/patch | DN-GD-GP031 | YES | W(10%) | R | H
10 | Trim Shape & Final Compaction (Clegg Hammer Reading) |  | Sub Sup/Downer Eng | Clegg Hammer reading 35 CIV | After every 1m | DN-GD-GP031/Clegg Log | YES | W | W(10%) | H
11 | Surfacing |  | Sub Sup/Downer Eng | Chip Seal refer GP047/Premix refer GP041 | Atleast 1 check/patch | DN-GD-GP031 | YES | R | R | H
12 | Test and Check |  | Sub Sup/Downer Eng | No more than 10mm depression with 2 meter straight edge | Atleast 1 check/patch | DN-GD-GP031 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 05/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Mill & Fill
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair Surface Depression - Mill and Fill Method |  |  | DN-GD-GP041/Insitu Stabi. Log/ Excavation Log/Scala Log |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) |  |  | Ground Distrubance Permit/Clegg Value Log |  |  |  | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Preparation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP041/Ground Distrubance Permit | YES | W(10%) | R | H |  |  | W & I | Supplier
2 | Milling |  | Sub Sup/Downer Eng | Check depth with a straight edge or string line | Every 10m or based on the site length | DN-GD-GP041 | YES | W(10%) | R | H
3 | Base Layer Acceptance (Clegg Value) |  | Sub Sup/Downer Eng | Value of 25-35 needed | After every 1m | DN-GD-GP041/Clegg Log | YES | W(10%) | R | H
4 | Application of Binder (Tack Coat) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP041 | YES | W(10%) | R | H
5 | Premix Selection |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP041 | YES | W(10%) | R | H
6 | Laying Premix Material |  | Sub Sup/Downer Eng | Lay Premix in even thickness layers | In-process | DN-GD-GP041 | YES | W(10%) | R | H
7 | Final Compaction |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP041 | NO | W(10%) | R | H
8 | Blinding |  | Sub Sup/Downer Eng | Blinding with sand and restore road marking | In-process | DN-GD-GP041 | NO | R | R | H
9 | Test and Check |  | Sub Sup/Downer Eng | Any depression must be less than 5mm | In-process | DN-GD-GP041 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 05/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Fabric Seal
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Fabric Seal |  |  | DN-GD-GP046/Ground Distrubance Permit |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the site |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP046/Ground Distrubance Permit | YES | R | R | H |  |  | W & I | Supplier
2 | Prepare the surface |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP046 | YES | W(10%) | R | H
3 | Lay the Fabric |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP046 | YES | W(10%) | R | H
4 | Two Coat Seal |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP046 | YES | W(10%) | R | H
5 | Site Monitoring |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP046 | YES | W(10%) | R | H
6 | Sweeping and Marking |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP046 | YES | W(10%) | R | H
7 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP046 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 06/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## AWT
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
AWT – Unbound Granular | [6 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Preliminary and General | [11 empty] | W & I | Supplier
1.1 | Construction Program Completion |  | Sub Sup/Downer Eng | Best Practice Contract Specific MMP | Before work Commence | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date. | NO | W(10%) | R | H
1.2 | Approved RQP |  | Sub Sup/Downer Eng | Contract Specification | Before work Commence | Principal Acceptance according to guidelines in appendix 6.3 | YES | W(10%) | R | H
1.3 | Traffic Management/TMP |  | Sub Sup/Downer Eng | CoPTTM | Before Traffic Management Setup | TMP checked and approved Plans approved Current EED (if applicable) | YES | R | R | H
1.4 | Notification of intention to start work |  | Sub Sup/Downer Eng | Notification | Before work commences | Letter drop to local residents. Where required and defined by SWAMP, VMS, social media/media advertising | YES | R | R | H
2 | Setout/Site Preparation
2.1 | Setout/Survey |  | Sub Sup/Downer Eng | Best Practice | Per installation | Survey Records | YES | W(10%) | R | H
2.2 | Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Sub Sup/Downer Eng | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | YES | R | R | H
2.3 | Permit to dig/Authority to Work/close approach permits |  | Sub Sup/Downer Eng | Downer Permit to work or Equvilent | Before work commences | Organisational approval | YES | R | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
AWT - Granular Overlay | [6 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
2.4 | Cultural/Heritage Risk Assessment |  | Sub Sup/Downer Eng | WK Cultural & Heritage Risk Model | Before work commences | Local kiwi has been notified of intent to start work | YES | R | R | H |  |  | W & I | Supplier
2.5 | Archaeological Risk |  | Sub Sup/Downer Eng | WK Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | YES | R | R | H
2.6 | Traffic Management Setup |  | Sub Sup/Downer Eng | Traffic Management Plan | Before work commences each day | Traffic management complies with TMP | YES | W(10%) | R | H
2.7 | Machine Control Survey Control |  | Sub Sup/Downer Eng | On Site | Before using machine control | Verification of survey control points and setup | YES | W(10%) | R | H
2.8 | Machine Control Accuracy Verification |  | Sub Sup/Downer Eng | On Site | Before using machine control | Digital design set-out data is consistent with on site marks | YES | W(10%) | R | H
2.9 | Prepare String Sheet (Digital) |  | Sub Sup/Downer Eng | On Site | Before using machine control | Digital design set-out data is consistent with existing formation | YES | W(10%) | R | H
3 | Preparatory Work
3.1 | Earthwork and Stripping
3.1.1 | Shoulder Stripping |  | Sub Sup/Downer Eng | On site |  | Shoulder stripping completed | YES | W(10%) | R | H
3.1.2 | Cut/Excavation |  | Sub Sup/Downer Eng | On site | Tape measure from set-out or existing CL, as per design | Meets design drawings of cross-sectional extent | YES | W(10%) | R | H
3.2 | Drainage Structure
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
AWT - Granular Overlay | [6 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
3.2.1 | Culverts: Excavation Inlet / Outlet Gradients |  | Sub Sup/Downer Eng | NZTA F/3 | Once | Consistent gradient in and out | YES | W(10%) | R | H |  |  | W & I | Supplier
3.2.2 | Culverts: Pipe materials / class |  | Sub Sup/Downer Eng | NZTA F/3 2.1 | Once | Meets appropriate AS/NZ standard reletive to specified type | YES | W(10%) | R | H
3.2.3 | Culverts: Bedding contact |  | Sub Sup/Downer Eng | NZTA F/3 5.1 | continuous | uniform contact over full length of pipe | YES | W(10%) | R | H
3.2.4 | Other Structures |  | Sub Sup/Downer Eng |  | continuous | Constructed to design drawings and relevant standards | YES | W(10%) | R | H
3.3 | Ancillary Work
3.3.1 | Ancillary Items as per design Example: - Retaining Walls - Rock Benching - Signage - Vegetation/Trees - Kerb and Channel - Footpath - Crossing Details - Underground Services - Service Covers |  | Sub Sup/Downer Eng | As per Specification | Once | Constructed to design drawings and relevant standards | YES | W(10%) | R | H
3.4 | SubSoil Drainage
3.4.1 | Subsoil Drain Construction |  | Sub Sup/Downer Eng | As per Specification | each site | As per design drawings and/or NZTA F/2 Specification (if required or specified) | YES | W(10%) | R | H
3.4.2 | Inlets/Outlets |  | Sub Sup/Downer Eng | As per Specification |  | Connect to sump/catchpit, Concrete Apron, Open Channel, Inspection Eyes. | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
AWT - Granular Overlay | [6 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
3.5 | Pavement Widening and Digouts | [11 empty] | W & I | Supplier
3.5.1 | Excavation |  | Sub Sup/Downer Eng | Onsite | Scala Test at each Chainage (L & R Shoulders) | Subgrade CBR to be valiodated with design report. See section 5.4 refer to existing depth | YES | W(10%) | R | H
3.5.2 | Subbase Material Properties |  | Sub Sup/Downer Eng | TNZ M/3. 1986 | Once | Meet speeding design requirements or NZTA M/3 guidance | YES | W(10%) | R | H
3.5.3 | Density Lab testing in accordance with B/2. Only required if new subbase construction is within the carriageway line. If no compaction testing under sealed shoulders. |  | Sub Sup/Downer Eng | NZS 4407. 1991/Solid density test 3.7/TNZ B/2.2005/WC test 3.7/ NZS 4402. 1986/MDD W/C test 4.1.3/ | The less of: a) Test per stockpile or new seal. b) 1 test every 5000m2 (In place) | OWC as determined in the lab. When sampling stock pile for lab. Take NDM for W/C offset. Record moisture contenet and take sample from beneath NDM to dry in the even. Two W/C reading and samples. MDD as the two higher results from lab and field. Ensure Platuae test is done at OWC from lab value and with NDM moisture offset. | YES | W(10%) | R | H
3.5.4 | Construction only required when new construction is in carriageway lane. If no compaction testig under sealed shoulders |  | Sub Sup/Downer Eng | NZS 4407. 1991 Test 4.2.2/TNZ B/2.2005 | 5 test per homogenious lot of upto 1000m2 of laid pavement | Subbase average ≥ 95% MDD Minimum ≥ 92% MDD | YES | W(10%) | R | H
4 | Pavement Including Sealed Shoulders
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
AWT – Unbound Granular | [6 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
4.1 | Imported Basecourse Material Testing | [11 empty] | W & I | Supplier
4.1.1 | Production Properties Note: Running course to be produced from the same type and source of material as the basecourse. |  | Sub Sup/Downer Eng | TNZ M/4:2006 NZS 4407 :1991 Test 3.8.1/Test 3.14/Test 3.6 /Test 3.4 | 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | TNZ M/4: Cl.4.2.3 Aggregate broken face content in each of the three aggregate fractions between 37.5mm and 4.75mm ≥ 70% by weight and has 2 or more broken faces. Sand equivalent > 40 NB Downer Policy that only SE compliant basecourse allowed unless stabilised. PI ≤ 5 | YES | W(10%) | R | H
4.1.2 | B/02 Lab Testing |  | Sub Sup/Downer Eng | NZS 4407:1991 Solid Density Test 3.7/NZS 4407:1991 W/C Test 3.7/NZS 4402: 1986 MDD and W/C Test 4.1.3 TNZ B/2: 2005 | The lesser of: a) 1 test per stockpile or new seam b) 1 test every 5000m2 (in place) | OWC as determined in the lab. When sampling stockpile for lab, take NDM for W/C offset. Record moisture content and take sample from beneath NDM to dry in the oven. (Two W/C readings and samples). MDD as the higher of the two results from lab and field. Ensure plateau test is done at OWC from Lab Value and with NDM moisture offset | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
AWT – Unbound Granular | [6 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
4.1.3 | Source Properties Note: Running course to be produced from the same type and source of material as the basecourse |  | Sub Sup/Downer Eng | TNZ M/4: 2006 NZS 4407 :1991 Test 3.10 NZS 4402: 1986 Test 4.13 NZS 4407: 1991 Test CBR 3.15 NZS 4407:1991 Test 3.11 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve. Soaked CBR ≥ 80% when compacted/tested in accordance with both tests. Must have quality index of AA, AB, AC, BA, BB or CA | YES | W(10%) | R | H
4.1.4 |  |  | Sub Sup/Downer Eng | NZS 4407:1991 Test 3.11 NZTA T15 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | T15 Specification | YES | W(10%) | R | H
4.2 | Construction QA
4.2.1 | Pavement surface milling/scarification |  | Sub Sup/Downer Eng | Visual inspection after milling | Overview of underlying defects that may required digout/replace | Photographic condition of surface condition and visual inspection record | YES | W(10%) | R | H
4.2.2 | Compaction/Degree of Saturation (DOS) |  | Sub Sup/Downer Eng | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Basecourse : Average ≥ 98% MDD Minimum ≥ 95% MDD Subbase: Average ≥ 95% MDD Minimum ≥ 92% MDD DOS ≤ 80% from Solid Density and %W | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
AWT – Unbound Granular | [6 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
4.2.3 | Surface shape/profile Layer thickness. Tolerances: width unconstrained. Tolerances: width constrained. Visual appearance |  | Sub Sup/Downer Eng | Visual inspection Cut/fill tolerance check Straight edge. Confirm offset from lift pegs. Stringline or tape survey from leveling system of grader/lift pegs | 1 test per 60m. 2 at every lift peg or per 180 m2. 3 at every lift peg or per 180 m2 | ≤10mm variance from 3m straight edge. Gradual deviations. No ponding if crossfall > 1%. Overlay Thickness meets design but not >200mm OHS. Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design. Where lift pegs are used: -5mm +15mm or ±5mm at lip of concrete channel OR GPS level controlled grader. -20mm -100mm Zero. No loose chip remaining. | YES | W(10%) | R | H
4.2.4 | Roughness |  | Sub Sup/Downer Eng | Visual inspection after sweeping | Immediately prior to sealing | 100m Rolling NAASRA Average ≤ 60 Maximum ≤ 70 | YES | W(10%) | R | H
5 | Shoulder and addition Surfacing Preparation
5.1 | Slope |  | Sub Sup/Downer Eng | Visual inspection with smart level |  | Slopes consistent | YES | W(10%) | R | H
5.2 | Compaction |  | Sub Sup/Downer Eng | Drive over 4T, check wheeltracks | All shoulders | Vehicles can drive on shoulders without significant indentation/soft surface | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
AWT – Unbound Granular | [6 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
5.3 | Additional Surfacing Preparation - Side Roads - Accesses - Driveways - Dish Channels - High Shoulders |  | Sub Sup/Downer Eng | Per Design | Before/During Sealing | Have all areas of additional surfacing on the design been prepared and marked for sealing? | YES | W(10%) | R | H
5.4 | Soiling |  | Sub Sup/Downer Eng |  | All areas required grassing | Soiling has been done where required | YES | W(10%) | R | H
5.5 | Grassing |  | Sub Sup/Downer Eng |  | All areas required grassing | Grassing has been done where required | YES | W(10%) | R | H
6 | Pavement finishing and Surfacing
6.1 | Completed construction pavement surface = Mosaic surface, Pre-sealing walkover and checks |  | Sub Sup/Downer Eng | A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ | Overview of site for tight mosaic surface. Before sealing | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping. All other necessary checks have been done & accepted | YES | W(10%) | R | H
6.2 | Pre-seal Area Check |  | Sub Sup/Downer Eng | On Site tape-measure | Before sealing | Check prepared and marked area for sealing against design to check whether full area of design ready for surfacing | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
AWT – Unbound Granular | [6 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
6.3 | Sealing TMP and aftercare process |  | Sub Sup/Downer Eng | See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site |  |  | YES | W(10%) | R | H
6.4 | Sweeping of Sealing works and handover to Roadmarkers |  | Sub Sup/Downer Eng | Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor. |  |  | YES | W(10%) | R | H
6.5 | Post-seal Area Check |  | Sub Sup/Downer Eng | On Site tape-measure | After Surfacing | Check sealed area meets design | YES | W(10%) | R | H
7 | Improvements
7.1 | Improvement guardrails singnage footpaths |  | Sub Sup/Downer Eng | Visual Inspection | All signs/marker | Replace in same position, heights etc | YES | W(10%) | R | H
8 | Site Reinstatement/Clearance
8.1 | Roadmarking |  | Sub Sup/Downer Eng | Visual inspection | All markings | Replaced in same position, or per design | YES | W(10%) | R | H
8.2 | Traffic Services/Marker pegs/ Signs/Markings/RRPMs Replaced |  | Sub Sup/Downer Eng | Visual inspection | All signs/markers | Replaced in same position, height etc | YES | W(10%) | R | H
8.3 | Draine Cleared |  | Sub Sup/Downer Eng |  |  |  | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
AWT – Unbound Granular | [6 empty] | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
8.4 | Envirnomental Controls Removed |  | Sub Sup/Downer Eng | Visual check | All installed measures | Any silt fences or other controls are removed | YES | W(10%) | R | H
8.5 | Traffic Management Removed |  | Sub Sup/Downer Eng | Visual check | When safe, after all physical works completed | All traffic management removed from site safely | YES | W(10%) | R | H
8.6 | Site left clean & tidy |  | Sub Sup/Downer Eng | Visual check | After vacating site | Stockpiles removed, Plant removed, Litter cleared from site | YES | W(10%) | R | H
9 | As Built Records
9.1 | Collect asset data |  | Sub Sup/Downer Eng |  | During construction | All relevant as built information collected. | YES | W(10%) | R | H
9.2 | Enter asset data into RAMM and/or register(s) |  | Sub Sup/Downer Eng | RAMM | At completion of work. | All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file. | YES | W(10%) | R | H
9.3 | Construction Completion Report |  | Sub Sup/Downer Eng | Contract Specification | At completion of work. | Checked and approved | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 11/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Two Coat Chip Seal - Spraybar
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
First Coat - Two Coat Chip Seal (Spraybar Method) |  |  | DN-GD-GP048/Ground Distrubance Permit |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Weather |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP048 | NO | R | R | H |  |  | W & I | Supplier
2 | Site Preparation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP048 | YES | W | W(10%) | H
3 | Binder Spray - First Coat |  | Sub Sup/Downer Eng | Maintain 100mm Overlap | Atleast 1 check/patch | DN-GD-GP048 | YES | W(10%) | R | H
4 | Spreading Chip - First Coat |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP048 | YES | W(10%) | R | H
5 | Prepare for Second Coat |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP048 | NO | W(10%) | R | H
6 | Second Coat |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP048 | YES | W(10%) | R | H
7 | Site Monitoring |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP048 | NO | W(10%) | R | H
8 | Sweeping and Marking |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP048 | NO | R | R | H
9 | Test and Check |  | Sub Sup/Downer Eng | Check there is 100mm overlap | Atleast 1 check/patch | DN-GD-GP048 | Nno | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 06/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Culvert and Drainage Inspection
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Culvert and Drainage Inspection |  |  | DN-GD-GP080 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Calibration |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP080 | YES | W(10%) | R | H |  |  | W & I | Supplier
2 | Inspection |  | Sub Sup/Downer Eng | Use the Drainage Inspection Guide | In-process | DN-GD-GP080 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 06/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Culvert Instal less than 900mm
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Install a Concrete Culvert Less Than 900mm in Diameter |  |  | DN-GD-GP082/Ground Distrubance Permit |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP082/Ground Distrubance Permit | YES | R | R | H |  |  | W & I | Supplier
2 | Setting Out |  | Sub Sup/Downer Eng | Check the Start, end and invert level is set out | In-process | DN-GD-GP082 | YES | W | W(10%) | H
3 | Excavation |  | Sub Sup/Downer Eng | Lay Bedding 100mm deep | Regular Interval | DN-GD-GP082 | YES | W(10%) | R | H
4 | Prepare the Base |  | Sub Sup/Downer Eng | Meaasure pipe collar location | Atleast 1 check/Culvert | DN-GD-GP082 | YES | W | W(10%) | H
5 | Prepare Pipes |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP082 | NO | W(10%) | R | H
6 | Lay Pipes |  | Sub Sup/Downer Eng | 300mm bedding material both side | Regular Interval | DN-GD-GP082 | YES | W(10%) | R | H
7 | Backfilling |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP082 | YES | W(10%) | R | H
8 | Restore Pavement |  | Sub Sup/Downer Eng | Refer GP030 | In-process | DN-GD-GP082 | YES | W(10%) | R | H
9 | Test and Check |  | Sub Sup/Downer Eng | Inlet and Outlet should be within ±25mm for level | Atleast 1 check/Culvert | DN-GD-GP082 | YES | W | W(10%) | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 06/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client