## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - CONOC NETWORK - Sealed Pavement Repair - Digout | itp |  |  |  |  | ITP - CONOC NETWORK - Sealed Pavement Repair - Digout
checkpoint | 1 - Preparation
label | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | Accept / Reject Criteria - GAP=DEPTH/1.5
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030/Ground Distrubance Permit
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Excavation
label | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | Accept / Reject Criteria - The bottom of the digout should match slope of the pavement surface
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | Records Required - YES
label | ENGINEER - YES
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Checking the base (Scala Test)
label | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | Accept / Reject Criteria - Base is strong enough to safely carry the load
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030/Scala Log
label | Records Required - YES
label | ENGINEER - W
label | SUPERVISOR - W(10%)
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Filter Fabric
label | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | Accept / Reject Criteria - Lay the fabric when Subgrade reached
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Subsoil Drainage
label | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | Accept / Reject Criteria - Refer GP089
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Backfill and Compact (Clegg Hammer Reading)
label | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | Accept / Reject Criteria - Atleast 35 CIV
label | Frequency Of Inspection Or Test - After every 1m
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030/Clegg Log
label | Records Required - YES
label | ENGINEER - W
label | SUPERVISOR - W(10%)
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Final shape and Trim
label | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | Accept / Reject Criteria - Shape and trim the repair to prsent a tidy apperance
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Surfacing
label | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | Accept / Reject Criteria - Chip Seal refer GP047/Premix refer GP041
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Test and Check
label | Controlled By : (Position) - Sub Supervisor/Downer Engineer
label | Accept / Reject Criteria - No more than 6mm depression with 2 meter straight edge
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP030
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - Sealed Pavement Repair - Insitu Stabilisation | itp |  |  |  |  | ITP - CONOC NETWORK - Sealed Pavement Repair - Insitu Stabilisation
checkpoint | 1 - Site Preparation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Avoid Seal Joint within the wheel path
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031/Ground Distrubance Permit
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Asphalt Pavement
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - If greater than 50mm deep, remove asphalt from site and dipose of properly
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Depressions
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Compact lightly (2 passes)
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Cement Application Quantity
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Spread Cement
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Too much or too little could cause failure
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Roatry Hoeing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Start from the edge of the patch and hoe the entire area at design depth
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Make Edge as Straight as possible
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Aim to have material with a max. size 40mm
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Water Application
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Add enough water to make the material sticky
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Initial Compaction
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - High Amplitude 5 passes Low Amplitude 3 passes No Vibration 1 pass
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Trim Shape & Final Compaction (Clegg Hammer Reading)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Clegg Hammer reading 35 CIV
label | Frequency Of Inspection Or Test - After every 1m
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031/Clegg Log
label | Records Required - YES
label | ENGINEER - W
label | SUPERVISOR - W(10%)
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Surfacing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Chip Seal refer GP047/Premix refer GP041
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | Records Required - YES
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - No more than 10mm depression with 2 meter straight edge
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP031
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - Repair Surface Depression - Mill and Fill Method | itp |  |  |  |  | ITP - CONOC NETWORK - Repair Surface Depression - Mill and Fill Method
checkpoint | 1 - Preparation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Ground Distrubance Permit
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Milling
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Check depth with a straight edge or string line
label | Frequency Of Inspection Or Test - Every 10m or based on the site length
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Base Layer Acceptance (Clegg Value)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Value of 25-35 needed
label | Frequency Of Inspection Or Test - After every 1m
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041/Clegg Log
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Application of Binder (Tack Coat)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Premix Selection
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Laying Premix Material
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Lay Premix in even thickness layers
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Final Compaction
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Blinding
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Blinding with sand and restore road marking
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Any depression must be less than 5mm
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP041
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - Fabric Seal | itp |  |  |  |  | ITP - CONOC NETWORK - Fabric Seal
checkpoint | 1 - Prepare the site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046/Ground Distrubance Permit
label | Records Required - YES
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Prepare the surface
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Lay the Fabric
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Two Coat Seal
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Site Monitoring
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Sweeping and Marking
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP046
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP - CONOC NETWORK - AWT - Unbound Granular | itp |  |  |  |  | ITP - CONOC NETWORK - AWT - Unbound Granular
section | 1 - Preliminary and General
checkpoint | 1.1 - Construction Program Completion
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Best Practice Contract Specific MMP
label | Frequency Of Inspection Or Test - Before work Commence
label | Spec. Ref, Procedure Or Method Statement - Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date.
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Approved RQP
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Contract Specification
label | Frequency Of Inspection Or Test - Before work Commence
label | Spec. Ref, Procedure Or Method Statement - Principal Acceptance according to guidelines in appendix 6.3
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Traffic Management/TMP
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - CoPTTM
label | Frequency Of Inspection Or Test - Before Traffic Management Setup
label | Spec. Ref, Procedure Or Method Statement - TMP checked and approved, Plans approved, Current EED (if applicable)
label | Records Required - YES
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Notification of intention to start work
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Notification
label | Frequency Of Inspection Or Test - Before work commences
label | Spec. Ref, Procedure Or Method Statement - Letter drop to local residents. Where required and defined by SWAMP, VMS, social media/media advertising
label | Records Required - YES
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Setout/Site Preparation
checkpoint | 2.1 - Setout/Survey
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Best Practice
label | Frequency Of Inspection Or Test - Per installation
label | Spec. Ref, Procedure Or Method Statement - Survey Records
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - NZAUAG Guide to Working on the Road
label | Frequency Of Inspection Or Test - Before work commences
label | Spec. Ref, Procedure Or Method Statement - Zero service strikes
label | Records Required - YES
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Permit to dig/Authority to Work/close approach permits
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Downer Permit to work or Equvilent
label | Frequency Of Inspection Or Test - Before work commences
label | Spec. Ref, Procedure Or Method Statement - Organisational approval
label | Records Required - YES
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - First Coat - Two Coat Chip Seal (Spraybar Method) | itp |  |  |  |  | ITP - CONOC NETWORK - First Coat - Two Coat Chip Seal (Spraybar Method)
checkpoint | 1 - Weather
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Site Preparation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | Records Required - YES
label | ENGINEER - W
label | SUPERVISOR - W(10%)
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Binder Spray - First Coat
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Maintain 100mm Overlap
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Spreading Chip - First Coat
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Prepare for Second Coat
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Second Coat
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Site Monitoring
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Sweeping and Marking
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Check there is 100mm overlap
label | Frequency Of Inspection Or Test - Atleast 1 check/patch
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP048
label | Records Required - Nno
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - Culvert and Drainage Inspection | itp |  |  |  |  | ITP - CONOC NETWORK - Culvert and Drainage Inspection
checkpoint | 1 - Calibration
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP080
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Inspection
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Use the Drainage Inspection Guide
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP080
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC NETWORK - Install a Concrete Culvert Less Than 900mm in Diameter | itp |  |  |  |  | ITP - CONOC NETWORK - Install a Concrete Culvert Less Than 900mm in Diameter
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082/Ground Distrubance Permit
label | Records Required - YES
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Setting Out
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Check the Start, end and invert level is set out
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | Records Required - YES
label | ENGINEER - W
label | SUPERVISOR - W(10%)
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Excavation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Lay Bedding 100mm deep
label | Frequency Of Inspection Or Test - Regular Interval
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Prepare the Base
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Meaasure pipe collar location
label | Frequency Of Inspection Or Test - Atleast 1 check/Culvert
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | Records Required - YES
label | ENGINEER - W
label | SUPERVISOR - W(10%)
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Prepare Pipes
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Lay Pipes
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - 300mm bedding material both side
label | Frequency Of Inspection Or Test - Regular Interval
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Backfilling
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Restore Pavement
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Refer GP030
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - Inlet and Outlet should be within ±25mm for level
label | Frequency Of Inspection Or Test - Atleast 1 check/Culvert
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP082
label | Records Required - YES
label | ENGINEER - W
label | SUPERVISOR - W(10%)
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT