## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP2 - Plastering Checklist |  |  |  |  | Yes | ITP2 - Plastering Checklist V1 | 0b3d0138-4cb5-4555-9027-703c841128fa
checkpoint-status |  |  | checkpoint | Set Out
label | c51deb79-0918-55a9-8944-cd53da8ce60a |  | note | As per current drawings
checkpoint-status |  |  | checkpoint | Door Frames - Installed plumb, level and correctly fixed
checkpoint-status |  |  | checkpoint | Frame Walls
label | e657f982-b91e-5aaa-8436-ff736b718707 |  | note | Floor/Ceiling track to be secured to structure at no less than 600mm internally and 100mm from ends
checkpoint-status |  |  | checkpoint | All required noggins are installed
label | e14f70e1-bf36-57f0-9239-6575eb81cd91 |  | note | Installed as per marks by other trades
checkpoint-status |  |  | checkpoint | Thermal+Acoustic insulation installed
label | c90b65f8-889d-5776-b938-14579d293cae |  | note | All insulation tight with no gaps
checkpoint-status |  |  | checkpoint | Ensure LL pre sheet sign off completed - attach below if possible
checkpoint-status |  |  | checkpoint | Sheet Walls
label | af48b836-a845-55c0-8d1b-84d100e90d3d |  | note | Sheets need to be installed as per CSR specifications. Firewalls screwed at no more than 200mm spacings on edge and 300mm internally. Wet areas field screws at 200mm max centres.
checkpoint-status |  |  | checkpoint | Firecaulk
label | be2d4f0e-f1bf-505f-af4a-619a60b53507 |  | note | Ensure sheets have 10-15mm gap before caulking
checkpoint-status |  |  | checkpoint | Frame Ceilings
label | c67be62f-b97b-5c05-a107-c4f8c7f26c49 |  | note | Ensure framing is installed as per Studco Ceiling System specifications. Perimeter tracks to be fastened at no more than 600mm centres and no more than 50mm from the stud location.
checkpoint-status |  |  | checkpoint | Sheet Ceilings
label | df844be3-137b-548d-8f99-b4d7ee8671eb |  | note | Sheets installed as per CSR specifications
checkpoint-status |  |  | checkpoint | Stop & Sand
label | ecdb809f-c511-5e07-a90d-1818c4df142c |  | note | All joins to Australian standard and screw holes double checked
checkpoint-status |  |  | checkpoint | Scrape & Sweep
label | 157ca772-bf14-5a8e-beb6-4cfb69e8fa91 |  | note | Area clean
checkpoint-status |  |  | checkpoint | Signature sign off attached below
label | 172a108e-eb5e-5f43-8cee-fc71f03dead9 |  | note | This is to confirm M. Pirovano has carried out all necessary inspections and verifies that the work has been completed and conforms to the contract specification(s)
checklist-flat |  |  | checklist | Delivery Docket Upload Checklist |  |  |  |  | Yes | Delivery Docket Upload Checklist | 1d50298e-165e-4b1f-85b1-672e65bf9075
checkpoint-status |  |  | checkpoint | Delivery docket uploaded - attach below