## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-114-CIV-CPD -Jemena Conduit Bore Rev 1 | itp |  |  |  |  | ITP-114-CIV-CPD -Jemena Conduit Bore Rev 1
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-114-CIV-CPD-Inspection & Test Plan - Horizontal Directional Drilling
label | ITP Description: Jemena Conduit Bore
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 1
label | Revision Date: 12/12/2023
label | ITP created by: Lachlan Morris/Pat Sabaruddin
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1.1 - IFC Drawings
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
checkpoint | 1.2 - VESI D&C Standard
label | Reference - VESI_URD_003
checkpoint | 1.3 - Plastic Industry Pipe Association - Industry Guidelines
label | Reference - PIPA POP 003
checkpoint | 1.4 - Australian Standards
label | Reference - AS 2033, AS4142
section | 2. Preliminary Works/ Materials
checkpoint | 2.1 - Electrical Conduits
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
label | Acceptance Criteria - Conduit Grade PE100, SDR 13.6
label | Reference:TeamBinder Material Approval Number:
label | Method - Document Review
label | Frequency - Prior to commencement
label | Category - HP
label | Responsibility - PE/SE
label | Verifying Documents - Teambinder approval number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Grout
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | Acceptance Criteria - N/A
label | Method - Document Review
label | Frequency - Prior to commencement
label | Category - HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminary Works/ Procedures
checkpoint | 3.1 - Check that current revision drawings are being used
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | Acceptance Criteria - Drawing revison must be confirmed with the design manager
label | Method - Document review
label | Frequency - Prior to commencement
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - Design drawings.
date | Date Completed:
checkpoint | 3.2 - Auditor accreditation
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
label | Acceptance Criteria - Auditors are to be VESI accredited
label | Method - Document review
label | Frequency - Prior to commencement
label | Category - HP*
label | Responsibility - PE/SE
label | Verifying Documents - Teambinder approval number
date | Date Completed:
checkpoint | 3.3 - PE Welders Qualifications
label | Reference - AS 2033, PIPA-POP-003
label | Acceptance Criteria - PE welders are to be qualified and regularly certified by a suitable RTO to PMBWELD301E
label | Reference:Teambinder Hold point release number:
label | Method - Document review
label | Frequency - Prior to commencement
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - Teambinder approval number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set-out
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003; cl5.10.13
label | Acceptance Criteria - Set out line and level of drilling works.
label | Method - Set out line and level of drilling works.
label | ○ Survey to mark out existing services.
label | ○ Must maintain a min. clearance as per VESI D&C 5.10.13.
label | Frequency - Measure, Visual
label | Category - Each element
label | Responsibility - IP
label | Verifying Documents - Surveyor, SE/PE/SPE
date | Date Completed:This ITP
checkpoint | 4.2 - Draw ropes
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, AS4142
label | Acceptance Criteria - All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
label | Method - Document review/ Visual
label | Frequency - Prior to commencement
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Material compliance certificate
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Conduit welding
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, PIPA-POP-003
label | Acceptance Criteria - Joints are to be butt welded.
label | ○ Weld map to be supplied and identify unique joint numbers.
label | ○ Butt Welding records to be supplied.
label | Method - Document review
label | Frequency - All Joints
label | Category - IP
label | Responsibility - SE/Site Supervisor/Survey
label | Verifying Documents - Sign ITP, Butt Welding Records
date | Date Completed:
checkpoint | 5.2 - Drill rig setout
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | Acceptance Criteria - Location as per current Drill shot plans
label | Method - Measure, Visual
label | Frequency - Prior to commencement
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.3 - Installation of Pipeline (Trenchless method)
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
label | Acceptance Criteria - Drill to be installed as per the survey setout.
label | ○ Bore logs to be supplied.
label | ○ When multiple conduits are installed into one bore hole care shall be taken to ensurethe conduits do not rotate during installation. Accurate detailing of conduit positions must be undertaken.
label | Method - Document review, Visual inspection
label | Frequency - During pilot bore and conduit installation
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Bore logs
date | Date Completed:
checkpoint | 5.4 - Plug pulling
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | Acceptance Criteria - Mandrel with 90% of the pipe diameter to be pulled thrugh each conduit to ensure the conduit hasent been compressed.
label | Method - Record and Review
label | Frequency - All Pipe
label | Category - HP*
label | Responsibility - SE/SPE
label | Verifying Documents - Sign ITP, Visual of pipe pull pictures. Subcontractor Test Record
date | Date Completed:
checkpoint | 5.5 - Draw rope
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | Acceptance Criteria - All draw ropes must be continious between shafts and have 2m slack in the shaft.
label | Method - Visual
label | Frequency - All Pipe
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Sign ITP.
date | Date Completed:
checkpoint | 5.6 - Auditing
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | Acceptance Criteria - Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
label | Method - Record and Review
label | Frequency - All Pipe
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - Sign ITP, Auditing Report
date | Date Completed:
checkpoint | 5.7 - Reinstatement
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | Acceptance Criteria - Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
label | Method - Visual
label | Frequency - Each shaft
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.8 - Subcontractor ITP
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | Acceptance Criteria - Acceptance and closeout of subcontractor ITP
label | Method - Document review
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/SPE
label | Verifying Documents - Sign ITP Completed
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - As-built Survey
label | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
label | Acceptance Criteria - Survey as built report to be compiled.
label | ○ Borelog obtained from subcontractor
label | ○ Autocad and PDF reports are to be supplied to:
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Survey As Report
date | Date Completed:
checkpoint | 6.2 - Red-line / As-constructed IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
label | Method - Document Review
label | Frequency - Once, after construction of the design package
label | Category - WP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP