## Bored Pile
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C1603A Gorge Descent Retaining Wall |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Bored Pile |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: 1 |  |  |  | Corresponding Work Instruction: |  | (insert Sharepoint link to Construction Work Plan folder here) |  | Compliance with Work Instructions and Specifications
Detailed Location: Waikare Gorge Descent Retaining Wall - SH2 RS577 RP13.922
Chainage: 13985.00m - 13980.00m
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Initials (Grey if not required) | Date(s)
1 | Survey Setout | H | Contractor to set out grid lines as per contract drawings and specification. | Prior to commencement | Inspection | Consistency with Construction Drawing | Design Engineer Approval | Site Engineer | CPS
2 |  | M | Any services in the area are to be clearly marked before any work commence. | Prior to commencement | Survey | Service location conducted by asset owner, marked out with dazzle on site. | Photos, log, site inspection | Site Engineer
3 |  | H | On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer | Prior to commencement | Survey | If the set out is found to be incorrect, the works shall again be set out by the Contractor and re- checked by the Engineer. | Design Engineer Approval (RFI), ConQA | Site Engineer | CPS
4 |  | M | Timber post spacing and clearance to be in line with the drawing specifications. Set out should allow for clearance, angle and spacing of centres | Prior to commencement | Inspection | lMAX 1.10m centres lset at 4 degrees from vertical l100mm of clearance on all sides of pile l100mm minimum cover of concrete at base. | Photos, log, site inspection | Site Engineer
5 |  | W | Minimum Pole embedment to be as outlined in specifications | Prior to commencement | Inspection | Pole minimum embedment to be be 3.25m, unless otherwise stated in the pole schedule on drawing C013 | Photos, log, site inspection, ConQA | Site Engineer | CPS
6 | Pile Material Compliance - Timber Poles | W | The timber poles are to be radiata pine, high density selected in accordance with and complying with NZS 3605:2001 for cross-section, length, straightness, strength and branding. All materials used in the works shall be new unless otherwise specified. | Prior to commencement | Document review | The Engineer shall be provided with a certificate of compliance | Document/ ConQA | Site Engineer | CPS
7 |  | M | The poles must be H5 treated in accordance with NZS 3640, H5. | Prior to commencement | Document review | The Engineer shall be provided with a certificate of compliance that the poles have all been treated to NZS 3640, H5. | Document/ ConQA | Site Engineer
8 |  | W | Poles are to be peeled and not machine shaved and not steam treated. All cut ends, notches or drill holes shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative before sealing with a bituminous sealer. Cut ends shall not be in contact with soil. | Prior to commencement | Visual Inspection | Engineer to inspect as accordance with specifications | Photos, log | Site Engineer | CPS
9 | Pile Material Compliance - Concrete | W | Concrete mix design(s) shall be submitted to the Engineer in writing prior to placing concrete and approved before placing concrete. | Prior to commencement | Document review | Engineer to approve design prior to commencement | Design Engineer Approval | Site Engineer | CPS
10 |  | M | All concrete delivered to site shall be produced strictly in accordance with the approved mix design | Prior to pouring concrete | Concrete Delivery Dockets | Site engineer to inspect delivery dockets | Concrete Delivery Dockets | Site Engineer
11 |  | M | The concrete used to backfill around the timber poles must have a minimum 28-day compressive strength of 20MPa. Concrete batch crush test supplied by concrete supplier for 28 days. | Each batch | Document review | 28 day strength of 20MPa | Test Reports, Lab Testing Register | Site Engineer
12 | Pile Line | M | Check if the bench the has been excavated/filled can accommodate the entire pile line | Prior to Commencement | Visual Inspection | Site engineer to inspect against relevant drawings | CS-4011 | Site Engineer
13 |  | W | Drilling is to be carried out for every second pole, and poles shall be placed and concreted for at least 24 hours before any drilling for intermediate holes | Each Pile | Visual Inspection | CPS engineer to inspect | Photos, log | Site Engineer | CPS
14 | Drill Rig Set Up | W | Check drilling performance, verticality and position using equipment of sufficient capacity for the ground conditions. | Each Pile | Visual Inspection | Site supervisor to inspect | CS-4011 & CS-4083 | Site Engineer | CPS
15 |  | W | Timber poles are installed in pre-drilled holes to the dimensions and at the locations and batters shown on the drawings, | Each Pile | Visual Inspection | CPS engineer to inspect inspect as accordance with specifications | Photos, log, site inspection | Site Engineer | CPS
16 | Pile Bore Condition & Logs | H | Inspect pile bore condition, pile depth, rock socket length and toe level | Each Pile | Visual Inspection | CPS engineer to inspect inspect as accordance with specifications | CS-4011 & CS-4083 | Site Engineer | CPS
17 |  | W | The Contractor shall maintain a log describing the type of soil and rock, the ground water level and the general ground conditions encountered in each hole excavation; hole location, reference number, and total depth of hole below ground level. | Each Pile | Document review, visual inspection | Information shall be provided to the Engineer at the end of each day's work. | Document | Site Engineer | CPS
18 |  | M | The chosen method of excavation shall minimise overbreak and prevent collapse of ground outside the hole excavation. All loose material is to be removed from the base of the hole before post installation and concreting | Each Pile | visual inspection | Areas of overbreak are to be reinstated in an approved manner | Monitor, inspect | Site Engineer
19 |  | M | The contactor must minimise the impact that the drilling has on the environment.All material collected from the drilling process will need to be removed from the site. | Each Pile | Document review | All drilling must be in line with the EMP and other environmental protection documents | Monitor, review document with Environmental team | Site Engineer
20 |  | M | Check that holes are not to be left open overnight. | Close of works each day | visual inspection | Site supervisor to check at close of works each day | Visual check | Site Engineer
21 | Pile Bore tolerances | H | The Contractor shall inform the Engineer for an inspection of the excavation by a suitably qualified geotechnical professional | Completion of stage or bore drilling | Inspection | Contractor to notify engineer Geotechnical Engineer to attend and approve excavation | Geotechnical Engineer Approval | Site Engineer | CPS
22 |  | H | The hole must be excavated to the tolerances outlined in the specifications | Each Pile | Inspection | l Pole hole diameter +50mm / -0mm l Hole plan position at all depths +/- 20mm l The pole shall not vary any more than 2 degrees from 20 degrees | Geotechnical Engineer Approval | Site Engineer | CPS
23 | Timber Pile tolerances | H | Timber poles shall then be set into the holes, complying with the tolerances outlined in the specifications | Each Pile | Inspection | l Deviation of pole centre from line in plan +/- 10mm l Pole top reduced level +/- 10mm l Pole base reduced level +/-50mm | Geotechnical Engineer Approval | Site Engineer | CPS
24 | Concrete Pumping Operations | M | Ensure the Permit to Concrete Pump & Pump Operator Checksheet has been completed before concrete pumping commences | Prior to commencement | Document review | Site Engineer to compete CP and PO checksheets | CS-4029 & CS-4002 | Site Engineer
25 | Concreting | M | Concrete pre pour inspection | Prior to concrete pour | Visual inspection | A pre pour inspection checksheet to be completed outlining: - Pre pour inspection checksheet to be completed | CS-4011/ TBD | Site Engineer
26 |  | M | Concrete dockets checked for correct mix and concrete site testing undertaken. Dockets to the Engineer and keep a record of the volume of concrete placed. | Prior to concrete pour | Test Results | NZS 3104 Concrete dockets match design | CS-4090 | Site Engineer
27 |  | M | The concrete in each hole shall be completed as one continuous operation | Each Pile | Inspection | Concrete Inspection Record | Photos, log, site inspection, Document | Site Engineer
28 |  | M | Securing of poles in position, then the approved concrete mix shall be poured around the timber pole with concrete being tremmied if required | Each Pile | Inspection | Concrete Inspection Record | Photos, log, site inspection, Document | Site Engineer
29 |  | M | Check concrete placement method and finish | At completion of pour | Visual Inspection, Document Review | Concrete Inspection Record | CS-4011 | Site Engineer
30 | Survey As Built | M | Survey final position and R.L. of each pile, produce As-Built drawings | Each Pile | Measurement / Survey | As-Built Drawing | Survey receipt | Site Engineer
31 | Lot Number QA File | M | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
32 |  | M | Check all piling records are completed and signed by the relevant signatory. | At completion of Lot | Document Review |  | All relevant documents | Site Engineer
33 | As-builts | M | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date: