## Timber Pole Retaining Wall
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C1603A Waikare Gorge Descent Retaining Wall |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Timber Pole Retaining Wall & backfill |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: 1 |  |  |  | Corresponding Work Instruction: |  | (insert Sharepoint link to Construction Work Plan folder here) |  | Compliance with Work Instructions and Specifications
Detailed Location: Waikare Gorge Descent Retaining Wall - SH2 RS577 RP13.922
Chainage: 13985.00m - 13980.00m
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Initials (Grey if not required) | Date(s)
1 | Survey Setout | H | Contractor to set out grid lines as per contract drawings and specification. | Prior to commencement | Inspection | Consistency with Construction Drawing | CPS Engineer Approval | Site Engineer | CPS
2 | Timber Lagging Material Compliance | W | The lagging must be radiata pine planks of normal density, . All . | Prior to commencement | Document review | The Engineer shall be provided with a certificate of compliance: l H4 treated in accordance with NZS 3640, H4 l Cut ends or notches shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative | Material receipt | Site Engineer
3 |  | M | Each section of lagging shall span a minimum of three poles. | Prior to commencement | Inspection | Inspect and document span of lagging | Photos, site inspection | Site Engineer
4 | Backfill Material Compliance | W | The granular aggregates for use behind the wall shall be open course graded clean washed durable aggregate | Prior to commencement | Document review | lCrushing resistance of not less than 100kN when tested in accordance with NZS 4407:1991 lBe crushed aggregate with a min. 50% broken faces (NZS 4407 Test 3.14); lFree of organic and other deleterious material; and lMeet the particle size grading envelope outlined in the specifications table in drawing C200 | Materials receipt, test results | Site Engineer | CPS
5 |  | W | The Contractor shall test a representative sample of the proposed granular aggregate to be used to determine the maximum dry density and optimum moisture content, standard compaction and the particle size distribution | Prior to commencement | Document review | lNZS 4402: 1986 Test 4.1.1, lNZS 4402: 1986 Test 2.8 .2 | Materials receipt, test results | Site Engineer | CPS
6 |  | W | The test results shall be no older than 3 months so that they represent the actual proposed materials. | Prior to commencement | Document review | Check testing results are less than 3 months old | Materials receipt, test results | Site Engineer
7 |  | M | All material sampling and testing shall be completed by a suitably qualified laboratory and laboratory personnel | Prior to commencement | Document review | l IANZ registered laboratory l laboratory certified to ISO 9001 or 9002 | Certification | Site Engineer
8 | Geotextile Material Compliance | W | The geotextile filter fabric lining the excavation and wall, Examples of acceptable materials are 'Duraforce AS410' and 'Bidim A29' or similar approved equivalent. | Prior to commencement | Document review | non-woven geotextile and meet the requirements of TNZ F/7:2003 for strength Class C and filtration Class 1 | Material receipt | Site Engineer | CPS
9 |  | M | The geotextile's properties, testing, storage and installation shall comply with the requirements of Transit NZ | Prior to commencement | Document review | TNZ F/7:2000 | Material receipt | Site Engineer | CPS
10 | Subsoil drainage Material Compliance | W | The subsoil drainage pipe shall be smooth bored, perforated 110mm dia. HDPE or PE complying with NZS 7604:1981 and TNZ F/2:2000. The perforations shall be circular 6.5 mm (+1.5 mm) in diameter, arranged as shown in the Appendix 1 of TNZ F/2:2000, “Pipe Subsoil Drain Construction”. | Prior to commencement | Document review | complying with: l NZS 7604:1981 l TNZ F/2:2000 | Material receipt | Site Engineer | CPS
11 |  | M | Outlet and connecting pipes shall be unperforated. | Prior to commencement | Document review, Visual Inspection | complying with: l NZS 7604:1981 l TNZ F/2:2000 | Material receipt, site inspection | Site Engineer
12 |  | W | The drainage pipe shall be wrapped in a drainage blanket geo-composite, such as 'Filter sleeve' or equivalent approved. | Prior to commencement | Document review, Visual Inspection | Confirm drainage blanket before install | Material receipt, site inspection | Site Engineer | CPS
13 | Timber Lagging Installation | M | The timber lagging shall be placed against the back of the poles so that they fit closely to the poles and to the lagging board below. Only lightweight compaction to be used within 0.5 m of lagging with care to avoid lagging deformation. All lagging joints shall be located against a pole. Lagging joints shall be staggered so that there is a continuous lagging board above and below each joint. | Pre/ During install | Visual Inspection | Confirm lagging is placed correctly, and no heavy compaction conducted within 0.5m | site inspection, Photos, log | Site Engineer
14 |  | M | The lagging shall be held in place using screws. No boards with obvious defects shall be used e.g. severe warping, knots etc. | Pre/ During install | Visual Inspection | Confirm and document screw installation is correct and lagging timber is appropriate | site inspection, Photos, log | Site Engineer
15 | Geotextile Filter fabric installation | M | Geotextile filter fabric shall be placed in the locations shown on the drawings. At joins the fabric shall be overlapped by a minimum of 200mm. | Pre/ During install | Visual Inspection | At joins overlapped by a minimum of 200mm | site inspection, Photos | Site Engineer
16 |  | M | The Contractor shall take care not to damage the fabric during installation. Any tears shall be repaired at the Contractors expense by placing additional fabric over the damaged area, with a 200mm overlap on all sides | Pre/ During install | Visual Inspection | tears shall be repaired by contractor, overlapped by a minimum of 200mm | site inspection, Photos | Site Engineer
17 | Subsoil Drainage | W | The subsoil shall be placed as shown on the drawings. Outlets from the subsoil shall be constructed to discharge water clear of the site, onto stable ground, with sufficient fall across the length of the subsoil pipe to prevent silting. | Pre/ During install | Visual Inspection | Outlets from the subsoil shall be constructed to discharge water clear of the site | site inspection, Photos | Site Engineer | CPS
18 |  | H | The location of the outlets shall be determined in conjunction with the Engineer on site | Pre install | Visual Inspection, Document review | HOLD POINT: CPS engineer to review and approve location of outlets | CPS Engineer Approval | Site Engineer | CPS
19 | Retaining Wall Backfill | W | The Contractor shall ensure that the method of placement and compaction permits safe labour about the excavation. | Prior to commencement | Document review, Visual Inspection | Temp works confirmation for excavation area, for placement and compaction | site inspection, Photos | Site Engineer | CPS
20 |  | M | Lightweight compaction shall be undertaken within 1 m of the wall face, to prevent damaging wall components. | Pre/ During install | Visual Inspection | Not heavy compaction works within 1m | site inspection, Photos | Site Engineer
21 |  | M | The backfill material shall be placed and compacted in layers of no more than 200mm loose depth. Each layer shall be compacted by hand operated mechanical plate compactors, heavy compaction may be used from 1 m behind the wall to aid compaction. Care shall be taken to avoid striking or damaging the wall components with compaction equipment. | Pre/ During install | Visual Inspection | layers of no more than 200mm loose depth compacted by hand operated mechanical plate compactors | site inspection, Photos | Site Engineer
22 |  | M | 1m behind the wall compaction requirements vary from within 1m. But Care shall be taken to avoid striking or damaging the wall components with compaction equipment. | Pre/ During install | Visual Inspection | Compaction shall be no less than 95% of the Maximum Dry Density heavy compaction may be used | site inspection, Photos | Site Engineer
23 |  | W | At least 3 sets of at least 5 NDM tests shall be carried out, Back-fill shall be compacted in layers no greater than 200 mm loose 'lifts'. Clegg Hammer tests shall be conducted every second lift along the length of the wall. | During install | Document review | l 3 sets of at least 5 NDM tests l Carried out at approx. 1/3, 2/3 and finish level. l Results shall be forwarded to the Engineer within 24 hours of the tests being carried out | site inspection, Photos, test results | Site Engineer | CPS
24 | Subsurface drainage | M | All the surface water should be diverted away from the proposed retaining wall. | Pre/ During install | Visual Inspection | Subsurface designed on site in a way to ensure surface water is diverted away from the retaining wall. | site inspection, Photos | Site Engineer | CPS
25 | Survey As Built | M | Ensure all works comply with design prior to carrying on with next construction process | At completion of sub soil drainage line | Survey |  | Survey receipt | Site Engineer
26 | Lot Number QA File | M | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
27 | As-builts |  | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction+B72 Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date:

## Sheet2
12 | 3 | 3 | 4 | 4 | 5