## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Gorge Descent - C1603A - Bored Pile | itp |  |  |  |  | ITP - Gorge Descent - C1603A - Bored Pile
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Contractor to set out grid lines as per contract drawings and specification.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Design Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Any services in the area are to be clearly marked before any work commence.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Service location conducted by asset owner, marked out with dazzle on site.
label | Records - Photos, log, site inspection
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - If the set out is found to be incorrect, the works shall again be set out by the Contractor and re- checked by the Engineer.
label | Records - Design Engineer Approval (RFI), ConQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Timber post spacing and clearance to be in line with the drawing specifications. Set out should allow for clearance, angle and spacing of centres
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - MAX 1.10m centres
label | ○ set at 4 degrees from vertical
label | ○ 100mm of clearance on all sides of pile
label | ○ 100mm minimum cover of concrete at base.
label | Records - Photos, log, site inspection
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Minimum Pole embedment to be as outlined in specifications
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Pole minimum embedment to be be 3.25m, unless otherwise stated in the pole schedule on drawing C013
label | Records - Photos, log, site inspection, ConQA
checkpoint | 6 - Pile Material Compliance - Timber Poles
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The timber poles are to be radiata pine, high density selected in accordance with and complying with NZS 3605:2001 for cross-section, length, straightness, strength and branding. All materials used in the works shall be new unless otherwise specified.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - The Engineer shall be provided with a certificate of compliance
label | Records - Document/ConQA
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The poles must be H5 treated in accordance with NZS 3640, H5.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - The Engineer shall be provided with a certificate of compliance that the poles have all been treated to NZS 3640, H5.
label | Records - Document/ ConQA
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Poles are to be peeled and not machine shaved and not steam treated. All cut ends, notches or drill holes shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative before sealing with a bituminous sealer. Cut ends shall not be in contact with soil.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineer to inspect as accordance with specifications
label | Records - Photos, log
checkpoint | 9 - Pile Material Compliance - Concrete
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Concrete mix design(s) shall be submitted to the Engineer in writing prior to placing concrete and approved before placing concrete.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Engineer to approve design prior to commencement
label | Records - Design Engineer Approval
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
label | Conformance Criteria - Site engineer to inspect delivery dockets
label | Records - Concrete Delivery Dockets
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The concrete used to backfill around the timber poles must have a minimum 28-day compressive strength of 20MPa. Concrete batch crush test supplied by concrete supplier for 28 days.
label | Frequency - Each batch
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - 28 day strength of 20MPa
label | Records - Test Reports, Lab Testing Register
checkpoint | 12 - Pile Line
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check if the bench the has been excavated/filled can accommodate the entire pile line
label | Frequency - Prior to Commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Site engineer to inspect against relevant drawings
label | Records - CS-4011
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Drilling is to be carried out for every second pole, and poles shall be placed and concreted for at least 24 hours before any drilling for intermediate holes
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS engineer to inspect
label | Records - Photos, log
checkpoint | 14 - Drill Rig Set Up
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check drilling performance, verticality and position using equipment of sufficient capacity for the ground conditions.
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Site supervisor to inspect
label | Records - CS-4011 & CS-4083
checkpoint | 15 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Timber poles are installed in pre-drilled holes to the dimensions and at the locations and batters shown on the drawings,
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS engineer to inspect, inspect as accordance with specifications
label | Records - Photos, log, site inspection
checkpoint | 16 - Pile Bore Condition & Logs
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect pile bore condition, pile depth, rock socket length and toe level
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS engineer to inspect, inspect as accordance with specifications
label | Records - CS-4011 & CS-4083
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The Contractor shall maintain a log describing the type of soil and rock, the ground water level and the general ground conditions encountered in each hole excavation; hole location, reference number, and total depth of hole below ground level.
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, visual inspection
label | Conformance Criteria - Information shall be provided to the Engineer at the end of each day's work.
label | Records - Document
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The chosen method of excavation shall minimise overbreak and prevent collapse of ground outside the hole excavation. All loose material is to be removed from the base of the hole before post installation and concreting
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - visual inspection
label | Conformance Criteria - Areas of overbreak are to be reinstated in an approved manner
label | Records - Monitor, inspect
checkpoint | 19 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The contactor must minimise the impact that the drilling has on the environment.All material collected from the drilling process will need to be removed from the site.
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - All drilling must be in line with the EMP and other environmental protection documents
label | Records - Monitor, review document with Environmental team
checkpoint | 20 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check that holes are not to be left open overnight.
label | Frequency - Close of works each day
label | Inspection / Test Method submission, visual inspection, testing, measure, review - visual inspection
label | Conformance Criteria - Site supervisor to check at close of works each day
label | Records - Visual check
checkpoint | 21 - Pile Bore tolerances
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Contractor shall inform the Engineer for an inspection of the excavation by a suitably qualified geotechnical professional
label | Frequency - Completion of stage or bore drilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Contractor to notify engineer, Geotechnical Engineer to attend and approve excavation
label | Records - Geotechnical Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The hole must be excavated to the tolerances outlined in the specifications
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Pole hole diameter +50mm / -0mm
label | ○ Hole plan position at all depths +/- 20mm
label | ○ The pole shall not vary any more than 2 degrees from 20 degrees
label | Records - Geotechnical Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 23 - Timber Pile tolerances
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Timber poles shall then be set into the holes, complying with the tolerances outlined in the specifications
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Deviation of pole centre from line in plan +/- 10mm
label | ○ Pole top reduced level +/- 10mm
label | ○ Pole base reduced level +/-50mm
label | Records - Geotechnical Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 24 - Concrete Pumping Operations
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure the Permit to Concrete Pump & Pump Operator Checksheet has been completed before concrete pumping commences
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Site Engineer to compete CP and PO checksheets
label | Records - CS-4029 & CS-4002
checkpoint | 25 - Concreting
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Concrete pre pour inspection
label | Frequency - Prior to concrete pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - A pre pour inspection checksheet to be completed outlining:
label | – Pre pour inspection checksheet to be completed
label | Records - CS-4011/ TBD
checkpoint | 26 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Concrete dockets checked for correct mix and concrete site testing undertaken. Dockets to the Engineer and keep a record of the volume of concrete placed.
label | Frequency - Prior to concrete pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Test Results
label | Conformance Criteria - NZS 3104 Concrete dockets match design
label | Records - CS-4090
checkpoint | 27 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The concrete in each hole shall be completed as one continuous operation
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Concrete Inspection Record
label | Records - Photos, log, site inspection, Document
checkpoint | 28 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Securing of poles in position, then the approved concrete mix shall be poured around the timber pole with concrete being tremmied if required
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Concrete Inspection Record
label | Records - Photos, log, site inspection, Document
checkpoint | 29 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check concrete placement method and finish
label | Frequency - At completion of pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | Conformance Criteria - Concrete Inspection Record
label | Records - CS-4011
checkpoint | 30 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Survey final position and R.L. of each pile, produce As-Built drawings
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement / Survey
label | Conformance Criteria - As-Built Drawing
label | Records - Survey receipt
checkpoint | 31 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 32 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check all piling records are completed and signed by the relevant signatory.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - All relevant documents
checkpoint | 33 - As-builts
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - Asbuilt Drawing