## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Waikare Gorge Descent - C1603A - Ground Anchor | itp |  |  |  |  | ITP - Waikare Gorge Descent - C1603A - Ground Anchor
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Test Anchor Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location of the tests (to be agreed with the Engineer, two tests shall be completed), and 1 pull test location.
label | Frequency - At least 1 week prior to Testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Consistency with Construction Drawing and agreed with Engineer
label | Records - Design Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Any services in the area are to be clearly marked before any work commence.
label | Frequency - At least 1 week prior to Testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Service location
label | Conformance Criteria - Service location conducted by asset owner, marked out with dazzle on site.
label | Records - Asset owner report, site inspection
checkpoint | 3 - Steel Anchor Rod Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Design Life of 30 years
label | ○ Design Working Load (DWL) per Anchor: 168kN
label | ○ Anchor rod diameter: minimum 25mm threaded bar, with a minimum yield strength of 500 Mpa
label | ○ Minimum anchor rod length: 12m
label | Frequency - At least 1 week prior to Testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Design Working Load (DWL) per Anchor: 168kN
label | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | Records - Materials receipt
checkpoint | 4 - Steel waler Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The steel structural sections for the Waler assemblies shall be primed with ethyl silicate or alkali silicate zinc rich primer in accordance with AS/NZS 4680, ASNZS 2312 Part 1 Paint Coatings and NZTA S9 respectively.
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - AS/NZS 3679.1, AS/NZS 4680, ASNZS 2312 Part 1
label | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | Records - Materials receipt
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The Contractor shall provide the engineer with test certificates giving the tensile and yield strengths of the steel used to manufacture the structural steels and steel plates at least seven days prior to the fabrication of waler.
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Test certificates of tensile and yield strengths, 7 days prior to installation, 150 mm x 75 mm PFC WALER BEAM
label | Records - Materials receipt, test results
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Confirmation of waler dimensions
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - 150 mm x 75 mm PFC WALER BEAM
label | Records - Materials receipt
checkpoint | 7 - Bearing Plate Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Bearing plates shall be steel with a minimum yield strength of 350MPa and the final size and thickness shall be confirmed by the Contractor in conjunction with the anchor supplier.
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - minimum yield strength of 350MPa
label | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | Records - Materials receipt
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Confirmation of plate dimensions
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - 16mm stiffener plates
label | ○ 150x150x20 plates
label | ○ 200x80x6 plates
label | ○ 250x300x16 plates
label | ○ 250x250x16 plates
label | ○ 100x100x6 washers
label | ○ 200x80x6 plates
label | Records - Materials receipt, test results
checkpoint | 9 - Hex nut/ Washer Plate Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Shall be standard, heavy-duty, high strength, structural quality only, flat base, machined from steel, designed for use with the all-threaded anchor rod.
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - conforming to Grade AS/NZS 1252
label | ○ Develop more than 125% of the yield strength of the anchor rod & ultimate strength of not less than 100% of the guaranteed ultimate tensile strength
label | ○ Hex nut/washer shall be hot dipped galvanised.
label | ○ Certified mill test results
label | Records - Materials receipt, test results
checkpoint | 10 - Mechanical Couplings Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Mechanical couplings, when required, may be used to splice the anchors.
label | ○ The couplings shall be stainless steel and wrapped in Denso Tape to satisfy double corrosion protection requirements.
label | ○ Grub screws or locknuts shall be installed and mechanically tightened either side of the mechanical couple
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Inspection
label | Conformance Criteria - 100% of the guaranteed ultimate tensile strength of the anchor rod
label | ○ Steel conforming to AS/NZS1252.
label | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | Records - Materials receipt, test results
checkpoint | 11 - Anchor Construction Submittals
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Contractor shall submit a construction plan and detailed construction sequence to the Engineer at least 1 week to commencing pull-out testing
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Document outlining Start date, working drawings, methods, manufacturer certificates, detailed construction sequence
label | Records - Submitted documents
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Anchor Construction Submittals - Working drawings
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The contractor needs to supply working drawings which outline the details and location of the pull out tests
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Installation method
label | ○ Location of the tests (approved by CPS)
label | ○ Testing methods and equipment
label | ○ Ground anchor Schedule
label | Records - Document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Anchor Construction Submittals - Ground Anchor Schedule
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The contractor needs to supply a ground anchor schedule which outlines the strength and detailing requirements:
label | ○ Ground anchor number
label | ○ Ground anchor DWL
label | ○ Ground anchor DUC
label | ○ Ground anchor capacity reduction factors for rod & pull-out
label | ○ Type and size of anchor rod;
label | ○ Anchor inclination;
label | ○ Minimum total anchor rod length;
label | ○ Corrosion protection system.
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Anchor submittal Document outlining strength and detailing meets specification
label | Records - Document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Anchor Construction Submittals - Testing Methods
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Details of the jacking frame and appurtenant bracing.
label | ○ Identification number and certified calibration records for each test jack and pressure gauge and
label | ○ load cell to be used. Calibration records to include the date tested, device identification number, and the calibration test results and shall be
label | ○ conducted by a qualified independent testing laboratory within forty-five (45) working days prior to submittal
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Anchor submittal Document outlining strength and detailing meets specification
label | ○ Certified for an accuracy of at least 2 percent of the applied certification loads
label | Records - Document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Anchor Construction Submittals - Testing equipment
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Testing equipment shall include dial gauges, dial gauge support, jack and pressure gauge, electronic load cell, and a reaction frame. Contractor shall provide the description to the Engineer prior to testing.
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - description of test setup and jack, pressure gauge and load cell calibration curves
label | Records - Document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The testing reaction frame shall be sufficiently rigid and of adequate dimensions such that excessive deformation of the testing equipment does not occur.
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Reaction frame sufficiently rigid
label | ○ Support and centre jackover anchor rod
label | ○ Jack, bearing plates and stressing anchorage aligned with rod to as not require repositioning during test
label | Records - Anchor Test log, photos, submittal doc
checkpoint | 17 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Test load shall use hydraulic jack and pressure gauge. The pressure gauge shall be graduated in 500 kPa increments or less. The jack and pressure gauge shall have a pressure range not exceeding twice the anticipated maximum test pressure.
label | ○ Monitor the anchor load during the pull-out test with both the pressure gauge and the load cell. Use the load cell to maintain constant load during the creep test portion of the pull-out test.
label | Frequency - Prior/ during testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, visual inspections
label | Conformance Criteria - Jack and pressure gauge shall have a pressure range within requirements
label | ○ Gauge graduated in specified increments
label | Records - Anchor testing submittal, Anchor testing log
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Measure the anchor head movement with a dial gauge capable of measuring to 0.025 mm. Use two dial gauges when the test setup requires reaction against a soil cut face.
label | Frequency - Prior/ during testing
label | Conformance Criteria - Gauge capable of 0.025mm used
label | ○ Sufficient travel to conduct test
label | ○ Visually aligned gauge parallel with axis of anchor
label | ○ Two gauges used during reaction against a soil cut face
label | Records - Visual inspection, photos, Anchor testing log
checkpoint | 19 - Anchor Construction Submittals - Ground anchor report
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - As-built drawings showing the location and orientation of each ground anchor, anchor capacity, total anchor length as installed. Ground anchor test results, graphs and supporting interpretation
label | Frequency - within twenty (20) calendar days after completing installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Ground anchor report sent to engineer within twenty (20) calendar days containing:
label | ○ Ground anchor test results
label | ○ As-built drawings
label | Records - Report, document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - Ground Anchors
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - store steel and accessories without damage or contamination. All materials shall be stored on timber pallets on hard ground in a secure area, clear of any construction operations.
label | Frequency - Throughout works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | Conformance Criteria - Stored on timber pallets
label | ○ Hard Ground
label | ○ Secure Area
label | Records - site inspection, Photos
checkpoint | 21 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Anchor components incorporated in the wall shall be free of corrosion and physical damage at the time of placement
label | Frequency - Throughout works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | Conformance Criteria - Free of corrosion and physical damage, Placed so will not damage ground
label | Records - site inspection, Photos
checkpoint | 22 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Works shall be carried out in accordance with NZGS (2023) Ground Anchors: Design and Construction Guideline. Should any discrepancies between the relevant codes and standards contained in the above Guideline and this Specification arise, they shall be brought to the attention of the Engineer
label | Frequency - During Installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | Conformance Criteria - NZGS (2023) Ground Anchors: Design and Construction Guideline
label | Records - site inspection, Photos
checkpoint | 23 - Ground Anchors - Tolerances
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Anchors shall be installed at an angle within ±2 degrees of the angle of the theoretical centreline and shall be located horizontally on the face of the wall accurately
label | Frequency - During Installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Angle within ±2 degrees of the angle of the theoretical centreline plus or minus 25 mm from the position shown on the drawings.
label | Records - site inspection, Photos
checkpoint | 24 - Ground Anchors - Anchor Testing
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - No-load greater than 10% of the design load can be applied to the ground anchor prior to testing. The maximum test load shall not exceed 80% of the specified minimum ultimate tensile strength of the anchor rod.
label | Frequency - During Installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection,
label | Conformance Criteria - Pull-Out Test Schedule <80% min ULT load
label | Records - Pull out test log
checkpoint | 25 - Ground Anchors - Pull out Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Pull-out testing shall be carried out on one sacrificial ground anchor, The pull-out test shall be done at a location and elevation agreed and approved by the Engineer.
label | Frequency - Prior to installation of anchors
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - Conducted prior to installation, Location approved by CPS Engineer
label | Records - Pull out test log, Submittal
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 26 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The pull-out test shall be carried out to 150% of the Design Working Load (DWL) and the contractor shall supply a larger anchor rod (if required) to safely accommodate the maximum test load. Anchor movements during the Creep Test shall be measured and recorded.
label | Frequency - During Pull out testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - Refer to the Pull out test schedule
label | – – – – – – – – – –
label | Pull-Out Test Schedule
label | – – – – – – – – – –
label | Load ¦¦ Hold Time
label | – – – – – – – – – –
label | 0.05 (DWL) ¦¦ 1 minute
label | 0.25 (DWL) ¦¦ 10 minutes
label | 0.5 (DWL) ¦¦ 10 minutes
label | 0.75 (DWL) ¦¦ 10 minutes
label | 1.00 (DWL) ¦¦ 10 minutes
label | 1.25 (DWL) ¦¦ 10 minutes
label | 1.50 (DWL) ¦¦ (creep test) 60 minutes
label | – – – – – – – – – –
label | ○ Recorded at 1, 2, 3, 5, 6, 10, 20, 30, 40, 50 and 60 minutes
label | ○ Maintained within 2% of the intended load
label | Records - Pull out test log
checkpoint | 27 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The alignment load (AL) should not exceed 5% of the DWL. Dial gauges should be set to zero after the alignment load has been applied.
label | Frequency - During Pull out testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - AL not exceed 5% of the DWL
label | Records - Pull out test log
checkpoint | 29 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The results of the pull-out test, along with calculations and their interpretation shall be forwarded to the Engineer
label | Frequency - During Pull out testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - Engineer to send through approval within 48 hours of receiving results
label | Records - Pull out test log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 30 - Ground Anchors - Proof Testing of Anchors
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The proof tests shall incrementally load each ground anchor in accordance with the Proof Test Loading Schedule and in conjunction with the specifications 5.7.3.3
label | Frequency - During Proof testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - Proof testing completed on two anchors as selected by the Engineer
label | Records - Anchor Proof test log
checkpoint | 31 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The maximum test load in a proof test shall maintain a constant load. The load-hold period shall start as soon as the maximum test load is applied and the ground anchor movement with respect to a fixed reference shall be measured
label | Frequency - During Proof testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - recorded at 1, 2, 3, 4, 5, 6 and 10 minutes. If creep test up to 10 minutes exceeds 1 mm, the maximum test load shall be held for an additional 50 minutes
label | Records - Anchor Proof test log
checkpoint | 32 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The remaining anchors should also be tested to the same methodology up to 1.00 of the DWL unless approved otherwise by the Engineer.
label | Frequency - During Proof out testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - Total movement within the 10 minute hold is less than 1 mm between 1 and 10 minutes.
label | Records - Anchor Proof test log
checkpoint | 33 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Survey final position and R.L. of each anchor, produce As-Built drawings
label | Frequency - Each anchor
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement / Survey
label | Conformance Criteria - As-Built Drawing
label | Records - Survey receipt
checkpoint | 34 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 35 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check all anchor records are completed and signed by the relevant signatory.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Document Review
checkpoint | 36 - As-builts
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing