## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Waikare Gorge Descent - C1603A - Retaining Wall & Backfill | itp |  |  |  |  | ITP - Waikare Gorge Descent - C1603A - Retaining Wall & Backfill
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Contractor to set out grid lines as per contract drawings and specification.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - CPS Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Timber Lagging Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The lagging must be radiata pine planks of normal density, All.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - The Engineer shall be provided with a certificate of compliance:
label | ○ H4 treated in accordance with NZS 3640, H4
label | ○ Cut ends or notches shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative
label | Records - Material receipt
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Each section of lagging shall span a minimum of three poles.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Inspect and document span of lagging
label | Records - Photos, site inspection
checkpoint | 4 - Backfill Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The granular aggregates for use behind the wall shall be open course graded clean washed durable aggregate
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Crushing resistance of not less than 100kN when tested in accordance with NZS 4407:1991
label | ○ Be crushed aggregate with a min. 50% broken faces (NZS 4407 Test 3.14);
label | ○ Free of organic and other deleterious material; and
label | ○ Meet the particle size grading envelope outlined in the specifications table in drawing C200
label | Records - Materials receipt, test results
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The Contractor shall test a representative sample of the proposed granular aggregate to be used to determine the maximum dry density and optimum moisture content, standard compaction and the particle size distribution
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - NZS 4402: 1986 Test 4.1.1, NZS 4402: 1986 Test 2.8 .2
label | Records - Materials receipt, test results
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The test results shall be no older than 3 months so that they represent the actual proposed materials.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Check testing results are less than 3 months old
label | Records - Materials receipt, test results
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All material sampling and testing shall be completed by a suitably qualified laboratory and laboratory personnel
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - IANZ registered laboratory, laboratory certified to ISO 9001 or 9002
label | Records - Certification
checkpoint | 8 - Geotextile Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The geotextile filter fabric lining the excavation and wall, Examples of acceptable materials are 'Duraforce AS410' and 'Bidim A29' or similar approved equivalent.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - non-woven geotextile and meet the requirements of TNZ F/7:2003 for strength Class C and filtration Class 1
label | Records - Material receipt
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The geotextile's properties, testing, storage and installation shall comply with the requirements of Transit NZ
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - TNZ F/7:2000
label | Records - Material receipt
checkpoint | 10 - Subsoil drainage Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The subsoil drainage pipe shall be smooth bored, perforated 110mm dia. HDPE or PE complying with NZS 7604:1981 and TNZ F/2:2000. The perforations shall be circular 6.5 mm (+1.5 mm) in diameter, arranged as shown in the Appendix 1 of TNZ F/2:2000, “Pipe Subsoil Drain Construction”.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - complying with:
label | ○ NZS 7604:1981
label | ○ TNZ F/2:2000
label | Records - Material receipt
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Outlet and connecting pipes shall be unperforated.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | Conformance Criteria - complying with:
label | ○ NZS 7604:1981
label | ○ TNZ F/2:2000
label | Records - Material receipt, site inspection
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The drainage pipe shall be wrapped in a drainage blanket geo-composite, such as 'Filter sleeve' or equivalent approved.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | Conformance Criteria - Confirm drainage blanket before install
label | Records - Material receipt, site inspection
checkpoint | 13 - Timber Lagging Installation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The timber lagging shall be placed against the back of the poles so that they fit closely to the poles and to the lagging board below. Only lightweight compaction to be used within 0.5 m of lagging with care to avoid lagging deformation.
label | ○ All lagging joints shall be located against a pole. Lagging joints shall be staggered so that there is a continuous lagging board above and below each joint.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Confirm lagging is placed correctly, and no heavy compaction conducted within 0.5m
label | Records - site inspection, Photos, log
checkpoint | 14 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The lagging shall be held in place using screws. No boards with obvious defects shall be used e.g. severe warping, knots etc.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Confirm and document screw installation is correct and lagging timber is appropriate
label | Records - site inspection, Photos, log
checkpoint | 15 - Geotextile Filter fabric installation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Geotextile filter fabric shall be placed in the locations shown on the drawings. At joins the fabric shall be overlapped by a minimum of 200mm.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - At joins overlapped by a minimum of 200mm
label | Records - site inspection, Photos
checkpoint | 16 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The Contractor shall take care not to damage the fabric during installation. Any tears shall be repaired at the Contractors expense by placing additional fabric over the damaged area, with a 200mm overlap on all sides
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - tears shall be repaired by contractor, overlapped by a minimum of 200mm
label | Records - site inspection, Photos
checkpoint | 17 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The subsoil shall be placed as shown on the drawings. Outlets from the subsoil shall be constructed to discharge water clear of the site, onto stable ground, with sufficient fall across the length of the subsoil pipe to prevent silting.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Outlets from the subsoil shall be constructed to discharge water clear of the site
label | Records - site inspection, Photos
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The location of the outlets shall be determined in conjunction with the Engineer on site
label | Frequency - Pre install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document review
label | Conformance Criteria - HOLD POINT: CPS engineer to review and approve location of outlets
label | Records - CPS Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - Retaining Wall Backfill
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The Contractor shall ensure that the method of placement and compaction permits safe labour about the excavation.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | Conformance Criteria - Temp works confirmation for excavation area, for placement and compaction
label | Records - site inspection, Photos
checkpoint | 20 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Lightweight compaction shall be undertaken within 1 m of the wall face, to prevent damaging wall components.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Not heavy compaction works within 1m
label | Records - site inspection, Photos
checkpoint | 21 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The backfill material shall be placed and compacted in layers of no more than 200mm loose depth. Each layer shall be compacted by hand operated mechanical plate compactors, heavy compaction may be used from 1 m behind the wall to aid compaction.
label | ○ Care shall be taken to avoid striking or damaging the wall components with compaction equipment.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compaction shall be no less than 95% of the Maximum Dry Density, heavy compaction may be used
label | Records - site inspection, Photos
checkpoint | 22 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - 1m behind the wall compaction requirements vary from within 1m. But Care shall be taken to avoid striking or damaging the wall components with compaction equipment.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compaction shall be no less than 95% of the Maximum Dry Density, heavy compaction may be used
label | Records - site inspection, Photos
checkpoint | 23 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - At least 3 sets of at least 5 NDM tests shall be carried out, Back-fill shall be compacted in layers no greater than 200 mm loose 'lifts'. Clegg Hammer tests shall be conducted every second lift along the length of the wall.
label | Frequency - During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - l 3 sets of at least 5 NDM tests
label | ○ Carried out at approx. 1/3, 2/3 and finish level.
label | ○ Results shall be forwarded to the Engineer within 24 hours of the tests being carried out
label | Records - site inspection, Photos, test results
checkpoint | 24 - Subsurface drainage
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All the surface water should be diverted away from the proposed retaining wall.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Subsurface designed on site in a way to ensure surface water is diverted away from the retaining wall.
label | Records - site inspection, Photos
checkpoint | 25 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all works comply with design prior to carrying on with next construction process
label | Frequency - At completion of sub soil drainage line
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
checkpoint | 26 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 27 - As-builts
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing