## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Waikare Gorge Descent - C1603A - Bored Pile | itp |  |  |  |  | ITP - Waikare Gorge Descent - C1603A - Bored Pile | dfd895ab-e858-4f4a-96ce-1a1e1215b4e4
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Contractor to set out grid lines as per contract drawings and specification.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Design Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Any services in the area are to be clearly marked before any work commence.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Service location conducted by asset owner, marked out with dazzle on site.
label | Records - Photos, log, site inspection
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - If the set out is found to be incorrect, the works shall again be set out by the Contractor and re- checked by the Engineer.
label | Records - Design Engineer Approval (RFI), ConQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Timber post spacing and clearance to be in line with the drawing specifications. Set out should allow for clearance, angle and spacing of centres
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - MAX 1.10m centres
label | ○ set at 4 degrees from vertical
label | ○ 100mm of clearance on all sides of pile
label | ○ 100mm minimum cover of concrete at base.
label | Records - Photos, log, site inspection
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Minimum Pole embedment to be as outlined in specifications
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Pole minimum embedment to be be 3.25m, unless otherwise stated in the pole schedule on drawing C013
label | Records - Photos, log, site inspection, ConQA
checkpoint | 6 - Pile Material Compliance - Timber Poles
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The timber poles are to be radiata pine, high density selected in accordance with and complying with NZS 3605:2001 for cross-section, length, straightness, strength and branding. All materials used in the works shall be new unless otherwise specified.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - The Engineer shall be provided with a certificate of compliance
label | Records - Document/ConQA
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The poles must be H5 treated in accordance with NZS 3640, H5.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - The Engineer shall be provided with a certificate of compliance that the poles have all been treated to NZS 3640, H5.
label | Records - Document/ ConQA
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Poles are to be peeled and not machine shaved and not steam treated. All cut ends, notches or drill holes shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative before sealing with a bituminous sealer. Cut ends shall not be in contact with soil.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineer to inspect as accordance with specifications
label | Records - Photos, log
checkpoint | 9 - Pile Material Compliance - Concrete
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Concrete mix design(s) shall be submitted to the Engineer in writing prior to placing concrete and approved before placing concrete.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Engineer to approve design prior to commencement
label | Records - Design Engineer Approval
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
label | Conformance Criteria - Site engineer to inspect delivery dockets
label | Records - Concrete Delivery Dockets
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The concrete used to backfill around the timber poles must have a minimum 28-day compressive strength of 20MPa. Concrete batch crush test supplied by concrete supplier for 28 days.
label | Frequency - Each batch
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - 28 day strength of 20MPa
label | Records - Test Reports, Lab Testing Register
checkpoint | 12 - Pile Line
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check if the bench the has been excavated/filled can accommodate the entire pile line
label | Frequency - Prior to Commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Site engineer to inspect against relevant drawings
label | Records - CS-4011
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Drilling is to be carried out for every second pole, and poles shall be placed and concreted for at least 24 hours before any drilling for intermediate holes
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS engineer to inspect
label | Records - Photos, log
checkpoint | 14 - Drill Rig Set Up
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check drilling performance, verticality and position using equipment of sufficient capacity for the ground conditions.
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Site supervisor to inspect
label | Records - CS-4011 & CS-4083
checkpoint | 15 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Timber poles are installed in pre-drilled holes to the dimensions and at the locations and batters shown on the drawings,
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS engineer to inspect, inspect as accordance with specifications
label | Records - Photos, log, site inspection
checkpoint | 16 - Pile Bore Condition & Logs
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect pile bore condition, pile depth, rock socket length and toe level
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS engineer to inspect, inspect as accordance with specifications
label | Records - CS-4011 & CS-4083
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The Contractor shall maintain a log describing the type of soil and rock, the ground water level and the general ground conditions encountered in each hole excavation; hole location, reference number, and total depth of hole below ground level.
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, visual inspection
label | Conformance Criteria - Information shall be provided to the Engineer at the end of each day's work.
label | Records - Document
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The chosen method of excavation shall minimise overbreak and prevent collapse of ground outside the hole excavation. All loose material is to be removed from the base of the hole before post installation and concreting
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - visual inspection
label | Conformance Criteria - Areas of overbreak are to be reinstated in an approved manner
label | Records - Monitor, inspect
checkpoint | 19 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The contactor must minimise the impact that the drilling has on the environment.All material collected from the drilling process will need to be removed from the site.
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - All drilling must be in line with the EMP and other environmental protection documents
label | Records - Monitor, review document with Environmental team
checkpoint | 20 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check that holes are not to be left open overnight.
label | Frequency - Close of works each day
label | Inspection / Test Method submission, visual inspection, testing, measure, review - visual inspection
label | Conformance Criteria - Site supervisor to check at close of works each day
label | Records - Visual check
checkpoint | 21 - Pile Bore tolerances
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Contractor shall inform the Engineer for an inspection of the excavation by a suitably qualified geotechnical professional
label | Frequency - Completion of stage or bore drilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Contractor to notify engineer, Geotechnical Engineer to attend and approve excavation
label | Records - Geotechnical Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The hole must be excavated to the tolerances outlined in the specifications
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Pole hole diameter +50mm / -0mm
label | ○ Hole plan position at all depths +/- 20mm
label | ○ The pole shall not vary any more than 2 degrees from 20 degrees
label | Records - Geotechnical Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 23 - Timber Pile tolerances
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Timber poles shall then be set into the holes, complying with the tolerances outlined in the specifications
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Deviation of pole centre from line in plan +/- 10mm
label | ○ Pole top reduced level +/- 10mm
label | ○ Pole base reduced level +/-50mm
label | Records - Geotechnical Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 24 - Concrete Pumping Operations
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure the Permit to Concrete Pump & Pump Operator Checksheet has been completed before concrete pumping commences
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Site Engineer to compete CP and PO checksheets
label | Records - CS-4029 & CS-4002
checkpoint | 25 - Concreting
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Concrete pre pour inspection
label | Frequency - Prior to concrete pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - A pre pour inspection checksheet to be completed outlining:
label | – Pre pour inspection checksheet to be completed
label | Records - CS-4011/ TBD
checkpoint | 26 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Concrete dockets checked for correct mix and concrete site testing undertaken. Dockets to the Engineer and keep a record of the volume of concrete placed.
label | Frequency - Prior to concrete pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Test Results
label | Conformance Criteria - NZS 3104 Concrete dockets match design
label | Records - CS-4090
checkpoint | 27 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The concrete in each hole shall be completed as one continuous operation
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Concrete Inspection Record
label | Records - Photos, log, site inspection, Document
checkpoint | 28 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Securing of poles in position, then the approved concrete mix shall be poured around the timber pole with concrete being tremmied if required
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Concrete Inspection Record
label | Records - Photos, log, site inspection, Document
checkpoint | 29 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check concrete placement method and finish
label | Frequency - At completion of pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | Conformance Criteria - Concrete Inspection Record
label | Records - CS-4011
checkpoint | 30 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Survey final position and R.L. of each pile, produce As-Built drawings
label | Frequency - Each Pile
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement / Survey
label | Conformance Criteria - As-Built Drawing
label | Records - Survey receipt
checkpoint | 31 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 32 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check all piling records are completed and signed by the relevant signatory.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - All relevant documents
checkpoint | 33 - As-builts
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - Asbuilt Drawing
checklist-flat | ITP - Waikare Gorge Descent - C1603A - Ground Anchor | itp |  |  |  |  | ITP - Waikare Gorge Descent - C1603A - Ground Anchor | 4c352ada-8bb8-4301-a3c3-d998d7d962f8
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Test Anchor Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location of the tests (to be agreed with the Engineer, two tests shall be completed), and 1 pull test location.
label | Frequency - At least 1 week prior to Testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Consistency with Construction Drawing and agreed with Engineer
label | Records - Design Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Any services in the area are to be clearly marked before any work commence.
label | Frequency - At least 1 week prior to Testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Service location
label | Conformance Criteria - Service location conducted by asset owner, marked out with dazzle on site.
label | Records - Asset owner report, site inspection
checkpoint | 3 - Steel Anchor Rod Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Design Life of 30 years
label | ○ Design Working Load (DWL) per Anchor: 168kN
label | ○ Anchor rod diameter: minimum 25mm threaded bar, with a minimum yield strength of 500 Mpa
label | ○ Minimum anchor rod length: 12m
label | Frequency - At least 1 week prior to Testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Design Working Load (DWL) per Anchor: 168kN
label | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | Records - Materials receipt
checkpoint | 4 - Steel waler Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The steel structural sections for the Waler assemblies shall be primed with ethyl silicate or alkali silicate zinc rich primer in accordance with AS/NZS 4680, ASNZS 2312 Part 1 Paint Coatings and NZTA S9 respectively.
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - AS/NZS 3679.1, AS/NZS 4680, ASNZS 2312 Part 1
label | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | Records - Materials receipt
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The Contractor shall provide the engineer with test certificates giving the tensile and yield strengths of the steel used to manufacture the structural steels and steel plates at least seven days prior to the fabrication of waler.
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Test certificates of tensile and yield strengths, 7 days prior to installation, 150 mm x 75 mm PFC WALER BEAM
label | Records - Materials receipt, test results
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Confirmation of waler dimensions
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - 150 mm x 75 mm PFC WALER BEAM
label | Records - Materials receipt
checkpoint | 7 - Bearing Plate Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Bearing plates shall be steel with a minimum yield strength of 350MPa and the final size and thickness shall be confirmed by the Contractor in conjunction with the anchor supplier.
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - minimum yield strength of 350MPa
label | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | Records - Materials receipt
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Confirmation of plate dimensions
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - 16mm stiffener plates
label | ○ 150x150x20 plates
label | ○ 200x80x6 plates
label | ○ 250x300x16 plates
label | ○ 250x250x16 plates
label | ○ 100x100x6 washers
label | ○ 200x80x6 plates
label | Records - Materials receipt, test results
checkpoint | 9 - Hex nut/ Washer Plate Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Shall be standard, heavy-duty, high strength, structural quality only, flat base, machined from steel, designed for use with the all-threaded anchor rod.
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - conforming to Grade AS/NZS 1252
label | ○ Develop more than 125% of the yield strength of the anchor rod & ultimate strength of not less than 100% of the guaranteed ultimate tensile strength
label | ○ Hex nut/washer shall be hot dipped galvanised.
label | ○ Certified mill test results
label | Records - Materials receipt, test results
checkpoint | 10 - Mechanical Couplings Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Mechanical couplings, when required, may be used to splice the anchors.
label | ○ The couplings shall be stainless steel and wrapped in Denso Tape to satisfy double corrosion protection requirements.
label | ○ Grub screws or locknuts shall be installed and mechanically tightened either side of the mechanical couple
label | Frequency - Prior to Install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Inspection
label | Conformance Criteria - 100% of the guaranteed ultimate tensile strength of the anchor rod
label | ○ Steel conforming to AS/NZS1252.
label | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | Records - Materials receipt, test results
checkpoint | 11 - Anchor Construction Submittals
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Contractor shall submit a construction plan and detailed construction sequence to the Engineer at least 1 week to commencing pull-out testing
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Document outlining Start date, working drawings, methods, manufacturer certificates, detailed construction sequence
label | Records - Submitted documents
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Anchor Construction Submittals - Working drawings
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The contractor needs to supply working drawings which outline the details and location of the pull out tests
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Installation method
label | ○ Location of the tests (approved by CPS)
label | ○ Testing methods and equipment
label | ○ Ground anchor Schedule
label | Records - Document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Anchor Construction Submittals - Ground Anchor Schedule
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The contractor needs to supply a ground anchor schedule which outlines the strength and detailing requirements:
label | ○ Ground anchor number
label | ○ Ground anchor DWL
label | ○ Ground anchor DUC
label | ○ Ground anchor capacity reduction factors for rod & pull-out
label | ○ Type and size of anchor rod;
label | ○ Anchor inclination;
label | ○ Minimum total anchor rod length;
label | ○ Corrosion protection system.
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Anchor submittal Document outlining strength and detailing meets specification
label | Records - Document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Anchor Construction Submittals - Testing Methods
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Details of the jacking frame and appurtenant bracing.
label | ○ Identification number and certified calibration records for each test jack and pressure gauge and
label | ○ load cell to be used. Calibration records to include the date tested, device identification number, and the calibration test results and shall be
label | ○ conducted by a qualified independent testing laboratory within forty-five (45) working days prior to submittal
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Anchor submittal Document outlining strength and detailing meets specification
label | ○ Certified for an accuracy of at least 2 percent of the applied certification loads
label | Records - Document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Anchor Construction Submittals - Testing equipment
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Testing equipment shall include dial gauges, dial gauge support, jack and pressure gauge, electronic load cell, and a reaction frame. Contractor shall provide the description to the Engineer prior to testing.
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - description of test setup and jack, pressure gauge and load cell calibration curves
label | Records - Document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The testing reaction frame shall be sufficiently rigid and of adequate dimensions such that excessive deformation of the testing equipment does not occur.
label | Frequency - One week prior to install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Reaction frame sufficiently rigid
label | ○ Support and centre jackover anchor rod
label | ○ Jack, bearing plates and stressing anchorage aligned with rod to as not require repositioning during test
label | Records - Anchor Test log, photos, submittal doc
checkpoint | 17 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Test load shall use hydraulic jack and pressure gauge. The pressure gauge shall be graduated in 500 kPa increments or less. The jack and pressure gauge shall have a pressure range not exceeding twice the anticipated maximum test pressure.
label | ○ Monitor the anchor load during the pull-out test with both the pressure gauge and the load cell. Use the load cell to maintain constant load during the creep test portion of the pull-out test.
label | Frequency - Prior/ during testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, visual inspections
label | Conformance Criteria - Jack and pressure gauge shall have a pressure range within requirements
label | ○ Gauge graduated in specified increments
label | Records - Anchor testing submittal, Anchor testing log
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Measure the anchor head movement with a dial gauge capable of measuring to 0.025 mm. Use two dial gauges when the test setup requires reaction against a soil cut face.
label | Frequency - Prior/ during testing
label | Conformance Criteria - Gauge capable of 0.025mm used
label | ○ Sufficient travel to conduct test
label | ○ Visually aligned gauge parallel with axis of anchor
label | ○ Two gauges used during reaction against a soil cut face
label | Records - Visual inspection, photos, Anchor testing log
checkpoint | 19 - Anchor Construction Submittals - Ground anchor report
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - As-built drawings showing the location and orientation of each ground anchor, anchor capacity, total anchor length as installed. Ground anchor test results, graphs and supporting interpretation
label | Frequency - within twenty (20) calendar days after completing installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Ground anchor report sent to engineer within twenty (20) calendar days containing:
label | ○ Ground anchor test results
label | ○ As-built drawings
label | Records - Report, document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - Ground Anchors
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - store steel and accessories without damage or contamination. All materials shall be stored on timber pallets on hard ground in a secure area, clear of any construction operations.
label | Frequency - Throughout works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | Conformance Criteria - Stored on timber pallets
label | ○ Hard Ground
label | ○ Secure Area
label | Records - site inspection, Photos
checkpoint | 21 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Anchor components incorporated in the wall shall be free of corrosion and physical damage at the time of placement
label | Frequency - Throughout works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | Conformance Criteria - Free of corrosion and physical damage, Placed so will not damage ground
label | Records - site inspection, Photos
checkpoint | 22 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Works shall be carried out in accordance with NZGS (2023) Ground Anchors: Design and Construction Guideline. Should any discrepancies between the relevant codes and standards contained in the above Guideline and this Specification arise, they shall be brought to the attention of the Engineer
label | Frequency - During Installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | Conformance Criteria - NZGS (2023) Ground Anchors: Design and Construction Guideline
label | Records - site inspection, Photos
checkpoint | 23 - Ground Anchors - Tolerances
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Anchors shall be installed at an angle within ±2 degrees of the angle of the theoretical centreline and shall be located horizontally on the face of the wall accurately
label | Frequency - During Installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Angle within ±2 degrees of the angle of the theoretical centreline plus or minus 25 mm from the position shown on the drawings.
label | Records - site inspection, Photos
checkpoint | 24 - Ground Anchors - Anchor Testing
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - No-load greater than 10% of the design load can be applied to the ground anchor prior to testing. The maximum test load shall not exceed 80% of the specified minimum ultimate tensile strength of the anchor rod.
label | Frequency - During Installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection,
label | Conformance Criteria - Pull-Out Test Schedule <80% min ULT load
label | Records - Pull out test log
checkpoint | 25 - Ground Anchors - Pull out Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Pull-out testing shall be carried out on one sacrificial ground anchor, The pull-out test shall be done at a location and elevation agreed and approved by the Engineer.
label | Frequency - Prior to installation of anchors
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - Conducted prior to installation, Location approved by CPS Engineer
label | Records - Pull out test log, Submittal
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 26 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The pull-out test shall be carried out to 150% of the Design Working Load (DWL) and the contractor shall supply a larger anchor rod (if required) to safely accommodate the maximum test load. Anchor movements during the Creep Test shall be measured and recorded.
label | Frequency - During Pull out testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - Refer to the Pull out test schedule
label | – – – – – – – – – –
label | Pull-Out Test Schedule
label | – – – – – – – – – –
label | Load ¦¦ Hold Time
label | – – – – – – – – – –
label | 0.05 (DWL) ¦¦ 1 minute
label | 0.25 (DWL) ¦¦ 10 minutes
label | 0.5 (DWL) ¦¦ 10 minutes
label | 0.75 (DWL) ¦¦ 10 minutes
label | 1.00 (DWL) ¦¦ 10 minutes
label | 1.25 (DWL) ¦¦ 10 minutes
label | 1.50 (DWL) ¦¦ (creep test) 60 minutes
label | – – – – – – – – – –
label | ○ Recorded at 1, 2, 3, 5, 6, 10, 20, 30, 40, 50 and 60 minutes
label | ○ Maintained within 2% of the intended load
label | Records - Pull out test log
checkpoint | 27 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The alignment load (AL) should not exceed 5% of the DWL. Dial gauges should be set to zero after the alignment load has been applied.
label | Frequency - During Pull out testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - AL not exceed 5% of the DWL
label | Records - Pull out test log
checkpoint | 29 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The results of the pull-out test, along with calculations and their interpretation shall be forwarded to the Engineer
label | Frequency - During Pull out testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - Engineer to send through approval within 48 hours of receiving results
label | Records - Pull out test log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 30 - Ground Anchors - Proof Testing of Anchors
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The proof tests shall incrementally load each ground anchor in accordance with the Proof Test Loading Schedule and in conjunction with the specifications 5.7.3.3
label | Frequency - During Proof testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - Proof testing completed on two anchors as selected by the Engineer
label | Records - Anchor Proof test log
checkpoint | 31 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The maximum test load in a proof test shall maintain a constant load. The load-hold period shall start as soon as the maximum test load is applied and the ground anchor movement with respect to a fixed reference shall be measured
label | Frequency - During Proof testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - recorded at 1, 2, 3, 4, 5, 6 and 10 minutes. If creep test up to 10 minutes exceeds 1 mm, the maximum test load shall be held for an additional 50 minutes
label | Records - Anchor Proof test log
checkpoint | 32 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The remaining anchors should also be tested to the same methodology up to 1.00 of the DWL unless approved otherwise by the Engineer.
label | Frequency - During Proof out testing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | Conformance Criteria - Total movement within the 10 minute hold is less than 1 mm between 1 and 10 minutes.
label | Records - Anchor Proof test log
checkpoint | 33 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Survey final position and R.L. of each anchor, produce As-Built drawings
label | Frequency - Each anchor
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement / Survey
label | Conformance Criteria - As-Built Drawing
label | Records - Survey receipt
checkpoint | 34 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 35 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check all anchor records are completed and signed by the relevant signatory.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Document Review
checkpoint | 36 - As-builts
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
checklist-flat | ITP - Waikare Gorge Descent - C1603A - Retaining Wall & Backfill | itp |  |  |  |  | ITP - Waikare Gorge Descent - C1603A - Retaining Wall & Backfill | e4173bd3-2a17-4f67-a764-abb84968d108
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Contractor to set out grid lines as per contract drawings and specification.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - CPS Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Timber Lagging Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The lagging must be radiata pine planks of normal density, All.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - The Engineer shall be provided with a certificate of compliance:
label | ○ H4 treated in accordance with NZS 3640, H4
label | ○ Cut ends or notches shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative
label | Records - Material receipt
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Each section of lagging shall span a minimum of three poles.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Inspect and document span of lagging
label | Records - Photos, site inspection
checkpoint | 4 - Backfill Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The granular aggregates for use behind the wall shall be open course graded clean washed durable aggregate
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Crushing resistance of not less than 100kN when tested in accordance with NZS 4407:1991
label | ○ Be crushed aggregate with a min. 50% broken faces (NZS 4407 Test 3.14);
label | ○ Free of organic and other deleterious material; and
label | ○ Meet the particle size grading envelope outlined in the specifications table in drawing C200
label | Records - Materials receipt, test results
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The Contractor shall test a representative sample of the proposed granular aggregate to be used to determine the maximum dry density and optimum moisture content, standard compaction and the particle size distribution
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - NZS 4402: 1986 Test 4.1.1, NZS 4402: 1986 Test 2.8 .2
label | Records - Materials receipt, test results
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The test results shall be no older than 3 months so that they represent the actual proposed materials.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Check testing results are less than 3 months old
label | Records - Materials receipt, test results
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All material sampling and testing shall be completed by a suitably qualified laboratory and laboratory personnel
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - IANZ registered laboratory, laboratory certified to ISO 9001 or 9002
label | Records - Certification
checkpoint | 8 - Geotextile Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The geotextile filter fabric lining the excavation and wall, Examples of acceptable materials are 'Duraforce AS410' and 'Bidim A29' or similar approved equivalent.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - non-woven geotextile and meet the requirements of TNZ F/7:2003 for strength Class C and filtration Class 1
label | Records - Material receipt
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The geotextile's properties, testing, storage and installation shall comply with the requirements of Transit NZ
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - TNZ F/7:2000
label | Records - Material receipt
checkpoint | 10 - Subsoil drainage Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The subsoil drainage pipe shall be smooth bored, perforated 110mm dia. HDPE or PE complying with NZS 7604:1981 and TNZ F/2:2000. The perforations shall be circular 6.5 mm (+1.5 mm) in diameter, arranged as shown in the Appendix 1 of TNZ F/2:2000, “Pipe Subsoil Drain Construction”.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - complying with:
label | ○ NZS 7604:1981
label | ○ TNZ F/2:2000
label | Records - Material receipt
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Outlet and connecting pipes shall be unperforated.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | Conformance Criteria - complying with:
label | ○ NZS 7604:1981
label | ○ TNZ F/2:2000
label | Records - Material receipt, site inspection
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The drainage pipe shall be wrapped in a drainage blanket geo-composite, such as 'Filter sleeve' or equivalent approved.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | Conformance Criteria - Confirm drainage blanket before install
label | Records - Material receipt, site inspection
checkpoint | 13 - Timber Lagging Installation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The timber lagging shall be placed against the back of the poles so that they fit closely to the poles and to the lagging board below. Only lightweight compaction to be used within 0.5 m of lagging with care to avoid lagging deformation.
label | ○ All lagging joints shall be located against a pole. Lagging joints shall be staggered so that there is a continuous lagging board above and below each joint.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Confirm lagging is placed correctly, and no heavy compaction conducted within 0.5m
label | Records - site inspection, Photos, log
checkpoint | 14 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The lagging shall be held in place using screws. No boards with obvious defects shall be used e.g. severe warping, knots etc.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Confirm and document screw installation is correct and lagging timber is appropriate
label | Records - site inspection, Photos, log
checkpoint | 15 - Geotextile Filter fabric installation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Geotextile filter fabric shall be placed in the locations shown on the drawings. At joins the fabric shall be overlapped by a minimum of 200mm.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - At joins overlapped by a minimum of 200mm
label | Records - site inspection, Photos
checkpoint | 16 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The Contractor shall take care not to damage the fabric during installation. Any tears shall be repaired at the Contractors expense by placing additional fabric over the damaged area, with a 200mm overlap on all sides
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - tears shall be repaired by contractor, overlapped by a minimum of 200mm
label | Records - site inspection, Photos
checkpoint | 17 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The subsoil shall be placed as shown on the drawings. Outlets from the subsoil shall be constructed to discharge water clear of the site, onto stable ground, with sufficient fall across the length of the subsoil pipe to prevent silting.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Outlets from the subsoil shall be constructed to discharge water clear of the site
label | Records - site inspection, Photos
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The location of the outlets shall be determined in conjunction with the Engineer on site
label | Frequency - Pre install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document review
label | Conformance Criteria - HOLD POINT: CPS engineer to review and approve location of outlets
label | Records - CPS Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - Retaining Wall Backfill
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The Contractor shall ensure that the method of placement and compaction permits safe labour about the excavation.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | Conformance Criteria - Temp works confirmation for excavation area, for placement and compaction
label | Records - site inspection, Photos
checkpoint | 20 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Lightweight compaction shall be undertaken within 1 m of the wall face, to prevent damaging wall components.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Not heavy compaction works within 1m
label | Records - site inspection, Photos
checkpoint | 21 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The backfill material shall be placed and compacted in layers of no more than 200mm loose depth. Each layer shall be compacted by hand operated mechanical plate compactors, heavy compaction may be used from 1 m behind the wall to aid compaction.
label | ○ Care shall be taken to avoid striking or damaging the wall components with compaction equipment.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compaction shall be no less than 95% of the Maximum Dry Density, heavy compaction may be used
label | Records - site inspection, Photos
checkpoint | 22 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - 1m behind the wall compaction requirements vary from within 1m. But Care shall be taken to avoid striking or damaging the wall components with compaction equipment.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compaction shall be no less than 95% of the Maximum Dry Density, heavy compaction may be used
label | Records - site inspection, Photos
checkpoint | 23 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - At least 3 sets of at least 5 NDM tests shall be carried out, Back-fill shall be compacted in layers no greater than 200 mm loose 'lifts'. Clegg Hammer tests shall be conducted every second lift along the length of the wall.
label | Frequency - During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - l 3 sets of at least 5 NDM tests
label | ○ Carried out at approx. 1/3, 2/3 and finish level.
label | ○ Results shall be forwarded to the Engineer within 24 hours of the tests being carried out
label | Records - site inspection, Photos, test results
checkpoint | 24 - Subsurface drainage
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All the surface water should be diverted away from the proposed retaining wall.
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Subsurface designed on site in a way to ensure surface water is diverted away from the retaining wall.
label | Records - site inspection, Photos
checkpoint | 25 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all works comply with design prior to carrying on with next construction process
label | Frequency - At completion of sub soil drainage line
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
checkpoint | 26 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 27 - As-builts
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing