## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Quality - Cable Tray / Ladder
| Scope |  |  | Site QA
Rows
|  | Terminal - Lots - Cable Tray & Conduits - Basement - CABLE TRAY | dynamic | Site QA | Terminal | Lots - Cable Tray & Conduits | Basement - CABLE TRAY
|  | Terminal - Lots - Cable Tray & Conduits - Upper Basement - CABLE TRAY | dynamic | Site QA | Terminal | Lots - Cable Tray & Conduits | Upper Basement - CABLE TRAY
|  | Terminal - Lots - Cable Tray & Conduits - Ground Floor - CABLE TRAY | dynamic | Site QA | Terminal | Lots - Cable Tray & Conduits | Ground Floor - CABLE TRAY
|  | Terminal - Lots - Cable Tray & Conduits - Second Floor | dynamic | Site QA | Terminal | Lots - Cable Tray & Conduits | Second Floor
|  | Terminal - Lots - Cable Tray & Conduits - Landside - Switchrooms | dynamic | Site QA | Terminal | Lots - Cable Tray & Conduits | Landside | Switchrooms
|  | TERS - LOTS - CABLE TRAY & CONDUIT | dynamic | Site QA | TERS | LOTS - CABLE TRAY & CONDUIT
|  | FUEL FARM - LOTS - CABLE TRAY & CONDUIT | dynamic | Site QA | FUEL FARM | LOTS - CABLE TRAY & CONDUIT
Columns
|  | Receipt of Cable Tray delivery to site & storage |  | Receipt of Cable Tray delivery to site & storage
|  | Set out to be confirmed with latest AFC Drawings |  | Set out to be confirmed with latest AFC Drawings
|  | Accessories to be factory made items |  | Accessories to be factory made items
|  | Correct Levelling & Alignment |  | Correct Levelling & Alignment
|  | Correct bracket & safe fixing |  | correct bracket and safe fixing
|  | Correct Bends used (Cable Ladder) |  | Correct Bends used (Cable Ladder)
|  | Cable Tray Checked For Sharp Edges |  | Cable Tray Checked For Sharp Edges
|  | Containment Earthing - As Per the Standards |  | Containment Earthing - As Per the Standards
|  | Photos attached |  | Photos attached.
Quality - In Ground Conduit Install
| Scope |  |  | Site QA
Rows
|  | Terminal - Lots - Cable Tray & Conduits - Landside - In Ground HV CONDUITS - LOTS | dynamic | Site QA | Terminal | Lots - Cable Tray & Conduits | Landside | In Ground HV CONDUITS | LOTS
|  | Terminal - Lots - Cable Tray & Conduits - Landside - LV AND ICN CONDUIT INSTALL | dynamic | Site QA | Terminal | Lots - Cable Tray & Conduits | Landside | LV AND ICN CONDUIT INSTALL
|  | Terminal - Lots - Cable Tray & Conduits - Landside - Switchrooms | dynamic | Site QA | Terminal | Lots - Cable Tray & Conduits | Landside | Switchrooms
|  | TERS - LOTS - CABLE TRAY & CONDUIT | dynamic | Site QA | TERS | LOTS - CABLE TRAY & CONDUIT
|  | FUEL FARM - LOTS - CABLE TRAY & CONDUIT | dynamic | Site QA | FUEL FARM | LOTS - CABLE TRAY & CONDUIT
Columns
|  | Receipt of conduit delivery to site & storage |  | Receipt of conduit delivery to site & storage. (ITP Reference Item 1)
|  | Set out |  | Set out. (ITP Reference Item 2)
|  | Excavation - Correct trenching alignment & depth |  | Excavation - Correct trenching alignment & depth. (ITP Reference Item 3)
|  | Conduit Installation |  | Conduit Installation. (ITP Reference Item 4)
|  | Spacer Frame Installation |  | Spacer Frame Installation. (ITP Reference Item 5)
|  | Change of direction/bend Installation, correct bending radius used as per drawing |  | Change of direction/bend Installation, correct bending radius used as per drawing. (ITP Reference Item 6)
|  | Bellmouths installed within Insitu Pits |  | Bellmouths installed within Insitu Pits. (ITP Reference Item 7)
|  | Glue Conduits together |  | Glue Conduits together. (ITP Reference Item 8)
|  | TSB Installation around & above conduits |  | TSB Installation around & above conduits. (ITP Reference Item 9)
|  | 150mm cover of backfill above TSB |  | 150mm cover of backfill above TSB. (ITP Reference Item 10)
|  | Warning tape installation above 150mm cover |  | Warning tape installation above 150mm cover. (ITP Reference Item 11)
|  | Back fill & compact |  | Back fill & compact. (ITP Reference Item 12)
|  | Rope & pathway test |  | Rope & pathway test. (ITP Reference Item 13)
|  | Sealing of conduits |  | Sealing of conduits. (ITP Reference Item 14) HOLD POINT
Quality - Precast Pit Install
| Scope |  |  | Site QA
Rows
Columns
Quality - Inground LV & Communication Conduits
| Scope |  |  | Site QA
Rows
Columns
Quality - Transformer Installation
| Scope |  |  | Site QA
Rows
Columns
MAIN DISTRIBUTION BOARDS
| Scope |  |  | Site QA
Rows
Columns
Quality - Distribution Boards
| Scope |  |  | Site QA
Rows
Columns