## CHK-CIV-RSS Fill Installation
ConQA Team Notes:
Document Title: |  | CHK-004-STR-BRUNT-RSS Walls-Fill Placement
Check list Description: |  | RSS Walls-Fill Placement
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2023-07-12
ITP created by: |  | Jon De Castro
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | To be Available for Brunt Rd Only
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Soil Reinforcement-Straps | VR682.08 IFC Drawings | Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels. Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing. | Visual | Each strap | IP | SE/PE | This Checklist Signed-off
2 | Soil reinforcements-Connections | Installation Manual | Correct number of reinforcing element shall be attached to each panel | Visual | Each panel | IP | SE/PE | This Checklist Signed-off
3 | Soil reinforcements-Connections | IFC Drawings | Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel - Bolts are to be snug tight. | Visual | Each Fill Layer | IP | SE/PE | This Checklist Signed-off
4 | Soil reinforcements-Plan arrangement | IFC Drawings | Plan positions of Grid Strips are to be as per IFC Drawings. - Grid Strips shall not overlapped | Visual | Each Fill Layer | IP | SE/PE | This Checklist Signed-off
5 | Soil reinforcements-Plan arrangement | IFC Drawings VR682.06 | Plan positions of Grid Strips are to be as IFC Drawings. - Grid Strips are not to pass over pile cap. RSS used in conjunction with a bridge abutment shall be independent of the bridge structure. | Visual | Where applicable | IP | SE/PE | This Checklist Signed-off
6 | Soil reinforcements-vertical deviation | IFC Drawings MRP-052-C-RFL-DRG-33-CBE-CSW-1702 | The vertical deviation of the soil reinforcement shall be within +1% (upwards) and -0.3% (downwards) of the soil reinforcement length, relative to the connection height. Avoid clash with drainage as directed in IFC Drawings. | Measure Survey | Each fill Layer | IP | Surveyor/SE | This Checklist Signed-off
7 | Fill-Pacement | VR204.10 VR682.16 | Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm. All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps. Plant or vehicles shall not be allowed to traffic over or work on reinforcing elements until the reinforcement is protected by a minimum 150 mm layer of fill material. | Measure Visual | Each fill layer | IP | PE/SE/Supervisor | This Checklist Signed-off
8 | Select backfill-moisture content | IFC Drawings | Moisture content of the backfill shall be maintained evenly at all times. Moisture content shall be within +0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry. [Free Text] Attach Test Reults | Documet review | Each Fill Layer | IP | PE/SE | This Checklist Signed-off
9 | Select backfil - placement | IFC Drawings | Select backfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density. Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system. No large compaction equipment shall be allowed in this zon. Compaction beyond 1 meter of the wall face shall be in accordance with Temporary works design. | Measure Visual | Each fill layer | IP | PE/SE/Supervisor | This Checklist Signed-off
10 | Test Roll / Proof Roll | Section 173.03 Section 204.12 | All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling | Visual Inspection | Each fill layer | HP | Nominated Authority | This Checklist Signed-off ConQA HP Release
11 | Compaction and Moisture Content Testing Frequency & Acceptance | IFC Drawings VR 204.14 Table 204.131 VR 682.16 | Testing frequency shall be in accordance with Vicroad Specification section 204.14 (Scale A) The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed. Compaction Requirement to be Scale A: Characteristic Density Ratio 99%. (6 tests per lot) Lot size: Type A Material - the lesser of one day's production or 5000sqm Attach: Compaction & Moisture Content Test Results | Review Document Measure | Each Fill Layer | IP | SE/PE/SPE | This Checklist Signed-off
12 | Post Compaction Material Property Testing | IFC Drawings | Material Properties Testing (Scale A) CBR ≥ 8% and Swell ≤ 1.5% LL ≤ 30% PI ≤ 12% Grading: 150mm 100% 37.5mm 60-100% 9.5mm 25-100% 2.36mm 15-100% 0.60mm 10-100% 0.075mm 0-15% Select backfill must meet the minimum requirements of VR Section 204 for Type A Filling. Attach: Post Compaction Material Property Test Results | Review Document Measure | Each Fill Layer | IP | SE/PE/SPE | This Checklist Signed-off
13 | As-built Conformance Survey | MRPA Quality Management Plan | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances Attach: Survey As-built / Survey Report | Document Review | Each Fill Layer | IP | Surveyor SE/PE/SPE | This Checklist Signed-off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /