## CHK-CIV-RSS Pre-cast panel
ConQA Team Notes:
Document Title: |  | CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation
ITP Description: |  | RSS Walls-Precast Panel Installation
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2023-07-12
ITP created by: |  | Thilan Rathnayake
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | To be Available for Brunt Road Only
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Panels-survey set out-Tolerance | IFC Drawings VR 682.20 | Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations) Above must be checked with surveyor prior to backfill | Measure | Base course panels | IP | Surveyor/PE | This Checklist Signed-off
2 | Mark-up panel for construction team | Construction Manual | - Mark number of strips per row on the back of each panel. - Mark design locatoin (Wall number, row and column) as per elevation drawings on the back of each panel | Visual | Each panel | IP | SE/Supervisor | This Checklist Signed-off
3 | Panel installation | IFC Drawings | RSS Panels are to be installed as per IFC Drawings and specified schedule. - Check for correct architectural pattern - Check for Weephole Locations - Check the 19mm nominal gap to be maintained between panels - Check the min 1:40 slope to be maintained (RSS Panels must lean backwards to this slope) - Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall - Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm - Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap - the wall level shall not deviate from the specified level by more than ±20mm - the tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height - The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V) Above must be checked with Surveyor prior to backfill | Visual Measure | Each panel | IP | SE/Supervisor | This Checklist Signed-off
4 | Panel installation- Corner Panels and Panels interfacing Abutment | IFC Drawings | - 20mm nominal gap between panels and Abutment wall is to be mainatined - 300mm wide x 6mm thk Galvanized plates fixed to abutment wall and Adjacent panel as per IFC drawings. - 600mm wide BITAC tape installed Folded plates must be installed installed at coner panels and panels adjecent to abutments Above must be checked with Surveyor prior to backfill | Measure | Where applicable | IP | SE/PE | This Checklist Signed-off
5 | Install Rubber Bearing Pads | IFC Drawings | 3X19mm bearing pads must be installed per panel - Centre of the outer bearing pads must be 200mm+/-10mm from the edge of the panel Above must be checked with Surveyor prior to backfill | Visual Measure | Each panel | IP | SE/Supervisor | This Checklist Signed-off
6 | Filter fabric -Installation | IFC Drawings VR 682.11 | Install Filter Fabric against all vertical and horizontal joints | Visual | Each course of panel installation | IP | SE/Supervisor | This Checklist Signed-off
7 | Drainage-Vertical Strip Drain | IFC Drawings VR 682.11 | Install 300mm wide vertical strip drain as per IFC Drawings and in accordance with VR 682.11 at every vertical joint between panels in RSS wall. Ensure no gap is formed between strip drain and RSS panels | Visual Measure | Each course of panel installation | IP | SE/Supervisor | This Checklist Signed-off
8 | Panel installation-Survey reference points | VR 682.21 | To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS | Visual | Each course of panel installation | IP | Surveyor/SE | This Checklist Signed-off
9 | Traceability of precast units and records | VR 620.09 | Unique ID of precast panel is recorded. ATTACH: marked-up elevation drawings or installation record with reference to panel ID | Visual | Each panel | IP | SE/PE | This Checklist Signed-off
10 | Panels installation - As-built Conformance Survey | IFC Drawings VR 682.06 VR 682.17 VR 682.20 | The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions - Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall - Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm - Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap - the wall level shall not deviate from the specified level by more than ±20mm - the tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height - The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V) Above must be checked with Surveyor prior to backfill Attach: Conformance Survey Report | Survey Measure | Each course of panel installation | HP* | Surveyor/PE | This Checklist Signed-off
11 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This Checklist Signed-off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /