## Sheet1
ConQA Team Notes:
Document Title: |  | CHK-006-STR-BRUNT-RSS Walls-Precast Panel Material Inspection
ITP Description: |  | RSS Walls-Precast Panel Material Inspection
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2023-07-12
ITP created by: |  | Jon De Castro
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | To be Available for Brunt Road Only
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Delivery Details | Delivery Dockets/ Packing List | Enter: Delivery Docket Number: [Free text box]: Enter: Delivery Date: [Free text box]: Enter:Element ID / Birth Certificate: [Free text box]: Attach: Delivery Docket and packaging Slip | Document Review Visual | Each Delivery | IP | PE/SE | This Checklist Signed Off
2 | Packaging Inspection-Quantity | Delivery Dockets/ Packing List | Does the number of packages in the delivery match that listed on the freight list/packaging slip? | Visual | Each Delivery | IP | PE/SE | This Checklist Signed Off
3 | Packaging Inspection-Delivery Contents | Delivery Dockets/ Packing List | Do the contents of the delivery match the freight list/packaging slip? | Document Review Visual | Each Delivery | IP | PE/SE | This Checklist Signed Off
4 | Packaging Inspection-Birth Certificate | Delivery Dockets/ Packing List / Panel IDs | Is the delivery accompanied by Precast items Birth Certificates? Precast components are to be marked on the birth certificate. Cast date and lot are to be marked on the birth certificate. | Document Review | Each Precast item | IP | PE/SE | This Checklist Signed Off
5 | Packaging Inspection-Transport | Delivery Dockets/ Packing List | Is the condition of packaging acceptable. Precast items are protected from damage during the transport | Visual | Each Precast item | IP | PE/SE | This Checklist Signed Off
6 | Fault IDs: | Delivery Dockets/ Packing List/ IFC Drawings | For each precast type delivered, check for the following: 1-Identification markings match the panel type 2-Panels fabricated as per drawings 3-Cracks 4-Spalling/Damage to concrete surface 5-Exposed Reinforcement 6-Damage to Anti-Graffiti coating 7-Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist Signed Off
7 | Check for Faults - 1 | Item 6 on this Checklist | For Each Precast type delivered: Enter: Panel Identificatio:[FREE TEXT BOX]: Enter:Quantity:[FREE TEXT BOX]: Enter:Fault ID if any:[FREE TEXT BOX]: | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist Signed Off
8 | Check for Faults - 2 | Item 6 on this Checklist | For Each Precast type delivered: Enter: Panel Identificatio:[FREE TEXT BOX]: Enter:Quantity:[FREE TEXT BOX]: Enter:Fault ID if any:[FREE TEXT BOX]: | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist Signed Off
9 | Check for Faults - 3 | Item 6 on this Checklist | For Each Precast type delivered: Enter: Panel Identificatio:[FREE TEXT BOX]: Enter:Quantity:[FREE TEXT BOX]: Enter:Fault ID if any:[FREE TEXT BOX]: | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist Signed Off
10 | Check for Faults - 4 | Item 6 on this Checklist | For Each Precast type delivered: Enter: Panel Identificatio:[FREE TEXT BOX]: Enter:Quantity:[FREE TEXT BOX]: Enter:Fault ID if any:[FREE TEXT BOX]: | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist Signed Off
11 | Check for Faults - 5 | Item 6 on this Checklist | For Each Precast type delivered: Enter: Panel Identificatio:[FREE TEXT BOX]: Enter:Quantity:[FREE TEXT BOX]: Enter:Fault ID if any:[FREE TEXT BOX]: | Visual Measure | Each precast type delivered | IP | PE/SE | This Checklist Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /