## ITP-CIV-RSS Walls
ConQA Team Notes:
Document Title: |  | ITP-044-STR-Brunt-RSS Wall Main
ITP Description: |  | RSS Wall Main ITP
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2023-07-07
ITP created by: |  | Thilan Rathnayake
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP for Brunt Road Project Only. This ITP is to be read in conjunction with CHK-004-STR-BRUNT-RSS Walls-Fill Placement Rev0, CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0), CHK-006-STR-BRUNT-RSS Walls-Precast Panel Material Inspection Rev0
Inspection & Test Plan - RSS Wall Main ITP
[9 empty] | Revision: | 0
[9 empty] | Date: | 07/07/23
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Applicable Specs/Standards | VicRoads Section 682 Nov 2018 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Applicable Specs/Standards | VicRoads Section 204 Dec 2015 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Applicable Specs/Standards | VicRoads Section 610 Feb 2020 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Applicable Specs/Standards | IFC drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.5 | Applicable Specs/Standards | BTN 009 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.6 | Applicable Specs/Standards | AS5100-2007 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.1 | Concrete-Leveling Pad | IFC drawings | CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS; [Free text]: Teambinder MA Ref Number: | Document Review | Each element | HP | Nominated Authority | Conqa HP Release
2.2 | Select Backfill | IFC Drawings | Select fill shall comply with the requirements of the RSS designer: UNIT WEIGHT: 22 kN/m³ INTERNAL FRICTION ANGLE ≥ 36.0° COHESION: 0 kPa Gradation: 150mm : 100% PASSING 37.5mm : 60 TO 100% PASSING 9.5mm : 25 TO 100% PASSING 2.36mm : 15 TO 100% PASSING 0.6mm : 10 TO 100% PASSING 0.075mm : 0 TO 15% PASSING Electrochemical Properties: RESISTIVITY >1000 Ω-cm CHLORIDES <200 mg/kg SULPHATES <200 mg/kg ORGANIC CONTENT 0% Structural Properties: COEFFICIENT OF UNIFORMITY ≥ 5 LIQUID LIMIT ≤ 30% PLASTICITY INDEX ≤ 12 The select backfill must meet the minimum requirements of VicRoads Section 204 for Type A Filling. [Free text]: TeamBinder MA Ref Number: | Document Review | Each material specification | HP | Nominated Authority | Conqa HP Release
2.3 | General Backfill | IFC Drawings | Backfill behind the reinforced block shall have the properties specified in the IFC Drawings. Geotechnical Design Parameters for Embankment (Type A) Fill: Effective Friction Angle: ≥ 36.0° Effective Cohesion: 0-3 kPa Unit Weight: 22 kN/m³ [Free text]: TeamBinder MA Ref Number: | Document Review | Each material specification | HP | Nominated Authority | Conqa HP Release
2.4 | Perforated Pipe-material | IFC Drawings | Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2 [Free text]: TeamBinder MA Ref Number: | Document Review Measure | Each element | HP | Nominated Authority | Conqa HP Release
2.3 | Material Conformance - Folded plates | IFC Drawings | GRADE 250 D41 300x6MM FOLDED GALV. PLATE [Free text]: TeamBinder MA Ref Number: | Document Review | Each raw | HP | Nominated Authority | Conqa HP Release
2.5 | Bearing Pads, Filter Fabric, Geotextile, Strip Drains & Chimney Drains | IFC Drawings | Refer to relevant IFC Drawings for details of these incidental materials. [Free text]: TeamBinder MA Ref Number: | Document Review | Each material specification | HP | Nominated Authority | Conqa HP Release
3 | Preliminaries-Documents
3.1 | RSS Precast Panels QA Documentations | Subcontractor Methodology and Procedures | RSS Precast Panel Supplier is required to provide the following Quality Assurance documentation prior to casting of precast panels. - Quality Management Plan - Works Procedures - Concrete mix design - Concrete crack repair procedure - Concrete crack repair ITP - Weld procedure qualification records - Precast panel liftring design - ACRS cert for steel reinforcement - Concrete pre-pour records template - Concrete pour records template - Concrete post-pour records template - Concrete cover check records template - Record of dimensional measurements Collate: Precast Quality Assurance Documentation so it can be uploaded into a Hold Point in Teambinder (don't attach here) [Free text]: TeamBinder Hold Point Ref Number: | Document Review | Once for each type of panels | HP | Nominated Authority | Conqa HP Release
4 | Pre-construction Activities
4.1 | Levelling Pad-Survey Set out | IFC Drawings | Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the IFC Drawings and VicRoads Specification | Measure Visual | Each retaining Wall | IP | Surveyor SE/PE | This ITP Signed Off
5 | Construction / Installation Activities
5.1 | Form Levelling pad | IFC Drawings | Form timber shutters to edge of levelling pad Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing The leveling course level shall NOT deviate from the specified level by mor than ±3mm. 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained | Measure Visual | Each Lot | IP | SE/Site Supervisor | This ITP Signed Off
5.2 | Leveling Pad Concrete Pour | IFC Drawings | Concrete to be placed in accordance with VR Section Section 610. Leveling pad concrete strength shall be 25 MPa minimum. [Free text]: TeamBinder MA Ref Number: Attach: Concrete Delivery Docket & Pour Record | Visual | Each Lot | IP | SE/Site Supervisor | This ITP Signed Off
5.3 | Leveling Pad Concrete Testing | IFC Drawings | Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b) Attach: Concrete Compcressive Test Report | Document Review | Each Lot | IP | PE | This ITP Signed Off
5.4 | Levelling Pad-Post Pour Survey-Levelling Course | IFC Drawings | Levelling course level shall not deviate from the specified level by more than ±3mm Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations) Attach: As-built Survey Conformance | Measure Visual | Each RSS Wall | IP | PE/SE/ Surveyor | This ITP Signed Off
5.5 | Precast RSS Wall Panels Installation | VR Section 682.17 | The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions. Refer to Precast Panel Installation Checklist for each course of panels. Attach: Lot map | Visual Measure | Each course of facing panel | HP* | PE/SE | CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0
5.6 | Precast RSS Wall - Drainage | IFC Drawings | 300mm Wide Strip Drain along back of RSS Precast Panel at 2m c/c with 100mm clear distance from straps. 100mm dia. perforated subsurface longitudinal draiange (1:100 Fall) 500mm nominal above existing surface level wrapped in geotextile and encased in free draining material. Chimney drain min 300mm wide comprising A5 or B2 filter material in accordance with VR Section 702. Perimiter of chimney drainage wrapped in BIDIM A24 (or approved equivalent) non-woven geotextile overlapped by 150mm min. at joints. Refer to Precast Panel Installation Checklist for each course of panels. Attach: Lot Maps | Visual Measure | Each course of facing panel | HP* | PE/SE | CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0
5.7 | RSS Select Fill | IFC Drawings VR Section 682.16 | The Contractor shall submit Compaction & Moisture Content Test Results (Scale A) for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed. Refer to Fill Placement Checklist for each fill layer. Attach: Lot Maps | Visual Test Measure | Each layaer of fill | HP* | PE/SE | CHK-004-STR-BRUNT-RSS Walls-Fill Placement Rev0
6 | Post-construction / Post-installation Activities
6.1 | As-built Conformance Survey | MRPA Quality Management Plan | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances Attach: Survey As-built / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0 CHK-004-STR-BRUNT-RSS Walls-Fill Placement Rev0
6.2 | Wall Post Construction Monitoring (This is part of the on-going monitoring of the RSS panels post installation) | VR Section 682.20 VR Section 682.21 | The Contractor shall take measurements of the position of the RSS at the points defined in VR Section 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period. a) plan position shown on the drawings, at base of wall shall not exceed +/-15 mm; (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall; (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm; (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height; (e) the wall level shall not deviate from the specified level by more than +/-20 mm; (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap. The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey. Attach: Surveyor pick-ups / measurements. | Measure Survey | In accordance with VR Section 682 | IP | Surveyor Completions | Survey Monitoring Report (Refer back to CND)
6.3 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0 CHK-004-STR-BRUNT-RSS Walls-Fill Placement Rev0
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /