## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-040-STR-Brunt-Crossheads | itp |  |  |  | Yes | ITP-040-STR-Brunt-Crossheads | 0df3df74-7b1a-46ac-9670-03a76ca36598
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | b27e02bd-a3bd-55c4-adbb-7ae2ea5d5f55 |  | note | Reference - VicRoads Section 602 October 2007
label | ffae9433-8834-5ea4-96f5-8d3c4af86b6a |  | note | Acceptance Criteria - N/A
label | dcfd8a5c-5404-5cfa-963c-68fc312a8820 |  | note | Method - N/A
label | a3d5a28c-9a4f-5675-b78b-75b86f359daa |  | note | Frequency - N/A
label | 95d17df0-aa69-521a-97a9-2b5c0248e7b7 |  | note | Category - N/A
label | ff4e7392-46ad-5c34-92d9-0131d5c4d832 |  | note | Responsibility - N/A
label | 286caf76-0051-57f9-b4c5-7a41fd4a8df6 |  | note | Verifying Documents - N/A
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 1e6805a4-02ec-570e-bcd5-08ee451ab745 |  | note | Reference - VicRoads Section 610 February 2020
label | 8643fd40-2c93-5175-86cc-34a1645e1e90 |  | note | Acceptance Criteria - N/A
label | ec12a90f-cca4-5fe9-837a-35ccc67e3768 |  | note | Method - N/A
label | e5bbd377-ed40-59a1-a2b3-20fa3b14ca6a |  | note | Frequency - N/A
label | dba2365c-95e4-58d8-a6d3-addc8e397a57 |  | note | Category - N/A
label | 1c58e7d1-d1c7-5f99-94a3-33cdb4b4cfa4 |  | note | Responsibility - N/A
label | 00cde830-cd5f-5f34-9fb5-9125eb5acd1f |  | note | Verifying Documents - N/A
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 1927c941-cbc6-5019-8660-5254e525166d |  | note | Reference - VicRoads Section 611 November 2018
label | 787de003-e96a-5b9a-a448-44aec24ceabf |  | note | Acceptance Criteria - N/A
label | 9d86c5a4-ff5e-584d-b2b8-e7ef8a68fa55 |  | note | Method - N/A
label | f7fd4255-6313-5dd0-ac0d-241f1deddc01 |  | note | Frequency - N/A
label | 23a2c1d3-067b-5086-be81-c7278a62cea8 |  | note | Category - N/A
label | c76851d1-43f1-5cd0-9bd4-bb9ac83d3748 |  | note | Responsibility - N/A
label | 577fec26-ce59-5921-9f9d-f46b69883893 |  | note | Verifying Documents - N/A
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 7be9747c-bc23-54be-9233-c50d9594172e |  | note | Reference - VicRoads Section 614 June 2017
label | 67c8e5e5-d33c-5df2-8216-3922f89d57cb |  | note | Acceptance Criteria - N/A
label | d17fd006-d929-5c32-a4d8-90e6a3584bad |  | note | Method - N/A
label | 297bfd2a-4dee-592c-9d02-4dfe6c3f16f8 |  | note | Frequency - N/A
label | 5fc10871-3891-54ca-8e39-3006d7e5bd74 |  | note | Category - N/A
label | cdf16ebc-fb2f-536d-9fea-5456ed1c920f |  | note | Responsibility - N/A
label | 591ba7c4-ee1a-529d-a8c5-92438e0cb0b3 |  | note | Verifying Documents - N/A
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | b6f7f1ac-8d06-5997-b9a8-2b88180f267b |  | note | Reference - AS3810.1 2018
label | 35b1594d-b99a-50a9-8eca-7d376d4f4195 |  | note | Acceptance Criteria - N/A
label | 7d44adca-7e50-5e3f-a012-1693227b8082 |  | note | Method - N/A
label | b7ba4732-568f-5382-aac7-0f8e38d69069 |  | note | Frequency - N/A
label | e4b8c650-06fa-57b7-85ba-2a4f05fc4b1c |  | note | Category - N/A
label | 86d3a37b-015b-5082-833d-3290a58e44b3 |  | note | Responsibility - N/A
label | 4d339497-ea86-5b50-913d-016e3bebb42e |  | note | Verifying Documents - N/A
checkpoint-status |  |  | checkpoint | 1.6 - Non Dependent
label | 4285755e-655d-5616-83e8-c0e9984faa05 |  | note | Reference - IFC Drawings
label | 61e4615c-d2a0-5d12-811d-044a405b75b8 |  | note | Acceptance Criteria - N/A
label | 56b6850e-9c12-575f-8842-a35b86042806 |  | note | Method - N/A
label | d0b3c59d-3af3-572f-8e78-556dafe45df5 |  | note | Frequency - N/A
label | 8c3ff816-4a40-5a90-aa52-4dbbdba42cb1 |  | note | Category - N/A
label | ae0eaf4a-6b06-54ba-802a-a7934b44d817 |  | note | Responsibility - N/A
label | d7782900-0a60-5799-8567-6a136881e208 |  | note | Verifying Documents - N/A
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix
label | 918edcb4-81e1-530e-9d1a-b8b4c572f762 |  | note | Reference - 610.07 Table 610.071 IFC Drawings
label | e1a92914-15f3-5ccc-bc48-4115f886e5ae |  | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Enter: Teambinder Material Approval number [free text box]
label | 31caf27d-b691-53c6-befa-2e4aa2e077c7 |  | note | Method - Document Review
label | e28ef35e-e155-57e3-8f6e-b340de18209f |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | 2b77ec8e-894f-5486-93c9-3ddf48eb4673 |  | note | Category - HP
label | d0a54058-3f28-5500-9a0a-e61fab8a10bf |  | note | Responsibility - Nominated Authority
label | 78cf7dd5-1895-5220-b6d0-61e098bf7619 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | 421ad706-39d3-5088-917f-6b4ddf84599a |  | note | Reference - 611.05 (a)
label | 48d3f568-5c01-520d-99b2-2eb40253a41d |  | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box]
label | 23930ca5-ee26-5567-a66a-a1e560bd0a05 |  | note | Method - Document Review
label | 0cfc3e95-fed7-567f-a1b3-be30d4d118a0 |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | b3d56112-e4af-5979-bdb6-83d43eac8934 |  | note | Category - HP
label | 6f7dec3e-d645-5192-815e-87d815f55c45 |  | note | Responsibility - Nominated Authority
label | d6f94f03-ef28-551e-a7f9-652daee5aab5 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Bar Chairs/Aspros Certification
label | 1cef25d7-6f85-5a72-8268-5fadc5db4da2 |  | note | Reference - 610.26 (a)
label | 6220aef8-62e7-5d50-b1b5-226bdd856dde |  | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads. Concrete aspros require annual compressive strength and soluble salt testing is required. Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
label | 20dcbb55-3013-5ee2-a64a-dfa343b20f87 |  | note | Method - Document Review
label | e88c864e-633c-5755-b68e-3c48a0d04705 |  | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | 60441de4-35d9-5924-a163-98da58bf71c2 |  | note | Category - HP
label | 802db343-794f-5f36-8d51-7dd80a2f09ce |  | note | Responsibility - Nominated Authority
label | 89f2a046-9e76-5c17-b46a-d3f65f5b21b0 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Evaporative Retardant
label | a2947c71-87fa-5491-bb49-b253a633fcc5 |  | note | Reference - 610.17 (f)
label | fd859f12-b12d-53dd-813b-f12c14f3a319 |  | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
label | 753a7a2c-c676-53a3-821c-b5411cf6f4e8 |  | note | Method - Document Review
label | e565407e-f510-5cc2-9bb8-19a2b81f1485 |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | cba30253-fd5e-5370-8b67-a3e1d038fa53 |  | note | Category - HP
label | 63f32dfb-2eee-5b95-ad71-620d958754e6 |  | note | Responsibility - Nominated Authority
label | 6a407cba-ec3c-50ee-9195-b1f0e7c0b3c2 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Curing Compound
label | 98f01bcd-2515-52cb-b5f6-8f5b2ec0588d |  | note | Reference - 610.23 (d)
label | b94e7cf7-a7c4-5cd1-be5c-91af20b02043 |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
label | c4ba51c4-6c22-542b-962c-33cef24de85f |  | note | Method - Document Review
label | 6d7d1877-bfe4-5585-86c7-d033dd367c6a |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | ff5f208e-7e1e-53d4-81ac-95000c4aa81c |  | note | Category - HP
label | 9e00c9ce-6f11-530e-89bf-d47f4ff1ea53 |  | note | Responsibility - Nominated Authority
label | 5bcc536f-c24b-5388-bc1e-5eb72270baf4 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
label | f160812d-e3ff-5f99-92ff-de4b6e4b17f7 |  | note | Reference - 610.18 (a) (i)
label | c3227d0f-b5c4-51df-8693-f6ac4e0d917d |  | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | b2767d9a-302a-5232-9456-2343092653b0 |  | note | Method - Document Review
label | 5e461b58-e190-5154-8173-496a6de513c1 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 3e2d2090-4049-56e0-82eb-4c1651685388 |  | note | Category - HP
label | 883d92ea-14a6-5881-8d14-774bef18d609 |  | note | Responsibility - Nominated Authority
label | 22f669da-9e51-5dc9-8df2-aa3b00af6745 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Concrete Sampling and Testing Procedure
label | 98101f73-23a2-5a6a-b9df-cc4d7d867547 |  | note | Reference - 610.18 (a) (v)
label | 3ba7dd65-438f-58b5-bce9-441dcbdfdc71 |  | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 3d742dc4-89d7-5f3b-8b4c-7853963fccb6 |  | note | Method - Document Review
label | 1db625e1-dc4f-5e98-ac07-7cf4453fe201 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | bd67564a-e828-50ce-baa0-423c89cf6743 |  | note | Category - HP
label | 22e3591f-efde-5779-b2f4-5a273036ef58 |  | note | Responsibility - Nominated Authority
label | 4ec0d086-ccb1-52fd-9153-aa5b7d1475d7 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
label | 6dc4edc5-1c92-54d7-8fb4-fc38ba7a685c |  | note | Reference - 610.18 (a) (iv)
label | 9b3f6f8f-6c86-5b4e-8715-3e8a7143d2f7 |  | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements. Minutes of this meeting to be submitted to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 3946dfe2-252b-5480-8289-83754a1f1b3d |  | note | Method - Document Review
label | 3213ba14-256d-557a-9f77-706546399329 |  | note | Frequency - Once, 1 week prior to placement of concrete
label | dd1935fc-1457-5ac0-8614-78e8b18800a9 |  | note | Category - HP
label | 9efa6ca0-c0f9-56c7-a1ea-395c6d55ef91 |  | note | Responsibility - Nominated Authority
label | 1e8c5879-02da-538b-a8dc-9564a88153d6 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
label | 5ea6b2fd-58a0-5d19-b444-46a1e6452d91 |  | note | Reference - 610.17 (a)
label | 1c0fc2ff-02af-504c-8355-70ffc433dd4f |  | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | afe5d178-8293-5baf-826e-7b5e082a7099 |  | note | Method - Document Review
label | 7364801b-789c-577a-95fc-98a2426d7756 |  | note | Frequency - Once, 2 weeks prior to placement of concrete
label | 10b0f276-fc2f-58aa-8efb-b22c5c6535af |  | note | Category - HP
label | b275b502-d78e-5a64-a999-da14e716fd9d |  | note | Responsibility - Nominated Authority
label | a68b835c-45c9-51dc-b9d3-9a9ca3147a65 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
label | 3aae0f2f-f22b-5c4e-a851-e7bf6b38ca7b |  | note | Reference - 610.23 (a)
label | 642e9225-2876-5d24-95fd-e0ba0d2afd0c |  | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | ac470752-fb9e-5b86-85ae-9ae771ddd6b3 |  | note | Method - Document Review
label | 159fb69e-44d1-5608-a0a4-391556830f69 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | ef8152c7-02e8-55c3-83c4-1ee60d199b70 |  | note | Category - HP
label | 533e00ac-98e3-5a46-93e6-5b31cf4d3cd2 |  | note | Responsibility - Nominated Authority
label | b8a29ee7-7153-55ca-9074-e7d4ccf3cc6a |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Concrete Drilling Procedure
label | 16ab8fa8-bd83-5447-9f52-06027e275e31 |  | note | Reference - 610.46
label | 6e061024-196d-564d-bf69-f9479d316ca4 |  | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services. The planned locations and drilling procedure shall be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 81a73c3d-c5d9-5b4a-89f8-b20c7c24d87a |  | note | Method - Document Review
label | 7227a096-842b-5d0f-a920-96ad0a3f5fcb |  | note | Frequency - Where applicable, once, 2 days prior to drilling
label | f8b627a6-e501-552c-ae5d-e2745127063f |  | note | Category - HP
label | f2f1d1d5-868b-5a6a-a3ae-a005419d053b |  | note | Responsibility - Nominated Authority
label | 430af4b0-37f5-5485-a1a1-e7a6a09210c3 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Temprature difference measuring-Calibration
label | 12f6306e-7351-5020-b9c6-459486d8e395 |  | note | Reference - MRPA Quality Management Plan
label | 5cef6a4c-1b8a-5861-b124-57254ae4edde |  | note | Acceptance Criteria - Calibration records for Themocouples are valid and up to date. Attach: Calibration certificate
label | 9a0c08cf-9b46-56bd-afdd-d44dc6a5b1ef |  | note | Method - Document review
label | 85e1c8a3-832e-5a0b-972c-ab9b7c0c4389 |  | note | Frequency - Where applicable
label | 3bd3d113-faa8-5cc9-bd20-61b613722dee |  | note | Category - HP*
label | 57b4f106-11ff-5c81-8d33-a034ed70af0c |  | note | Responsibility - PE
label | 6b96458e-ce5d-5d88-9af0-9762ecb8330e |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
label | 43526566-3504-5165-88fe-fbb5ca2897a8 |  | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
label | 1de32447-6063-5cc2-b2b5-64d7bd771623 |  | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
label | adcf6ce9-cf15-5c3f-a698-572fa7498e85 |  | note | Method - Document Review
label | 7cb6c8f8-1109-52a5-83e1-4d378540d159 |  | note | Frequency - Where applicable, once, prior to welding
label | 99c32091-8bea-5619-99cc-435504dabd62 |  | note | Category - HP
label | a5b6a8cb-42ea-5d0f-8489-cffdab4d6d8c |  | note | Responsibility - Nominated Authority
label | 72084f31-b242-580d-adc9-43041bc3ec71 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | 4a22cc0a-8cca-5946-b69e-e6eac22c1791 |  | note | Reference - MRPA Quality Management Plan
label | 684e6bb2-c252-501d-9656-cc5034f030d6 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 98d9944f-67b7-5ad4-a164-fae860024707 |  | note | Method - Document Review
label | 6a85a2f4-b48d-5f0f-8904-ef45d6993d7c |  | note | Frequency - Prior to starting Works and at regular intervals
label | 40f28076-0f78-5248-ba90-0cec46ff06ee |  | note | Category - HP*
label | 18b35bed-8178-5f76-8c83-1968f2ee5d56 |  | note | Responsibility - All
label | c05ca8f3-267b-569a-b38d-4f6adc906f9c |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out
label | b818dde3-7602-518f-b1c2-3844f2ab74fa |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472
label | 556dc52b-43ba-59b6-823a-375507e402d3 |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element. Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | 7b072249-790d-533f-8557-88f2d0586d7b |  | note | Method - Measure Visual
label | 57aaac33-640d-5585-a77e-03a062db17a7 |  | note | Frequency - Each element
label | 8c22ecdc-550e-55d1-af90-9283076249ba |  | note | Category - IP
label | 7528832c-c774-5583-b0de-d7050d70fea0 |  | note | Responsibility - Surveyor SE/PE
label | 28c234a6-b109-51bb-82b7-9b78a88703fe |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.3 - Abutment / Pier Wall Work Lots
label | c379fa4a-636b-598b-96d2-37af22101559 |  | note | Reference - TeamBinder Work Lots
label | fb99a79d-9833-54a1-af4b-481f00029de5 |  | note | Acceptance Criteria - Related abutment / pier wall work lots are closed. - abutment / pier wall design strength is achieved - As-Built Survey performed - Related abutment / pier walls NCMs are closed. Enter: Abutment / Pier Wall Lot numbers: [FREE TEXT]
label | 4ea2f308-352c-5fec-9a11-2e2c3220bd40 |  | note | Method - Doument Check
label | f2050a72-874c-5c82-8645-b0f2ee58d2d2 |  | note | Frequency - Each Element
label | 53c98460-2528-54fc-8fd5-083bb2623d8c |  | note | Category - HP*
label | 085e5e0b-3bad-5495-a489-1cad26af26ef |  | note | Responsibility - PE
label | d692abb4-5579-5f4c-a6b7-b09e4c6ba091 |  | note | Verifying Documents - This ITP Signed Off Pile Cap Lots Closed-Out
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Formwork Design and Construction
label | a05c905b-7151-5f79-a2a9-c4b61bf2dc15 |  | note | Reference - IFC Drawings 614.04 614.05 614.06
label | 350af9a0-008d-5e60-820f-f07be33bd51c |  | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected.
label | 4c7a085a-3d3c-5304-9f00-2e10f5fecc45 |  | note | Method - Document Review Visual Measure
label | 6284c549-5770-5bc1-93af-c7ddb75c50e0 |  | note | Frequency - Each type of element
label | fddc320f-0913-5986-b20b-b16d667489d1 |  | note | Category - IP
label | 49f47fc5-8c82-50d2-9a81-a1b627596a9c |  | note | Responsibility - Temporary Works Designer Proof Engineer SE/PE/SPE
label | 58a220be-4d06-59e9-8a7d-948c3dc4e236 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | 48559d8e-5b1d-5cfd-bc12-3821ec1ff0db |  | note | Reference - 614.08
label | efa73ba2-e7c0-54dc-98b1-e5aed8f028ed |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Crossheads with heights greater than 2.0 metres Any member for which self-compacting concrete is proposed. Attach: Attachment A Attach: Attachment B
label | cb4142e9-45f0-5061-8e39-137a27bf550c |  | note | Method - Document Review Visual Measure
label | 857539d4-fa76-5fdf-bad6-f4e13d02a380 |  | note | Frequency - Each element (where greater than 2m)
label | 5e762c19-15d7-5a63-9855-f18807d607a2 |  | note | Category - HP
label | ab4f7337-6efd-53ba-8275-efb8ea27021c |  | note | Responsibility - Temporary Works Designer Proof Engineer
label | 6bd5bcc0-1c7a-55c5-ae9e-096166be64c1 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | dbca33b8-c2ed-5c54-a7b1-39aa6387475c |  | note | Reference - 614.08
label | d9ada07f-bc81-5db2-95eb-fc6b13f4820e |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Crossheads with heights less than 2.0 metres Attach: Attachment C
label | 17b618c5-09c2-50c7-a729-1b7c960f67a3 |  | note | Method - Document Review Visual Measure
label | c398905c-8b48-5d13-86c8-e9414e4434a3 |  | note | Frequency - Each element (where 2m or less)
label | e1fc8d57-15a0-51fd-89f3-9104faa30e95 |  | note | Category - HP
label | eecc1478-245c-5625-9d54-b112ae7ac22f |  | note | Responsibility - Temporary Works Designer Proof Engineer
label | 30e04448-3425-5dec-b4f1-2b395d70bc94 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Pre-pour Survey
label | 8375b679-f42a-5468-bdb0-5b326e6a6ee9 |  | note | Reference - 610.47 (a) Table 610.472
label | ac065a9b-3f12-5b14-9b78-41dfbdf9ce18 |  | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | 5693bb02-4db0-54d9-b0d9-cc1311ec0596 |  | note | Method - Measure Visual
label | ddddac92-d684-51bf-97fb-e922bd36c737 |  | note | Frequency - Each element
label | 9e62f2b9-b698-5f75-8ae1-f8eadb2d067b |  | note | Category - HP*
label | af422d34-5fec-5e5d-bf70-934cdccb1824 |  | note | Responsibility - Surveyor SE/PE/SPE
label | 9517f1e2-2def-586e-a7ae-e968f0ce0596 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.5 - Reinforcement Placement
label | 9a04260f-72ed-5537-806a-ff1dd1348b5e |  | note | Reference - IFC Drawings 611.06 611.09 611.10 611.11 611.12
label | 9d6bf065-dc53-5da0-bd20-f2cc60eccaea |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings. Projecting reinforcement is the correct length and location. Splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour. Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | e6c96f7e-c7dc-526d-9418-92ab16012672 |  | note | Method - Measure Visual
label | 6cda1915-d726-5b89-8181-52242ee00407 |  | note | Frequency - Each element
label | 84d2f6a3-fef7-536d-9e5e-4c9e73ca665d |  | note | Category - IP
label | 1cd00d7e-2ea4-5693-9c46-099d13a2df48 |  | note | Responsibility - Foreman SE/PE/SPE
label | 570072b6-00af-5322-9650-7e8cdec0df09 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.6 - Cast-in Items
label | c61b20b8-bf6b-5510-9adb-79fba456db7f |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | c369328c-5ace-5575-8161-b74a8735af2f |  | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement. Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress. Tack welding of any cast-in items shall be performed by someone pre-qualified to do so. Grout tubes shall be fastened at regular intervals to prevent kinking. Placement tolerances to comply with the IFC drawings, if not specified, use the following: i. Bolts, ferrules, projecting bars & couplers = ±3mm ii. Running dimensions of a group of the above = ±6mm iii. Ducts and conduit location = ±12mm iv. Diameter of ducts and conduits = ±3mm
label | 085b72f5-9646-58a5-b431-91a62fe6322b |  | note | Method - Measure Visual
label | 8a8a4c45-5df1-5b6f-9ae6-f3340ae9f3ab |  | note | Frequency - Where applicable, each element
label | 1b04e21d-0952-5d86-8c26-eada22ce12f9 |  | note | Category - IP
label | c447ac9e-9b30-5f85-b914-47d8d52eba8f |  | note | Responsibility - Foreman SE/PE/SPE
label | 0f084027-0412-50f7-9f76-6305a952ecc4 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.7 - Thermal Differential Monitoring
label | 070eaade-8423-56af-9527-ec48caca95cc |  | note | Reference - 610.22
label | 09761e02-987a-5788-89ee-572df79f82f9 |  | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | dfca3876-cd23-521c-a131-bdf6f88bb51d |  | note | Method - Measure
label | 499c51ac-eb3e-513e-9163-1355f57a510f |  | note | Frequency - Where applicable, each element
label | 9238e603-d9cf-5700-9b25-efe31d49b092 |  | note | Category - IP
label | 00cf57c7-41d9-5991-92c2-b554d437b3c3 |  | note | Responsibility - Foreman SE/PE/SPE
label | 1c570081-7c75-5691-85b8-bee49b1f5d7f |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.8 - Pre-pour Inspection
label | d554e54b-b30f-509f-a3d8-1dcb577c1446 |  | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | e4ee19e2-9cb6-57f8-8cc9-272c17425930 |  | note | Acceptance Criteria - Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority All foreign material has been completely removed from the forms. ATTACH: Pre-Pour Checklist
label | e88c3d50-2280-52d7-9647-dbb1267d16c5 |  | note | Method - Measure Visual
label | 4bbd4333-6c8a-5254-aec9-6556ed860891 |  | note | Frequency - Each element
label | dd0acafe-034b-5e99-9257-dbf24ae4e0eb |  | note | Category - HP
label | 3f87274f-b955-59f6-8c0c-ccce086e1703 |  | note | Responsibility - Nominated Authority
label | 800d902e-2236-5079-8962-424ae6acad82 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.9 - Weather Conditions & Evaporation Limits
label | 655bef1d-965f-5b01-ba40-ddd154cde961 |  | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
label | efa039c9-e681-529b-b9c7-3210d7ca83bc |  | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record.
label | fbc58ff0-a45b-5a3a-951a-de99d1aeb309 |  | note | Method - Measure Visual
label | 48d4782a-4c78-5541-a251-96c4c2b77e7b |  | note | Frequency - Each element
label | 7ab5c6a3-027f-5dea-804b-c400bfbae4e2 |  | note | Category - IP
label | 39214867-76e6-5336-8078-6b2fd220c52c |  | note | Responsibility - Foreman SE/PE/SPE
label | 9b2688b2-2632-5939-9c4b-49e74bfc455d |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.1 - Concrete Testing - Sampling Frequency
label | 56916cde-7a10-533e-8364-4acaa213e5b8 |  | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
label | 969b00ca-003d-5169-ba31-ad1cb1b27831 |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing). Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork. Record: Required information on the Concrete Pour Record.
label | 81480667-cf08-58df-9b45-e4dcfea06500 |  | note | Method - Test
label | 3eebebc6-5572-545f-a0ec-639b82203d3a |  | note | Frequency - Each element
label | a0f272b3-ccbf-53c4-b91f-ca6aa7ebba4d |  | note | Category - IP
label | e2c5ffbb-243c-5d28-b29f-ea9b9287d26e |  | note | Responsibility - Concrete Tester Foreman SE/PE/SPE
label | 73bd296d-f903-5a55-85d6-4a85b1ae4ca4 |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.11 - Concrete Testing - Slump
label | 1660eb06-4a81-55d4-8b70-c92e207d0d3c |  | note | Reference - 610.16 (c)
label | 960d6af4-1945-5f81-a355-389e26a78684 |  | note | Acceptance Criteria - Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record.
label | 37f86e25-f7c5-594e-9a60-37171106a012 |  | note | Method - Test
label | bcc116a7-e941-5804-8e12-d5279d75b0a4 |  | note | Frequency - Each sample of Standard or Superplasticised Concrete
label | eb31cbcf-de15-592c-882c-1b87a3ac9236 |  | note | Category - IP
label | 9873cede-cf33-5f77-aacf-6d1a92dc3738 |  | note | Responsibility - Concrete Tester
label | 49fc3606-5232-564e-b5d1-0a1d6fdf0ecf |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
label | 98c0aa97-37b6-5622-86b3-58e2667c3e59 |  | note | Reference - 610.13 (b)
label | 6f010b1a-0cf4-59ae-a08c-1c463a1cfd28 |  | note | Acceptance Criteria - Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record.
label | e94ac6be-3fc8-59ce-89e2-0e3fbf9c9421 |  | note | Method - Test
label | 2bf65978-a881-5051-8904-9a8c431e87d5 |  | note | Frequency - Each sample of Self-compacting Concrete
label | c404afe3-852a-55f5-a5a9-2ed95962fc19 |  | note | Category - IP
label | e3e83cf2-2578-565b-94ff-13c246522302 |  | note | Responsibility - Concrete Tester
label | 38fbf372-81ce-5ce8-b01a-29fbcd0b3e54 |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
label | ff419925-61e1-5016-9ee2-418ff5ec0ec5 |  | note | Reference - Site Sampling & Testing Procedure
label | e3d312d9-042c-563d-a8c4-eecab742bc12 |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record.
label | ffddce52-8b2d-557b-b028-3203f0f35dee |  | note | Method - Test
label | d9ddbaaa-7268-551b-a258-6d4b5c293be8 |  | note | Frequency - Each sample
label | 6ee1ccf3-6fe3-5283-8faf-0771f987bff6 |  | note | Category - IP
label | 3c33a3f7-fb7e-5d44-b5c2-8ca9aff4ea52 |  | note | Responsibility - Concrete Tester
label | a2145eda-d740-5205-b386-9bd0d503f5ce |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.14 - Supply & Discharge Rates
label | f9f4dc53-dbda-5fac-b131-95451aa92e41 |  | note | Reference - 610.13 (a) & (f)
label | c5558aad-49c1-50e1-9a38-4ff3773b2caa |  | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed. No water is to be added once discharge commences. Maximum time between batching trucks is 25 minutes. Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants. Concrete that stiffens or is showing signs of stiffening shall not be used. Record: Required information on the Concrete Pour Record.
label | 9cb29739-ca5d-5c3a-9404-22d6fa96de20 |  | note | Method - Measure Visual
label | ee13608e-74f2-5896-a9ec-a72510e5dbf6 |  | note | Frequency - Each load
label | 9fd3268e-32df-54c8-9456-ea8f7fde7358 |  | note | Category - IP
label | cef3e338-786c-5334-9946-78167c58e28b |  | note | Responsibility - Foreman SE/PE/SPE
label | 397306ee-3475-5fa0-a449-bd6e7808ff34 |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.15 - Placement & Compaction
label | 2e4940f0-2109-5e70-8891-0449c8b0b1a4 |  | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b) 610.18 (d) (i)
label | 9d188a50-ae2d-5344-ba61-df14a2317a76 |  | note | Acceptance Criteria - All concrete batches are traceable. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Concrete is not dropped freely from a height exceeding 2m. Concrete is not moved horizontally by use of vibrators. Adequate compaction is ensured Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments. Concrete layers are not more than 350mm Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence. Vibration continued at each point until air bubbles cease to emerge from the concrete. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets
label | 5b3051c0-7105-50df-8354-5a7e6c65b280 |  | note | Method - Visual
label | 24975b6a-5b8d-554f-b9b8-4f18531ab0ef |  | note | Frequency - Each load
label | ac224157-12c9-5fa4-8e9b-fa782d4d7d33 |  | note | Category - SP
label | a13f59ae-e425-5fdb-bbfd-c8ae18f6ac02 |  | note | Responsibility - Foreman SE/PE/SPE
label | a520eb1d-ef99-5808-a542-4a50c14d559b |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.16 - Surface Finishes
label | 671404c4-d7aa-546e-87a8-ab9999d925a3 |  | note | Reference - IFC Drawings 610.31 610.20
label | f9390968-dc06-58a7-b18e-aa3634732ca1 |  | note | Acceptance Criteria - Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 8157bfe9-e5b5-5383-b160-bf60eff6c54f |  | note | Method - Visual
label | 517d2803-3a2c-5b9f-88b4-9a870467c7ea |  | note | Frequency - Each element
label | 51b5cb06-bc34-5cb4-99c7-07e1d80a8fcc |  | note | Category - IP
label | 8c7b7bd8-27c4-5c92-a7b6-e36c77d9472c |  | note | Responsibility - Foreman SE/PE/SPE
label | b26db7e3-42f9-5473-8c13-81733c2ecf4b |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.17 - Curing-Top Surface
label | 57fc6b60-402c-5a8d-b2a9-bb55e3d7b2d6 |  | note | Reference - IFC Drawings
label | df315db6-4ba4-5534-b7c3-e7c6b03d4eb4 |  | note | Acceptance Criteria - Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | 22e849c5-e151-5532-9c4e-f8c197f94eb9 |  | note | Method - Visual
label | e12659ad-4824-5511-9ab8-4167dbb3d7b0 |  | note | Frequency - Each element
label | 7fcff00b-565e-5730-a434-c009221669ad |  | note | Category - IP
label | 515014a5-212f-5400-98e2-af1e67ff5acd |  | note | Responsibility - Foreman SE/PE/SPE
label | f27411f6-cfbe-59dc-bab9-7c8c89924f38 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.18 - Curing after formwork removal
label | ba8119b7-25c8-5a43-984e-6b823da6a8a9 |  | note | Reference - IFC Drawings
label | 799cafa6-3f75-55be-aa51-4a898d7461cb |  | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | 2610e6ce-1fd2-580f-a3f3-4f57c9bae9f1 |  | note | Method - Visual
label | 11a047be-5506-52ca-9fbd-940fb4aa9973 |  | note | Frequency - Each element
label | 0440a80e-cac6-5fdc-84cf-759a68644a89 |  | note | Category - IP
label | bb990bb9-496d-543e-b900-534de4abce16 |  | note | Responsibility - SE
label | 6a3585b1-9c18-5045-8cc7-f5d40738d1a6 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Thermal Differential Monitoring
label | 98f468ca-9ba7-58c7-890a-c0fafb9df112 |  | note | Reference - 610.22
label | f9ffc736-205e-5c3d-a375-ff997d2f20c5 |  | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints. Attach: Thermal Monitoring Report
label | 237ab443-f0ca-50e6-9389-26398358d58b |  | note | Method - Document Review
label | 0cd841d1-7ff4-5f55-9173-808df6a05be4 |  | note | Frequency - Where applicable, each element
label | b42786bb-18f9-596e-9d6a-3dfc37b00f74 |  | note | Category - IP
label | 144dbf8d-8963-5a64-8b51-42d68c08765b |  | note | Responsibility - Foreman SE/PE/SPE
label | 06f865aa-824b-53dd-9eec-3b26bff028c0 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
label | 4e03f94f-be01-5211-aa1c-6c60fc5173a5 |  | note | Reference - IFC Drawings
label | 23cb961a-ddcf-5371-8740-e4eaf2a6d42d |  | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 43e1b657-c423-5cb8-a935-eeffd19ff604 |  | note | Method - Document Review
label | ba82acc7-fde8-5903-9f31-4d4f07de2965 |  | note | Frequency - Where applicable, each element
label | 0012e05d-28dc-5dc8-b227-8f1a0c0b79a8 |  | note | Category - IP
label | 4eea8a01-a114-505e-ba53-612db767b395 |  | note | Responsibility - Foreman SE/PE/SPE
label | f6e85855-2e8f-5a81-b4a7-54eb87fa715a |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.3 - Surface Inspection - Cracks
label | 89620f70-ec61-545c-bbde-e8557db56b6b |  | note | Reference - 610.24
label | 2758516c-6d18-5ed6-9196-1f1e44edce36 |  | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1) If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair. Attach: Post-pour Checklist
label | 30f970bb-7b06-5486-9fab-8deca58dc9df |  | note | Method - Visual Measure
label | ab96af6d-fc82-56fd-8ccb-ecfe009aecfb |  | note | Frequency - Each element
label | 9aad0867-be7a-52fe-afb8-d6e5aef78cc9 |  | note | Category - IP
label | 20851d8b-e99d-50fa-a081-59d44a965dee |  | note | Responsibility - SE/PE/SPE
label | 06f2703d-1497-55eb-b86a-0b3a7067cf18 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.4 - Surface Inspection - Surface Finish
label | ac3e2410-75df-5173-a744-c0558f8efd45 |  | note | Reference - IFC Drawings 610.31 (a) - (n) 610.32
label | aa49abe4-0182-57a2-83b1-86d19f45f614 |  | note | Acceptance Criteria - Comply with the IFC drawings and specifications. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair. Attach: Post-pour Checklist
label | 53829b38-606f-590a-a1d7-ced8a5ce90bd |  | note | Method - Visual
label | 6c11cf1f-3845-5d1e-bf19-203db4a3015d |  | note | Frequency - Each element
label | 057af62e-4e54-559f-88d8-39ed8bd5c279 |  | note | Category - IP
label | 640e3f1f-982e-5100-82a2-573688064af1 |  | note | Responsibility - SE/PE/SPE
label | e04f75ff-22ba-58cb-96e3-443d0e9587c7 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.5 - Measurement of Concrete Cover
label | 51191e84-7760-5e5f-b89d-4c26b6c49679 |  | note | Reference - 610.34
label | fb0b1cac-310f-5292-a28d-366134e796a7 |  | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area. Minimum 10 no. measurements recorded in each area. Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority. Attach: Covermeter Check Record
label | e96ba2f2-e62a-5721-882f-3a11c5b56ab1 |  | note | Method - Measure
label | 52f8268e-14dc-5a5d-b82d-0ab90e6c3ede |  | note | Frequency - Each element
label | 401f8ed4-12bf-50b5-98e3-61ac695d3a09 |  | note | Category - IP
label | e9515fe0-b57e-5a8e-9c1c-20a9193a7707 |  | note | Responsibility - SE/PE/SPE
label | b7bcd815-a450-5da7-b391-bc37d1b9179a |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | 93f0aec6-e247-5319-8f3b-6048c41b7cea |  | note | Reference - Placement of Fill Material Against Concrete 610.35
label | 7ff6682c-3d4f-5c45-a355-d6b5ea52a950 |  | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour. Proposed placement of fill material against concrete prior to 14 days from casting shall comply with the early application of loading requirements as per VR610.16(l) or maturity testing requirements as per VR610.16(m). Attach: Concrete Test Results or Maturity Test Results
label | 670f36f0-f640-57d9-aacb-cafc21273890 |  | note | Method - Document Review
label | 0d783648-7291-5191-afea-7d5a5b03e8dd |  | note | Frequency - Where applicable, each substructure element
label | 65025062-941e-5a82-a8ca-f11961f91d53 |  | note | Category - SP
label | eb16fc23-bceb-5abd-9df4-828793069435 |  | note | Responsibility - Foreman SE/PE/SPE
label | 218a70fe-3d5c-5226-86cd-d1828fe87ee3 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.7 - Compressive Strength Test Results
label | 000593ad-5c2e-5439-893c-25e3755e5c7d |  | note | Reference - IFC Drawings Table 610.05.051 610.16 (g)
label | 3202c9fa-8dda-54f6-a2fd-db2f496e2bd6 |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results
label | 425c742a-30ef-5603-a32a-34114c6faee3 |  | note | Method - Document Review
label | 1144a892-0394-579a-80f5-0dff0087a9c8 |  | note | Frequency - Each cylinder
label | 520e280e-3993-5464-a7df-5aa461981720 |  | note | Category - IP
label | 0bad5ad8-31d6-57c0-bb14-9c73c7de9f25 |  | note | Responsibility - SE/PE/SPE
label | 1296c5f0-6067-54ee-b52d-a7cc533e224d |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.8 - As-built Survey
label | bfb193a9-24d3-55a6-8786-7ab287c647a0 |  | note | Reference - IFC Drawings 610.47 Table 610.472
label | 5b72b0db-c4aa-541f-a2da-16abedc334a3 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element. Attach: Survey As-builts / Survey Report
label | 4e0744ab-e0d8-5863-ae68-8bea3d70d182 |  | note | Method - Document Review
label | 03c62e78-25e5-5e94-8248-ab8b19602479 |  | note | Frequency - Each element
label | 51611656-e8c2-5e23-b7a4-1f53ea64ddfa |  | note | Category - IP
label | 5a2e9cd2-943b-5d40-93a8-6acd1f73d144 |  | note | Responsibility - Surveyor SE/PE/SPE
label | 98e67c7c-2b22-5fc0-9b24-d481576eace5 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
label | cf0bd29a-5c5b-58a6-a5f7-604ed039ade4 |  | note | Reference - MRPA Quality Management Plan
label | 1d7e2348-4c6a-5b56-aa94-3a429e9db1b1 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | be18b9c3-41e8-559e-808f-1d0ddfeda1de |  | note | Method - Document Review
label | 7cbe5143-69e0-5c6e-90cf-5d013f75684e |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 86fd1693-d25a-5824-ae8d-70916a1dcdcf |  | note | Category - HP*
label | 2af0cf3a-7018-5fb1-9e9c-29bc1065127a |  | note | Responsibility - SE/PE/SPE
label | 7cb2bddd-415c-529d-b921-1ba53f42843a |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | Final Inspection
label | 274fa4f1-8cc6-5c73-a542-6611f151d5bd |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 6986390d-871c-5db7-ae1c-44740ef89e15 |  | textbox | Print Name:
text | 61b07c1f-a48d-5637-9471-f83ecee6941c |  | textbox | Position:
text | c32a73a9-08ac-555b-8d15-e7c1c1b44270 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-019-CIV - Conduit & Pits - Rail (Supply and Install) | itp |  |  |  | Yes | ITP-019-CIV - Conduits & Pits - Rail (Supply and Install) | 10482046-fbfb-4ebb-93c9-6e3092ba1ab9
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | f5f2e605-ff9c-584e-8af5-7e105d3e9ed7 |  | note | ITP-019-CIV-Brunt-Conduit & Pits-Rail (Supply & Install)
label | f0c9db2b-f6bc-5d22-9dd1-ae628970b8dd |  | note | Conduit & Pits - Rail (Supply and Install)
label | afc16df7-5ab8-5198-8002-4f59cf4c9793 |  | note | CIV
label | 3e7dbcb5-8836-5dd3-aa82-50aff6ba3407 |  | note | 0
label | f52cd485-d011-5213-b0d3-d775f181853e |  | note | 13/01/2023
label | 9fe5cd5f-a9b1-58f0-bf27-c56f3d61f756 |  | note | Shubham Bajaj (Sammy)
label | 5ca1fb1d-3644-589e-8a7a-60567332f935 |  | note | Jon De Castro
label | 66f93ac0-90cb-5f8b-818f-7cc762e4f33a |  | note | This ITP is to be used in Brunt Rd only.
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 7000b2a5-bc0b-5dae-bf94-1a50fe67650d |  | note | Reference - IFC Drawings L1-CHE-STD-043 (VRIOGS 012.2.1) L1-CHE-SPE-070 Australian Standards MRPA Standards
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Conduits
label | 1a2e5641-4981-55cc-95d8-bc200ee6d9ed |  | note | Reference - HV Conduit: AS 2053 - HV Conduit (boring): AS 4130 - Comms Conduit: AS/ACIF S008:2006 - LV Conduit: AS/ NZS 3000 - 2000. - L1-CHE-STD-043 - L1-CHE-SPE-070-
label | c3d31b76-c761-5345-b989-1782e338d2c3 |  | note | Acceptance Criteria - LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness LV & COMMS CONDUITS TO HAVE A MIN 600mm BENDING RADIUS Inspect materials upon delivery and attached delivery dockets.
label | 54d92a46-d7e3-5eb9-9039-59f8c16a520e |  | note | Method - Visual Document Review
label | 68014b69-0e72-5ca5-b207-573c74db7ee6 |  | note | Frequency - Each Material Type, Each Delivery
label | 23932b10-fbad-5efb-a718-483460d0852a |  | note | Category - IP
label | e3997368-ffcd-521a-9481-1722e2f3a753 |  | note | Responsibility - SE/PE
label | 11fb24a2-bfef-56be-a396-0518a4e98791 |  | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
checkpoint-status |  |  | checkpoint | 2.2 - Pits and Pit Lids
label | 3e25cad9-a5a5-540a-b3bc-169967ed69e8 |  | note | Reference - IFC Drawings -VRIOGS -012.2.1 Section -6.15-16 - VRIOGS 012.2.1 Section 6.9 - VRIOGS 012.2.1 Cl. - 6.7 (c) - L1-CHE-SPE-070 Cl. -10 -AS1289-
label | ae0286d0-bfa8-52c3-b81b-d34f38a74fa4 |  | note | Acceptance Criteria - Pits: -Pits located within 1.5m of nearest rail, pit to be 300LA Railway loading - Pits 900x900mm or greater, multipart pits lids to be used. -Pit Lids: Pit Covers shall comply with AS3996-2006 - Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C. - LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6) -Inspect materials upon delivery and attached delivery dockets.-
label | 6f680932-7548-51b9-8592-1b43c44ac4ce |  | note | Method - Visual Document Review
label | 3fd0dfdc-c724-53bb-9d01-9ef21ebadbf5 |  | note | Frequency - Each Material Type, Each Delivery
label | 10f7d7b4-8b90-56ae-85d6-c42f7334aff9 |  | note | Category - IP
label | 3db869ea-2788-541a-90c6-abbb10af596a |  | note | Responsibility - SE/PE
label | 1ce80539-56e1-5d21-8c31-2ddb03ddef03 |  | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
checkpoint-status |  |  | checkpoint | 2.3 - Warning/Marker Tape
label | 19b8d005-9b23-575f-ad8a-ec7bd8cf25bb |  | note | Reference - IFC Drawings AS/NZ 2648.1 TS-SP-013 L1-CHE-STD-043 6.4
label | 5d829ec8-65ac-541c-8a45-2a85037768b6 |  | note | Acceptance Criteria - Warning/Marker Tape: Above LV: 150mm minimum wide orange coloured PVC ‘DANGER RAILWAY SIGNALLING CONDUITS’
label | 9436ed88-be1b-5186-adc4-acf6a5e58844 |  | note | Above Comms: 75mm minimum wide white coloured PVC ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
label | d5235150-3157-515e-99a4-3f24dd0aee4d |  | note | Above HV: 300mm minium width orange coloured PVC 'Danger - Electrical Cable Below'
label | 0d5cf6cb-aeb5-50db-b8cb-6b06bcb86af6 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 95970bf9-eb68-54b8-9f13-327dc13025bb |  | note | Method - Visual Document Review
label | aecdd65e-1b37-59c4-ba7f-7f10e9aeb314 |  | note | Frequency - Each Material Type, Each Delivery
label | 4702353a-b047-5b10-aad3-458147742f9d |  | note | Category - IP
label | c8f17d97-c376-5fc4-be9b-1e94ceb95668 |  | note | Responsibility - SE/PE
label | e89f21bd-5d8a-54c1-918d-7d7a8fc28fdc |  | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
checkpoint-status |  |  | checkpoint | 2.4 - Protection Barriers
label | 8a37118a-3924-587e-9d51-45abc496b36b |  | note | Reference - IFC Drawings L1-CHE-STD-070 10.3.3 AS4702
label | 3120690f-430e-5e26-85a8-28c6eba85fd8 |  | note | Acceptance Criteria - Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days Inspect materials upon delivery and attached delivery dockets.
label | 62f63b42-6498-5138-bdd6-2b68dc7223c2 |  | note | Method - Visual Document Review
label | 1ba15ade-ffe0-52ae-908e-e7300d019009 |  | note | Frequency - Each Material Type, Each Delivery
label | 845efd91-d37e-546a-8834-ceb2e6ac1b08 |  | note | Category - IP
label | 5b24d959-e81f-5a69-93fb-dcb02eeec2c9 |  | note | Responsibility - SE/PE
label | 0813e889-c9db-59e8-a322-ece83e6afc78 |  | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
checkpoint-status |  |  | checkpoint | 2.5 - Backfill Material (stabilised sand)
label | fc849307-a4b8-5fbe-b51f-dc89f84a10fb |  | note | Reference - IFC Drawings L1-CHE-STD-043 Section 2 Table 1
label | b41d9d70-017a-585f-8ed3-289ee2a0aaee |  | note | Acceptance Criteria - Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits. Inspect backfill material. Attached delivery dockets (if applicable).
label | ac059ad7-e386-50fd-8eb8-a22e4860a703 |  | note | Method - Visual Document Review
label | 26ff958e-9fe5-5fb6-9e2a-59480aa1c5d7 |  | note | Frequency - Each Material Type, Each Delivery
label | 716dd006-8d38-5f23-a5ec-ded1f6edd0ed |  | note | Category - IP
label | b6d4af4d-2f94-5fd9-86b3-2745c04fe548 |  | note | Responsibility - SE/PE
label | 14094ae7-514e-5061-8ec9-0741b90906b0 |  | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
checkpoint-status |  |  | checkpoint | 2.6 - Bedding Sand
label | 51d353cf-3d5b-58f7-8b2e-801c52de9767 |  | note | Reference - IFC Drawings AS2758.1
label | d1ea6e61-fa75-5bf5-b068-271597493481 |  | note | Acceptance Criteria - Bedding Sand shall be a clean sand that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
label | 4cabd3b2-444e-5c86-b36d-a2f87bae9cdb |  | note | Method - Visual Document Review
label | cc9d9b7a-f81e-516e-aa3d-3b6cbce30f9f |  | note | Frequency - Each Material Type, Each Delivery
label | 8e497d93-d921-52ad-b9de-462b06835397 |  | note | Category - IP
label | d821f960-9a70-5aea-b5b8-941981a8112b |  | note | Responsibility - SE/PE
label | 49c522d3-32af-5770-b482-8f74b7cd6b93 |  | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
checkpoint-status |  |  | checkpoint | 2.7 - Draw Wires
label | a21e2381-b3d6-5832-86fb-a784bfe99c26 |  | note | Reference - TS-SP-013 AS 4142
label | 0b4ce6d4-b3fe-59fd-a676-66e6b87785ea |  | note | Acceptance Criteria - 6 mm diameter polypropylene blue/yellow
label | f21dc47a-2e1c-580e-8c32-8854cf5a1993 |  | note | Method - Document Review
label | b654a229-62e4-5c0c-9672-68155b9951cc |  | note | Frequency - Each Material Type, Each Delivery
label | 5a700b49-8951-529e-885f-07db9bc61451 |  | note | Category - IP
label | b82b10fd-92cf-5c55-91d8-49b047feee63 |  | note | Responsibility - SE/PE
label | 360f9dff-4221-53fc-b4d4-8fd22ff186fa |  | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
checkpoint-status |  |  | checkpoint | 2.8 - Concrete Mix - Trench
label | 2486c569-a575-5c8c-8361-42253ea4e5d3 |  | note | Reference - L1-CHE-STD-043
label | 5ac4b019-c799-5d47-8df3-e989f6157aaa |  | note | Acceptance Criteria - Concrete strength at 28 days shall be not less than 25MPa. Chemical admixtures or fly ash shall not be used
label | ade23e7d-b422-5e50-a3be-9029fcef81f6 |  | note | Method - Document Review
label | 3ee93585-2698-571e-9ae7-a42078825a96 |  | note | Frequency - Each Material Type, Each Delivery
label | 38021260-8f68-5365-86ed-8f3e22321111 |  | note | Category - IP
label | 8e854544-7261-5fa5-ae92-e8b580c1c1b8 |  | note | Responsibility - SE/PE
label | 61f5a9f6-b3ad-57e0-b62c-e537cf55d778 |  | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
checkpoint-group |  |  | section | 3. Prelimnaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Services
label | 4f73390a-8ec7-53eb-8615-d8048612bf66 |  | note | Reference - Services CAD file
label | c09a53c8-0b92-526f-b220-c5fad1f72f2b |  | note | Acceptance Criteria - All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit). Survey to mark out existing services.
label | c393a1cd-e412-5246-8075-87b442734d00 |  | note | Method - Visual
label | 0826e828-aba0-52b6-af9b-90fb81c34d1c |  | note | Frequency - Prior to commencement of works
label | d8d5aa4a-63f6-52b0-9d6a-92d162a7c422 |  | note | Category - IP
label | 8c0e5a58-f118-5d28-b448-b2f09b7dae34 |  | note | Responsibility - SE/Site Supervisor
label | 0909aeb7-c15d-5225-9927-f18967cc6645 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 3.2 - CSR Works Procedure
label | 8319042b-97b4-5cdb-b6e8-cd9b41899a81 |  | note | Reference - WAP_BRU_201
label | 7daf1245-ba81-5550-86f4-61233f160119 |  | note | Acceptance Criteria - WAP to be reviewed and signed by all relevant stakeholders along with Rail Safety highlighting works proedure with in the Rail Corridor
label | a3bd840e-d56d-5867-b484-1b5696fe3676 |  | note | Method - Document Review
label | 96afa029-bc3e-577b-820a-aed15b8e1eba |  | note | Frequency - Prior to commencement of works
label | ccb15b3c-7f02-5c38-8ae6-388c4ca1f523 |  | note | Category - HP*
label | b12b12c5-e50f-537b-966b-a67c4c38058e |  | note | Responsibility - SE/Site Supervisor
label | d477e924-b384-5633-aa9f-415cfaafa7d9 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | f6aeb431-97df-5c58-bb61-dc9a0b8b5e77 |  | note | Reference - IFC Drawings
label | f7897f00-4768-56e1-8432-2bb08cd26ee9 |  | note | Acceptance Criteria - Survey to set out trench alignment and pits, and establish construction control (alignment and level).
label | f4edd5ff-826c-51e4-ae2c-3f4df49d42bf |  | note | Method - Measure Visual
label | 9c72ceb0-cc50-5349-9a1a-e7c19cd92c03 |  | note | Frequency - Each element
label | f31f08b2-fe81-57a8-8c23-788ba4595e82 |  | note | Category - IP
label | 1e809443-e7fd-5a69-976d-13ed6d43af32 |  | note | Responsibility - Surveyor SE/Site Supervisor
label | 8da1f169-a897-50d7-b3e0-2bffb7c13808 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 4.2 - IFC Drawings
label | c8553c6f-7ddb-59e9-88a3-b0437d52b970 |  | note | Reference - IFC Drawings
label | 7f3eba87-8ebf-5d9d-971e-f088c39da223 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | c6ed01ca-d710-504c-b0c9-5332568ac2f1 |  | note | Method - Document Review
label | 16802713-3117-5e2d-9748-4e371b0b2e82 |  | note | Frequency - Prior to commencement of works and at regualr intervals
label | e01a3a4f-6a54-58ac-8a42-5f8690c55db3 |  | note | Category - IP
label | 97af38ec-7cbd-596d-bfb2-9e1272409415 |  | note | Responsibility - SE/Site Supervisor
label | 6891a9b3-b37e-5cd8-a15d-ec70b3dfe123 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Trench Excavation
label | 31e168b2-9b16-574a-9a51-148afc20d816 |  | note | Reference - IFC Drawings L1-CHE-SPE-070 7.3 Table 2 L1-CHE-STD-043 L1-CHE-STD-070 7.1c
label | 2f9938d0-2e44-5cc7-881e-de3d6d132396 |  | note | Acceptance Criteria - Trench profile and depth as per IFC drawings. Edge of trenching to be a min. 2m from strucutres/pile foundation (unless it is mounting the structure) and a min. 4m from the rail for HV and 3m from the rail for LV & Comms The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits. The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
label | 7a311320-809c-5cda-99c1-a58ad60e15df |  | note | Method - Measure, Visual
label | cd04608c-d208-5eef-8240-b4698fd1a48a |  | note | Frequency - Each lot
label | 778f455a-959c-5590-8031-ef84bf5c9add |  | note | Category - IP
label | 6277b753-4ad2-5b12-a03f-c15a18415412 |  | note | Responsibility - SE/Site Supervisor
label | 573388ad-968d-54b3-b39f-68ac3df1a654 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.2 - Trench Stability
label | 0ee562ce-980e-5d98-a929-fb2516f7ad67 |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings MRPA Standards
label | 9b31f2f2-f67a-5dc7-b6d8-49f17f2ed42d |  | note | Acceptance Criteria - Trench stability check: - Shoring, - benching - geotech signoff Attached Geotech Report
label | f752b05d-52c0-5310-b989-53e8db433feb |  | note | Method - Visual, Document Review
label | 818f1ecb-2a23-5c7c-9321-534fbd702df8 |  | note | Frequency - Each lot
label | 3922c741-b48d-5a37-902b-30ef7ba69a6d |  | note | Category - IP
label | 3fac6657-ca7c-5acf-b904-358b78739879 |  | note | Responsibility - SE/Site Supervisor
label | 0ec11a44-ddf6-5098-829b-d7734e37c8b9 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.3 - Placement of Bedding Sand for Conduits
label | 983ca552-ff7a-5bc6-a7b7-00717df3ec87 |  | note | Reference - IFC Drawings L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070
label | 11382dbc-f616-5d2b-8114-852ca946134d |  | note | Acceptance Criteria - 100mm of bedding sand/crusher dust to be places at the base of trench.
label | 48470d92-f1a2-5c0b-ba79-7a3e8fda940f |  | note | Method - Measure, Visual
label | f485fae3-901e-565d-8d75-66450f1cc5d4 |  | note | Frequency - Each lot
label | f01b30b1-e20d-5242-a146-d007e3b1de9e |  | note | Category - IP
label | c31b5283-1499-52dc-abf3-eb7f3f39373d |  | note | Responsibility - SE/Site Supervisor
label | 07751179-7e43-50e8-879c-f3c1223e2ef6 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.4 - Conduit Placement & Configuration
label | a6c6b201-e994-5a4b-8b9b-87613f485936 |  | note | Reference - IFC Drawings L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 L1-CHE-STD-077
label | 6de8075a-c26c-5171-9ce8-56f63142f8c8 |  | note | Acceptance Criteria - Conduits are configured in accordance with IFC drawings and meet cable separation requirements. Min Cover - HV: 1000mm - VicTrack: 650mm - Signalling: 800mm - LV: 800mm - Electrolysis: 800mm - SCADA: 800mm - MTM Comms: 600mm - 800mm below water coarses (stab sand encasement) - 1200mm Under VicRoads Roads & top of Rail - 900mm below council roads
label | 52109e8f-9d0e-589f-8091-e91f4fc75f29 |  | note | Method - Measure, Visual
label | 97cb5454-4ebc-54df-abcf-d5e494d0084f |  | note | Frequency - Each lot
label | e9b3c849-24ff-5da9-926a-8406ada3e9db |  | note | Category - IP
label | 748bfda5-fef7-5f7c-a2fe-4a11dea5395d |  | note | Responsibility - SE/Site Supervisor
label | 9c7f27fb-4453-52c9-8360-78a13731a27d |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.5 - Separation of Services
label | bf75eb71-d0c9-5f1c-8061-5fbc9cedbc2f |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 L1-CHE-STD-077 IFC Drawings
label | 47d107ae-3f46-54c1-a688-c821d3de20e3 |  | note | Acceptance Criteria - Separation of services - HV: Min. seperation distance between HV conduits at least 50mm - VicTrack: fiber 300mm from HV - Utility: 300mm to utilities - Rail: When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 9271bbb6-803d-5e26-bdc2-3a021bb59326 |  | note | Method - Measure, Visual
label | b820c892-0aab-589d-a39f-3cb44fd00e65 |  | note | Frequency - Each lot
label | ad4a7b47-e6ab-5b59-bc84-3cdf7ec1b622 |  | note | Category - IP
label | b4749dd0-3fc0-5b99-9d94-f408dff65d72 |  | note | Responsibility - SE/Site Supervisor
label | 5eb73bd7-ca90-5d00-8875-d513ba020e2e |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.6 - Joints
label | be6757fb-0a1f-5b38-81c1-de267131a034 |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
label | ab06d936-00cd-5449-9514-8c47754b54dd |  | note | Acceptance Criteria - All conduit joints shall be made by utilising the spigot and socket ends. Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer. The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer. Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
label | 9e99e3dd-4735-531d-ba78-3354093d1c2e |  | note | Method - Visual
label | 5ab51977-7faf-5117-825d-0c58294707c5 |  | note | Frequency - Each Joint in each trench
label | 1bb473e9-4570-53a2-866f-a867909b3e28 |  | note | Category - IP
label | a99fb1e4-d449-5582-918f-6ae36fcd2d7c |  | note | Responsibility - SE/Site Supervisor
label | 8b4e2294-bed6-57b4-b92a-58b401ca99a9 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.7 - Conduit Inspection
label | ced848d7-c95c-57d6-a01b-af82f8c1deed |  | note | Reference - L1-CHE-STD-070 16
label | 8cfdbd39-e3a6-5921-af8a-c517ce021eb9 |  | note | Acceptance Criteria - Provision shall be made for inspection of cable routes by NA, MTM/VicTrack representatives prior to backfilling.
label | 1ba591ac-2b8c-5e28-b8b4-522b06af1aa9 |  | note | Method - Visual
label | 68d52625-82e0-572e-968b-cbd969d7a9ce |  | note | Frequency - Each lot
label | 1daccdff-ce36-51a2-82d4-821f5796a3a1 |  | note | Category - HP*
label | 1b796cec-32f5-5db6-9ce7-a0fe75e55267 |  | note | Responsibility - SE/PE MTM / VicTrack Rep.
label | 196fd312-0ab9-5d12-a924-b8e6ab16735d |  | note | Verifying Documents - This Itp
checkpoint-status |  |  | checkpoint | 5.8 - Bedding Sand Installation
label | 6439821d-3b0a-539e-a5bd-a29205128f05 |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 CL13.1 IFC Drawings
label | 72a7b0e5-1a18-5401-b9ab-1f968be75fcc |  | note | Acceptance Criteria - Bedding sand/crusher dust extends 50mm past edge of conduits. Bedding sand/crusher dust extends 100mm above conduits. Attach Delivery Dockets
label | 661712aa-8df0-5490-818b-e209e90f1993 |  | note | Method - Visual
label | eecd0b27-272b-5097-9354-1ed3696afb05 |  | note | Frequency - Each lot
label | a4985578-d821-5d17-b35e-f3ce1478f9e4 |  | note | Category - IP
label | daac82f3-f1fb-5e29-b525-218b85b0082f |  | note | Responsibility - SE/Site Supervisor
label | 5abb78f0-df4a-5bb6-9158-a11045bf9abb |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.9 - Marker Tape
label | 2ee9f90e-4145-5378-a563-2f07150328eb |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-SPE-070 Cl10.3.3
label | ea796636-5a11-508f-bc19-296cc487ec72 |  | note | Acceptance Criteria - Warning Tape installed a min. 300mm above top conduit or a min. 300mm above HV protection barrers. Tape to be one continuous length. VicTrack to inspect the Marker Tape placement..
label | 75fcfd03-06b3-5a50-bbaf-7f81adb1f4e8 |  | note | Method - Visual
label | 6ca8df7e-7644-5467-bccd-bc1d15389b7c |  | note | Frequency - Each lot
label | 6ec070f3-d5b1-5108-970a-408932a29d3a |  | note | Category - HP*
label | c52de600-d7ed-5fcf-bb40-0c1b9eb6736b |  | note | Responsibility - SE/PE MTM / VicTrack Rep
label | c9e61785-68a2-541a-8140-f35aa48d2b15 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.1 - Backfill Installation for Conduits
label | 1215f506-abf1-5139-9ca9-ede5e01cf9be |  | note | Reference - IFC Drawings L1-CHE-STD-043 clauses 6.15 and 6.16
label | edc87b66-8158-5c51-bc1f-d5d8c7bd32d3 |  | note | Acceptance Criteria - Backfill per trench profile - 150mm layers of 3% stabe sand - conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
label | 2f4d802d-425e-5859-a56e-297e22e71eb5 |  | note | The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement
label | e9f9cb0a-8098-509d-8a1d-82263a9db34b |  | note | Trenches under road pavement - backfill to be same material as the road formation material.
label | 8451879b-4f26-5339-9b7f-c910670d5e39 |  | note | Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits
label | 3f000d7c-733d-58b8-b372-7630f7aa04ac |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 54fab800-c369-5e22-89c9-fe84dd44a732 |  | note | VicTrack to be notified and witness the first layer of backfilling.
label | 9a1821d5-508f-5050-a919-8bfaa59c1665 |  | note | Attached Delivery Dockets
label | 45f12870-344a-54de-a597-8347f0d98f16 |  | note | Method - Visual
label | 7f6780f7-4556-57aa-a027-dcfe4158bfbb |  | note | Frequency - Each lot
label | e054a422-473a-57dc-a243-abe0613a5c31 |  | note | Category - HP*
label | 4f7acf9a-7389-58b8-98cd-17c679e45b16 |  | note | Responsibility - SE/PE MTM / VicTrack Rep
label | 5160af98-1cdf-5927-8ca9-e8874b0522d9 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.11 - Signalling Pits LV Pits Electrolysis Pits SCADA Pits MTM Comms Pits
label | 6bec5f74-c885-5f3d-aef2-e757cee5278a |  | note | Reference - L1-CHE-STD-043 Cl7.14.o, Cl7.14.g
label | 1d8a676b-ac6e-5a5b-a758-fda8f59c4dd3 |  | note | Acceptance Criteria - - intervals no greater than 400m (electrolysis 190m) - 3m from rail - Access Roads, Class D lids - Footpaths and non traffiacl areas, Class C Lids
label | ca60609a-f573-574a-a8b1-e26df6cd0dd8 |  | note | Method - Visual, Measure
label | 19aea829-8f98-5e76-b018-1988f0372fa2 |  | note | Frequency - Each Pit
label | ee60dfc8-7418-50a8-9648-c5076a7b8666 |  | note | Category - IP
label | a44e682f-ab1a-5488-a3f1-6c8450159698 |  | note | Responsibility - SE/Site Supervisor
label | 215f8f04-4b82-5607-a92e-f2a0b83aa21b |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.12 - Additional Considerations
label | 21d3f3c6-1ed6-5144-b0ba-f8a1d3d68635 |  | note | Reference - IFC Drawings
label | ef0651f6-25f8-569f-b27e-c92a1eae2f6b |  | note | Acceptance Criteria - Access tracks to pits Safe access and egress (i.e. lid doesn't open up with workers back to the rail) Hand rail & retaining wall installed as required
label | 6bfe9811-c054-5aae-a9a0-6371e1d481a8 |  | note | Method - Viual
label | 3ca3f387-87ee-5d3a-8b58-96f53179df75 |  | note | Frequency - Each Pit
label | 45dea665-6bcd-56d4-bd84-7466e81e0a53 |  | note | Category - IP
label | 2064a6ac-9ee8-59bb-906f-188136bbb6d8 |  | note | Responsibility - SE/Site Supervisor
label | e285c370-3a67-5266-8817-540bf5059bf1 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.13 - Bedding for Pit Installation
label | 1d1acdf6-c1f3-5b02-abc9-9a446c743353 |  | note | Reference - L1-CHE-STD-070 Cl 7.21.u L1-CHE-STD-043
label | 82b8bb32-922b-5bbc-88d2-78360c8b0c88 |  | note | Acceptance Criteria - 150mm of crushed rock under pit extending 500mm past the pit Drainage arrangements shall be provided at the base of each pit. Attach Delivery Dockets
label | b456a94d-3797-5db3-af27-601c479058aa |  | note | Method - Viual, Measure
label | 2f97c633-239a-50c2-9837-9ca78c3d262f |  | note | Frequency - Each Pit
label | 5812cc8f-bc37-57b2-a63d-3ba306b406e2 |  | note | Category - IP
label | dfac8c14-7629-5348-af3d-be469b668120 |  | note | Responsibility - SE/Site Supervisor
label | d6594ec0-47f7-52c2-b28c-e671c275430f |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.14 - Pit Orientation
label | d21be06d-2f50-5a3c-96cd-1744f3e3b54a |  | note | Reference - IFC Drawings
label | 5dbffe02-ed8c-5dab-afa0-9e70abbb177a |  | note | Acceptance Criteria - Pit to be parallel to track and parallel to conduit route.
label | c53d0e23-54b9-5807-88f7-a62027ffd390 |  | note | Method - Viual
label | 623b01cb-b4be-50a1-8531-9a3d84396ccf |  | note | Frequency - Each Pit
label | 7612ded7-bb59-51c0-960b-c314d06053af |  | note | Category - IP
label | 2b960379-9c78-5540-8fe2-3df45f6b04fe |  | note | Responsibility - SE/Site Supervisor
label | a46448a1-6778-5d6d-9404-d45a2483a7d3 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.15 - Pit Installation
label | 31e183c5-69bf-5835-9bb1-23dc245d9fbf |  | note | Reference - IFC Drawings
label | 7cf89215-7515-5610-930e-4054b39d807c |  | note | Acceptance Criteria - Pit installed to design specifications Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
label | 15dd1e46-b3fd-50cf-8881-0493526c6c5e |  | note | Method - Viual
label | d83f4381-0d7a-5b64-9c97-cc3fa783f34e |  | note | Frequency - Each Pit
label | 578f0d3b-e5ba-50f4-8103-9dc9021b71e3 |  | note | Category - IP
label | b8b56d36-719f-5a65-bcf0-b81c14c1854e |  | note | Responsibility - SE/Site Supervisor
label | 73f98bc9-2259-5b5c-b0a9-54fc79838d1b |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.16 - Conduit Entry onto Pits
label | 01c846da-35b1-5346-9efa-76909fbe342e |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
label | 75a71957-ec19-5c32-86dc-6b1715adbcf9 |  | note | Acceptance Criteria - Lowest conduit 100mm from the pit chamber floor.
label | f4f05fb6-29b3-5e3d-b7c3-42e4a26eb8e1 |  | note | Method - Visual, Measure
label | 2c1ab7d3-10b2-5373-b4b2-cc9f308ba35e |  | note | Frequency - Each Pit
label | e9039d61-8f84-5fb3-b948-5c6194ea4d63 |  | note | Category - IP
label | c55852c7-d1f6-5156-af38-34425ce3e753 |  | note | Responsibility - SE/Site Supervisor
label | e9e5cbe1-12f3-5a39-9176-8eb00ccca1df |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.17 - Tracer Wire
label | b6d86eda-a4aa-5ff2-80a3-c9911c34d790 |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
label | 148a025a-d9c4-51c1-a8c7-e4eb959ed6a9 |  | note | Acceptance Criteria - Warrning tracer wire for Vic Track routes to be drilled into pits and crimped off. If tracer wire broken needs to Crimped
label | d9c50d8a-4e2e-50fd-b41d-8102437f9dcf |  | note | Method - Visual
label | 0bb1ed8d-8bf8-5c0b-a8d5-cf8c76951063 |  | note | Frequency - Each VicTrack Pit
label | a2f69fb4-9fb3-5a72-820e-1e3bc3219a2c |  | note | Category - HP*
label | 8bed12df-4265-5e8c-958f-47230c7d80d8 |  | note | Responsibility - SE/PE, MTM / Vic Track Rep
label | 2d564c82-26ea-591b-93ce-a5a56d34cbc6 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.18 - Spigots and Bell Mouths
label | 3a5ed17b-1292-5ac2-8c83-1874ac823b70 |  | note | Reference - L1-CHE-SPE-070_9.3.4
label | 67b40699-8e04-5c49-af5c-b199ecd02ee4 |  | note | Acceptance Criteria - All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigots. HV Conduit entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
label | 5075ed70-a410-58a4-bd81-dd465bc9ed00 |  | note | Method - Visual, Measure
label | f95af92d-d40a-5e40-9ac9-f4e8e6093ffb |  | note | Frequency - Each Pit
label | cf326f79-269a-57ea-af0d-ffcf1b042d13 |  | note | Category - IP
label | 019d64f4-e77f-5b39-a911-33f5d28a6330 |  | note | Responsibility - SE/Site Supervisor
label | 7a71d65f-2062-5643-ac67-256b9393309b |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.19 - Draw Ropes
label | 4fddd25a-2e50-5faa-8dac-60f5122ab73f |  | note | Reference - VRIOGS 012.2.1
label | ae2a31d0-adb9-5f0f-b602-bd1484ba3aef |  | note | Acceptance Criteria - The draw wire shall be continuous for the complete length of the conduit run. The draw wire shall have a minimum of 2 metres of slack within every pit.
label | f0295b7f-2df6-5b71-b42e-a608abd1f9c5 |  | note | Method - Visual
label | bb04d2e8-e4f3-50f1-89a5-e65002b50f04 |  | note | Frequency - Each Pit
label | b6ddd768-834b-55d9-92af-1c61bff578fd |  | note | Category - IP
label | fbeb27cc-01b2-58a7-97ed-2e158416fb60 |  | note | Responsibility - SE/Site Supervisor
label | 385a5488-fb42-52ac-9085-d01bcd3ee125 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.2 - Backfill and Compaction Testing (if applicable) arouns Pits
label | f34712a4-4629-51ca-951a-4ef63e31ab8d |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
label | b43e99b3-7e22-5bec-9f96-045452c9fe68 |  | note | Acceptance Criteria - Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
label | 86d7362b-9e72-5c52-8af6-60da91022eb0 |  | note | Sand within sand pits to be compacted in layers no more than 250mm layers
label | 25af188a-d434-5389-a3cf-8b1598a754af |  | note | Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
label | 4dd85bb9-4962-5a69-b7e0-5e19baedd459 |  | note | Attach Test Report
label | 84aadcfa-8cab-5d77-ab61-9ff66d6cd181 |  | note | Method - Document Review, Visual
label | c17f066a-ccce-592b-8623-bee914e7a491 |  | note | Frequency - Each Pit
label | 157733a2-96ba-5c65-835d-a04bd0d385fd |  | note | Category - IP
label | c689da68-6299-5651-a09e-df7799513497 |  | note | Responsibility - SE/Site Supervisor
label | adfc0dee-98df-51e0-ae47-9033a21f1a3c |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.21 - Spare Conduits
label | 6aa8e623-4824-5e92-b800-03b855ff89db |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
label | d1b025a1-af11-529b-aac2-f516bab063ab |  | note | Acceptance Criteria - Spare conduits to be sealed and to be included on survey report.
label | f760e199-67d3-509c-bff5-2dc9c4feab0d |  | note | Method - Visual
label | 8e47d88a-0574-5c79-a413-4ebd4fed19da |  | note | Frequency - Each Pit
label | 572a128a-e120-52e5-aba6-88b37b930a43 |  | note | Category - IP
label | e9aad2e9-9405-5ba8-8e26-5704716c8a71 |  | note | Responsibility - SE/Site Supervisor
label | 3332dde4-4bb0-58df-a2be-a883cc5ca7cb |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.22 - Pit Lables
label | fcaeb923-984d-59cc-a6f5-2bf1352b80de |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
label | 1886d953-0a8c-573b-ad19-bdff48bad2f1 |  | note | Acceptance Criteria - Pit labels Brass Label (30mm x 150mm) - HV: DANGER - Railway High Voltage - VicTrack: Victrack Comms - Signalling: Rail Sign Comms - LV Pits: Electrical - Electrolysis: Electrolysis - SCADA: Rail Sign Comms - MTM Comms: Rail Sign Comms
label | be068c4a-fdbc-5cb7-b4b5-83353c698c47 |  | note | Method - Visual
label | c6b04755-352c-5fd0-8725-f6ac82c7dad4 |  | note | Frequency - Each Pit Lid
label | cb3e1c0d-4ea6-5bf5-bdbe-beb4d532712f |  | note | Category - IP
label | 62faa399-ecc6-5637-80af-9a98d828830c |  | note | Responsibility - SE/Site Supervisor
label | 78a35a19-dfe2-5eb3-b383-49434e56f93e |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.23 - Pit Numbers
label | 00f40897-f49f-506b-ac7c-dceaf55700e1 |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
label | 1850fa58-26b6-5e26-931f-b212a4505035 |  | note | Acceptance Criteria - Pit Number Brass Label (30mm x 150mm) - HV (22kVV Feeders): ###HV - DC (HV Feeders for OHLE): ###DC - VicTrack: ###C - Signalling LV: ###SL - Signalling HV (2.2 or 3.3kv): ###SH - LV Pits: ###L - Electrolysis: ###E - SCADA: ###MS - MTM Comms: ###M
label | 4136458b-7750-5dda-859e-4a4feafd0a35 |  | note | Method - Visual
label | f5e0ea52-3a68-5ff6-86f6-bff2fa17e015 |  | note | Frequency - Each Pit Lid
label | 3c18a722-73be-53f3-baff-d282f401efad |  | note | Category - IP
label | 2e4d0544-f8ae-5adc-a066-ce6e313da7fe |  | note | Responsibility - SE/Site Supervisor
label | 922a44a0-bac8-5c84-9bd9-befc1fc18d32 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.24 - Cable Route Markers
label | 76144e2c-9d32-56bb-b798-72a0c14e63e9 |  | note | Reference - L1-CHE-SPE-070_13.2 STD_E0169 and STD_E0170 AS 4799 STD G0003 and STD G0004
label | 851593a3-d4bf-529e-9865-4432b44abf58 |  | note | Acceptance Criteria - Cable Route Markers - points entering & leaving the rail corridor - no greater than 100m spacing - Change of direction (more than 5 degrees) - White posts with marker plates for conduit runs
label | a2c4cced-3ec8-5cdb-a5df-2593006d3056 |  | note | Method - Visual
label | dde5e227-af25-5233-8a21-81ea915d0507 |  | note | Frequency - Per Cable Route
label | 77140785-815c-5d0a-a7c5-1abfc2b839ae |  | note | Category - IP
label | 2ec1825a-3131-5a94-92a6-13b1318521ea |  | note | Responsibility - SE/Site Supervisor
label | 92464743-752e-5dd0-9a9f-2083d2d62077 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.25 - Cable Pulling
label | 1494b263-e790-5ad5-a651-456fc0af211e |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
label | c9535c07-e04b-581e-8634-9d1d88708e1c |  | note | Acceptance Criteria - Cable pulling to be witnessed by MTM/Vic Track and to be signed off.
label | bbdeacc4-7dd7-56e5-9eb7-000f6bd60a5b |  | note | Method - Visual
label | ce0a57de-9675-5e21-9b32-15812b6505eb |  | note | Frequency - Per Cable
label | dba4d3f2-a7ce-5cd6-9626-8be6b9aa0999 |  | note | Category - HP*
label | 474ee7e6-7362-5d2c-b506-07fe3c4b24c1 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | bd760feb-58ca-5224-99e0-eb3055eeca9f |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.26 - Cable Labels
label | 9ef4c9a8-fa9f-5704-9850-6bf884198749 |  | note | Reference - L1-CHE-SPE-070 Section 13.3
label | efad579a-3661-5e1f-b9d1-144f6e4286bb |  | note | Acceptance Criteria - All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints. The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
label | db7184c0-91c8-523c-8a5e-1b918cde877d |  | note | Method - Visual
label | bf02e5a2-0b10-58bf-9b89-39a34dcdfc08 |  | note | Frequency - Per Cable
label | accb6718-bf60-554a-be21-ca1362f3fe60 |  | note | Category - HP*
label | 74044936-4613-5e6d-902a-ac8db4105c17 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | 9b40c73c-5ec2-5c4c-a5c6-86fe8b7bf6a4 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.27 - Cable Joints
label | 47dcd337-e290-5aba-a232-d5866aaa4a1b |  | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
label | f4979caf-7a3d-578f-9e9b-c4f8f47ec52a |  | note | Acceptance Criteria - Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
label | 28ce7dd7-acdc-5a80-bebb-da227bb23e0a |  | note | Method - Visual
label | 6b0e7a25-6a73-5a31-8e4c-b58b98dc4f48 |  | note | Frequency - Per Joint / Termination
label | fdc4d8a5-c058-5414-bb21-5d1981be273c |  | note | Category - HP*
label | 82a72261-7740-52f9-91fc-33b9d728b414 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | d8d9b669-8174-5dc3-9e64-fcfd35b05734 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 02106fe5-d566-5b85-98cd-a1dcc18d12dc |  | note | Reference - IFC Drwings L1-CHE-SPE-070 Section 13.1
label | d7ae121c-bd83-5853-a896-8374bb78c956 |  | note | Acceptance Criteria - Survey report to include but not limited to: - Cable joint locations. - Cable pit locations (Corners) - Pit dimensions & pit lid type - Under line crossings - Under road crossings - Changes of direction - Spare Conduits - Conduits labelled as per trench profile - every 10m - Other significant points of the cable route Attached Survey Report
label | 94afee7e-64b6-5e7a-ba07-69b0937eda7f |  | note | Method - Document Review
label | b59d4a09-0d06-5844-9d5f-19485cfeb6e3 |  | note | Frequency - Each Lot
label | 9dd4d079-ae23-5898-9c6e-353133039da1 |  | note | Category - IP
label | f80025b6-b905-5028-8249-9419356af0af |  | note | Responsibility - SE/PE
label | 4a7d1749-f277-5aee-9c95-df47d4bf8421 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.2 - Handover Check
label | 36959fc4-1351-5557-b4ac-8b7bd36e550b |  | note | Reference - IFC Drawings
label | a256166c-16b0-57a8-9d36-2959eeeb1411 |  | note | Acceptance Criteria - Handover check completed for Testing and Commisioning. Attach MTM/Vic Track Check Sheet (Signed-off)
label | 4ea092cb-cee5-5635-b6f3-8a4413911cf4 |  | note | Method - Document Review
label | 91226f36-24e5-5000-bddc-573f2454c21c |  | note | Frequency - Each Lot
label | 9f42d629-13b9-58ae-a16f-cc418daa4139 |  | note | Category - HP*
label | 243e7650-8bb6-54a2-b774-b0d45203c161 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | 341268b9-7221-56d7-afdb-66a4f3420b38 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.3 - Testing and Commissioning
label | 4761b513-130e-54c7-be0c-2eac06929c23 |  | note | Reference - IFC Drawings
label | 2bc7534d-a4bd-50e4-8d0e-e0e47e35e524 |  | note | Acceptance Criteria - Testing and Comminsiong to be completed Attach Testing and Comminsiong Report
label | 9e155767-af8b-5295-b8d7-eceb90ee37af |  | note | Method - Document Review
label | b0867c87-652a-5a61-80c5-246fd20e093d |  | note | Frequency - Each Lot
label | 8c71499c-15cb-59a8-9382-08808b0e21a1 |  | note | Category - HP*
label | bde653dd-1100-54ed-a88d-9175c9f8c3e9 |  | note | Responsibility - PE, MTM/VicTrack Rep
label | 05f4da77-ea4c-5ef3-9f5d-635e089da9c7 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | 1eb887ad-d2c9-5b90-8429-d24b8886d8e2 |  | note | Reference - MRPA Quality Management Plan
label | a0d218be-7278-5693-ae27-4f9a72d8e886 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 5f2b5974-f034-5c87-a837-8b055c750b1e |  | note | Method - Document Review
label | 43d06d31-b21e-5d03-bf0b-3e9f529fc409 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 02360c91-5c9a-518f-8db9-1f6e878a5bf0 |  | note | Category - HP*
label | 79a480a4-be4e-5faa-bee5-924856dbef33 |  | note | Responsibility - SE/PE/SPE
label | 3e71145f-3e36-5b89-aa40-a0a52e143f42 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | 3d519fc7-4d88-525b-b612-f6f6a689afdd |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | f7ac4b8f-c17d-5d54-90cb-f484b7552b0f |  | textbox | Name:
text | 39d9ba1c-8668-5096-b3be-284178b5df4e |  | textbox | Position:
text | e1aaeb98-a9ec-5db1-a282-6eec7ced6bbd |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation | itp |  |  |  | Yes | ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation | 41e0c697-a58c-4e2c-a5aa-26507684652e
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 8efa6ac7-1af9-566e-ad45-6c8092f1aa3b |  | note | Document Title: ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
label | db3736db-7a5b-5aa2-aac4-469ed7495b1d |  | note | ITP Description: Stormwater Drainage Supply & Installation
label | 2040fe3b-04ea-59a3-a0ab-bb016f32c9ef |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 72211ba2-e5c1-5ddd-8d5c-a661487da60f |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 0508fab6-a678-54d6-8ef0-8dd1dbb96404 |  | note | Revision Number: 0
label | feca692b-ea2e-547b-a65e-682bdeafeeb8 |  | note | Revision Date: 15/06/2023
label | f0f06b29-7376-5966-b9d4-30854fc26287 |  | note | ITP created by: Kamel Alshobaki
label | f98f0887-e7c6-5797-9b79-83e914c58d0b |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | b19d3ec8-6437-5778-88d2-d888367a8c01 |  | note | Reference - VicRoads Section 701 (May 2020)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 1cfa6932-1c82-513c-ba0f-55bc1a6e56c2 |  | note | Reference - VicRoads Section 705 (June 2021)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 7061884d-9d02-5b78-9dbb-ddedb5553253 |  | note | Reference - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | a19f1b1c-9b49-537b-b5ab-944cdd7a8ed4 |  | note | Reference - CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 17aa524a-ddea-59d4-8a55-44a82dd335ef |  | note | Reference - CHK-002-CIV-Stormwater Drainage Pits Installation Rev 0
checkpoint-status |  |  | checkpoint | 1.6 - Non Dependent
label | 509ccfc7-c0e9-5eb0-9ff0-17ecba712120 |  | note | Reference - CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
label | beafd793-64c9-5261-b53d-ef61c4274144 |  | note | Reference - VR Section 701.04, VR Section 701.05, VR Section 701.09
label | 992d77ce-7504-5d6b-9bff-d8d9364f9763 |  | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and VR Sections 701.05 & 701.09
label | 552c4f00-2ba0-5f1c-a110-bbcf118317fc |  | note | • Precast reinforced concrete box culverts shall comply with the requirements of VR Section 701.04
label | 3836f5f4-f4fa-53c0-af57-a05602ed61fa |  | note | • Rubber ring joints shall comply with the requirements of AS 1646
text | 10abda73-fd7b-5f4b-8c05-c7cd0f0ba145 |  | textbox | Enter: Teambinder Material Approval number
label | b8d17af5-f190-584e-9b71-662323a7bb2f |  | note | Method - Document Review
label | 4c7a6422-475e-54b7-a645-a3ef9f8e173c |  | note | Frequency - Each lot
label | 36806afa-3f72-59ac-8519-03d2543f5b71 |  | note | Category - HP
label | 3a0d5bed-0645-54a7-a26c-7e3c9e9435de |  | note | Responsible person - Nominated Authority
label | f1350160-a5a9-5cf6-a319-eef155ad97f0 |  | note | Verifying Documents - ConQa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Precast Drainage Pit
label | 54719274-398f-5209-84c6-f52d3d62dcf6 |  | note | Reference - VR Section 705.07, VR Section 705.04, VR Section 705.09
label | 82c92b6d-8d2c-5849-985b-d83e0a193511 |  | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with VR Section 705.07 & 705.09
label | 6df2cbea-d001-51dc-b5d5-d3970a406fae |  | note | • All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of VR Section 705.04. Concrete grades shall comply with Table 705.041
text | 269c96fa-be97-5a74-bc3b-b5c4f2a1205f |  | textbox | Enter: Teambinder Material Approval number
label | 39eb13e5-b872-52b9-a615-965cc0cbfdc2 |  | note | Method - Document Review
label | bdd5fe2c-2a19-58cc-90c5-b6575ac4d9fe |  | note | Frequency - Each lot
label | 60c30fae-6fb3-5a50-9c1d-22e463d777b0 |  | note | Category - HP
label | 2fcc6cef-8ede-5339-9e85-101366e6e0c5 |  | note | Responsible person - Nominated Authority
label | f35ab8ef-0350-5f68-adb7-f3de64da22ff |  | note | Verifying Documents - ConQa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Cast in Place Drainage Pit
label | 4b87532c-9284-5bcb-9bb9-caf2b07a9f45 |  | note | Reference - VR Section 705.06 IFC Drawings
label | 88325314-2481-5650-bbc7-cd6141946096 |  | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of VR Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | e4fd580a-ba63-556e-8f4e-118446246cb2 |  | note | Method - Document Review
label | 4e43e2c5-0480-573c-b045-a6f9ba662a33 |  | note | Frequency - Each lot
label | 929c4ada-6198-5192-9bfe-e6f14ea2029f |  | note | Category - HP
label | e885cb91-cc36-5a3d-8f8c-78f306db5192 |  | note | Responsible person - Nominated Authority
label | ff00914a-9b1b-555b-9c03-a21b32f57bdc |  | note | Verifying Documents - ConQa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Drainage Pit - Step Irons
label | 29367844-bdd6-5b08-a63b-4e1d2e80ed58 |  | note | Reference - VR Section 705.04, VR Section 705.12
label | dd001160-c1ed-5d4b-9027-df26165ffa47 |  | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | bb6a9eae-8a99-5220-a6ce-25ff98015832 |  | note | • Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with VR Section 705.12
text | 93168828-d157-5c14-bed2-c25d9cf94129 |  | textbox | Enter: Teambinder Material Approval number
label | 18c170e3-5f87-543c-8a42-dc5cc815aafc |  | note | Method - Document Review
label | 58b99ac5-7b1a-5c56-b995-68d4f815df66 |  | note | Frequency - Each lot
label | ee9aed34-3e70-5783-9639-d8155a9d9ac8 |  | note | Category - HP
label | f346954f-6415-5cb1-8b58-0d8ffe2f4a7f |  | note | Responsible person - Nominated Authority
label | c6a40ef2-237b-570e-a448-eda1abfa6f3b |  | note | Verifying Documents - ConQa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Drainage Bedding Material
label | a54cc0ee-11be-51a7-8435-fad9afa0dffb |  | note | Reference - VR Section 701.09
label | 42926976-e375-5e1b-8bd1-c008e6494045 |  | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | 19403b49-59ed-56eb-af78-79bc58c5633f |  | textbox | Enter: Teambinder Material Approval number
label | 09ae3c2d-3135-5a0b-837f-985263614209 |  | note | Method - Document Review
label | 9f5690fe-56f7-5785-a33f-c3eee114bbd1 |  | note | Frequency - Each lot
label | e92f6911-d171-5b46-bcc7-aaf6aefa212c |  | note | Category - HP
label | aad5bd5a-85aa-5672-b297-106851194110 |  | note | Responsible person - Nominated Authority
label | 8ba688c2-f867-53bc-9477-9dd7d213b224 |  | note | Verifying Documents - ConQa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Drainage Backfill Material
label | a6ea9783-3a9d-5af8-bbf3-72cc0a6deec3 |  | note | Reference - VR Section 701.09, VR Section 701.19
label | 60fb09a7-24f4-5171-a950-da79861302c7 |  | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | 36707ec3-bc28-551a-bd67-eca140c5fc7b |  | note | • Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with VR Section 701.19
text | 57f4e67d-e3e7-53b4-bdcd-10ad37cae90a |  | textbox | Enter: Teambinder Material Approval number
label | b1350551-c72a-590e-b6f8-00f9153c5c9c |  | note | Method - Document Review
label | f3d9b4ba-c10c-551b-a940-96b561a3f375 |  | note | Frequency - Each lot
label | 260805b1-7965-57cd-ad0a-5c1258755f8f |  | note | Category - HP
label | ecfb820f-58ea-5c24-8eef-82290673155c |  | note | Responsible person - Nominated Authority
label | 315ff527-3c40-52b8-84ea-e07668ed62ae |  | note | Verifying Documents - ConQa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 - Subcontractor ITP (where required)
label | b346fefd-3197-5a15-b26c-a97b51205f5b |  | note | Reference - Subcontractor ITP
label | 2ee65426-7ce7-5160-8388-cbb2da243536 |  | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
label | 66607613-f10a-5938-ab63-a991a0309555 |  | note | • Attach: Approved Subcontractor ITP
label | 49cc36c3-8d83-5b0e-9a87-cb6ded23d1a1 |  | note | Method - Document Review
label | fb069165-6154-54c5-a167-1eeb304fb8ed |  | note | Frequency - Each Lot
label | 52267484-5a92-58d4-ab18-8c2f7ed600db |  | note | Category - HP
label | 965b0c6a-89fc-5977-adf4-30949f6e87a1 |  | note | Responsible person - Nominated Authority
label | 5c551a93-1fab-5d22-92db-42770603e4d5 |  | note | Verifying Documents - ConQa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out - Pits & Pipes
label | f61cd40a-bdbe-5d7c-9e0a-f56fa589abf4 |  | note | Reference - IFC Drawings VR Section 701.10
label | f94fabb0-6d3d-5610-b5ea-650d5251aa7c |  | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | 8e08840d-0a9a-5fdc-b49b-9563dccf3e3e |  | note | • Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | 0656b119-b153-52c2-9b8d-61a0b61b21c4 |  | note | Method - Survey
label | 71bf9684-02f8-5b3c-906c-3d14d4969c08 |  | note | Frequency - Each Lot
label | 00b1750f-2f31-5f0b-9cd0-1164909833a8 |  | note | Category - HP*
label | c750e803-594f-5cf2-9b01-b021666573e8 |  | note | Responsible person - PE
label | 65cec57b-2b6a-50ff-b308-756d9074a31f |  | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
label | 6843d0dc-7083-5f73-8d3e-f151e7e62b26 |  | note | • CHK-002-CIV-Stormwater Drainage Pits Installation
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Pits - Excavation
label | d9fb2314-20f2-5689-a4c9-f6485ecdd73c |  | note | Reference - IFC Drawings VR Section 705.05
label | 94b1f337-96f6-5d84-b99c-5125e02105ea |  | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | 1e5bca5b-d1ef-58d5-84b4-598124beb473 |  | note | Method - Visual inspection, Measure
label | 3c04a529-bbb0-58fb-a985-aaf5fec2ff89 |  | note | Frequency - Each Lot
label | e51d549d-7f68-5070-ab55-b68eddb3fcd8 |  | note | Category - IP
label | 1b0863bb-666d-5f22-bd09-b59a2531d2e0 |  | note | Responsible person - SE
label | 7c74fd68-1741-54fb-b409-c0a0d002ac64 |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.2 - Pits - Placement of Bedding Material
label | 6ee9bf49-2002-5fbe-87d6-dd9c1be7d977 |  | note | Reference - IFC Drawings VR Section 705.05
label | 14f40619-e8e1-5e89-860b-849acbbb6d76 |  | note | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | f855a180-923b-5827-941a-318fa267845e |  | note | • > 80mm for clay foundations
label | f3ad8be9-b490-51b8-ab02-fe849c810de6 |  | note | • > 150mm for rock foundations
label | df8e9e65-6856-51f2-97fb-e1bd94bfbfec |  | note | Method - Visual inspection, Measure
label | 23f885ee-b7bb-5b6f-be95-eedc9aefc8dd |  | note | Frequency - Each Lot
label | 5acd2abe-eb02-5162-b567-da9b3bc095df |  | note | Category - IP
label | cbb1461a-82ed-5e4f-ac19-b4d2171d9da1 |  | note | Responsible person - SE
label | 225a9c35-7a2b-5051-8495-8440a0dba373 |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.3 - Pits - Bedding Testing
label | bfc5e01b-4739-573f-b816-923d7d9aeb3b |  | note | Reference - IFC Drawings VR Section 701.20
label | d8a22b2d-ea11-5923-afad-b51653bec59a |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | ee2993d5-5a3e-5ecd-b8d3-8a392a27b4d7 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 21c866e7-1e40-5d55-b0ac-418f4fc47783 |  | note | Method - Compaction Test
label | 5ae29770-8ab3-518f-90a1-2745cd1dc23e |  | note | Frequency - Each Lot
label | 2fe55d11-4eb2-55af-a716-3fed30f92d9c |  | note | Category - IP
label | c22d38b7-9cff-5778-8d9c-f9cebe99e8c7 |  | note | Responsible person - SE
label | af057cfc-ec6f-53d2-9992-2a1e3b26aca5 |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
label | ecf83090-6dbe-5963-be21-6c51c607d4ab |  | note | Reference - IFC Drawings VR Section 701.10
label | 8625197f-c2cc-5904-a6bd-eaa43e0784e9 |  | note | Acceptance Criteria - Survey pick-up to verify:
label | 6fb5ef44-7053-59d4-9ecc-2f7cac035abd |  | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | 51bd31d4-61e9-5363-88c6-6bf0269d1109 |  | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | 39eed91f-f0e0-5708-b952-b7aa9d0250da |  | note | Method - Visual inspection, Measure
label | e5b0f36e-c299-5ce2-9187-3a099ca506a9 |  | note | Frequency - Each Lot
label | 0b62b24f-4051-5790-b95e-52211e106190 |  | note | Category - IP
label | 90a7743b-91e7-5976-8a7c-274a7f277364 |  | note | Responsible person - SE
label | 18a49315-88f7-5018-9952-16d55710db6a |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
label | 625cb1a6-4ff5-5c28-8363-cdab3903fe7e |  | note | Reference - IFC Drawings
label | 22cac150-d5cf-598c-a60a-eb11f5dbb822 |  | note | • VR Section 705.06
label | c62a181b-8057-5b08-b10f-9556ee4a3daf |  | note | • VR Section 610
label | df9b5087-1613-5833-8e12-418fe2b97e4c |  | note | • VR Section 611
label | 6e62b6fd-90c2-58ec-af9f-3e5e039ddd10 |  | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of VR Section 610 and 611.
label | 964fbd77-6b0e-5eb1-a25c-1bd41114b90d |  | note | • Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | 5829fe93-e143-5228-8eb2-616ecf83a1b6 |  | note | Method - Survey, Measure
label | c1095af3-60bc-5d5e-bbff-8ec9f5f17d81 |  | note | Frequency - Each Lot
label | 6168af60-98df-516b-b9a1-385cf2add5bb |  | note | Category - IP
label | 44ac9791-2ac0-51fa-87f7-a7b73985a09b |  | note | Responsible person - SE
label | df641de4-c3c5-55cf-8037-6b3662e3d1d0 |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.6 - Pits - Jointing & Drainage Connections
label | b1eea6a1-fe41-57f0-b075-0a3d9558e338 |  | note | Reference - VR Section 705.11
label | b3604eae-3d9c-5eac-92ef-7631eb8d14b7 |  | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with VR Section 705.11.
label | 551f82b1-a90b-5f6a-82d1-96b966322d76 |  | note | • Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | 730c888f-c15e-5a0a-b62a-dc346cfc4204 |  | note | • Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | 8d07d1f1-9c6f-5cb1-937a-59d758857bb0 |  | note | • Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | 680a1612-7203-5085-812c-1e00303aa38f |  | note | Method - Visual inspection, Measure
label | 8ef94bed-86c1-52d3-81ad-819cc2edc002 |  | note | Frequency - Each Lot
label | 150117f8-a458-52a3-b075-d73af00352bb |  | note | Category - IP
label | 80584a05-702a-5fc3-acbc-dd68dcb36434 |  | note | Responsible person - SE
label | 07b5b70f-f3cf-51f4-bd7f-0c5092fed2e1 |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.7 - Pits - Shaping of Floor
label | 85d4f19e-1d7d-55f7-981a-ff8ca8a017bd |  | note | Reference - VR Section 705.13
label | d5c3a9ca-72b8-5502-83d9-b2004128de77 |  | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with VR Section 705.13.
label | 8b8277da-e178-54bf-ac2d-8a2e40d3b978 |  | note | Method - Visual inspection, Measure
label | 7e2be60a-2345-5d9d-84d6-1aeeeffa3adb |  | note | Frequency - Each Lot
label | 06ab661a-b9c4-5a41-80df-75fdb304660b |  | note | Category - IP
label | 5ea84f62-e7b3-5336-8927-b219bf0142e3 |  | note | Responsible person - SE
label | 76fb2369-7366-52e3-bcc7-aa0084a26281 |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.8 - Pits - Step Irons
label | d1a86954-7e66-5f0d-827b-f8cbf31ff305 |  | note | Reference - IFC Drawings VR Section 705.12
label | 19350d53-7c1b-58d7-adb4-a3dba078f255 |  | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | 5fc0a94e-1cb8-590f-ba30-b0eb8d4a475a |  | note | • Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | e4a605f5-98b2-511b-9c91-da7a3f1fe11f |  | note | Method - Visual inspection, Measure
label | 8da764ec-56de-5b0d-82b7-8e7625b00919 |  | note | Frequency - Each Lot
label | f1754124-a620-5682-938d-2ae32036a0d7 |  | note | Category - IP
label | 2436f2d5-a965-5ef5-9e16-617e511b1375 |  | note | Responsible person - SE
label | 3019903d-908b-5f0f-913b-22f41f3b80c6 |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.9 - Pits - Fitting of Covers
label | 733ca8bc-6d1c-5085-9c42-627dc07dac56 |  | note | Reference - IFC Drawings VR Section 705.17
label | 2947ffe6-90a4-5789-aaf5-dc38cdb24c49 |  | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | d9457adb-7435-5c3d-ac64-ce3a32ca4376 |  | note | • Height shall be within 10mm of the design level.
label | 6e52d8a2-39ff-5475-88ad-b4c248065b1a |  | note | Method - Visual inspection, Measure
label | e4ff1cf7-6322-5e08-b6f7-cad58be68b02 |  | note | Frequency - Each Lot
label | 1ea4532b-b7e0-53fe-bff8-7a59dc193afe |  | note | Category - IP
label | fc48d455-6845-5616-867c-52e79a321e82 |  | note | Responsible person - SE
label | b95b421d-6206-5218-aa42-782cfd26aa07 |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.10 - Pits - Pit Lids
label | 81a5466b-3566-5a49-8229-3cef73a42a4d |  | note | Reference - IFC Drawings
label | ae3bcbf9-d601-5910-a70c-1ce447ea68e1 |  | note | Acceptance Criteria - All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | acb492cc-5885-5c2f-8ce9-0b86db4a33e5 |  | note | Method - Visual inspection
label | 4d1a2c2e-381c-5cd6-b6a5-4ed42ae0b1ed |  | note | Frequency - Each Lot
label | 031aeff2-57bf-568c-8900-96fd27a47b37 |  | note | Category - IP
label | d994d795-7c96-5026-b86d-a50db01dfbb0 |  | note | Responsible person - SE
label | 7aea9fd3-cecb-5904-bc3c-a388f3397a09 |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
label | d567fcef-f7ba-5f0a-b906-43164ad4ab5b |  | note | Reference - VR Section 705.18
label | c848f6bd-7913-5ea7-a2c9-e9ae5a5df2c3 |  | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | 276cc002-85cf-504d-8a33-f9bb40e52bf9 |  | note | Method - Visual inspection, Measure
label | 34f64ea1-8e1a-53f6-b921-77129dd0e7ef |  | note | Frequency - Each Lot
label | e7e92a5c-aa38-590b-a916-461c8ca74933 |  | note | Category - IP
label | ef0355ae-4569-58a7-be2f-b5bf61da5c43 |  | note | Responsible person - SE
label | c100aa6f-692b-57a9-ac24-7b63bf005d2b |  | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
checkpoint-status |  |  | checkpoint | 5.12 - Pipes - Trench Excavation
label | 4804863b-00ac-57e7-8fe7-43c06ca70dba |  | note | Reference - IFC Drawings VR Section 701.15
label | c106b9d3-6811-56e2-b667-b83e53a4e76c |  | note | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | 174510a6-410f-57c3-94dc-be49136c747c |  | note | • > 300mm, < 600mm for RCP
label | 7b11c222-6cab-5e5a-b2bd-2f2b21c3f444 |  | note | • > 150mm for Flexible Pipe
label | 582487af-ab21-5826-a997-6208bd87ab88 |  | note | • The base of the trench shall be compacted to refusal using mechanical plant.
label | 09c5b94e-e486-5219-82c7-1ad5a247818d |  | note | Method - Visual inspection, Measure
label | 494e8155-22c7-5fcf-b2ee-6cf6a27346f0 |  | note | Frequency - Each Lot
label | 85358741-c236-56ab-a700-0acedd100568 |  | note | Category - IP
label | 56c09457-eb69-5a83-ae30-b0568f3351b2 |  | note | Responsible person - SE
label | db1a6f57-880f-504c-bc4d-d69600bee306 |  | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
checkpoint-status |  |  | checkpoint | 5.13 - Pipes - Bedding Placement
label | fa07745f-f8ba-527d-8ee8-bfe8951a64a0 |  | note | Reference - IFC Drawings VR Section 701.16
label | 91aa7c07-9763-53b9-bb88-5f9489744938 |  | note | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | 9ccbfce7-716f-56cc-aa40-cba4bde32d99 |  | note | • > 100mm where D<1500mm
label | 53745984-9d27-5cd1-81e1-b2e001575d45 |  | note | • > 200mmwhwere D≥1500mm
label | f22e8efe-0809-5916-a946-25383b1ca764 |  | note | • Bedding material shall be placed and compacted in layers <150mm loose thickness
label | 263686cf-ac22-55f9-90e7-c140dffb31d5 |  | note | Method - Visual inspection, Measure
label | 6a7959fa-a770-5147-8255-85d158960619 |  | note | Frequency - Each Lot
label | 0263112b-b064-5407-8320-6abab1af6a18 |  | note | Category - IP
label | e198b368-348b-5ba1-a798-881e1c5f4a05 |  | note | Responsible person - SE
label | 6899f1dc-6a80-5237-86fa-9ed6354756be |  | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
checkpoint-status |  |  | checkpoint | 5.14 - Pipes - Bedding Testting
label | a05f90d3-b49b-57cd-93f5-5be51533c198 |  | note | Reference - IFC Drawings VR Section 701.20
label | ed695119-c1d8-5595-bcc5-59c4358cc6f5 |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | 7c25a1f6-461e-511d-9da5-8a37ac489d28 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | e16b9cb1-c649-57e3-8b4d-50e07b63d7ea |  | note | Method - Compaction Test
label | 7b5bcb7e-2b1e-550b-be0f-c79ff3a9cd04 |  | note | Frequency - Each Lot
label | cafb0a46-55e9-5e4e-8229-da6923a9bad7 |  | note | Category - IP
label | 164dc4e2-9478-5cb0-9005-29cebc2394f6 |  | note | Responsible person - SE
label | 917dba58-312b-5634-9bcc-93e34e1bc049 |  | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
checkpoint-status |  |  | checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
label | 1d1c089b-4ba4-5fe1-a637-32044ce0b1a6 |  | note | Reference - IFC Drawings VR Section 701.17 VR Section 701.20
label | 31f8ae21-a529-5dd6-ba06-b9d736bd4b88 |  | note | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
label | ff7981d8-ee51-588d-8565-751f7ba664d0 |  | note | • Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | 12673478-c059-5ef4-88c5-94a894be392a |  | note | • Gaps between spigot and socket are in accordance with the manufacturers specifications
label | 6dab23a2-8e4f-5ad3-b7d1-e52c4c3fc50d |  | note | • The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | ee342e3e-6de3-5105-b0af-bbd69d364f2b |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 3bf1b8e9-05fc-531c-aec3-73dd83970287 |  | note | • The spacing for multiple row culverts shall be as shown in Table 701.171
label | 71643c3e-0dbb-57ba-bd53-b1bc4e921421 |  | note | Method - Visual inspection, Measure
label | 3206e281-963a-5e3f-8bd0-3e157c8043fb |  | note | Frequency - Each Lot
label | c3e79654-ff32-5a5a-8353-503957b9f146 |  | note | Category - IP
label | 68ac4b92-8add-5e24-b3d6-c32e53fd7478 |  | note | Responsible person - SE
label | a5a1d846-712b-574f-bc3a-d4c3e4558102 |  | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
checkpoint-status |  |  | checkpoint | 5.16 - Pipes - Lifting Holes
label | c54f8b3f-99e5-5874-865f-bb3d4e73567d |  | note | Reference - VR Section 701.18
label | df84039c-4096-5862-8eaa-0d898dd2f714 |  | note | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 20f800dc-db11-5bea-80b5-2d925c2c5c4d |  | note | Method - Visual inspection
label | dcc71987-a14e-5456-8404-5a8199902279 |  | note | Frequency - Each Lot
label | e9013fe5-ba89-5076-84ab-0bacff747269 |  | note | Category - IP
label | 5b739b73-904a-594b-bce3-6737e4a40cfa |  | note | Responsible person - SE
label | 6a71fca6-0521-5693-a488-ff7dfa800ea3 |  | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
checkpoint-status |  |  | checkpoint | 5.17 - Pipes - As-built survey pick-up
label | 10e0de15-3a18-5281-a611-ab805252c237 |  | note | Reference - IFC Drawings VR Section 710.10
label | a00cc557-b861-5815-a1c2-c90bbbc61e14 |  | note | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
label | 730ffbbe-c389-5db9-a1ac-d7b3b45c2b73 |  | note | – Offset pits to kerb +/- 20mm
label | 95c9849e-92ff-58f9-b659-ecc4043c42d9 |  | note | – Plan location pits not adjacent to kerb +/- 100mm
label | 2f0911c2-f5ef-5891-afd9-d72c3c78806d |  | note | – Invert level of pipes at pits +/- 50mm
label | 1e9c5060-5c7c-53cf-bcde-7018ac1f2ea1 |  | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | 607b9978-7228-5316-8b65-9eecd062e064 |  | note | Method - Survey
label | f55aff1c-d78d-59a3-aa22-6d2544082ba9 |  | note | Frequency - Each Lot
label | 61381203-699e-53e0-9d0a-81a735eb6748 |  | note | Category - IP
label | c423da6f-efe4-5b05-a37b-4ef0c9bf366c |  | note | Responsible person - SE
label | d391a1da-97af-545d-9726-7cae58da8620 |  | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
checkpoint-status |  |  | checkpoint | 5.18 - Pipes - Backfill Placement
label | f2067180-da17-5ead-bb56-1494a82b9f0c |  | note | Reference - IFC Drawings VR Section 701.16
label | 4d2ecb88-a5ce-5ef9-9e23-6030203e3b13 |  | note | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | 9de304b4-89ba-5068-bc33-c9d9427de064 |  | note | • Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
label | 16468e4a-3bb6-5517-84e7-97de819742d2 |  | note | Method - Visual inspection, Measure
label | 97d3b62c-9d9d-5118-92c2-f9e3b1f1a4b6 |  | note | Frequency - Each Lot
label | 9023400d-f99e-5b02-bf62-fd524ac717c7 |  | note | Category - IP
label | e1448e5c-c9b7-5974-8f5a-05da8666ec0b |  | note | Responsible person - SE
label | 2fcc708b-5b9d-573f-8cfd-6cc125ce08d7 |  | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
checkpoint-status |  |  | checkpoint | 5.19 - Pipes - Backfill Testing
label | 0a8eb066-6033-5199-a3d1-48e71dc22fcd |  | note | Reference - IFC Drawings VR Section 701.20, VR Section 701.29
label | 589501c9-9e60-52a7-a70a-57a671e3c82b |  | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | 8181a654-cb8c-544f-aabe-c6bab7cb7f34 |  | note | • Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 9fec84df-9591-5e81-b0d4-407c0138187f |  | note | Method - Visual inspection
label | e2b8ba20-d6c0-54e7-ba33-cc947160b366 |  | note | Frequency - Each Lot
label | 6c424115-fb61-52af-ad04-40f81538f51b |  | note | Category - HP*
label | 86765749-4929-5286-bc9d-bc4a23a21e00 |  | note | Responsible person - PE
label | d96d94c1-4353-54cf-97e1-c31337ea5240 |  | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Flushing & CCTV
label | 248d4bd0-9dd6-5f8f-816e-9c32f9f6460f |  | note | Reference - VR Section 701.28, VR Section 701.30
label | 49e60912-8e59-5bc6-a131-14272eb57f54 |  | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | c0469bd1-d49a-58f8-b28a-71175062e784 |  | note | • All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | e55b88a5-9ffc-5b31-94c4-dfe2b6b6ea76 |  | note | • Attach: Flushing Record, CCTV Reports
label | bff42331-e081-5415-aeae-01f288e879dc |  | note | Method - Record Review
label | 0d110ece-336f-514d-991c-9b78aa023465 |  | note | Frequency - Each lot
label | 5dfbcd92-4a34-52a6-b1af-9b11d1139e0d |  | note | Category - HP
label | 354020e4-5b2d-57f4-b46f-f99c0938b03e |  | note | Responsible person - Nominated Authority
label | 3e4d23c7-9fa6-56f9-b632-5d16f0e6a2c0 |  | note | Verifying Documents - ConQA HP Release
label | f9db3d03-989d-56b2-9d6b-677fc6220e65 |  | note | • Flushing Record
label | 50ba27d4-5124-5812-a2ce-0265b1e0761b |  | note | • CCTV Reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - As Built Survey
label | 0e225f8a-4ef6-5b3c-a74c-322d40820977 |  | note | Reference - VR Section 701.10
label | fc0e9cf3-266d-50a0-ade0-c95563df34d6 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in VR Section 701.10
label | 209f19c0-ee24-5859-b80b-adbfee796373 |  | note | • Attach: As-Built Survey Conformance
label | 75f73bb5-0e58-5446-825f-a2946e1ca5d6 |  | note | Method - Document Review
label | c77a35a2-8493-562d-a960-8503194ba1d3 |  | note | Frequency - Each lot
label | f18135c7-91f6-5523-ab87-fd3c7651319f |  | note | Category - IP
label | 618a92bb-ee18-5112-80cc-482a4304bdd8 |  | note | Responsible person - SE
label | edcbd096-f65c-5cea-baea-05994866f11a |  | note | Verifying Documents - ConQA HP Release
label | c9e8315b-2e96-548e-b8f9-3a276174b582 |  | note | • As Built Survey Report
checkpoint-status |  |  | checkpoint | 6.3 - Repairs to Damaged Pipes
label | 7b9a097b-d2e6-5651-a8a6-4825f629a84e |  | note | Reference - VR Section 701.31
label | 52e7a1d5-3c8c-53f2-81a1-250a718d99fe |  | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | 1cbe2fd4-c1a9-5812-8219-f16d3eabe1e6 |  | note | • cracks wider than 0.5 mm
label | 4a6567c7-4e4c-58e5-8282-55587e45b3ab |  | note | • spalling of concrete
label | 568d0f15-c5ca-5678-be0c-92009775c7e1 |  | note | • exposed reinforcement
label | 87e60f9d-55e5-54d0-b75a-76bd2c77c106 |  | note | • joints that are not fully engaged.
label | 0b89da14-d72b-576d-b8f5-aee4ea5b8e1e |  | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
label | 5cc0d524-e108-504c-a67f-6a833083e071 |  | note | • longitudinal cracks greater than 2 mm
label | 98f3b334-54d3-5097-aa32-ba32b792dd22 |  | note | • circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked VR Sections exceeding 3 mm
label | c7fb7299-da9f-5b61-8154-de7dcb582243 |  | note | • circumferential cracks around part of the circumference with width greater than 4 mm
label | 526daa26-1851-5cee-acb1-bcd51b90a2ee |  | note | • penetrations with area greater than 400 mm2
label | a51b71df-0404-5d0d-ba5f-269b09982004 |  | note | • pipe joints that are separated.
label | d6bdc9be-ac4c-5ada-aa23-acc008232089 |  | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | 7c53dd06-e94e-5a07-b15a-f343009ef3aa |  | note | • hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | 858f1709-aaf9-540a-9bd9-24ecd4654e7d |  | note | • fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | 18e58c5a-ce4f-51e8-b3c6-48200f08a905 |  | note | • spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of VR Section 689.
label | 55251157-71eb-5585-8557-0caba6752234 |  | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | 0b99f227-4315-52df-97be-80ff87486999 |  | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | 5db42065-5a1d-5d9f-b0b2-76e6375714cf |  | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | 5f1da88a-6a83-51b0-b80d-bdecbd9663ae |  | note | Method - Document Review for Repair Procedure
label | 687a776a-b8a3-5e91-a7c0-561a16fdf7f1 |  | note | • CCTV Report Review
label | dff0e0f9-2755-57a9-ac35-8d5092c177f9 |  | note | • Visual Inspection
label | a662cd0e-d0cb-58a0-9413-cdc0ea99a8c4 |  | note | Frequency - Each lot
label | d24c08d0-3c27-5ad5-8da8-252743eb3a84 |  | note | Category - HP
label | fdd8f4a7-a546-5bbd-b9df-e5d5eea679dd |  | note | Responsible person - Nominated Authority
label | 61b5d7bc-7ef6-5967-a6e8-59c9d20ab2a2 |  | note | Verifying Documents - ConQA HP Release
label | 31c199fa-08ea-511e-9328-be3608cd1932 |  | note | • Approved Repair Procedure
label | fadb8d15-7fe8-5467-8bc8-a33dfe72ed57 |  | note | • Post Repair CCTV Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | dc063b04-b3e9-5a28-9640-bec24a7e6529 |  | note | Reference - MRPA Quality Management Plan
label | 9396f3af-5ce2-56e8-9c27-ee6bc329da33 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | 08648456-0933-5f10-9b27-2566ca57db7e |  | note | Method - Document Review
label | bc90dfc8-0c0e-5b81-8564-55f5cdbe4206 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 0728496b-4af2-545f-bb6b-f7aa63ab06d1 |  | note | Category - HP*
label | 8c75e4e4-0eaa-510c-9054-a1148d4c8ff7 |  | note | Responsible person - PE
label | 65c06473-3595-583a-b041-78df49fe645f |  | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
label | 0773d1c4-5b33-5bb5-90cf-370e4375ed58 |  | note | • CHK-002-CIV-Stormwater Drainage Pits Installation
checkpoint-status |  |  | checkpoint | Final Inspection
label | 40b5a903-4867-59a3-9557-7a032c934f8d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | dcaa0d72-6d0c-542e-9f51-c05689dcc9ec |  | textbox | Name:
text | 7a468cba-5efe-5f9f-84bf-3a7a4330d0bc |  | textbox | Position:
text | 142ff31b-27f7-50c7-abd2-f6dcaf34b1fa |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-023-CIV-BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS | itp |  |  |  | Yes | ITP-023-CIV-BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS | 5135b347-e346-4d44-9786-99f7d9d757f4
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 608bc9b8-4d24-5d38-8891-0f38e64678cd |  | note | Document Title: ITP-CIV-BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS
label | ca96d36b-f70b-5d75-9dfc-0c053d3f6941 |  | note | ITP Description: BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS
label | d5d90515-c32b-5b54-9eac-ae6999e7faff |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 1d058632-9d65-5d46-a8c0-ed7806381eb3 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 630b59b7-9ecc-5f2a-9596-bfe06562b01d |  | note | Revision Number: 0
label | 16c94da3-ada3-5aa7-abac-e2ce93bc7022 |  | note | Revision Date: 28/02/2023
label | ada22881-16bb-5602-a5e6-d113b0220b9d |  | note | ITP created by: Jason Lee
label | c3c6a086-f2c2-54d0-bbe1-2d6db8bbe43d |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | f1eefa63-acc0-50ff-865e-5c16f1e0f582 |  | note | Reference - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 612f1174-30b4-5612-aeb7-d81e60576044 |  | note | Reference - VicRoads Section 173
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 524ad304-c04b-52be-a39a-14b9a87c27a5 |  | note | Reference - VicRoads Section 204
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 0af22688-0632-5ee9-8f07-ef2266c62230 |  | note | Reference - VicRoads Section 176
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance
label | 662aa7f2-7db1-5c30-892d-96a85fb0034f |  | note | Reference - Section 204.04 (b) Table 204.041
label | cb99b706-879c-5c38-92ed-049b18b487af |  | note | ○ IFC Drawings (MRP-089-C-ACD-DRG-30-BFD-CBR-2848)
label | 26292d2e-7cbe-5478-a8eb-9c4094f79088 |  | note | Acceptance Criteria - REPLACEMENT MATERIAL (Type A) TO MEET THE REQUIREMENTS IN TABLE Note 1 of IFC Drawing MRP-089-C-ACD-DRG-30-BFD-CBR-2848, AND OTHERWISE CONFORMING TO TYPE A FILL REQUIREMENTS IN ACCORDANCE WITH VICROADS STANDARD SPECIFICATION SECTION 204 and Table 204.041
label | 77c9bd14-7c78-51fa-9999-3b3c0af52742 |  | note | ○ Table Note 1:
label | 27763cf5-0239-54d4-82e2-893a6461fe7b |  | note | • Assigned CBR ≥ 8%
label | 0833a489-aaa4-51ee-9719-7422165a6f2e |  | note | • Swell ≤ 1%
label | 206a15ec-5238-5e3e-b046-9dc59d60c892 |  | note | ○ Grading:
label | 40c3a798-a840-5651-bfcc-79340b36d7bd |  | note | • 75.0mm 100%
label | c7a19fc2-a40f-5f96-bbed-5ff9987ba560 |  | note | • 37.5mm 50-100%
label | b124536f-61a2-5f88-bde7-b29121257bd0 |  | note | • 4.75mm 25-65%
label | 81338221-8a3e-50be-ac7a-f9513d04b1c7 |  | note | • 0.425mm 10-25%
label | 9f51db48-6030-5079-99d6-981b3d45d887 |  | note | • 0.075mm <20%
label | 2f6a3436-f7b3-5f46-a98b-62c2bea26721 |  | note | ○ Reference: Material approval in Teambinder
label | 79dc5baf-6f17-5cbb-9b0c-4c00e4d8589e |  | note | Method - Document Review
label | a5159c8f-a6e0-5748-ac21-e1d17b5ee363 |  | note | Frequency - Once, for each material type
label | 5a8fbc55-df51-5374-9124-06cfd6f2060e |  | note | Category - HP
label | a867cd67-abc0-542b-9c15-21eee7eddc1a |  | note | Responsibility - Nominated Authority
label | f569e136-de27-580c-b2d5-47d59bf1ccee |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Pre-Commencement of Fill Works
label | 20672cf2-b148-554d-9e41-b9d550ebfcd4 |  | note | Reference - Section 204.10 (b)
label | dfa63c4f-ec8a-50a4-b62f-2c3364993950 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | b869729f-5b23-57ca-a047-140552a47fbb |  | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | dec48db6-93a2-5fc1-bf08-c9f6997f9dae |  | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
label | 78bd0182-29f5-5de2-a93a-fa176e139873 |  | note | ○ Reference: Subgrade Preparation Lot Number:
label | dc342577-ef9e-5a77-8724-2aed4bb852f6 |  | note | Method - Visual Inspection
label | a27a788f-bca9-5b39-bcbb-1cdfd15fb96c |  | note | Frequency - Prior to commencement of fill works
label | a293dc7a-0b23-517c-ac83-a1436db4899f |  | note | Category - HP
label | 84d6b0c6-4420-51f3-9862-e3b5207c93d8 |  | note | Responsibility - Nominated Authority
label | e26964b3-5403-5470-88cf-092561b90469 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out
label | aadb9fc0-f978-5096-b1a4-0975bed76e28 |  | note | Reference - IFC Drawings
label | 5518dc15-e984-56ff-8278-1a49be38e302 |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | 2670b42c-d8d1-568d-afb2-69fb0d3ed441 |  | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | 83d41b36-e4cf-55cf-bbde-d22f0155c1f7 |  | note | Method - Visual Inspection
label | 414b1747-20d9-5ae3-9d09-53d8015196a3 |  | note | Frequency - Each lot prior to commencement
label | bd350683-72de-59c0-bab1-afcba2bb3205 |  | note | Category - HP*
label | aa3b30c8-db19-517d-9fc2-cefa69f9569e |  | note | Responsibility - PE
label | 9fe2964f-8c4a-54b5-97d1-b40b4a07d019 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 4.2 - Flora and Fauna
label | a8cbc41c-34bc-5d4b-913c-5874be114e1b |  | note | Reference - Section 176.I1 IFC Drawings
label | e6236db1-71e8-58a1-91fb-56df9e82eb8b |  | note | Acceptance Criteria - Prior to removing any vegetation, an on site inspection with the Superintendent and other relevant authorities to confirm, identify and mark trees, vegetation to be removed. Any removal shall be consistent with the IFC drawings and any relevant permits.
label | 37ae1caf-20a7-5d59-8c20-e87747467047 |  | note | Method - Visual Inspection
label | 3aa48337-2aa5-5050-b5c0-fa98dcd83301 |  | note | Frequency - Each lot prior to commencement
label | 0364bfd1-ffb5-5acc-b75a-d6336a4406be |  | note | Category - HP*
label | e2945eda-97b0-553e-a092-504d712fdbc6 |  | note | Responsibility - PE
label | 6ae818f6-c701-5f88-a3a5-954277965355 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 5. Type A Fill Activities
checkpoint-status |  |  | checkpoint | 5.1 - Placing of Fill
label | c4a41537-a4d4-56d2-bc76-09bc427f8526 |  | note | Reference - Section 204.10 (d)
label | 45f3d688-a979-5346-a288-fb0e37531436 |  | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | 72ea836b-7949-52f2-98ac-7ae92a6b3c92 |  | note | Method - Visual Inspection
label | e5bcb441-730f-544e-ba12-55bec2a5c4d2 |  | note | Frequency - Each Lot
label | 1dc3e577-b107-53a5-b80e-20b2f5a3c1d0 |  | note | Category - WP
label | e3cd2c60-f327-51b0-a657-92d2f89d585d |  | note | Responsibility - SE/Site Supervisor
label | f00c1138-0099-5cef-abb2-672acd8b7ab0 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.2 - Fill at Structures
label | 7f451446-f853-5a70-9fe8-417ac45973cc |  | note | Reference - Section 204.11 (b)
label | 7361b002-7efc-5143-a005-b7df9573fab6 |  | note | Acceptance Criteria - No Fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent
label | ce6570a7-085f-54c8-a1d9-24a5f3bb2558 |  | note | ○ In addition to the placement of Type A material at bridge abutments as structural material, embankment material or backfilling within 3 metres of retaining walls, wing walls, all crown units, and culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
label | 9e164658-5500-5c01-ab2c-14fa5c228ed0 |  | note | Method - Site Inspection
label | 1a9b36fe-b4b7-5a25-a95a-9ca926688bcc |  | note | Frequency - Each Lot
label | 875cf3bc-4045-5cb3-bf6a-1bf63d4d044e |  | note | Category - HP*
label | bfe5a610-ff57-5c15-84c9-537560c11aa7 |  | note | Responsibility - SE/Site Supervisor
label | 16f6e1c4-3e7e-5bd1-b9c6-5e67268b223b |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.3 - Test Roll
label | 620bd7a1-e9bb-5e3a-8c73-c17586ef12df |  | note | Reference - Section 173.03, Section 204.12
label | 2004b4de-5424-57c5-b0e9-12cb750bdba2 |  | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | 9bd95ebb-cf3e-5fa1-a3f4-fb95bc37d23f |  | note | ○ Superintendent to be present during all test rolling
label | 6538ee20-03f9-52b3-81e2-eb7ccbb92091 |  | note | ○ Attach: Test/Proof Roll Checklist
label | 53ea0f67-0b8a-58f7-abb9-3823e4677085 |  | note | Method - Visual Inspection
label | 52ab74ff-f352-5348-844e-c4f07ec22c19 |  | note | Frequency - Each Lot/Layer
label | be77fb0f-18dd-56d0-b114-3b9671f717c4 |  | note | Category - HP
label | 7666143b-ae7d-5d54-a9a6-7f5eb6f48052 |  | note | Responsibility - SE/Nominated Authority
label | ff195926-3b1e-5ba6-8357-2464e52c23b6 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Compaction Testing
label | faeb565e-f6ae-5af8-a557-e441ccc4deb2 |  | note | Reference - Table 204.131
label | 25e4b16b-0a6a-5f78-b75d-b21c319d33ba |  | note | ○ Section 204.14 (c)
label | 9cdfec8c-ca86-5e76-837f-59e15ffb51c1 |  | note | ○ Table 204.142
label | e152780f-3fc2-5164-a8b2-6002fb7c3d4a |  | note | Acceptance Criteria - Testing as per 204.13. Ensure testing is tracked and reports available.
label | ad898289-eb07-5c69-8a7d-4319064a2cfe |  | note | ○ Standard Compactive Effort
label | 44d13e18-b539-5208-a1d4-3901a44a773c |  | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
label | f4b99e6f-6c17-518a-91a5-9d6475318bdf |  | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | fc734cb6-0011-51c3-b471-57850b9310ff |  | note | ○ Compaction and Moisture content
label | 875662f0-242f-595c-9163-8d48162061c3 |  | note | • Scale A: Characteristic Density Ratio 99%.
label | 2391f43f-c06c-5893-a738-7410071492f4 |  | note | • Scale B: Characteristic Density Ratio 98%.
label | f820ce71-ad7b-54e1-8794-bee85e69e046 |  | note | • Scale C: Mean Value of Density Ratio: 100%
label | fa31c371-2b6d-554a-a82e-f78d9f28d22d |  | note | ○ Lot size - the leser of one day's production or 4000sqm
label | 792aba6b-4829-53f3-94b4-1e8a1d0674c0 |  | note | ○ ATTACH: COMPACTION TEST RESULTS
label | d2fb14fd-b45c-50d0-80a2-9150638b4530 |  | note | Method - Review Document
label | d6d94bd4-83b0-5d86-b81a-5cecb1615005 |  | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work, subject to Superintendent satisfaction
label | 9c2a2d56-1b91-5db3-9466-163ade3570b9 |  | note | Category - HP*
label | fba1206e-653e-5566-956f-cc16a83c2433 |  | note | Responsibility - SE/Site Supervisor
label | e009323b-d14b-5a75-91d8-e0b86c0650df |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.5 - Preparation of final surface
label | 251716ad-556a-5604-80a3-41477a4e9e79 |  | note | Reference - Section 204.15
label | 1fd21efb-aeb7-5911-9327-9517d7058eb8 |  | note | ○ Section 204.03 (g)
label | f0f0eb05-e18a-56a5-a959-a7e6eeb83058 |  | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
label | 3403c884-f1ad-55ae-b0ee-96a6c7f320ca |  | note | Method - Measure
label | 1c1623ec-5542-5be9-8b8e-3b2b64ff7d5a |  | note | Frequency - Top layer
label | eea9d068-5397-55a8-b48a-5ef964dfe62b |  | note | Category - IP
label | 738ed636-a84e-545b-9ef2-8317aeb69139 |  | note | Responsibility - SE/Site Supervisor
label | 40827042-8ed6-59dc-bd94-7e8e0e7e5833 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.6 - Post Compaction Material Property Testing
label | 35d2043e-68f2-5d1f-9b80-8d3d76031471 |  | note | Reference - Table 204,041
label | 07dfe39a-22e7-50cf-b5ea-2437feaea6c8 |  | note | ○ Table 204.141
label | ba5e4bc7-792b-55ca-9c95-e3fb734af997 |  | note | ○ Section 204.14 (a) or b)
label | 900215c1-b1db-5386-9dde-75b281d00add |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | 59e29ec4-3f6e-56e1-92e6-accf71e35fed |  | note | • CBR ≥ 8% and Swell ≤ 1%
label | 7e913156-e812-5f6a-a648-aa3a0b636ee5 |  | note | • Max Permeability = N/A
label | cc1fb4d7-aa21-581a-904c-8ccd15458439 |  | note | • Grading: 75.0mm 100%
label | 7976b4cb-f2d8-502a-9e16-937c44e234e4 |  | note | • 4.75mm 25-65%
label | cdef815b-ea7a-5d8b-ae1b-d261b43537b6 |  | note | • 0.075mm <20%
label | 3de0bba3-1ea4-54c6-9e05-696be575488b |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | f76847da-0b81-57d2-bd8e-49d2e4491dd9 |  | note | ○ Scale A:
label | 1a13a0f1-f904-5a85-8a65-a0a2a038ad9b |  | note | ○ CBR & Swell
label | 3c21d6ca-bf9e-5d90-a121-e9ca10878a3c |  | note | • Initial - 1 Lot Test to determine Assigned CBR and swell
label | cd2e2fe7-7ccd-5e60-9d0c-00cc8cf66c08 |  | note | • Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | 481135cc-60dd-5872-9e01-f954e32d6f56 |  | note | ○ Max Permeability
label | 1f09b526-4420-5dec-80aa-3f78af5e72e4 |  | note | • Initial - 1 test per 2 lots
label | fd8d4ee3-01f7-50b8-ac65-8ad0c068d91b |  | note | • Reduced - 1 test per 4 lots
label | 3ac60a97-4d57-5e1a-a8d7-6de229565c19 |  | note | ○ Grading:
label | c9d24a67-22af-5689-8e82-d974d897248a |  | note | • Initial - 1 test for each lot tested for compaction
label | 84060d02-40e7-51ee-94d4-1f437af69935 |  | note | • Reduced - 1 test for every second lot tested for compaction
label | 34965bc1-9a79-5e6c-bf2b-fa9dc07b8646 |  | note | • Max. PI x%Passing 0.425mm & PI
label | 08d235df-ca38-509f-a09b-166eb1562d48 |  | note | • Initial - 1 test per 2 lots
label | 88914396-0a83-5f35-95b1-3966815ac428 |  | note | • Reduced - 1 test per 4 lots
label | de950fa9-b5cb-5c76-b503-e95af9d5b5a1 |  | note | ○ Scale B:
label | 11e71d21-719e-508a-b779-156f8a9188e1 |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 4122729a-c9c3-5d67-859d-bc5cdca6175b |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 5d99cb0a-b9f4-50ae-91de-69075112b4ea |  | note | ○ Attach: Post compaction test results:
label | da2c7bb3-7cc8-50fa-992e-6707c51c2dec |  | note | Method - Review Document
label | 61470146-bada-577d-9046-65b6a00aa958 |  | note | Frequency - Refer to Section 204
label | f0ab3b5e-405a-5881-adc7-418257da8073 |  | note | Category - IP
label | 3ef2fea3-2692-5e20-b1df-addb2a5ff1c5 |  | note | Responsibility - SE/Site Supervisor
label | 15009d7d-cb2a-586c-a6e4-14d883edf419 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Survey Conformance - Asbuilt
label | e082acaa-6cd9-5345-a688-6de9434d74c6 |  | note | Reference - VicRoads Section 204.03 (f), (g) and (h)
label | 30b209ef-9006-5dc1-aa09-7e71570bcc8a |  | note | ○ Table 204.031
label | cd9819cc-87f4-5388-931d-2823de73c69f |  | note | ○ Section 173.05
label | eaddbce7-087a-55f7-811c-95312be9e158 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 442b513f-9ed4-52ad-b5d5-c5a0c3b4aa59 |  | note | ○ Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173. The number of measurements taken within each lot shall not be less than the number specified in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
label | b00063e8-451a-5905-9e77-c542244140d1 |  | note | ○ Level tolerances Scale A:
label | 0ab770e6-5875-5f7c-a230-bfc3830076fb |  | note | • Range x = +5, -15mm
label | 95db91dd-c242-59a4-ad07-29cd781c0265 |  | note | • Max S = 12 mm
label | 239d3a92-883a-5fff-9bbe-5f3233620493 |  | note | • 80 measurements per lot
label | fab6e7fd-b117-5a68-9c31-883c29054caf |  | note | ○ Level tolerances Scale B:
label | 5e4e9774-2bb7-5f4a-93d9-9164ee44059b |  | note | • Range x = +5, -25mm
label | 05802788-4ac1-5687-86a8-8a268b0b205f |  | note | • Max S = 15 mm
label | 9a7630e3-2be6-5c2e-a43e-549a3c49f2cd |  | note | • 40 measurements per lot
label | 9a23cfa8-58c8-57f1-8d6c-4e1aab48f6b0 |  | note | ○ Level tolerances Scale C:
label | bd4da008-c09a-58aa-ba96-74c1795c1445 |  | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 7915a4a1-9956-560f-b72e-b76ae43bdbb3 |  | note | ○ Attach: As-built conformance report/data
label | 6024c497-8ee1-550c-9a18-824f7b1af4a1 |  | note | Method - Document Review
label | 0f19a731-9c97-5d5d-b2c4-5722d2bf2d2c |  | note | Frequency - Top of Type A
label | b8b8e46d-4941-5b4e-9a34-3ca779fa529e |  | note | Category - HP*
label | c4e1f084-99be-5d52-968f-fde6c98b4cd6 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 689c4a8f-2b51-5c9c-889e-cc11a2861cdd |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | fe93b47b-7914-53da-8b48-f6a3d7b2761b |  | note | Reference - MRPA Quality Management Plan
label | 8dabd54d-cbb4-5b83-b3f7-ff5aefa39ada |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 12db578d-b9be-5d13-bfa2-6983cea9d369 |  | note | Method - Document Review
label | 5a0776d9-7ff8-58de-ada5-b823c8839c33 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 2fefecb6-294c-568a-aec2-dc808131db6e |  | note | Category - HP*
label | 8db3229c-58b3-5cf0-b61b-834d9802fb6e |  | note | Responsibility - SE/PE/SPE
label | 8a8a1eea-b439-5085-998e-62e51e7e815c |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | f565b218-b6c5-5f08-881d-d5be63756a37 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 37664645-15e0-5c92-bbc3-ab90d8a0574f |  | textbox | Name:
text | 3bc3f19b-1517-572f-9011-7adfcae3fd19 |  | textbox | Position:
text | c5477d9c-bde2-5e04-97c4-414e76f970e6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-037-RAIL-Brunt & Camms-OHLE Structure Installation | itp |  |  |  | Yes | ITP-037-RAIL-Brunt & Camms-OHLE Structure Installation | 5924be4e-f723-4d5c-b99f-73d0a69f9920
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 6d72ed3f-6d78-5b8d-a5a0-64d3ae2aaaa2 |  | note | Document Title: ITP-037-RAIL-OHLE Structure Installation
label | 59e4878e-a961-5ccc-bf4d-73dccbc16053 |  | note | ITP Description: OHLE Structure Installation
label | abb7d608-347e-568d-b7aa-2d87bbc66e4a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 258625e6-11ec-5610-a204-efcd1f2f80db |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 9154e766-75b6-5c7c-8cd9-9f835e2a3b0c |  | note | Revision Number: 1
label | e7c49f81-0b7b-5dc6-970d-b9ac8428af14 |  | note | Revision Date: 16/05/2023
label | cabb008b-e37c-5696-8912-8240a303a35d |  | note | ITP created by: Nikhil Siram
label | 9517ee58-787c-5976-9a46-7d886a63afa3 |  | note | ITP approved for use by: MRPA Quality Team
checkpoint-status |  |  | checkpoint | 1.1 - Overhead Line Electrification
label | f4fb4320-5d00-52f4-a870-43194e472fe4 |  | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint-status |  |  | checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | c267b0e3-3f3a-5c05-a2bd-9f64e6b6976c |  | note | Reference - VRIOGS 001 AS 4100
checkpoint-status |  |  | checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | 29c058d4-1776-550e-ad3a-9d6d865ce53a |  | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
checkpoint-status |  |  | checkpoint | 1.4 - Fabrication of Steelwork
label | 2f0eeead-3395-533f-841c-d3f06f067d4f |  | note | Reference - VicRoads Section 630 January 2023
checkpoint-status |  |  | checkpoint | 1.5 - Structural Steel Work - Fabrication and Erection
label | a6f9eb5b-b3db-5b7b-9a18-8a64e59c90bf |  | note | Reference - AS 5131:2016
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Structural Steel Components and Fasteners
label | df164392-ce09-5e95-a929-0efa7df8c7a6 |  | note | Reference - IFC Drawings
label | c6d1648b-4187-5fb5-9a83-de9bc00864cf |  | note | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | 34cc1264-a6f9-5ed3-8a2b-3a7210f16442 |  | note | • Typically this consists of but not limited to:
label | 1f95a117-5b39-59e8-9e36-9fd36c3c35bf |  | note | i. Completed fabrication ITP
label | 945a0c42-6763-56d3-bcaa-450ef31544e4 |  | note | ii. Weld Procedure Specifications
label | c825d6e4-a776-583d-89d1-ef4080f720af |  | note | iii. Weld Procedure Qualifications
label | 453e1423-81f8-5b71-a54f-188f54128727 |  | note | iv. Welder Qualifications
label | 1a59b914-1059-5567-98d0-9fc13e00ee19 |  | note | v. Material Certificates
label | 8dd7fcd4-eb1a-5f8d-9502-22a7c50de144 |  | note | vi. Coating certificate(s)
label | b928ca54-1466-5e10-9553-046624c917fb |  | note | vii. Non-destructive Testing (NDT) Reports (if any)
label | d1be8dc9-e075-55fb-a2d3-8843bf721568 |  | note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | bbff11ec-8bcb-53c3-9be1-acb06e9e9304 |  | note | • Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
label | 089341a6-7e48-5916-a38f-44dfee34a0c3 |  | note | • Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
label | e05eea70-0d93-5e96-919c-63901617cdd3 |  | note | • All bolts nuts and washers are hot-dipped galvanized.
label | 8d83087e-b15f-58cd-a571-32c971918049 |  | note | Collate: Structural Steel Quality Assurance Documentation.
label | 013c0453-109f-545d-9ac1-b1b41853bd94 |  | note | Attach: Collated QA documents in ConQA
label | f2c47931-6fe2-5230-8f33-303bba3301d0 |  | note | Method - Document Review
label | 9791c0f6-8a97-5ddb-8219-994c8984b831 |  | note | Frequency - Where applicable/ Each element
label | cfe977da-c8d3-512a-859a-41d5355eb5a4 |  | note | Category - HP
label | dda9e098-76fa-5581-bb9b-9542a7cc0c79 |  | note | Responsible person - PE
label | 989fc628-2412-5a10-88b3-2b34fa6e32d9 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Bolted Connections Using Direct Tension Indicators (DTIs)
label | 52963a3b-5499-5d8e-823c-134f23016277 |  | note | Reference - AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
label | 0cc4aa85-9077-5b24-9600-3bc41398158c |  | note | Acceptance Criteria - Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
label | 43af5010-9b5d-5546-9b44-5951011cb367 |  | note | i. technical data sheet or information on the product
label | 03b83642-131e-5c25-8fde-37e80f3cfaac |  | note | Method - Document Review
label | 947519a7-b478-5a15-9b24-89914d2bec0e |  | note | Frequency - Where applicable, once
label | d2a8e7d2-0ce9-5873-90d4-0e90ff84db43 |  | note | Category - HP
label | 39e213a9-be5b-50c1-aea7-6dea51634da6 |  | note | Responsible person - Nominated Authority
label | 6a2c4d7f-1873-5157-8474-fae0d0b2343d |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Overhead Wiring Small Parts Steel and conductor wires
label | 92f6067f-dba4-59ec-8a1b-e2f2bfbe46db |  | note | Reference - Relevant MTM Standard Drawings
label | 6fbc421c-f570-5377-923b-2d51992ae560 |  | note | Acceptance Criteria - Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
label | e5bbef1d-01f8-5e79-8a11-2b30a1c9af1a |  | note | • Deliveries are to be inspected to match the purchase order
label | 09468182-8b6f-5bef-ae99-658391765fc1 |  | note | Attach: Purchase order/Delivery dockets/Certificate of conformity
label | 3fe302fb-200b-5b03-8196-220e7b645c22 |  | note | Method - Visual inspection and measurement
label | 68e78db9-111d-57ee-afdb-ff1a64702a20 |  | note | Frequency - Upon delivery
label | 6ca8959d-5d0b-5cc9-add4-007e70183bb6 |  | note | Category - IP
label | cc4a804b-5286-51aa-8ffd-58430212e1dd |  | note | Responsible person - PE
label | b129078b-efdb-550b-83f8-26c22d771b00 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 2.4 - Grout
label | 7957dfa1-65af-5562-8bed-69e36e7ccfba |  | note | Reference - IFC Drawings
label | 538f6a6e-206a-51e8-84f5-5869980d1c90 |  | note | Acceptance Criteria - All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
text | 8bdefdc1-ef5f-56e3-bc52-3b46dac67c55 |  | textbox | Enter: Teambinder Material Approval number
label | 6fc8816a-e807-52ec-8434-2e214f212dfc |  | note | Method - Document review
label | 5661ecbb-a853-5d09-8ee2-ee220c02523a |  | note | Frequency - Where applicable
label | 6d85827f-6c60-577c-974f-b99b98bc973f |  | note | Category - HP
label | 89d95a06-69c8-51af-a3a1-101d82558115 |  | note | Responsible person - PE
label | 5f34245f-48cc-5a5e-accf-1fbbd6b6f85d |  | note | Verifying Documents - This ITP / Material Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Installation Methodology & Works Method Statement
label | 171068ba-a4df-5a56-9869-0db14d2c2bc1 |  | note | Reference - AS5131 Clause 11.2.3
label | 0f41121b-531f-596d-9728-d61d547046c0 |  | note | Acceptance Criteria - Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
label | df7bea13-9b96-5bf0-82dd-e6c07b6d0203 |  | note | – Transported to site;
label | ff206edd-2257-5314-a69c-01cf2843a185 |  | note | – Handled on site;
label | 64e5f9c8-aa48-5b83-bc70-33044b389a13 |  | note | – Installation Procedure (subcontracor ITP's);
label | e9b4571c-ba79-534e-86b7-a5d711e80861 |  | note | Submission of Work Package Plan and MRPA approval and acceptance.
text | 1cebfb9e-38a8-5744-90bb-f06245352b5b |  | textbox | Enter: WAP number
label | 6923c8a0-e9c3-58b0-83c6-35f149fe6399 |  | note | Method - Document Review
label | 962b5dfc-5cf6-57f8-b4e0-ea073e74d6be |  | note | Frequency - Prior to Works Start
label | bcd02dec-2ac2-59ef-8b00-b4778fd46716 |  | note | Category - HP
label | 503721d8-4b51-514e-a4c3-a03fb4a484fc |  | note | Responsible person - MRPA/CAT5 Engineer
label | 97763b85-77d0-5541-ab1e-55ae313cdf7e |  | note | Verifying Documents - This ITP Signed Off
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Approval of IFC drawings
label | ce937adb-b587-55d4-82c5-607b201c3cbe |  | note | Reference - Contractor Design Management procedure
label | 920555af-3e5d-5e75-a074-62b6ef43a715 |  | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 70a4ccc3-8f70-5249-816f-c91bf5ea7df7 |  | note | Method - Document/Drawings Review
label | e2446ba0-1fc0-5058-8512-a4d63c846da6 |  | note | Frequency - Prior to Works and at regular intervals.
label | c2a7d4b4-7af3-525b-9786-46049fd3186d |  | note | Category - HP*
label | 0266a824-cd43-55bd-a5da-48568928301c |  | note | Responsible person - MRPA/CAT5 Engineer
label | fdbdb367-020c-5aa5-9e10-ace6145bd88c |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.2 - Cantilever assembled.
label | 86f53223-997b-52e3-b72b-c37b60ce98fc |  | note | Reference - Cantilever assembled as per IFC design.
label | c40c001a-4cd6-503c-8529-487185ca41cb |  | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | 43e36e3e-3276-5d9e-88d5-cd05885e8d06 |  | note | Attach: Signed off Cantilever fabrication Checkshit
label | 163bae1b-5bcd-5ea3-ac83-8592a89159db |  | note | Method - Visual, Document Review
label | 4642be35-681a-5c8c-9739-ed4c23e56525 |  | note | Frequency - Each Task prior to works start.
label | ae0cdaad-e69d-5b6d-94ff-6397a19ba158 |  | note | Category - IP
label | d65eb044-a10e-5075-b907-a7229203959f |  | note | Responsible person - MRPA/CAT5 Engineer
label | 4b1c0d7a-aa0e-5afd-ab9c-0fe3d6e90f37 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Mast istallation
label | aa625822-7699-5987-9c55-d5e0ba29b0e9 |  | note | Reference - IFC Drawings:
label | 2d27763c-a5b2-5441-a0aa-5615d1e709ee |  | note | Acceptance Criteria - Mast installed as per IFC. Mast rake is as specified in the drawings
label | e61034af-13ea-5efe-87d9-733be438919f |  | note | Method - Measure
label | 9541ea85-8426-5f5f-8650-5e7e382c479a |  | note | Frequency - Where applicable
label | e0cd6d96-a66a-5e4a-b7d6-e1c7fa028fd2 |  | note | Category - IP
label | 0787673a-b315-5afd-9233-1f7bc152c541 |  | note | Responsible person - PE
label | a322d063-ad54-5fee-8cfb-193124de5c59 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.2 - Cantilever installed.
label | 675eacb7-dfc2-5bce-b57a-b3f7c96b8f56 |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | 7a850a9c-672b-5a9e-97d8-d8bf202f2059 |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | 7262ac23-beb4-5218-a064-8f9144ee4844 |  | note | Method - Measure, Visual
label | cfa4a9d8-4e98-502d-9c18-4dc8241b1bcb |  | note | Frequency - Each OHLE Structure
label | f8060119-cf00-5903-8f47-59c904bfb3ed |  | note | Category - IP
label | 64dde716-2f5a-594b-8d90-86fea4d0508b |  | note | Responsible person - MRPA/CAT5 Engineer
label | 82d3e066-3d51-59d1-80f3-d2a59dfd8453 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.3 - Bearing type Joints TB Friction type joints TF
label | 08266f98-d97c-5583-a99b-00a0fa5cdf59 |  | note | Reference - IFC Drawings
label | bd864333-0f6f-5768-b6e8-6f3a11589b1f |  | note | Acceptance Criteria - BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
label | bb408d39-17a3-589b-bd7a-08f8e086142f |  | note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
label | c4f21ee7-bcc8-5803-ac31-16a1f33210f7 |  | note | – DTI squirts are to be visible for inspection
label | 674ab1e9-fa91-5b90-a0c7-4b8ef6eb3316 |  | note | Method - Visual
label | f9e90c6b-5182-5469-bb41-d2d8a590b8ca |  | note | Frequency - Where applicable
label | a5cbe38b-fded-52eb-944b-0eb5394fe12e |  | note | Category - IP
label | ea5fc9e6-d5c0-5e9f-9f3e-b4d02df97074 |  | note | Responsible person - PE
label | 5e77b6ed-bf7d-58bf-8e61-bcb961a6d6ee |  | note | Verifying Documents - This ITP Signed Off/Visible marks
checkpoint-status |  |  | checkpoint | 5.4 - Install SPS to correct height / position relative to track
label | 8c54d2c7-6aa7-514b-8485-ea94711db8c9 |  | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | da7b225a-37c5-5d8d-a176-6c58ee8e170a |  | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | 63ae7235-d0aa-5ac4-9446-bbff52779674 |  | note | Method - Measure, Visual
label | 83061b83-0149-589d-86fa-776afa364b99 |  | note | Frequency - Each OHLE Structure
label | 0ce7cbd5-1542-5885-9a7d-ae356578f6d2 |  | note | Category - IP
label | 3023e226-ccf6-52ff-8d56-cb72f4cf09fa |  | note | Responsible person - MRPA/CAT5 Engineer
label | e1c88c2d-9902-502e-93f1-f5a4d371889f |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.5 - Cantilever checked once installed.
label | cf2aa39e-e3ce-5c8b-88da-76cc12c8a3ae |  | note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
label | 5998ba3d-9481-5012-85de-152168705311 |  | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
label | 4b089b71-7891-5f97-a4fe-baf8435d31c3 |  | note | Method - Measure, Visual
label | 06e4fd63-e646-5837-afd6-dd04ee5488c2 |  | note | Frequency - Each OHLE Structure
label | c28bc4e4-4f59-51e1-a416-22921a0ea4b8 |  | note | Category - IP
label | dfadfe65-7855-5d33-8a01-ed0e8aaa45e3 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 646d5145-5742-532f-966c-de0ece4f73b2 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.6 - Base Plate Grout
label | db701ec4-3e19-55c6-847b-bbc27cb9d85e |  | note | Reference - IFC Drawings
label | 8b2d2df2-2d78-597c-81cb-4760a40d972d |  | note | Acceptance Criteria - Grout to be mixed as per manufacturer TDS.
label | 8398b1b5-40cb-5438-bf29-e0d5bac67466 |  | note | • Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
label | 37a1d5bd-ca01-5343-ad86-7ce432a252f7 |  | note | Method - Visual
label | 254b4394-104b-52c0-9735-180d1519cc84 |  | note | Frequency - Where applicable
label | f0d369d4-e850-53a1-9e65-23582cb60068 |  | note | Category - IP
label | 8b162e61-a4a5-5905-be16-dbaa0eb9bc84 |  | note | Responsible person - PE
label | c5b7a329-34f1-5f54-ba80-5dfa98f8cd33 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.7 - Installation of wire supports at the correct height and stagger.
label | 3415b506-0075-527d-ad4e-b58eae2e67f5 |  | note | Reference - Install as per design drawings.
label | 4d14147c-17bb-5c30-86b7-f918c8fef1db |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 79923a8b-7553-5982-899e-a9676fc48113 |  | note | Method - Visual
label | 6917ac62-ed8f-5f7f-94f1-40cdc8c81ae7 |  | note | Frequency - Each OHLE BWA structure
label | bb2d4409-cebc-5571-838d-83baef9ad15e |  | note | Category - IP
label | 45687855-7fdb-5878-b0fe-634de4dba562 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 505e2e25-6118-54d1-9fa3-3549991ae5b8 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.8 - Install to correct tension
label | 678e34a8-b471-5343-b559-c0412014d858 |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | 8d007b74-a143-50a8-85eb-8ad72d905a0c |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 3bee82f4-cab0-509b-964b-b0d03a913063 |  | note | Method - Measure, Visual
label | d39d8272-a5fc-5dc3-90c5-3f9440deff17 |  | note | Frequency - Prior termination
label | 3aeec4fb-fa07-5f69-9553-5b74cf5861a2 |  | note | Category - IP
label | 8b1fc78d-3a30-511f-b9ae-8f8a12c57107 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 3160ff55-a201-51a2-9734-f6f025949028 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Defects/Temporary Works
label | 98726157-e411-5c79-a6d1-580d1ba80c9b |  | note | Reference - IFC wiring layouts, cross sections and design drawings.
label | 1f2d7746-0ce3-5195-80e5-7eb6d7c9590f |  | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
label | 85f4c472-614a-5af7-b974-c337b1f1b0f1 |  | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | 7dd89858-318e-58a4-bed2-118ccc24c7e1 |  | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | e1c32b6d-7820-5439-a2c8-270bc6bd7e43 |  | note | Method - Document Review, Visual
label | 15bd0cf7-dce7-5526-aee8-6db048cca231 |  | note | Frequency - Each OHLE Structure
label | 2002e2a1-8292-5c9b-9197-7de1ad08c035 |  | note | Category - IP
label | a7739776-7f37-5d25-b0cf-0b22d4ea6a1a |  | note | Responsible person - MRPA/CAT5 Engineer
label | 39d754e3-29af-5b2e-b82f-5f84364afa14 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
label | 0cbf5164-d6f6-52f3-91c2-fefe15c89356 |  | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
label | 6c76a7b2-a17f-5b84-93cd-ff46b1e225c8 |  | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
label | 02205503-8a04-5215-8026-debc2173555c |  | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | 0d7bf166-dbf9-5b8d-9f70-bfa5462b8db7 |  | note | Method - Document Review, Visual
label | c786a896-18a5-540b-aa33-b68e777e1ee8 |  | note | Frequency - Each OHLE Structure
label | 78d813d0-d474-56c8-9120-31917c2cf689 |  | note | Category - IP
label | 07b9e0d5-2b0e-5e79-b170-c44416f16319 |  | note | Responsible person - MRPA/CAT5 Engineer
label | f01d40e0-8d53-5a75-94f5-285ea2cd0bcb |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 322bdee2-14d6-595a-9b73-171650de7002 |  | note | Reference - MTM Quality Management Plan
label | 237ac672-3945-548d-8c16-0699f1e6bc91 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | edcbd8e9-5613-52e3-9e6c-6ac20b7841d4 |  | note | Method - Document Review
label | 36dc12e7-e4a7-593b-9fd7-63243004f81b |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | a998f83e-3fc0-5454-a7cb-33e80899e0e6 |  | note | Category - HP
label | 994db6da-e9eb-50cc-aede-d0eaf2175eea |  | note | Responsible person - MRPA/CAT5 Engineer
label | 4243a3df-73a7-596b-b293-ec2b2b9cc738 |  | note | Verifying Documents - This ITP Signed Off
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | afb82533-6ecb-5bfc-b31a-3e89684cf43b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 0f67c1a0-b28b-5083-b647-75d95802f573 |  | textbox | Name:
text | 256973fd-337a-52af-8065-80e68f251fa9 |  | textbox | Position:
text | c7a75a95-8242-5957-83e0-216b787b1111 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-042-CIV-Brunt-Subgrade Prep for Embankment Fill | itp |  |  |  | Yes | ITP-042-CIV-Brunt-Subgrade Prep for Embankment Fill | 645f5382-e631-40dd-a051-649d8117a831
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | cbca5e68-26a0-5bcc-bd3a-9420206c9685 |  | note | Document Title: ITP-042-CIV-Brunt-Subgrade Prep for Embankment Fill
label | fc27eee5-f968-565e-aa6e-c0e2921d6f29 |  | note | ITP Description: Subgrade Prep for Embankment Fill
label | 92aff006-fa3e-595c-8120-b0c1e3a9b99d |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 49505fee-8465-55e6-a816-b6fe02259a2c |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 2932d344-427d-562d-8a78-d6155ee38e0b |  | note | Revision Number: 0
label | be7d4b48-3b2f-51d2-a54e-9eea9f52e31d |  | note | Revision Date: 13/06/2023
label | d747fd8a-3766-59c8-b14e-f238fc209cea |  | note | ITP created by: Jason Lee
label | ab1d22be-9138-5b2b-befc-198d4c6651c4 |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | d7332321-2909-5a96-aee1-3c88ba6ba497 |  | note | Reference - VicRoads Section 204 (Dec 2015)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | ab02c8a2-d7f2-5b7a-9c6a-00035ded8bf0 |  | note | Reference - VicRoads Section 173 (Oct 2008)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 7f03e866-912e-5a63-ab2d-d4d8bca0fee9 |  | note | Reference - IFC Drawings
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Non Dependent
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Non Dependent
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out
label | 36d14348-bb2e-58e1-be6e-c9ba1e3adf26 |  | note | Reference - IFC Drawings
label | 9735eae6-832b-56f4-9e10-9996af05c9de |  | note | Acceptance Criteria - The Area of Excavation has been set out in accordance with the drawings.
label | 73fcc080-7916-52b6-9b42-20be3291d420 |  | note | • Attach: IFC Drawings with lots marked-up (Lot Maps)
label | e38ffbdb-e45e-5ee0-8528-a139326c129e |  | note | Method - Verify
label | 5944d1f7-6321-583b-82d5-092f09c8cc62 |  | note | Frequency - Prior to Commencement of Excavation
label | 2ae712dc-2d7a-5833-986d-15a4921182ba |  | note | Category - IP
label | 9a9d88d7-60f3-53a7-910d-e3b49ce5be91 |  | note | Responsible person - PE/SE/Surveyor
label | 67bd86d6-22f9-5507-b6d2-a3d6af371040 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Excavation to Subgrade
label | 86b41c70-da2a-5f3f-af63-1e163b91cb0c |  | note | Reference - Section 204.06, Section 204.07 (b)
label | eb5655e8-e24b-5e97-a190-31edb3d970f3 |  | note | Acceptance Criteria - In situ material within 400mm of cut floor level to be consistent with IFC Drawings. Assigned CBR not less than Type A material and shall have swell less than 2.5%. If parameters are met, rip and re-compact to a depth of 150mm.
label | 65e66d00-c8a3-5736-b5bc-3fddd331eb9f |  | note | • If the material have an assigned CBR less than Type A material, it shall be removed to a depth of 400 mm below Cut Floor Level and replaced with conforming Type A Material.
label | 1b9cb9e2-fa90-53ea-b1c4-87cb2fbccc74 |  | note | • Attach: Laboratory Test Results
label | bfd2a48f-b0bb-5b5f-b775-e1f4234a1049 |  | note | Method - Verify - Document Review
label | 122d6b03-32e4-575b-a7a3-25b3630b039c |  | note | Frequency - Each Lot
label | dcd20aef-e90a-56c7-aa50-3fdfb762a8ec |  | note | Category - HP
label | 87d097d6-104c-5bee-91ad-d3182bec6a77 |  | note | Responsible person - Nominated Authority
label | 2c78d574-f6e1-5525-b218-817e7ef890d4 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Acceptance of Rock Subgrade (where applicable)
label | 4590097a-357c-5160-b7f6-1ec0b910f486 |  | note | Reference - Section 204.06 (f)
label | 3b358771-7429-5e42-9fd3-0686c7edac51 |  | note | Acceptance Criteria - Material shall be excavated to a depth of not less than 150mm below subgrade level in all areas on which pavement is to be placed and all loose material and soil shall be removed from the rock floor.
label | d60ff72a-3036-5b84-996f-f6c903b9c42e |  | note | • If any depressions lower than 150mm below subgrade is visible, it shall be cleaned of loose material and backfilled with 20mm Class 3, 3% Cement Treated Crushed Rock and compacted.
label | 7049e7f3-446d-5dee-84dc-d9f8471e2db3 |  | note | • A regulating Layer of Class 4, 20mm Crushed Rock shall then be placed above the rock to subgrade level in lieu of specified capping or selected material, in layers not exceeding thickness of 150mm.
label | 414ea3d9-21c3-5103-bf7c-8d66e0d9114d |  | note | • Attach: Delivery Dockets for verifications.
label | ebd39062-1aeb-5fb6-950b-114497db5c7c |  | note | Method - Site Inspection/Document Review
label | 4137f220-31d7-51b6-a345-ca6fc12efc4e |  | note | Frequency - Prior Construction of the regulating layer
label | 80d95dc4-75d4-517c-b409-32384a026edf |  | note | Category - HP
label | 105e8d8c-5b1c-5e9f-ae2f-219ec164b4be |  | note | Responsible person - Nominated Authority
label | 4de7174e-f002-5356-8ab7-ffe24b03631d |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Groundwater (where applicable)
label | 0a09bf71-99d7-5f1f-b10c-2949435edb74 |  | note | Reference - Section 204.06 (h)
label | 5c43b626-37f6-58ed-8edf-7b192e3239fd |  | note | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
label | 65f552d1-c860-5dfc-99b2-9b105514d241 |  | note | • The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | f9ef45a9-d5f9-57a6-a19f-409a1b22e7e6 |  | note | • Attach: TeamBinder Approval Reference No.
label | 6d77f956-4553-514d-865f-278002e61c35 |  | note | Method - Visual Inspection
label | a5698a0e-b54d-5db0-a89c-8ea2d870e6d3 |  | note | Frequency - Each Lot
label | 77946c52-881e-5455-9f78-a037db14732f |  | note | Category - HP
label | bfa4c83b-1e2c-5004-b30f-5a82197448a9 |  | note | Responsible person - Nominated Authority
label | 1237bcfe-76fc-5f37-9e3d-805647c35424 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Geotech Inspection
label | e135646e-4e73-5a3c-a4ff-9957309987f7 |  | note | Reference - IFC Drawings
label | d5cc26a0-ab6a-5b31-b947-656b23342a25 |  | note | Acceptance Criteria - Excavation is required until natural clay is exposed wiIh a minimum shear strength of 75 kPa, to be inspected by CMW prior to fill placement.
label | 63ef6f08-7605-52dc-898b-037069f9b82d |  | note | Method - Visual Inspection
label | dc0d3740-1fc8-50c4-8388-57aa8c343313 |  | note | Frequency - Each lot
label | bb109c6c-bbd4-57a3-b605-aeb5c45ebad6 |  | note | Category - IP
label | 61cee6c1-9412-5ccb-b792-38ac374df94b |  | note | Responsible person - SE/PE/SPE
label | 7c4019c3-f649-5421-bb05-9c4a4a62da99 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.5 - Proof Roll
label | a15a20ad-df6f-5ce8-891d-b9d7e0b50093 |  | note | Reference - Section 173
label | 2b9196e5-95b0-5374-abbe-d40ae5625350 |  | note | Acceptance Criteria - Each Layer shall be proof rolled with a superintendent present. Compliance with the proof rolling requirements shall be when an area withstands proof rolling without visible deformation or springing.
label | 94166d20-8c8d-5a12-a4ad-1fd51aa12b10 |  | note | • The plant for use in proof roll to comply with the following requirements:
label | b4657f61-b6a3-528f-b7e5-c83fef6169d7 |  | note | (i) Static smooth steel wheeled rollers shall have a mass of not less than 12 tonnes and a load intensity under either the front or rear wheels of not less than 6 tonnes per metre width of wheel.
label | b7e27d37-d21c-58ad-b41b-93b53f068f2e |  | note | (ii) Pneumatic tyred plant shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre. The area over which this ground contact pressure shall be applied shall not be less than 0.035 m2 per tyre.
label | 9ec47b98-f4b3-50b4-8aa7-31e1a013c563 |  | note | Method - Visual Inspection, Test Roll as per 173.03
label | 0d0ac7ed-5019-54ec-bf0f-88b420b70173 |  | note | Frequency - Each Lot/Layer
label | 3ed57775-5d33-5a97-9c21-574a4c64c8ea |  | note | Category - HP
label | ca7c941d-4d20-58a7-ade9-5c9319eba8a6 |  | note | Responsible person - Nominated Authority
label | 8f35eb8c-7fba-5827-8b1a-0a1743d6dedc |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Compaction & Moisture Content Testing
label | 6c776a5c-456b-5669-888b-02b130ca21fa |  | note | Reference - Table 204.131, Table 204.142
label | 5c4c2a2d-e759-566b-b005-b9a514d0c4b5 |  | note | Acceptance Criteria - Compaction Requirement to be Scale B: Characteristic Density Ratio 98%. (6 tests per lot)
label | d02fc6ee-2a63-5ba2-a231-9dbadcb188c5 |  | note | Once three consecutive lots of like material have achieved the requirements in the first test, minimum testing frequency can be seek with the Superintendent agreement.
label | 87bdfae0-9997-5666-b1b2-36ca681d65f9 |  | note | • Minimum Testing Frequency: Every second lot
label | f6765e42-f717-58c0-834d-cb77bca8f918 |  | note | ○ Lot size
label | 24ac778d-eb52-5390-98c3-b62068915579 |  | note | • Type A Material - the lesser of one day's production or 5000sqm
label | 2bd24dc1-f5d2-5f16-b97d-9fc5c4808149 |  | note | • Attach: Compaction & Moisture Content Test Results
label | 1b789f6c-6747-5422-99bf-1bd221277c14 |  | note | Method - Review Document
label | 9dc7b191-2858-5f71-a5bf-3a0121c0ade1 |  | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | 3531bfbc-b1d3-5f36-99fb-6498216dcc90 |  | note | Category - IP
label | 2b6eba39-ee80-5cda-94e8-3cc9df044868 |  | note | Responsible person - SE/PE/SPE
label | ff8e4299-3949-5dd4-8697-bf70bab9f4f0 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.7 - Post Compaction Material Property Testing - Type A Replacement Fill (where applicable)
label | b2cc095b-4f88-58b0-b66b-9d2e941102eb |  | note | Reference - Table 204.131 IFC Drawings
label | a53db9bf-6d18-5e71-9f58-3584847231f7 |  | note | Acceptance Criteria - Material Properties:
label | f8a27e38-18e5-5812-a3f8-6043374e93c5 |  | note | • CBR ≥ 8% and Swell ≤ 1.5% (Applicable for Type A Replacement Material)
label | 1154be21-15fe-5f44-8cd5-4b91a57145a5 |  | note | • Max Permeability = 5E-9 m/s
label | f4156624-575c-5036-b157-f868d51bd0b2 |  | note | ○ Grading:
label | 498c7e54-9f94-5784-9a14-0706f865a6cb |  | note | • 75.0mm 100%
label | bc284619-f024-5441-b064-bc37204b9004 |  | note | • 4.75mm 40-80%
label | d77a5646-d763-5662-b913-81080cc44913 |  | note | • 0.075mm 10-40%
label | fb5ba827-48dc-52e1-9c0c-6ff2e90d6133 |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6-25
label | f24ce557-992f-51c4-a844-30e489cd6d5e |  | note | ○ Scale B:
label | d4283035-e5fd-5400-be2f-491459a31e9e |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 88022160-5f18-5b8d-bb58-969b91b5ca59 |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | e47eab14-04b4-5a33-b754-da5cc55d1596 |  | note | • Attach: Post Compaction Material Property Test Results
label | 4aeb74ef-9d0d-5734-a77a-ad40846cd065 |  | note | Method - Review Document
label | 2c2d481e-22d0-5043-b98d-448326fb7d45 |  | note | Frequency - Each Lot/Reduced Testing Frequency Refer to Section 204
label | c79ada57-19bd-5083-8259-3c2d0339c646 |  | note | Category - IP
label | 007c638b-ebf8-5cdb-80de-3ba158139b2e |  | note | Responsible person - SE/PE/SPE
label | 26ddd561-ddf4-503b-8bdd-b94dc84c397b |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.8 - Post Compaction Material Property Testing - Natural Ground (where applicable)
label | a29d00d4-0e08-52ab-a686-e7b4c40dc10e |  | note | Reference - IFC Drawing Table 204.141
label | 3ec83c75-6514-58bf-b094-da8d427394f0 |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | 735c80c7-5e96-5e23-a168-4aeaf29cd77a |  | note | • CBR ≥ 2% (Applicable for Natural Ground)
label | e44c001f-bc37-5be5-a111-99eed0e296b2 |  | note | • Max Permeability = N/A
label | 810e7f5d-f3a5-5886-9e7e-468ce97de831 |  | note | ○ Scale B:
label | 47cae777-94d9-5209-afc4-aa2b4f585315 |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 43fda0b5-29b4-544b-8f07-d09c08d25286 |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 24d914fc-13e1-5048-86e0-16bea593154a |  | note | • Attach: Post Compaction Material Property Test Results
label | 7d11a6ee-b1cf-5667-9ba4-ba731d9b8ef1 |  | note | Method - Review Document
label | aa8a6305-70c2-56e7-85f1-76cd971f40ce |  | note | Frequency - Each Lot
label | 8765fe0f-736b-5cbb-952a-f98e84d49065 |  | note | Category - IP
label | 6511b0d5-96d5-5d1a-b482-66cd07a8ad5d |  | note | Responsible person - SE/PE/SPE
label | 8e075b2a-9ad5-57db-ad19-2209131d767f |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Survey Conformance
label | e0441fc9-6db8-5a97-a6d0-c0c3e22e884a |  | note | Reference - Table 204.031
label | 13201703-6e42-543e-9c97-44ac114f5d8d |  | note | Acceptance Criteria - Level tolerances (Scale B):
label | 35f54862-bcb6-538e-9a50-44c3e0fbc7b3 |  | note | • Range Mean = +5, -25mm
label | d7c0e9c9-9d51-5a2b-b5c7-92e6f053b04c |  | note | • Max Standard Deviation = 15 mm
label | d93e42ac-5d5b-5c94-8907-f2a36d81a2b5 |  | note | • 40 measurements per lot
label | 94d0a78c-6a9b-5dca-ab7c-2bc6faf4ae8d |  | note | • Attach: Survey Conformance Report
label | c5cc6c94-e1f8-5cf9-a6aa-ed81e122103b |  | note | Method - Review Document
label | c7d5bef4-ae8a-5715-b3cf-0cc1a59245b4 |  | note | Frequency - Top of Type A
label | 17d46b21-fe88-5836-960f-f6e4607543b8 |  | note | Category - IP
label | d94bb15b-b82b-5ad6-bdd8-6def3abf2d17 |  | note | Responsible person - SE/PE/Surveyor
label | 37d0c8bf-2b68-5782-9180-b7d57f2dc01f |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.1 - Non-conformance Report (NCR) Closure
label | e460289f-528e-5c50-9b9d-4886551cad72 |  | note | Reference - MRPA Quality Management Plan
label | 5d32c9e7-b991-54e6-abf6-c14b020bff67 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | f381bc78-3c95-5fa0-b31c-5d6deb21a499 |  | note | Method - Document Review
label | e6097d75-9321-52f7-8025-a77e18872954 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 95eee745-9ceb-550d-a016-81a447707eff |  | note | Category - HP*
label | 10261399-53c5-567d-bc5a-a0d89fd2f80b |  | note | Responsible person - SE/PE/SPE
label | 855b7ed6-e81b-5c5a-9608-2dca3f6f861b |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | Final Inspection
label | fa36a3b4-0307-557f-bb91-ff0c4db2053e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 321fe253-7058-59a6-a7c0-d8001395b0b0 |  | textbox | Name:
text | 470f1429-7595-5eba-8014-46a433950cc5 |  | textbox | Position:
text | 7e409433-1a9e-538f-9a71-56ac3b2b452f |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | CHK-002-CIV-Stormwater Drainage Pits Installation | itp |  |  |  | Yes | CHK-002-CIV-Stormwater Drainage Pits Installation | 7414c945-a4a0-4690-bc0b-05087ccd96fb
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | f59bd179-5879-5840-aee0-16ee86ef27c8 |  | note | Document Title: CHK-002-CIV-Stormwater Drainage Pits Installation
label | 1412a00e-2570-5053-b894-82ef6d077511 |  | note | ITP Description: Stormwater Drainage Pits Installation Checklist
label | d5c200c7-2087-5354-874c-5f9b907a86ba |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | d4354a69-d68e-5a38-a017-fbe34f60ab83 |  | note | Revision Number: 0
label | a34e1983-67b4-5d51-aaf1-4eb68a67447a |  | note | Revision Date: 20/06/2023
label | 9fd7cd56-fb67-5782-86b8-9ea0bf4d0ecb |  | note | ITP created by: Kamel Alshobaki
label | ce015939-e704-5c36-bb9c-18dc525bea34 |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | ccfaf275-1583-581a-be42-8900c0fe9a4f |  | note | Reference - VR Section 701
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 02d3b240-5119-5ab3-a32e-2824dcc9b105 |  | note | Reference - VR Section 705
checkpoint-status |  |  | checkpoint | 1.3 - Main ITP
label | 31627591-3b94-5448-b03f-11f62ff1d628 |  | note | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
label | 76684e03-f1b8-5520-ad18-1c35637e8f2c |  | note | Acceptance Criteria - This Checklist should be used in conjunction with ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
text | 159191b6-d1ad-5213-af76-a04a55a1bd1c |  | textbox | Enter: Main ITP Lot Number
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Bedding
label | 8af0af7d-55ee-56ee-9a9f-6213884936c1 |  | note | Reference - VR Section 701
label | 645061fd-99c8-5978-800f-b93df91f59a5 |  | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
label | 31fc2a6c-c822-5d9b-aeb1-4937b1e3fdd4 |  | note | • ATTACH: Bedding Material Delivery Docket
label | 1de837a3-a696-504c-8327-84630219f4d0 |  | note | Method - Document Review
label | 8817ce7b-cb8c-5f71-b664-f600596f2ebb |  | note | Frequency - Each Lot
label | 97715193-85a2-5900-9715-01cd53fbf96e |  | note | Category - HP*
label | 8944d2d7-05d4-51ca-b16b-1b60a7cb3302 |  | note | Responsible person - SE
label | 81190533-9cf0-5992-8b0f-40a3694f3ae0 |  | note | Verifying Documents - This Checklist Signed-Off
label | d7b1d269-0a88-5dfc-9963-91b23d07cece |  | note | • Material Delivery Docket
checkpoint-status |  |  | checkpoint | 2.2 - Backfill Material
label | 5bdb41a5-dd16-572e-bc79-0fa6ab563afc |  | note | Reference - VR Section 701
label | fe9e0ad2-6dbb-5993-84fa-4e868b8aff5b |  | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
label | 1779fd26-0c1c-57c7-88db-03b16bcfd546 |  | note | • ATTACH: Backfill Material Delivery Docket
label | 5faf6374-7df8-5d67-9b1c-a2c460220012 |  | note | Method - Document Review
label | f42ba87a-2294-5990-9636-f3b44380cf35 |  | note | Frequency - Each Lot
label | 8d8df435-e9b8-5d12-b9c5-6256ddfb2349 |  | note | Category - HP*
label | 86b8a1e4-3c89-59fb-a018-deb45a4b97aa |  | note | Responsible person - SE
label | be21ab9b-d81c-5f6e-b996-4cdfdee76759 |  | note | Verifying Documents - This Checklist Signed-Off
label | f4f9158d-8b99-502e-b710-d3640eb89ea5 |  | note | • Material Delivery Docket
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Subcontractor QA Submissions and Approved ITP
label | 3b726df6-22f5-5f3a-995b-22d620e2a4e7 |  | note | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
label | 9b5ead92-50ae-5e44-93cd-673042cb5471 |  | note | Acceptance Criteria - Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
label | bff24886-bf69-5c91-a605-92ff21201fb7 |  | note | • ATTACH: Subcontractor Signed ITP
label | e1aff119-ceb8-5933-b55f-0725acf408e1 |  | note | Method - Document Review
label | 83d071fa-77b9-51d9-bbf5-25d8d02adf27 |  | note | Frequency - Each Lot (in case undertaken by subcontractor)
label | 09172ac0-76d8-5be7-a1d7-d0f7fb4b1af3 |  | note | Category - HP*
label | 1aff64e7-64b7-5b73-a14d-f6b894fb4cb4 |  | note | Responsible person - SE
label | d2df3f76-2f71-5516-9c63-4040c7cfb210 |  | note | Verifying Documents - ConQA Hold Point Release
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out-
label | aebb569d-53e8-505e-b427-200b43347638 |  | note | Reference - VR Section 710.10
label | 4a318685-a67f-5077-873e-055a34cfd19f |  | note | Acceptance Criteria - Prior to commencement of excavation the Contractor shall confirm the position of pits with the Superintendent.
label | 1485c923-e5e7-5b15-9c3a-e9f7ef545229 |  | note | • PROVIDE MARK-UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
label | e84335c6-9251-520f-b239-8e7d55038ce0 |  | note | Method - Survey, Measure
label | 1b4f81a6-9b35-509f-b098-e0f508bdf3e2 |  | note | Frequency - Each Lot
label | 8f722dd7-6925-5eb8-922d-ce0a9de37f56 |  | note | Category - HP*
label | 447ae7fb-24e0-534e-83d6-708d85da5d10 |  | note | Responsible person - SE
label | 2b4c6f85-1f1d-533d-a6f5-3e92b046637e |  | note | Verifying Documents - This Checklist Signed-Off
label | fecda949-4d8e-5fe6-8a4e-e68ac5e58152 |  | note | • Attach Main Lot Map
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Survey Set Out
label | 96ba2c41-ade8-5b3c-872b-0449b796a064 |  | note | Reference - VR Section 701.10
label | febdb240-e17e-5935-9edd-7041d0c0f566 |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
label | 2fe0adab-90a9-559f-924f-239c05f76b2d |  | note | Method - Visual inspection
label | b11af633-30cd-5ae2-a3ae-78b21551af2e |  | note | Frequency - Each Lot
label | b4ceb6fa-4808-5e42-bd9a-08a98b262b36 |  | note | Category - IP
label | e4b3c213-1b69-5033-8535-671203ef0eb2 |  | note | Responsible person - SE
label | a0048655-15a3-57fe-825b-ea73b8190ead |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.2 - Pit Excavation
label | 98b0e06f-21f5-51ee-b939-49717b4c60fb |  | note | Reference - VR Section 705.05
label | 6b412beb-ed51-53ef-bd05-02affce60576 |  | note | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
label | f6b19b1f-f9e9-50e6-a9c2-e59609752770 |  | note | Method - Visual inspection
label | 6fd21d8b-43ee-5c39-8cca-3b00cc8543dc |  | note | Frequency - Each Lot
label | 791fd2e1-acd6-5a98-9cb9-121f18084f5e |  | note | Category - IP
label | aa6a4669-0b24-5e4b-8d75-28a1925cfe1e |  | note | Responsible person - SE
label | 5d3db2cf-c36a-5dd4-8b6c-14720655e9cc |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.3 - Excavation of Foundation
label | b25520d6-0f17-5c93-8e82-20882d0a8f24 |  | note | Reference - VR Section 705.05
label | 06634074-fb4b-52a1-a0d0-9ad41bb12274 |  | note | Acceptance Criteria - Bedding conforming to to 710.09 shall be supplied, placed and compacted to a thickness:
label | 70806e00-c297-5a68-aa87-376c924ec2e0 |  | note | • > 80mm for clay foundations
label | 4a7ff2fd-346b-5741-b9ff-70d4679974eb |  | note | • > 150mm for rock foundations
label | e6e67fb7-c9ee-5d89-9143-f0ec7e477cc7 |  | note | Method - Visual inspection
label | 4ba1992b-40e9-5224-a3c4-0a962e186b2c |  | note | Frequency - Each Lot
label | 96b3a43d-4d09-57c1-97b5-3e415b5ba180 |  | note | Category - IP
label | cfd96a48-268a-540b-be33-da9a75a65135 |  | note | Responsible person - SE
label | a7dcd240-6c37-5157-a7e0-60f7f24deb46 |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.4 - Placement of Pit - Conformity with drawings
label | c298dec4-1a1c-5e61-9e4d-c0041b4e6c3b |  | note | Reference - VR Section 701.10
label | 4b272ff8-265b-55ae-a96c-d92e47f086d9 |  | note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | 44235dcb-f761-5c2b-bb52-4b37fe565597 |  | note | • Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | 9bbca292-c416-5ed1-839a-4b9522a17070 |  | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | fcfdeabc-fba9-55df-9041-df9b7fb8b7bc |  | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | 8424613f-af2a-58a9-9e33-d18c33d269d6 |  | note | (c) invert level of pipes at pits ±50 mm
label | 6c9168e5-bb80-538e-a8e6-d31097ae6ca2 |  | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | 8da785b4-f829-5a97-b00e-c82f78b128d4 |  | note | • ATTACH: Survey Report / Data
label | 99ab7769-496c-5cd1-a28a-0f37c2bea2a8 |  | note | Method - Measure
label | 3211f42e-3460-5d5d-a20e-a7401a7aacaa |  | note | Frequency - Each Lot
label | ad18a625-2f9f-5e1e-bc17-0291f96d3d68 |  | note | Category - HP*
label | 2cf144a7-e711-5181-a2b3-2df58cfece2d |  | note | Responsible person - SE
label | beef68f1-490b-5b84-b185-25a1a76850bc |  | note | Verifying Documents - This Checklist Signed-Off
label | 3b3ee72b-0bfd-586e-a1af-a6d29a4e53c3 |  | note | • Attach Survey Report
checkpoint-status |  |  | checkpoint | 5.5 - Jointing
label | 777a39d3-f01b-5b9c-8e56-adb186b4d395 |  | note | Reference - VR Section 705.11
label | d895977f-67d3-5a3e-bc0b-f998f2d54895 |  | note | Acceptance Criteria - All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
label | e8f346a1-431f-5ffa-815a-11979163496f |  | note | • Exposed reinforcement shall be coated with an approved epoxy treatment
label | 1d4177da-a149-5357-b2fd-dd4bdda65685 |  | note | Method - Visual inspection
label | cc6c5b84-725c-5003-b657-89dd60b593ef |  | note | Frequency - Each Lot
label | c711b88c-a6d6-5aa9-ab0e-01a549f1ffd9 |  | note | Category - IP
label | f4fc6568-2601-5413-92a6-71f5327b678e |  | note | Responsible person - SE
label | b8fc93b5-0b6a-5974-a389-6accf67c934d |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.6 - Shaping of Floor
label | 4cd557a1-174b-575a-9760-3b7b2e400bab |  | note | Reference - VR Section 705.13
label | 15066479-78dc-5d3e-96ff-73694870bb40 |  | note | Acceptance Criteria - Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
label | 95c11416-d73b-5c34-a204-aff067fcc83f |  | note | Method - Visual inspection
label | 978f5ac7-78d8-5c09-9e27-cda12c9ba702 |  | note | Frequency - Each Lot
label | aadb179c-a01e-5f8f-870e-be4ded66f567 |  | note | Category - IP
label | 11715a55-911d-52ad-a4bb-00864fc4c0ac |  | note | Responsible person - SE
label | b24ad414-dfff-5cc0-97d3-aa31746afcbf |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.7 - Step Irons
label | 1e8f1cdd-f635-577e-a3d6-20cc0a9d406b |  | note | Reference - VR Section 705.12
label | 0c5830a2-6187-5c21-8a2f-573818a55348 |  | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
label | e9844158-89c7-59d2-a9a3-43d65761999c |  | note | Method - Visual inspection
label | 04a502b3-603b-5c0b-bc58-7783f4ac654b |  | note | Frequency - Each Lot
label | 8150cbf5-9439-52dc-9816-58e668ae2ac5 |  | note | Category - IP
label | f28c3b0c-2085-5c02-b3ad-64c606b3530a |  | note | Responsible person - SE
label | add271e7-469d-5340-bb87-75612d3cadb9 |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.8 - Fitting of Covers
label | 79372dc2-9f96-52ec-a609-06de5902f938 |  | note | Reference - VR Section 705.17
label | 102149d6-f5ec-5f35-b7e0-87767275e443 |  | note | Acceptance Criteria - Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
label | 533066db-40c3-51fe-a89f-cd3db695888f |  | note | • Height shall be within 10mm of the design level.
label | d5152618-321c-55e8-aa79-7fe6f7809d54 |  | note | Method - Visual inspection
label | 358c6a64-f9d1-5395-936c-cd7c929343d7 |  | note | Frequency - Each Lot
label | 398aee41-404d-509d-8277-e6b4fdee1863 |  | note | Category - IP
label | ee6e0b20-2558-5362-9bfa-bf5db20b649a |  | note | Responsible person - SE
label | 8f9ed847-56e9-599e-b2b5-c5fc7923644a |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.9 - Backfilling Around Drainage Pits
label | 2150627c-7c74-5bda-be1e-ffda710059e2 |  | note | Reference - VR Section 705.18
label | de5cb25c-0b36-5703-876e-c1bd8be09169 |  | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal.
label | 45a86d4a-f83b-5535-9575-4b794bd8bf76 |  | note | Method - Visual inspection
label | 21f3cc3a-3755-54e5-9efa-373af3b709c2 |  | note | Frequency - Each Lot
label | b70019e6-0b70-58df-ba32-745e50b4696d |  | note | Category - IP
label | ec6fb8d3-0c7d-52e6-955e-8dfb9e4503f3 |  | note | Responsible person - SE
label | 919c527f-7b59-56e6-8bd9-9579ad0db14b |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Compaction and Moisture content tests
label | 0164e669-65cb-596b-afcd-6bd750ca1ddf |  | note | Reference - VR Section 701.20
label | e6839a1b-de1c-5aa8-bb34-2bc74576eec4 |  | note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
label | 1f52a655-1729-582a-a4e9-03f33b814fc7 |  | note | • ATTACH: Compaction and Moisture content test results:
label | 6d043e8d-1a2a-5fea-8cca-3bd84a35208e |  | note | Method - Document Review
label | d8b7ecdd-74ac-52d6-b4c4-da1f683587a2 |  | note | Frequency - Each Lot
label | cc956f8a-48fb-5692-ad62-c0661dc079da |  | note | Category - IP
label | ed37b60f-f5e3-5ce5-a7f9-2107124d0d89 |  | note | Responsible person - SE/PE
label | f1627ae5-3bd6-596d-aa87-121bc45a888d |  | note | Verifying Documents - This Checklist Signed-Off
label | 22435112-adce-53d4-b8dc-d25cfaf8a21b |  | note | • Attach Test Results
checkpoint-status |  |  | checkpoint | 6.2 - CCTV Inspection
label | 5ca32182-9538-5d03-8561-0cf7e24fd583 |  | note | Reference - VR Section 701.30
label | 16822ded-fbd1-57c1-a816-d79ae699d760 |  | note | Acceptance Criteria - All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | 2561f72f-4cb9-5bb9-8068-1fe8c992c862 |  | note | • ATTACH: CCTV Report (PDF)
label | bd69d936-d8ff-5033-b185-6e28d0c51985 |  | note | Method - Document Review
label | 0e2cc413-98fa-57d6-90e0-3b064f0151cc |  | note | Frequency - Each Lot
label | 61b3ea4f-e3a6-5186-babf-c6c507b93a3d |  | note | Category - HP
label | dfe97c78-9e5e-5849-a088-9c00e9326050 |  | note | Responsible person - Nominated Authority
label | 244e18ef-a8d0-5db5-8fa9-522c9c201299 |  | note | Verifying Documents - ConQA HP Release
label | d0ffbe5d-1b76-55be-9935-0842fd234441 |  | note | • Attach CCTV Reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 7bf09ad0-0f54-574e-8c14-a50a01a61315 |  | note | Reference - MRPA Quality Management Plan
label | 8570bd23-cff5-59dc-956b-ac573edc46e0 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | ca6d3449-6cab-5948-b857-ccea6fd7c3a5 |  | note | Method - Document Review
label | 9430d7b1-6571-58b5-82ca-f7aaab7ce1b5 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 1477ae97-1afb-5ee9-8612-fd4a6b3eebaf |  | note | Category - HP*
label | 425ed2e8-b010-544d-ba32-0b27d099bf36 |  | note | Responsible person - PE
label | e1f7cab7-f23b-5b3a-ad94-789041e6428f |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | Final Inspection
label | 44998d2a-42cd-59b8-95b5-b05e15b13e4c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 5c356b69-2d02-57bf-bb59-f25ca9b69f7a |  | textbox | Name:
text | dece4c80-4120-50ff-b342-241d43b2cdc5 |  | textbox | Position:
text | 7a0000ca-6c8d-5d59-a36d-75730a413790 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-039-STR-Brunt-Abutment & Pier Walls | itp |  |  |  | Yes | ITP-039-STR-Brunt-Abutment & Pier Walls | 79c4b4f2-508c-4833-88c8-fb27cbc79373
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 4cccd459-ced3-573a-9143-d209910aa770 |  | note | Reference - VicRoads Section 602 October 2007
label | d0f04660-49ee-5faa-a2d9-b03494d550ca |  | note | Acceptance Criteria - N/A
label | 655a1364-55dd-5a44-91ac-49147e5c82cb |  | note | Method - N/A
label | b39e0f69-1115-538b-95c4-eec539ed358a |  | note | Frequency - N/A
label | d8508f09-bc82-5ead-ad85-c1aa94524492 |  | note | Category - N/A
label | 8ebe5b89-7c9a-5293-8006-f40b2fd9abe3 |  | note | Responsibility - N/A
label | 1b873118-8536-5718-a439-1e298e09b6f4 |  | note | Verifying Documents - N/A
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 4e7c8ba1-02b8-574c-9c0f-db4e5e304bd5 |  | note | Reference - VicRoads Section 610 February 2020
label | d8a92e7f-4160-5aa1-9f88-b783a7b5bd68 |  | note | Acceptance Criteria - N/A
label | 43921d0f-1977-5979-9a22-fdd4e9caf589 |  | note | Method - N/A
label | 58cdf3fc-d7d3-5f5c-b23d-e482b2729b05 |  | note | Frequency - N/A
label | e7bc0d0d-9695-53e2-baa9-8995f0e5a00f |  | note | Category - N/A
label | 85d0ce92-23e5-574d-a8a2-df06569f2167 |  | note | Responsibility - N/A
label | 112a1923-797c-54a0-a1f6-942665e8f5c1 |  | note | Verifying Documents - N/A
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | ec799ef9-552c-5ff7-b880-df6bd5fb602c |  | note | Reference - VicRoads Section 611 November 2018
label | 40dba7b2-cee3-5b9e-9642-e603224a79fe |  | note | Acceptance Criteria - N/A
label | c34f86a3-303f-55e5-9f6c-c196813b3df6 |  | note | Method - N/A
label | 6d48088a-141c-5fc7-a5dd-7725d04c6d2b |  | note | Frequency - N/A
label | b78d9171-ebf4-5409-9078-d9ceca5524d4 |  | note | Category - N/A
label | 3729502b-66db-5109-94da-51bbc9c872fc |  | note | Responsibility - N/A
label | 5f8eecca-98fe-5e5c-a0b5-492fe3774075 |  | note | Verifying Documents - N/A
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 25b93da6-a106-575e-8a0b-7a72986375e8 |  | note | Reference - VicRoads Section 614 June 2017
label | f1e4cc31-bbe4-5dac-b8d6-1871c3b7e73a |  | note | Acceptance Criteria - N/A
label | 574323d4-9226-5f2d-8d00-74fa8ae321f0 |  | note | Method - N/A
label | 0ef77b72-645e-58dd-a7ee-a61b08c648c9 |  | note | Frequency - N/A
label | 7ec60cd2-76f4-5b3f-8a5c-9ba0beabb2ea |  | note | Category - N/A
label | 3347fc0f-6a7e-5dad-aac7-74293e2ba061 |  | note | Responsibility - N/A
label | 6802dcf8-1ada-5a67-a808-c3807ba05c7c |  | note | Verifying Documents - N/A
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | c68f3e83-0179-5ebb-9bbd-9d7ea2f5d75e |  | note | Reference - AS3810.1 2018
label | ab92a0e9-07ea-5121-8284-090cf522f5cd |  | note | Acceptance Criteria - N/A
label | bd03dac7-d156-5b68-ab66-f2683924336f |  | note | Method - N/A
label | e84ed2db-5793-59a6-b0b6-b23666479e44 |  | note | Frequency - N/A
label | ce54ab53-b965-5a25-95c7-967262fc22fc |  | note | Category - N/A
label | 495a46de-23e6-5320-9f8e-7a8378792e57 |  | note | Responsibility - N/A
label | 60737339-2703-5e03-ac14-be4e84f36d66 |  | note | Verifying Documents - N/A
checkpoint-status |  |  | checkpoint | 1.6 - Non Dependent
label | cde843e5-264a-5a20-bfc5-110f2df1e343 |  | note | Reference - IFC Drawings
label | 3a5c7b19-c433-55b1-91d7-c0685696de23 |  | note | Acceptance Criteria - N/A
label | 90d20625-fea4-530c-8e6d-780b05d714c0 |  | note | Method - N/A
label | b262fe62-fbfc-5adf-abde-be5779071ede |  | note | Frequency - N/A
label | ea7edfb8-b0f9-5510-aefa-3bfa21954834 |  | note | Category - N/A
label | 494e2593-42fc-545a-aa21-f8c8a24b81f8 |  | note | Responsibility - N/A
label | 2586d5f9-a990-532e-83cd-21d9f58366c5 |  | note | Verifying Documents - N/A
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix
label | 5c9899c3-5ab9-5827-a282-e1e1fe250889 |  | note | Reference - 610.07 Table 610.071 IFC Drawings
label | 8beafd62-c37e-5b37-b124-ef3022efd2c4 |  | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Enter: Teambinder Material Approval number [free text box]
label | ebe9e65c-bc91-5078-9512-141d977e5876 |  | note | Method - Document Review
label | 7416527f-f177-56e7-bb60-0821d44a0fdf |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | 308e8a11-c2f1-565a-ada9-de63f1758b3e |  | note | Category - HP
label | f1279922-6211-5b32-b418-cd62bb810ee1 |  | note | Responsibility - Nominated Authority
label | b8fa37c9-09fc-5cd0-875b-8783297ccb0b |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | 4b963a42-68d3-5c2a-8169-5d2cb92cb05c |  | note | Reference - 611.05 (a)
label | 70ce63ae-1c53-5669-82db-fa918e4eb8d4 |  | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box]
label | 19c62f7b-3796-5c6c-acff-55950f8e8c5f |  | note | Method - Document Review
label | 60327a72-b1db-5eac-9667-27a30d87d942 |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | 6d4d2db3-a16e-5d81-b797-4f1b0982081f |  | note | Category - HP
label | 67a9ba7d-3945-5077-9c57-cc659a6a52e9 |  | note | Responsibility - Nominated Authority
label | b1690cfe-089c-5a82-be2e-d8d18bba5f45 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Bar Chairs/Aspros Certification
label | be656ef0-156f-5f83-811d-5e1d05bfabf9 |  | note | Reference - 610.26 (a)
label | 7b5b57de-1ae1-56fd-9924-eedc74f21703 |  | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads. Concrete aspros require annual compressive strength and soluble salt testing is required. Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
label | e8800d34-ae29-59dd-b834-9ebd6c2a971d |  | note | Method - Document Review
label | 94518050-ece1-5d5e-920f-beb71936485d |  | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | be94ac9b-ea0e-5bd9-a49a-01190aee7587 |  | note | Category - HP
label | 4a2963c9-4030-5abb-a520-0e6442bcbb4b |  | note | Responsibility - Nominated Authority
label | 8f47ddb0-e77c-516e-9859-df9d3551ef51 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Evaporative Retardant
label | 0b0e5a35-0113-5521-a8da-1f47a61efdb6 |  | note | Reference - 610.17 (f)
label | a48e8ab0-21de-5463-b2f6-f76d94d3f4be |  | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
label | c4d35dba-d8b1-5723-b61a-ae396d66e393 |  | note | Method - Document Review
label | 4f470773-a016-54f9-8fd3-2de1b90eb6fb |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | cc22510f-044d-55cd-86f4-6632e33899ef |  | note | Category - HP
label | dcf6d01b-8a48-57c2-b7aa-5e623f893a01 |  | note | Responsibility - Nominated Authority
label | 9d4a3266-3526-5760-936a-5acf47c1e77f |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Curing Compound
label | 383504b6-d72c-523d-956c-dfe687cbb9fd |  | note | Reference - 610.23 (d)
label | 76501349-083f-529c-af68-fe546f5f16ab |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
label | 04057559-edf6-57f5-8f7a-92c6fb241ed6 |  | note | Method - Document Review
label | eb184a1a-d1b7-53d5-b525-ded07fc01244 |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | 29c6b85d-c4cf-5e5d-8034-912eae992c10 |  | note | Category - HP
label | 936053de-5434-5ee8-abd6-fdab35825996 |  | note | Responsibility - Nominated Authority
label | abbcc674-3f39-55fe-b16b-a0d9b1904465 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
label | 64494500-181c-57ba-934e-0f006fe6f5a4 |  | note | Reference - 610.18 (a) (i)
label | 81188805-9441-56b4-83b0-0f19935f4bc2 |  | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 7ca36c4d-cff6-517f-89bc-a407a436d215 |  | note | Method - Document Review
label | 0247bbad-3b33-564b-ab8f-0839acd965e7 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 78eeefdd-dd7c-5ba1-ae60-85c6e9602bb3 |  | note | Category - HP
label | 862685b9-fba2-565a-9bb9-6c23072561bd |  | note | Responsibility - Nominated Authority
label | d8f37535-59f0-5a36-8232-17e4d253268e |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Concrete Sampling and Testing Procedure
label | f012a11b-42bc-53cf-a8e7-f934390242ad |  | note | Reference - 610.18 (a) (v)
label | 1aa48cde-8b63-5489-9841-3a3535652da0 |  | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 01f0e493-751e-5404-96fc-98463e6c33b9 |  | note | Method - Document Review
label | 343fd5ba-10b0-5846-bf37-47c5b9d3ad76 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | f1f45fa1-91fc-5c60-a50a-8dc23cd109db |  | note | Category - HP
label | 6adb57c4-c448-5715-a352-5814bffcf505 |  | note | Responsibility - Nominated Authority
label | d37c12b4-9b3f-51d4-baad-f201db5f58a1 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
label | b227db33-a623-5000-b426-ea4b7190ab25 |  | note | Reference - 610.18 (a) (iv)
label | cd136bc8-9abe-587a-8839-b7e5fbdc3d85 |  | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements. Minutes of this meeting to be submitted to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 33f45caa-eab6-5a09-a69a-bf146e820e82 |  | note | Method - Document Review
label | 5f4baef1-6299-5569-8294-76b1cbc16ecb |  | note | Frequency - Once, 1 week prior to placement of concrete
label | 18c488aa-65de-5059-98cb-1c2035d95308 |  | note | Category - HP
label | ee05f8be-cf5f-5870-9089-0530227de196 |  | note | Responsibility - Nominated Authority
label | 9fbcdcc8-0ac2-5a0e-84c2-679a2a87bf9a |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
label | 8982e95c-928b-54c0-9d60-a4877ca2d5e4 |  | note | Reference - 610.17 (a)
label | 3954bebc-631a-5892-a716-11e077f7b176 |  | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 52f49082-1b48-5d44-97d8-667c1c03c0b6 |  | note | Method - Document Review
label | 69f128ef-ca46-5fb8-8eff-6ca934c76822 |  | note | Frequency - Once, 2 weeks prior to placement of concrete
label | 418e7d50-2367-572b-9439-018f8de248cb |  | note | Category - HP
label | 8726db37-538d-5a9e-80f8-02da9da4f6ff |  | note | Responsibility - Nominated Authority
label | ad87a9df-26ba-55c0-8f24-3c910818cea4 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
label | 8dd025e0-6711-53f1-9d86-35c7c858f7d7 |  | note | Reference - 610.23 (a)
label | cbff9b0d-7a96-5cd6-961a-5b2da0fcc19f |  | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 8ddf1181-db23-52aa-bdab-e79a875dacbc |  | note | Method - Document Review
label | 88cbf9ff-da61-5771-a97c-8976f0db91f9 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 2e3faab8-8e9c-5a0c-974d-a2f5a8acb866 |  | note | Category - HP
label | 1b0675c1-5b6a-5c54-9108-c719257d552b |  | note | Responsibility - Nominated Authority
label | 0d760fbc-802c-5cc4-8e6f-3eafc9b18b07 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Concrete Drilling Procedure
label | 14436427-156e-5d6f-9db3-c936285a016b |  | note | Reference - 610.46
label | fba3c4ac-80aa-50f4-a953-51377e5394e9 |  | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services. The planned locations and drilling procedure shall be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 08f996c8-9a68-5e9f-bc02-4dd6d0716d8b |  | note | Method - Document Review
label | a4f16b3b-fa99-5399-8f0c-df40dac14c04 |  | note | Frequency - Where applicable, once, 2 days prior to drilling
label | b66a3910-e0b7-5ed4-b2b8-58403055ead4 |  | note | Category - HP
label | b3e17dcc-3f8d-5f78-95a1-2d8850ba6485 |  | note | Responsibility - Nominated Authority
label | 65b60b2f-7a38-5911-8597-100fddb17310 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Temprature difference measuring-Calibration
label | 58251653-b470-5847-bce0-bba9ce25f8a2 |  | note | Reference - MRPA Quality Management Plan
label | 88ba2adc-a8e5-595d-8f2b-740e4f45b7e2 |  | note | Acceptance Criteria - Calibration records for Themocouples are valid and up to date. Attach: Calibration certificate
label | de0817a7-040a-5a34-b618-fe59a4e43da1 |  | note | Method - Document review
label | 433a4966-696d-5d26-933b-592c9d68bec7 |  | note | Frequency - Where applicable
label | 4ef059b9-87c1-5269-870e-7b661fd6b6cb |  | note | Category - HP*
label | e097fee4-6360-57fa-a8fb-4f3b49e1460c |  | note | Responsibility - PE
label | 48e99013-5342-57d2-9802-81cdd8fb7275 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
label | 344b821b-f7bb-58c5-9f1e-2b6f7cd3b613 |  | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
label | 568e8ab7-ba0d-51b1-a339-ff59e9d0ca77 |  | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
label | 5d8b6331-54fd-5668-83f4-28535ceaf5ec |  | note | Method - Document Review
label | 705ea27e-f6af-554f-9846-266edc2c6142 |  | note | Frequency - Where applicable, once, prior to welding
label | 2914cf11-6112-595a-8db5-b7eaefad1f21 |  | note | Category - HP
label | bc21b9d0-e5ff-5847-8f8e-fa7c8500842e |  | note | Responsibility - Nominated Authority
label | f03e65f4-4851-5cde-b623-403ef1f947e9 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | 8cdf502f-6c51-5cb1-bec7-5c21b05d9f5c |  | note | Reference - MRPA Quality Management Plan
label | 928b859a-2f90-5ded-a030-d5287153094e |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | fc810e3e-d6a0-5614-a7a8-42d36a6d5ad7 |  | note | Method - Document Review
label | 51bac255-a183-591c-874b-5607339f29a1 |  | note | Frequency - Prior to starting Works and at regular intervals
label | 7b2589e6-4f8a-5ac6-8b10-0263d6f47f00 |  | note | Category - HP*
label | ccd8d590-8003-5534-a538-cfba4c6c994a |  | note | Responsibility - All
label | e97ad841-4116-5fe4-8bdb-c0d4d377d5ed |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out
label | 853e92cd-9757-5e5a-87c6-b9bea52cb472 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472
label | aa8de62d-4016-50c8-9258-f2d9c1eee94e |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element. Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | a0bd1962-5d96-5dec-98e3-9dc0f36e7646 |  | note | Method - Measure Visual
label | ab0768de-a12f-5cf6-96b4-709a86cfa290 |  | note | Frequency - Each element
label | e7b711ee-2797-571a-af6c-d5f243629307 |  | note | Category - IP
label | ca7c20a0-ff54-58d7-a596-31ed8712f1a1 |  | note | Responsibility - Surveyor SE/PE
label | ca2639fa-9aeb-5551-b6e7-67864f1701df |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.3 - Pile Cap Work Lots
label | 2a621d4f-ffd5-5114-b93d-d51352b18f56 |  | note | Reference - TeamBinder Work Lots
label | bd2a34b6-6508-5ab4-b46d-8eb68c61cd3e |  | note | Acceptance Criteria - Related pile cap work lots are closed. - Pile cap design strength is achieved - As-Built Survey performed - Related pile cap NCMs are closed. Enter: Pile Cap Lot numbers: [FREE TEXT]
label | 71162c70-465c-5cb7-9b46-227026dd57e8 |  | note | Method - Doument Check
label | 3290a5cf-98ee-567e-9254-59bc63e91c8f |  | note | Frequency - Each Element
label | a371902b-e4fc-5bef-ab7f-d13f2b6efe87 |  | note | Category - HP*
label | ad8b5344-ea3e-531d-9547-ecf78ef11a57 |  | note | Responsibility - PE
label | 7c33f0e3-d5f3-555a-abcb-f199aec84c81 |  | note | Verifying Documents - This ITP Signed Off Pile Cap Lots Closed-Out
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Formwork Design and Construction
label | b6059d7c-d858-55c3-9534-5442f9d1b94a |  | note | Reference - IFC Drawings 614.04 614.05 614.06
label | 77b6e89a-80cb-5a72-843c-12638adfa537 |  | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected.
label | 68456cc0-2d5a-5e81-9eb4-9906afb596db |  | note | Method - Document Review Visual Measure
label | e0bd3f63-a5c4-50b2-bff0-f9baa9989dd3 |  | note | Frequency - Each type of element
label | 403344f6-3fb4-522a-9fac-e798c8497da0 |  | note | Category - IP
label | 3e1ab3af-3395-532a-874e-3e86cf004bdb |  | note | Responsibility - Temporary Works Designer Proof Engineer SE/PE/SPE
label | d33ee62f-09dc-5c0b-8311-0d51154f28a0 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | a56bf123-8571-5b3b-a92e-bf40597ba434 |  | note | Reference - 614.08
label | 334358ee-c450-5401-882b-0c57a7bf7350 |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Abutment / Pier Walls with heights greater than 2.0 metres Any member for which self-compacting concrete is proposed. Attach: Attachment A Attach: Attachment B
label | 16ca4080-497d-58f3-8ae7-6e81d3f04f24 |  | note | Method - Document Review Visual Measure
label | 32396dba-8cd9-5807-9be7-bbcefeed4623 |  | note | Frequency - Each element (where greater than 2m)
label | 65a546f3-691c-5340-aaa3-56f6bce25282 |  | note | Category - HP
label | 7b6983c4-521d-52bb-b2e0-ce496db7f60d |  | note | Responsibility - Temporary Works Designer Proof Engineer
label | cd9585a6-7a9e-59c1-8e38-8930d079245b |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | 138079ea-c694-5e1c-97e8-6535f81e292e |  | note | Reference - 614.08
label | 872b02dc-1110-5576-94b3-ec9d3d28756f |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Abutment / Pier Walls with heights less than 2.0 metres Attach: Attachment C
label | e3ad572f-18ae-53ff-92ab-f1c42c36eb58 |  | note | Method - Document Review Visual Measure
label | fa3e65ef-b526-5918-8344-92efa3c3e32f |  | note | Frequency - Each element (where 2m or less)
label | e6bfe1c9-f6f8-5bb8-abe5-99ad94075902 |  | note | Category - HP
label | 1b707faa-90e4-560a-9020-8bbb4e3e72ee |  | note | Responsibility - Temporary Works Designer Proof Engineer
label | 5a52374f-ba16-5eef-897c-04402119b9da |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Pre-pour Survey
label | d2de03df-1cc4-5d09-947d-26e6b44bb951 |  | note | Reference - 610.47 (a) Table 610.472
label | a436d230-1fb2-53c1-8092-5a24a1202177 |  | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | f6f92731-0b0a-5c80-a476-2fbb3a3f1af6 |  | note | Method - Measure Visual
label | aee89be1-aa59-53a3-a9cd-27f34715e38e |  | note | Frequency - Each element
label | df04ef6b-1ed2-5728-bcc4-867097dff138 |  | note | Category - HP*
label | cdd10722-ea56-5f57-8a55-c49b44ff7302 |  | note | Responsibility - Surveyor SE/PE/SPE
label | ce3c9849-84cc-59e9-af58-c809668bffe3 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.5 - Reinforcement Placement
label | 444f12aa-7064-5ff3-869b-eb08ea22002d |  | note | Reference - IFC Drawings 611.06 611.09 611.10 611.11 611.12
label | 831d8b62-d820-51de-a7d9-e9a93e6208a4 |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings. Projecting reinforcement is the correct length and location. Splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour. Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | b0ef2ed9-b676-5f59-b5ef-a90d7a72755b |  | note | Method - Measure Visual
label | dc3990d1-5490-59d1-9d79-7d009a0182d0 |  | note | Frequency - Each element
label | 395dd28a-5e01-523c-bd95-93d65706b853 |  | note | Category - IP
label | b2ee29d8-a0e5-53c1-8cff-007938dbce82 |  | note | Responsibility - Foreman SE/PE/SPE
label | 79b6db57-e501-531e-b5f5-509e9405905e |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.6 - Cast-in Items
label | 42fd93b9-38ca-59d5-8ff8-d2aa4810da63 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | 1fea725a-d447-51bd-abcd-883b94bf9102 |  | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement. Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress. Tack welding of any cast-in items shall be performed by someone pre-qualified to do so. Grout tubes shall be fastened at regular intervals to prevent kinking. Placement tolerances to comply with the IFC drawings, if not specified, use the following: i. Bolts, ferrules, projecting bars & couplers = ±3mm ii. Running dimensions of a group of the above = ±6mm iii. Ducts and conduit location = ±12mm iv. Diameter of ducts and conduits = ±3mm
label | 573dba7c-bf2a-5031-8598-e756db730f8b |  | note | Method - Measure Visual
label | fc2b96f7-3c7d-5eda-a1bd-ba00df613750 |  | note | Frequency - Where applicable, each element
label | ab9dc972-c801-540f-a0f8-7e4992e140ac |  | note | Category - IP
label | 7b5a70fc-4999-5793-9919-c429b7c23a0d |  | note | Responsibility - Foreman SE/PE/SPE
label | 252d89d7-8579-5676-bd81-e9f26b3c5aa2 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.7 - Thermal Differential Monitoring
label | 0d7bf27e-8818-5871-b35c-9b1104b82717 |  | note | Reference - 610.22
label | ed2b2d8b-c29d-5034-a74f-95d0d8d4c1f0 |  | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | cc61d434-7fef-560b-8c6b-dbcd58d8d054 |  | note | Method - Measure
label | f4a9015c-8fa4-584e-9eef-505beabc51b7 |  | note | Frequency - Where applicable, each element
label | 99465483-aae4-54e2-a170-0b47adf2fb00 |  | note | Category - IP
label | 4617a105-da28-5d0d-9768-2d131af3d36b |  | note | Responsibility - Foreman SE/PE/SPE
label | 0be51540-bee3-50f5-b24a-a8620bfe8b18 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.8 - Pre-pour Inspection
label | f93cc9ef-31da-5e43-b0d9-99e8690e628a |  | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | 1ad31d6f-ea60-5971-9886-e447ddc150d7 |  | note | Acceptance Criteria - Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority All foreign material has been completely removed from the forms. ATTACH: Pre-Pour Checklist
label | 08cb289a-b6ea-50e1-945f-187ce2afeaad |  | note | Method - Measure Visual
label | 941461d9-d076-50b4-bd17-b9f6b66a978d |  | note | Frequency - Each element
label | 03f0622b-af69-5822-8d96-82b909c9f3ff |  | note | Category - HP
label | e5fa2ab6-262b-59ba-ba9a-b99f4f8d09c4 |  | note | Responsibility - Nominated Authority
label | 1fde2979-7fe1-53c1-bdca-4b49fe0710d3 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.9 - Weather Conditions & Evaporation Limits
label | e180ac65-be8f-5927-953b-2b780e7c7e22 |  | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
label | b8d76bee-d41c-5c23-8313-ecfc41499d20 |  | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record.
label | 93723221-91c6-523d-8adc-3742ee0618c5 |  | note | Method - Measure Visual
label | 92fde4d0-7811-5ce1-a552-f7187cc77429 |  | note | Frequency - Each element
label | 3c8fe2df-36d4-5d5e-9ad6-2e808a51dcff |  | note | Category - IP
label | 9f443025-0fb5-5f19-b5f4-3cb390d3f37f |  | note | Responsibility - Foreman SE/PE/SPE
label | 511bee15-07c6-56ae-afc5-c9c39705b8ac |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.1 - Concrete Testing - Sampling Frequency
label | 35a59115-02b3-5652-b477-739fd1208678 |  | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
label | bc055292-1f5d-5550-98f4-dc757bf48107 |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing). Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork. Record: Required information on the Concrete Pour Record.
label | 28002b3d-c2fb-5683-9a13-ca8b2dcf0bee |  | note | Method - Test
label | cddec7dd-58a7-595b-88d8-3c0d9aada2a6 |  | note | Frequency - Each element
label | e4a0b2f8-10ae-5bcd-b2ed-a23afbcdeb35 |  | note | Category - IP
label | 326db85e-4e3e-5a3f-8588-30530a4aab71 |  | note | Responsibility - Concrete Tester Foreman SE/PE/SPE
label | c7ecfdbd-d629-5188-afea-3837575bbc4b |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.11 - Concrete Testing - Slump
label | b2e17938-46a9-59ab-be6b-e1d6a00e6b7b |  | note | Reference - 610.16 (c)
label | f78167b5-57d8-530c-88c1-de8cac321803 |  | note | Acceptance Criteria - Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record.
label | a2816b0f-4128-50a5-928e-283eac3e7cc8 |  | note | Method - Test
label | efae318a-d39a-537e-a46b-a661abed720e |  | note | Frequency - Each sample of Standard or Superplasticised Concrete
label | f1b4d18f-7840-5838-9f03-e355aa3ae870 |  | note | Category - IP
label | 2546f268-5ae1-51f6-857e-d1acb1c51837 |  | note | Responsibility - Concrete Tester
label | d77c0756-9cfd-5876-9d30-3e90d8b27282 |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
label | efc93f8c-2a96-5555-91b6-2ee3b695a0f1 |  | note | Reference - 610.13 (b)
label | dff9c5d5-102a-5ae6-bffe-fddba54934ab |  | note | Acceptance Criteria - Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record.
label | 1802fa85-a773-5710-ae8c-ea50230a748e |  | note | Method - Test
label | cd3aff2f-67a4-54e1-aed9-361174a7c50f |  | note | Frequency - Each sample of Self-compacting Concrete
label | 06fbfd36-4f64-58e6-bff8-6324235f72d5 |  | note | Category - IP
label | 3a032d56-3003-53e3-933f-1aa68623301d |  | note | Responsibility - Concrete Tester
label | 83fd8cd3-3ac2-59a0-9a0a-5408aba81104 |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
label | d6746860-aac2-5042-9ab3-ddfe3f347119 |  | note | Reference - Site Sampling & Testing Procedure
label | a92d35ed-376a-5dba-b32f-8d8629889733 |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record.
label | ad5a9486-d291-53bd-89b3-f917a911ad5e |  | note | Method - Test
label | d8f7ea2c-3986-529f-ba6e-8b487fa48fb6 |  | note | Frequency - Each sample
label | bff41ff6-047e-584a-832a-25280d1de8e1 |  | note | Category - IP
label | 6090c487-5d58-5da1-b6db-f5da0af7fd95 |  | note | Responsibility - Concrete Tester
label | baa4f4f6-d4be-509e-b5ec-51bf3c435f6a |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.14 - Supply & Discharge Rates
label | 8b5e38ed-2da2-597c-ba52-a5e35fac89a8 |  | note | Reference - 610.13 (a) & (f)
label | 093dacfd-01b4-59c0-9dcd-e64022c29a59 |  | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed. No water is to be added once discharge commences. Maximum time between batching trucks is 25 minutes. Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants. Concrete that stiffens or is showing signs of stiffening shall not be used. Record: Required information on the Concrete Pour Record.
label | fa353945-b089-56f4-a35f-7c25c0b02172 |  | note | Method - Measure Visual
label | 89528c71-89aa-5f3b-9a92-6b51410c2dac |  | note | Frequency - Each load
label | 6c3ee74e-967e-58be-8a0f-8f8384b9ec49 |  | note | Category - IP
label | 1985b5f8-6cb1-5f35-b052-32e113f4e545 |  | note | Responsibility - Foreman SE/PE/SPE
label | a687c782-bf45-53f6-9cf1-57769eaeff2e |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.15 - Placement & Compaction
label | 18824c5d-c9bb-5e4e-8539-a5258a0a720a |  | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b) 610.18 (d) (i)
label | 69264839-d8e7-5731-a475-ba57b8cfe5af |  | note | Acceptance Criteria - All concrete batches are traceable. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Concrete is not dropped freely from a height exceeding 2m. Concrete is not moved horizontally by use of vibrators. Adequate compaction is ensured Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments. Concrete layers are not more than 350mm Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence. Vibration continued at each point until air bubbles cease to emerge from the concrete. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets
label | d34ccef8-e3ee-5323-bcba-498be7340bdd |  | note | Method - Visual
label | cdc23c14-1040-50f9-9d84-6c1c442e9487 |  | note | Frequency - Each load
label | 22da6b92-946c-5476-bb7e-0fae94a67070 |  | note | Category - SP
label | 7c889f7f-fbc2-5120-b776-9dcd3711165e |  | note | Responsibility - Foreman SE/PE/SPE
label | 4d472eec-585c-5d5c-952c-505113d3e2c0 |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.16 - Surface Finishes
label | 2740b497-342d-5e7c-b15a-b4f846a20e30 |  | note | Reference - IFC Drawings 610.31 610.20
label | 9d0b7f35-f20c-5c3f-b188-4f1b9a9a0aaf |  | note | Acceptance Criteria - Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | eba391f0-7d3b-5f96-90cd-ecb5c5dc71d8 |  | note | Method - Visual
label | f87ee014-fbfa-56d5-a811-935dc76c84fe |  | note | Frequency - Each element
label | dfc51f71-acb8-5f6b-a616-948527845b16 |  | note | Category - IP
label | b3863d0e-a95c-5ede-9f4c-002e96a1b1b6 |  | note | Responsibility - Foreman SE/PE/SPE
label | a1ee18b8-5c32-5e6d-884b-fc8cb5bb466a |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.17 - Curing-Top Surface
label | 58b36654-fe31-59f7-a324-174f781a9f33 |  | note | Reference - IFC Drawings
label | 85f47480-edb4-55bc-89d8-d3106269ab1f |  | note | Acceptance Criteria - Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | 0542af66-032c-55f6-8990-eba9effba401 |  | note | Method - Visual
label | ec665b74-00bb-58c8-a624-3e59031227e9 |  | note | Frequency - Each element
label | 37bea3b9-282b-557d-964e-27811e917ae3 |  | note | Category - IP
label | 09a0e070-8eb7-54a4-8129-3c1aa11f67cb |  | note | Responsibility - Foreman SE/PE/SPE
label | 8c2a29fe-9be1-59a4-a7ce-660baf74da85 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.18 - Curing after formwork removal
label | aef21db6-5e75-5288-8032-e9fe9a1df97c |  | note | Reference - IFC Drawings
label | 87fed6eb-895f-56bb-baeb-df091c19f381 |  | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | f94a5208-0924-5b12-80d7-7760a2f35d53 |  | note | Method - Visual
label | 2966387e-ed10-5b51-81fe-439c91a19618 |  | note | Frequency - Each element
label | 65a39e87-4e78-5adb-ba28-19d402c2d3a7 |  | note | Category - IP
label | 97df17e5-e619-5740-b7b2-f6fab8a51755 |  | note | Responsibility - SE
label | 3bb580dd-1937-5150-b195-b6863138ccc5 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Thermal Differential Monitoring
label | 10c56024-3e2d-56a8-9264-bf951dd9e175 |  | note | Reference - 610.22
label | f354c98a-0861-58d1-bf27-f63d57c8b0d4 |  | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints. Attach: Thermal Monitoring Report
label | 5789d657-d010-5e56-8624-16f786619708 |  | note | Method - Document Review
label | 7d4c31f2-c837-5afd-9d10-b7ec8adfd6a1 |  | note | Frequency - Where applicable, each element
label | af02e5d4-b22c-5301-9dac-b90f382eb5c4 |  | note | Category - IP
label | 5895347f-ce7a-526e-a2da-1426d7930fb2 |  | note | Responsibility - Foreman SE/PE/SPE
label | bb27bb5f-8372-5a0d-a70e-a1c81ff015ce |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
label | 73e8ec76-980e-5c07-94da-ee220a835c56 |  | note | Reference - IFC Drawings
label | 7d28667a-ead0-5708-8ae0-0d9bf286ff15 |  | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 9164f8ea-7361-5daa-81ea-919af1980ab8 |  | note | Method - Document Review
label | 02316d14-06c1-564a-a951-dba0ea5c5c16 |  | note | Frequency - Where applicable, each element
label | 13719a54-2220-5786-9a1f-b093e3dfe6cf |  | note | Category - IP
label | 13980211-aabf-5c97-abd3-deed0294a19b |  | note | Responsibility - Foreman SE/PE/SPE
label | 568745ef-39f7-557e-8616-f2a529639fb6 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.3 - Surface Inspection - Cracks
label | fe5ec126-bacd-55bc-a97a-5233f04130cb |  | note | Reference - 610.24
label | 3b657d28-8625-5c44-b6fb-b6cefc1c808f |  | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1) If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair. Attach: Post-pour Checklist
label | ade551e2-608c-5a69-8b8f-2d02fe369949 |  | note | Method - Visual Measure
label | f86da82b-bb4a-5ddb-ae4f-953d8e036ba6 |  | note | Frequency - Each element
label | 815874de-dc30-5858-aa34-3e07b1b4b3cc |  | note | Category - IP
label | f800e79f-5e67-5f95-b26f-897ec5de8728 |  | note | Responsibility - SE/PE/SPE
label | 8ab0d78e-a4f6-53c5-b931-c45c0d5e5361 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.4 - Surface Inspection - Surface Finish
label | 2ebdccea-19d9-55b5-b1d2-40a4a97b8cdf |  | note | Reference - IFC Drawings 610.31 (a) - (n) 610.32
label | 25424a33-a334-5c33-bc2d-89381f8ee200 |  | note | Acceptance Criteria - Comply with the IFC drawings and specifications. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair. Attach: Post-pour Checklist
label | 43377be1-5fbb-54a6-b8c4-40d11d0c0a0b |  | note | Method - Visual
label | 8efb1338-d924-58d8-9732-1365943f0036 |  | note | Frequency - Each element
label | 856bda69-aa42-5ba5-9f3a-8e7dc18747c5 |  | note | Category - IP
label | c49d4421-4389-5412-ac80-94558ddf1511 |  | note | Responsibility - SE/PE/SPE
label | e3d5b81f-b312-5476-af1e-7888feb60120 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.5 - Measurement of Concrete Cover
label | 669507af-275b-5c36-8fdc-1cba47c20fbf |  | note | Reference - 610.34
label | 7064b917-02df-586a-bc36-df09734b2c7a |  | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area. Minimum 10 no. measurements recorded in each area. Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority. Attach: Covermeter Check Record
label | ff911b46-d8fa-53c7-9e6c-87d7a4e25b1e |  | note | Method - Measure
label | 5b2822ff-1754-5674-bf6e-17f729cf353a |  | note | Frequency - Each element
label | fa219d24-2cad-58b0-8f3b-f1c1a847063a |  | note | Category - IP
label | 46412833-1ca2-5d8e-b1f6-714e2bc1e33c |  | note | Responsibility - SE/PE/SPE
label | 71faffb7-ae5f-54b5-9f13-f9f1656de7c2 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | 37a5317b-da01-5f29-8315-74e43d878764 |  | note | Reference - Placement of Fill Material Against Concrete 610.35
label | b598f4ff-841c-5be1-ba1b-7176fb8d1f57 |  | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour. Proposed placement of fill material against concrete prior to 14 days from casting shall comply with the early application of loading requirements as per VR610.16(l) or maturity testing requirements as per VR610.16(m). Attach: Concrete Test Results or Maturity Test Results
label | 36cc2882-23a6-5745-8029-50a564c3daf9 |  | note | Method - Document Review
label | 4b33a6a2-8a6d-5d96-b1c7-66a1a3092641 |  | note | Frequency - Where applicable, each substructure element
label | 31fe6c82-0d5f-5240-a564-67f795cc8891 |  | note | Category - SP
label | ff3fba5e-556e-5ada-88c8-3c0c2b4ec50c |  | note | Responsibility - Foreman SE/PE/SPE
label | 35d365ba-f707-5882-808b-04984df130f2 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.7 - Compressive Strength Test Results
label | 751caeac-6bd4-5b1f-9182-be1575ab072a |  | note | Reference - IFC Drawings Table 610.05.051 610.16 (g)
label | 9c431492-7d3f-55d1-81c4-4a6e598d4379 |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results
label | 37371031-ea59-5ee6-aedb-8a95af2d9817 |  | note | Method - Document Review
label | e331b9cc-3427-585b-b74c-beadbe289fa9 |  | note | Frequency - Each cylinder
label | 83f94358-0df1-596e-b4df-ab4695db92e9 |  | note | Category - IP
label | aa76bdb3-1f65-57ed-967a-3397d54c892a |  | note | Responsibility - SE/PE/SPE
label | e28bd86c-0a9d-5b0c-94a9-ac5e3dd099ef |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.8 - As-built Survey
label | be5e5621-44db-540a-8d66-4e7771f6428b |  | note | Reference - IFC Drawings 610.47 Table 610.472
label | 9c44c529-de07-5c25-a8b0-4d65d9ab7481 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element. Attach: Survey As-builts / Survey Report
label | 81ed64f3-7bf5-5de6-9e10-62057627d3f5 |  | note | Method - Document Review
label | 46c3e00f-210a-5b68-ba6e-565de02248db |  | note | Frequency - Each element
label | 439667f9-bd8e-54e2-bfe7-4fa8bf531df2 |  | note | Category - IP
label | 94cb8565-a0d4-5dea-816f-088d3cde89eb |  | note | Responsibility - Surveyor SE/PE/SPE
label | 3735b127-6757-5cd5-ae3e-49455d426593 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
label | 8f780748-2b7f-54b9-8ed7-11d4f3c81d59 |  | note | Reference - MRPA Quality Management Plan
label | 4dcee724-5247-5abb-a82d-bc843105d0ce |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 6ae15404-8b4a-53e8-8cad-87888fd5cf06 |  | note | Method - Document Review
label | 4429dd24-6f70-58f3-b683-0cd66acc088e |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 83188ce6-da23-5d7d-86a9-8f356d50aec8 |  | note | Category - HP*
label | 062fdf13-150d-5dfd-b79d-fd15e9cfaadc |  | note | Responsibility - SE/PE/SPE
label | bfac8609-f59f-5ecb-b168-24dd00f2141a |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | Final Inspection
label | b93b4bf0-ba64-59d3-904c-8682a7fc8f08 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 5869039b-5b46-5e16-ba36-92bca989c4f6 |  | textbox | Print Name:
text | 736ff85c-25b3-5b69-a890-bc69071408dc |  | textbox | Position:
text | 236e24a3-75c5-53a1-9d3c-e75f83ac52a2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-029-CIV-Brunt-Concrete Bus Bay |  |  |  |  | Yes | ITP-029-CIV-Brunt-Concrete Bus Bay | 7b04372d-fcd1-47de-9e8e-92dedac0ea69
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | caf9db12-2018-5750-8479-565821ebf315 |  | note | Document Title: ITP-CIV-BRUNT-Concrete Bus Bay
label | 411b6ec1-f607-5295-8af6-0851cff9b0d6 |  | note | ITP Description: BRUNT-Concrete Bus Bay
label | 3c9d0224-2f34-582a-87b6-abd5ea9a23c7 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 1bf9a3f1-2282-58a5-bc5a-aebe52a4467e |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 1e71785d-f8fb-5629-894c-0c48ba86d218 |  | note | Revision Number: 0
label | 922a279d-b268-5e01-9fb8-fa540481b9bb |  | note | Revision Date: 28/02/2023
label | 386e9fbd-ec37-5fc6-a3d2-75cf56ff5e0c |  | note | ITP created by: Jason Lee
label | 38a9b04b-acc2-54ae-b888-2a7f753671e8 |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | edef361b-85f5-5412-a5ff-d11c0b85ed1b |  | note | Reference - VicRoads Section 204 (Dec 2015)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | fe81b397-87f4-5da9-924a-6375168e4fc9 |  | note | Reference - VicRoads Section 173 (Oct 2008)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | cc6d33fb-9970-5873-93a4-c4e463c4da87 |  | note | Reference - VicRoads Section 306 (Feb 2023)
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 1400856e-20b4-5f43-8a07-b546c5816211 |  | note | Reference - VicRoads Section 610 (Feb 2020)
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 60e60bc0-dcc6-5f1b-95e8-254f6311ab98 |  | note | Reference - VicRoads Section 611 (Nov 2018)
checkpoint-status |  |  | checkpoint | 1.6 - Non Dependent
label | 7bfff9c1-5727-5208-ae94-b3c82af0e5c3 |  | note | Reference - IFC Drawings
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance - Subbase
label | 4c956041-cee8-513d-b408-7d36227e36d9 |  | note | Reference - Section 306.04
label | 0f08c28d-58a8-547a-bad6-56c1f636d241 |  | note | ○ Section 815.04
label | bf82a309-4200-5ef6-9165-fba6a5885c4d |  | note | ○ IFC Drawings
label | f760ddf3-1c3d-515b-bc54-a3d11bbd1756 |  | note | Acceptance Criteria - Cementitious Treated material shall comply with the requirements of Section 815.
label | a7c5505c-22ed-5751-b436-a4243d6867b4 |  | note | ○ CTCR mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02
text | 65b68e7c-7cba-5000-8974-e3625612abc8 |  | textbox | Enter: Teambinder Material Approval number
label | bfbbcd95-4894-55cf-b1c4-7c4d07745642 |  | note | Method - Document Review
label | 05387843-24af-5e06-9723-e8e97d5f6f12 |  | note | Frequency - Once, for each material type prior to start of works
label | ad41da11-c5e4-5ca8-939a-23473c30ec0e |  | note | Category - HP
label | 7bf5ce3e-e748-5edb-975f-648c4e743c32 |  | note | Responsibility - Nominated Authority
label | 10f6ea35-b18f-5180-b57f-ee0362f98a65 |  | note | Verifying Documents - ConQA HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix
label | 7148111b-7121-5f9c-9728-798d48484e5d |  | note | Reference - Section 610.07
label | 85709d76-7734-50ef-ba6b-a6e68750138d |  | note | ○ Table 610.071
label | f9ed9eed-11a3-59e9-9a48-d290829e0a64 |  | note | ○ IFC Drawings
label | a6018a0e-7a05-5d16-84e2-9ba760b24582 |  | note | Acceptance Criteria - Contractor shall submit to Superintendent the concrete mix design for approval 4 weeks prior to placement of concrete.
label | 98e8edb3-ca08-50ff-9740-b780980fe580 |  | note | ○ Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
text | 04d6f6af-3cd7-5285-b7e4-c863e2c7f857 |  | textbox | Enter: Teambinder Material Approval number
label | 8b17784f-37f1-5514-a9ba-ac4ec3508425 |  | note | Method - Document Review
label | e0919b8b-98cf-5e1c-b337-7372b2d21103 |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | 83242421-05f7-5ef0-bbc3-93b52548dd60 |  | note | Category - HP
label | 78902225-1448-5e36-9fda-959b26fe6f3e |  | note | Responsibility - Nominated Authority
label | 6352b70a-d392-5763-8df5-90cdc1a96d80 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - ACRS Certification (for Reinforcement)
label | a0a5d962-3baf-5384-8cea-dcf691937be1 |  | note | Reference - Section 611.05 (a) IFC Drawings
label | 2565475e-2548-5a2d-90f3-6aa80b05b4a0 |  | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
label | d303cfb0-2ead-5249-8cde-36f3323a4523 |  | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 199e9db4-5548-5100-8424-04c70947a048 |  | textbox | Enter: Teambinder Material Approval number
label | 8e81a99f-5d1e-5c7f-bc8a-9a944c65a7d1 |  | note | Method - Document Review
label | 43c16cdf-63b7-508a-8bef-23d4b304e651 |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | a4863fab-0d63-58fa-a272-03044bef21dc |  | note | Category - HP
label | 137ae5b5-0b54-5496-8424-5b583c43961b |  | note | Responsibility - Nominated Authority
label | e1c217ce-f7f5-5726-bc62-6417e5e63601 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Curing Compound (where required)
label | 80e514bf-917b-5167-9ba3-adcbeb6a5589 |  | note | Reference - Section 610.23 (d) IFC Drawings
label | b2c576be-7abf-52e8-b7bc-4dcebc1fd07d |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 46dfec42-3e3e-53dd-92ce-617cb5ddda2c |  | textbox | Enter: Teambinder Material Approval number
label | f32b40e3-8f95-5b97-9f04-dfa8fe68d1ba |  | note | Method - Document Review
label | a85fafbe-8ab9-5bc6-aae6-ea706bc873d3 |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | a40a9a01-7171-52bc-b45f-bc640144a5fa |  | note | Category - HP
label | c0282d51-27ff-5dfe-9461-2077eaebb229 |  | note | Responsibility - Nominated Authority
label | afdb636f-d818-5963-8ef5-5a8e40dca864 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - IFC Drawings
label | b3681098-cd40-5c21-8c29-de690581d7c9 |  | note | Reference - MRPA Quality Management Plan
label | f56ab2cf-4c6b-5e62-90ed-7b04cf043e23 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | bac24401-a4dc-5fba-9727-8e74d231aa4e |  | note | Method - Document Review
label | dee57f30-a1a4-5ab5-a192-ea585f7771b3 |  | note | Frequency - Prior to starting Works and at regular intervals
label | 013b3700-fe0c-563e-8411-7c884d94c709 |  | note | Category - HP*
label | 644a8ddb-8567-5d5f-94b0-226b34a1d8fb |  | note | Responsibility - All
label | 3df17921-7b28-5c2a-99e8-12b5f7c01269 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 3.2 - Curing Method
label | 4e4e63d8-4631-58af-9a9b-f522e5cc79b4 |  | note | Reference - Work Activity Pack / Works Procedure
label | efc22851-143f-5de0-ae68-44337ea97463 |  | note | Acceptance Criteria - Contractor shall submit to the Superintendent for review full details of the proposed methods of curing, as part of the concrete mix design submission, not less than four weeks prior to placement of concrete.
label | 711e7e2c-0046-5566-8d6f-66f6c8fa77d9 |  | note | ○ The Contractor shall not proceed with the placement of concrete until the curing method(s) has been reviewed and approved by the Superintendent.
text | 25fa41d4-8928-5509-b02b-6560729233aa |  | textbox | Enter: Teambinder Hold Point Ref No.
label | 11a9aaca-a2ae-5fa1-900f-b68c02f6b469 |  | note | Method - Document Review
label | 7da243b7-ab19-5df1-9167-365b88169386 |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | ffa80ee6-9685-5835-9cde-257d315ebddd |  | note | Category - HP
label | 8d86ae73-e02b-5d01-a89c-146968149ba9 |  | note | Responsibility - Nominated Authority
label | fa25f054-4fe8-5b71-94f0-ce56d7ff1a95 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out
label | 109bcee5-6efe-5f2a-a199-1bd2e7309e5d |  | note | Reference - IFC Drawings
label | 2dc038bd-7f87-5ac2-935d-9b6fb4dac946 |  | note | Acceptance Criteria - Area has been set out in accordance with the IFC Drawings.
label | f28904ba-0011-5989-9cd5-c260621dbe15 |  | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | a2d00555-3449-562b-a01a-38f7942d0372 |  | note | Method - Verify
label | 562dfa34-d3c6-5a84-87d9-8e26a20030fa |  | note | Frequency - Prior to commencement of excavation
label | 299ef434-dcb4-5871-83fe-9511be3d3f1b |  | note | Category - HP*
label | 983744d8-aec4-5c3d-b86d-3756c3340879 |  | note | Responsibility - SE/Surveyor
label | f66086fb-07d8-58c9-b8f7-3ae1ac2157b3 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Inspection of Subgrade Material Subgrade Material Properties
label | 27256ddf-bec6-52ea-a642-31d42309f2b7 |  | note | Reference - Section 204.06 (c)
label | 04f75cce-81d2-568f-9fba-3948a2a0b0bb |  | note | ○ Section 204.06 (e)
label | f48079be-11ab-5b4d-82e7-afcf404c2950 |  | note | ○ IFC Drawings
label | f83e3305-5ac7-5290-9cd2-2d1b3761edda |  | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | dd207e00-4ff8-5d81-9150-e1d31fa6aa67 |  | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | 1543ff6d-0b32-5939-ae35-eba76677c165 |  | note | ○ Assigned CBR ≥ 2.5%
label | a4979506-9bf4-59ad-a7ff-8ac72858b93b |  | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
label | 0785c31b-e7f2-5931-b85e-c0e1e1fd75d9 |  | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | 6263951a-93c5-56cf-98ca-e3dfb320fc80 |  | note | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
label | 8ee6880f-3e91-56b1-a24a-f01336628f7e |  | note | ○ Attach: Laboratory testing Verification:
text | cc0adc2f-1f24-576a-8655-e7d4203e43f4 |  | textbox | Enter: Type A fill Lot Number:
label | e8b1cc2f-3bf8-5e48-9388-3abf340d7451 |  | note | Method - Verify-Document Review
label | 3ec8fee5-4fe3-5702-82c7-fc87e8b6d6ef |  | note | Frequency - Each lot
label | 03a0c186-6618-5134-b0ca-238c4ffbfafb |  | note | Category - HP
label | 8ff8e024-d050-5f91-a39c-545d43933496 |  | note | Responsibility - PE/Nominated Authority
label | 956dd7e5-7171-523d-8a9c-71ae2d9161ae |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Material classified as Silt - Subgrade
label | 54c3241d-8dfc-50fc-bdce-eecfb1958fa4 |  | note | Reference - Section 204.04 b)
label | f2c82231-b2dd-5462-8869-ac54430cf833 |  | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | f403cc26-f4fe-5030-b4f4-1631dc9f6d3a |  | note | Method - Document Review
label | 40cd4aea-a43a-50fb-b835-29363bbdb6e1 |  | note | Frequency - Prior to commencing
label | cd0cfa96-a511-5fde-9b05-5172ec553c72 |  | note | Category - HP
label | c6110036-9414-5e87-b955-5648f087cbbc |  | note | Responsibility - SE/Nominated Authority
label | 86fc36ba-78ba-5ecc-9feb-94bb14b57ea2 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable) Subgrade
label | 0f90d9a1-07e8-5379-ba21-45391290ef7d |  | note | Reference - Section 204.06 (f)
label | 2555fc5b-985d-5d68-b42a-1cf37ed755fa |  | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | a9529f2b-6872-5f1a-a035-f9c1159fdaf0 |  | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | fb1fec35-270f-5bfa-99e1-8c1f0ed424dd |  | note | Method - Site Inspection/ Document Review
label | 85df7d4a-3de7-5810-a2e7-248a6916cb2d |  | note | Frequency - Prior construction of the regulating layer
label | 072ae39e-4519-57bd-96ad-df56098af0e2 |  | note | Category - HP
label | a97d530f-3275-5a13-8c90-e9891a698c5f |  | note | Responsibility - SE/Nominated Authority
label | 8cde1718-6e4d-5825-91f6-3e337ac5f5a7 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Unsuitable Material - Subgrade
label | 6c27cee8-abf5-5d59-83cf-4cc059fa44cf |  | note | Reference - Section 204.07 (d)
label | 0f074b48-917b-5f9f-ad50-aa000b675010 |  | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | c8864228-5773-511d-99e0-119f61d75f9d |  | note | Method - Visual inspection
label | 11b746b7-bca5-5e63-ae80-f2417c860002 |  | note | Frequency - Each lot
label | 8e779b8b-4fd2-5200-b13b-aea80d32bdcf |  | note | Category - HP
label | 8712d6d5-69cc-5bf2-a528-c4da247f9288 |  | note | Responsibility - SE/Nominated Authority
label | c166706f-cbcf-5bb2-81a2-b4d6f0a3b3fd |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Groundwater - Subgrade
label | 60d4a694-a9ea-5103-90cc-ea66e6cc8a9f |  | note | Reference - Section 204.06 (h)
label | 9250ec9a-7607-5b96-9192-5d737c3ddf9d |  | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | fdd53b23-05ef-5b40-aae0-04dd7bbdc3cc |  | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | 0f6fd019-09b0-57ac-a27e-a0dce53e672d |  | note | Method - Visual inspection
label | e73fa3f7-02ce-5f87-9ff1-b8cc3482ceff |  | note | Frequency - Each lot
label | 0d597a40-20af-5a07-a395-9fa8c7da113d |  | note | Category - HP
label | c07c6b72-548a-5e75-8e75-350a558733a4 |  | note | Responsibility - SE/Nominated Authority
label | c8315728-fd9d-5aa4-864e-ce81a56bc2b5 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Cut to Fill Zones - Subgrade
label | 3f2b269c-a77b-5ab2-af59-0a8100b4fd28 |  | note | Reference - Section 204.06 (g)
label | a832284e-e20f-5c84-bf32-43481992de01 |  | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | d39978ee-ec1d-5942-9df8-c034e8b33610 |  | note | Method - Site Inspection
label | 6a0e7c76-7881-5b13-92db-7f79d30dda23 |  | note | Frequency - Each lot
label | 2045e013-f45f-595b-93cb-42f3b79d561b |  | note | Category - IP
label | 694798ad-9ca7-5c8d-8414-36a8d1ae656d |  | note | Responsibility - SE/Site Supervisor
label | 8fd40f2b-b1e0-5393-bfe8-cbf268d3bbb8 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.7 - Proof Roll - Subgrade
label | 85522c6c-7845-555a-9045-d64149ff6e30 |  | note | Reference - Section 173
label | cb28fb58-ae76-519e-9ed8-35fa86fd4853 |  | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification.
label | 2c951033-e2d5-5dfb-a166-25c543e5c264 |  | note | ○ Attach: Proof Roll Inspection Checklist
label | 795bc2c6-9970-5753-aa70-a29d60868fb2 |  | note | Method - Visual inspection
label | a7f62046-d4bb-530c-8a05-c4879e28d01d |  | note | Frequency - Each lot
label | 15fce067-ef0b-5c94-b7c2-6a7c27041053 |  | note | Category - HP
label | 6b589ef1-b238-59ed-987c-65a4b004b517 |  | note | Responsibility - SE/Nominated Authority
label | 73b6f83f-e7ae-52b1-99b0-6defd25008fe |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 - Compaction Testing - Subgrade
label | 830b47c4-7f47-500b-a251-6928e61623aa |  | note | Reference - Section 204.13 Table 204.131
label | bb9e27ce-858d-5c6e-ba36-d66d8a452f47 |  | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | c45275dd-997a-5e63-9b24-713f4bd31e92 |  | note | ○ Ripped and re-compacted material below Cut Floor Level
label | d6e8bcd2-8051-53a6-9f6b-4fde0d45dbea |  | note | ○ Scale A: Characteristic Density Ratio 99%.
label | f88ed07e-3770-525b-a915-8d1db189520f |  | note | ○ Scale B: Characteristic Density Ratio 98%.
label | 2d94a38b-76a6-5725-9f2f-72465ab6dc2b |  | note | ○ Scale C: Mean Value of Density Ratio: 100%
label | e9278444-6cb5-5505-8d12-dfe5d46a40e5 |  | note | ○ Attach: Compaction Test Result
label | 8d9edd84-4c0c-534b-b5fd-fc7a39486b7a |  | note | Method - Document Review
label | 9d3a94f5-5590-5d3d-814c-960c4633a1c1 |  | note | Frequency - Each lot
label | ae2b712e-50c6-5315-93ee-40e6c333b4bf |  | note | Category - HP*
label | 1f6f7520-889b-5982-91f7-a441bccb3586 |  | note | Responsibility - PE/SE
label | 9b13259e-795c-513b-b154-5e1171dde4ca |  | note | Verifying Documents - ConQA Hold Point Release
checkpoint-status |  |  | checkpoint | 5.9 - Post Compaction Material Property Testing Subgrade
label | 39844e27-d52c-5000-b4ef-a7d14c358aef |  | note | Reference - Table 204,041
label | 3e6dec71-2932-5fd9-be21-9e73a81c244e |  | note | ○ Table 204.141
label | 3f274020-2f88-5c8b-8c1d-b8f347922054 |  | note | ○ Section 204.14 a) or b)
label | 6bb06da9-2b6d-5c2b-a0c3-9cfd02d5cd01 |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | 9c80d35a-a637-5985-bfe8-53120f1a9e17 |  | note | • CBR ≥ 3% and Swell ≤ 1.5%
label | ed26261e-90c3-5d1a-8344-7e848baddbf8 |  | note | • Max Permeability = 5X10-9 m/s
label | 8395085c-0b4f-5758-bf94-957d309d8ce3 |  | note | • Grading: 75.0mm 100%
label | dda184db-ff6f-5392-9b38-043bb985b25c |  | note | • 4.75mm 40-80%
label | a2f4030c-2507-5716-be3d-d774a8f34f05 |  | note | • 0.075mm 10-40%
label | 1e45dc2b-87a2-5066-bed8-c0ff92454f21 |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 95176f6a-9ff7-5714-a678-07762256d646 |  | note | ○ Scale A:
label | ac4e0572-cd9c-5c49-a5a7-7a05dadbbb30 |  | note | • CBR & Swell
label | 8b1e2deb-db78-564a-b766-b7117c155e9f |  | note | • Initial - 1 Lot Test to determine Assigned CBR and swell
label | fc04549e-3617-563e-b481-2628a4a61b04 |  | note | • Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | d9c94ed4-a23d-5771-9a5d-3089b4020cd8 |  | note | • Max Permeability
label | 4cd69abe-32fe-544a-865b-ff53b1b6d1c2 |  | note | • Initial - 1 test per 2 lots
label | 6efef97f-d05c-55eb-b87c-39c4e135289f |  | note | • Reduced - 1 test per 4 lots
label | b9399688-349e-5bf7-8325-79a238d42706 |  | note | • Grading:
label | 77591a59-8032-5f6d-ae13-68965d4513a6 |  | note | • Initial - 1 test for each lot tested for compaction
label | ca6ba866-1df1-5ac0-808b-117176caf46b |  | note | • Reduced - 1 test for every second lot tested for compaction
label | b4de1358-a734-5c04-9fa0-fc02d1b77401 |  | note | • Max. PI x%Passing 0.425mm & PI
label | 99e06d6b-8586-5fe7-979f-e3c7987b0348 |  | note | • Initial - 1 test per 2 lots
label | f6bb2e15-da14-59a6-8c95-09786cf7ecd7 |  | note | • Reduced - 1 test per 4 lots
label | 1d883054-2e45-5408-a9c2-8392141506c4 |  | note | ○ Scale B:
label | dcdb0b38-0e38-5258-9e83-85a1c0d387bd |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | d98f0934-39a1-5992-a3b1-fd50f3bb70e3 |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | fff2839b-a7cc-5388-beb5-7df599d3201f |  | note | ○ Attach: Post compaction test results / Attach Material Property Test Report
label | 91370acf-7647-54c8-8cca-233ce8137c85 |  | note | Method - Review Document
label | 2d715851-4804-5634-a6c4-700b1d6f6a9f |  | note | Frequency - Refer to Section 204
label | 10b93fca-1290-531e-91ae-a3fa4292ac9b |  | note | Category - IP
label | f4380798-678f-577e-9480-98732a7a912b |  | note | Responsibility - PE/SE
label | ce59f910-41fb-51e5-91c9-68874f73d936 |  | note | Verifying Documents - Sign ITP
checkpoint-status |  |  | checkpoint | 5.10 - Test Roll - Subbase
label | 967d7bab-a5e0-5b9b-9f8a-5d57c19afa8a |  | note | Reference - Section 306.10
label | c765a610-9dff-5c5b-8151-823c2e6597a6 |  | note | ○ Table 306.091
label | e038db28-54ba-5661-9c15-db53f68097f9 |  | note | Acceptance Criteria - Shall be test rolled in accordance with Section 173 within maximum allowable working time for the relevant binder and time of year as specified in Table 306.091
label | d3e20825-9212-5bcf-8938-fab2e53d10b7 |  | note | ○ Table 306.091
label | 2200545e-9bd9-5446-ac16-813db23f9302 |  | note | • Type GP - 2 hrs (Oct to Apr), 3 hrs (May to Sep)
label | 61ae5483-d56e-5877-80bd-9326c23de667 |  | note | • Type GB - 3 hrs (Oct to Apr), 5 hrs (May to Sep)
label | 8f0acf05-2794-58a0-beaa-afc77380d7c6 |  | note | • Slag/Lime Blend - 8 hrs (Oct to Apr), 12 hrs (May to Sep)
label | b4308e16-25fb-5bb0-b2d2-1fcd2b752f33 |  | note | Method - Testing
label | ebefb6b0-529c-581a-869d-c187cc9e15a7 |  | note | Frequency - Each Lot/Layer
label | 17ac3fc0-cdb6-5a90-9083-afe2a0973836 |  | note | Category - HP
label | 52f7b98a-e40f-5c1c-ab1a-a48f5681e8ca |  | note | Responsibility - Nominated Authority
label | 21a1552a-0350-5b49-8dbc-c4b779ce7df5 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.11 - Compaction Testing - Subbase
label | dc832e6b-3808-5066-9119-03344780e903 |  | note | Reference - Section 306.09
label | 799519d2-c3e7-51c9-90e4-ba3dbcbb446e |  | note | ○ Table 306.091
label | 762f6072-3d63-550e-8b47-58aa7f9c19e1 |  | note | Acceptance Criteria - If the Contractor proposes to use an alternative cementitous binder to those included in Table 306.091, laboratory test results shall be produced to the Superintendent showing that the binder satisfies the required working time determined in accordance with the VicRoads Test Method. In addition, the cementitious treated material using the alternative binder shall meet specified strength requirements.
label | ff55c439-a399-5ac4-bce3-6d69aa1c6e89 |  | note | ○ Characteristic Value of Density Ratio
label | 8438a92a-a17f-5fc3-821a-9093819aa850 |  | note | • Scale A - Not less than 96%
label | 2cbd5e9f-ad52-5340-942e-9d1e9694eb8d |  | note | ○ Mean Density Ratio
label | afeb0a1b-7f9b-5dac-8338-822516cc85b9 |  | note | • Scale B - Not Less than 96%
label | 65b9f80a-6b35-5f6a-a3dc-eaa25b133127 |  | note | ○ Attach Compaction Test Report
label | fc7f2520-5f8f-5b00-bb15-f8261fe1161b |  | note | Method - Review Document
label | c5d0d187-6557-5af1-8fca-c647e6fbb577 |  | note | Frequency - Scale A - 6 per lot, Scale B - 3 per Lot
label | 737b80a3-6463-59d4-a3a1-b7adfb9dfcdf |  | note | Category - HP
label | ec6ec993-ab55-5f08-a3fb-7116baedec3e |  | note | Responsibility - SE/Site Supervisor, Superintendent
label | a7bcae4a-ead5-56b8-8a01-55f5682eeac4 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.12 - Reinforcement Placement - Base
label | ecf9502f-1157-598a-9aa4-69e5ab79c417 |  | note | Reference - IFC Drawings
label | 84556406-ebbc-52d3-8abf-481b2ab01288 |  | note | ○ VicRoads SD 2071
label | 962d5ec9-169a-5134-be0f-5b3ecc9c81ae |  | note | ○ Section 611.06
label | ea8e669e-ea90-5606-96fb-40a2e9318a4e |  | note | ○ Section 611.09
label | 24959be5-92f7-5787-a201-703ec9ecc55b |  | note | ○ Section 611.10
label | 8718ae74-4180-5727-a35f-f868ab56d627 |  | note | ○ Section 611.11
label | 9e116de5-4aa5-5bd8-be92-b4e234052e47 |  | note | ○ Section 611.12
label | 7efc634b-d302-59df-ab4a-bab94738a5c0 |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the drawings.
label | 472b9b59-8d02-51d8-9ae8-4eb5c995abf3 |  | note | ○ Projecting reinforcement is the correct length and location.
label | 9d1c05d1-e0c8-5108-940d-4e70dff47c59 |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | 6f4cf99a-b077-549c-8c7f-5d16001b9b90 |  | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | ae21b4d9-5080-5541-b612-56cad5e2ede4 |  | note | ○ Minimum cover as shown on the drawings for each face has been achieved (including tie wire locations).
label | c37f20fc-9c5c-51aa-8e14-d2e572a1420a |  | note | Method - Measure, Visual
label | e8e50829-c6c8-59f2-8422-128e8ac57e52 |  | note | Frequency - Each element
label | 6ab8dcdf-4926-5b4b-b3f7-f4f2ea32d129 |  | note | Category - IP
label | 64b78505-86a5-5ae9-bf23-33dbe9e1ceec |  | note | Responsibility - Foreman, SE/PE/SPE
label | dc22e4c8-6fb7-5089-815b-683a9c854403 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.13 - Pre-pour Inspection - Base
label | a32e2e7e-595b-5c94-a5fa-2f130e15afd8 |  | note | Reference - IFC Drawings
label | 741c118c-f557-50ad-b177-7e27d4ab262b |  | note | ○ Section 610.18 (a) (ii) & (iii)
label | f0fb1b98-6f9d-5ce4-89f7-88bf46836472 |  | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 3a1c623a-5a22-5a9e-a770-4a60df6f64ad |  | note | ○ All foreign material has been completely removed from the forms.
label | b1df940f-a69a-57f0-99f1-dcd4c275f5f1 |  | note | Method - Measure, Visual
label | 6c6c658e-7c90-5934-bb50-b2ddb8b204f7 |  | note | Frequency - Each element
label | 3db5a9db-ce3b-56cc-b2b7-2a76c11b4479 |  | note | Category - HP*
label | 07014d9f-5f05-5a19-9821-c8f30045caac |  | note | Responsibility - SE/Site Supervisor, Superintendent
label | 5bb883be-bc7e-5af8-bff6-e8261221aee4 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.14 - Weather Conditions & Evaporation Limits - Base
label | 592c33ff-ec10-5e44-bb3e-4acf40032e8b |  | note | Reference - Section 610.17
label | 4e5409d0-49b0-570f-a619-6099548d9ef9 |  | note | ○ Section 610.17 (a) & (e)
label | 80938f8c-60de-567c-a068-e5120dbf521d |  | note | ○ Table 610.171
label | 9ca51774-01b1-5b29-b5c4-69d69b78609c |  | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | f0d3547d-992a-5df2-a655-fc7374040754 |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 76b278ac-77ca-57f6-b7e6-5b8c9e8d2d1d |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 960125e4-ca19-5cb4-a17d-69f4804762de |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | ca9d5847-9ce1-576b-9212-34058f01e8fd |  | note | ○ Record: Required information on the Concrete Pour Record.
label | b866aace-d854-545b-8797-12e3b04da5d2 |  | note | Method - Measure, Visual
label | f06753fa-b011-553e-8463-90e41070013c |  | note | Frequency - Each element
label | 9c8f4b28-183b-5725-b216-c220927c8654 |  | note | Category - IP
label | d275f000-83b5-5fbe-959b-032ca3c3b8c1 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 534bf274-303f-5a20-8a63-b068cdfb88d5 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.15 - Concrete Testing - Sampling Frequency - Base
label | e6d72e43-77d5-5f54-a143-1be4fc44458a |  | note | Reference - Section 610.16 (b)
label | 9628b2c4-a514-58b4-ba06-fbac01a2a454 |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | b428e355-2fab-5b4d-ad8e-38e715ee7993 |  | note | • 0m³ to 10m³ = 1 sample
label | e6e5eaf0-f86b-5e5f-9f04-1743375c070c |  | note | • 10m³ to 25m³ = 2 samples
label | 9cfa3145-34a6-5255-aad0-f57764a7eb5a |  | note | • 25m³ to 50m³ = 3 samples
label | 545f7875-4675-55b5-88b4-a08abdc595e2 |  | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 248a7a5b-3985-504b-a03e-55daf3f4ccde |  | note | • For each additional 50m³ and additional sample shall be taken.
label | 58cb67ee-18f4-5a86-a6f6-c8fc9f89d8b4 |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 3b415adc-2af1-5473-9e5b-25cef850f5e8 |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | da28969b-91bf-5a52-b6a6-07633e328405 |  | note | ○ Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | 23f57939-3df3-5aba-b610-60934d05110d |  | note | ○ Record: Required information on the Concrete Pour Record. Qty of samples taken
label | 2f92ee87-cd85-5830-be10-f3230c944d86 |  | note | Method - Testing
label | a1e77885-7df8-5568-9d45-ee5a88b163ba |  | note | Frequency - Each element
label | b53f36a0-57cc-5572-ae39-cefe066e7720 |  | note | Category - HP*
label | 88e69a7b-5dca-5774-8453-ff4933810c0d |  | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | 34d5593e-01fc-5d5a-850c-fdcad9d9cb72 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.16 - Concrete Testing - Slump - Base
label | 29a8ce74-cd4f-5b48-a043-de1b59ec33f9 |  | note | Reference - Section 610.16 (c)
label | 385241b8-9e7c-59f7-b126-4a18e66bf73b |  | note | Acceptance Criteria - Slump testing tolerances =
label | 7d069a5e-3fd4-5dd5-9bc2-8fe0022e8bbc |  | note | • <60mm = ±10mm
label | 7078828c-f1c5-5a9d-8ace-5986bfc76d84 |  | note | • ≥60mm to ≤80mm = ±15mm
label | ec1921a5-77d8-5434-a2e0-06c3d7fb1fcf |  | note | • >80mm to ≤110mm = ±20mm
label | fcfa5596-25fd-5d4e-abd7-d7678ef76305 |  | note | • >110mm to ≤150mm = ±30mm
label | b7edc4d9-38b1-5cee-8133-238f6d67e740 |  | note | • >150mm = ±40mm
label | cb8da4cd-4414-5b97-9d44-ff7f39f93728 |  | note | ○ Record: Required information on the Concrete Pour Record.
label | c8055676-30b2-5cb4-b4fa-7d1ba5501c1f |  | note | Method - Testing
label | c6f45d40-df2d-59d2-8e20-7b98690425c2 |  | note | Frequency - Each sample of Standard or Superplasticised Concrete
label | dd4da5ef-358c-5450-ab8c-0da343525b4d |  | note | Category - IP
label | e5a0733b-7be5-5c16-92a2-ee935bdd492b |  | note | Responsibility - Concrete Tester/SE
label | ff01d2cd-3c71-5f11-8cba-5ddf88a26d0c |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.17 - Concrete Testing - Spread, Passability & Viscosity - Base
label | 89d6d38c-f829-5154-84af-d7102e269707 |  | note | Reference - Section 610.13 (b)
label | fda8f12b-b951-5f93-8b85-13e72236b885 |  | note | Acceptance Criteria - Spread range = 550mm to 750mm
label | d617ef23-011a-55a8-86a7-d9e82753e868 |  | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 153b5924-c167-5526-afbd-6fee9f45130f |  | note | ○ Passability = ≤10mm (aggregate height differential)
label | d06f332d-2eee-54ce-b61d-21f63f8dc3ef |  | note | ○ Record: Required information on the Concrete Pour Record.
label | 657d6fb6-ed82-5b06-92f8-e6cd46bf032a |  | note | Method - Testing
label | b75e22fd-9243-558b-9d19-7dde7427dd99 |  | note | Frequency - Each sample of Self-compacting Concrete
label | 32d5ba1c-a139-508b-91b5-fbc4bb41590e |  | note | Category - IP
label | 34eb1525-cff8-5b36-bcb9-b64687658787 |  | note | Responsibility - Concrete Tester
label | cc230a73-5be8-545c-95a5-0cacfa1cef4e |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.18 - Concrete Testing - Compressive Strength Cylinders - Base
label | 84585246-2beb-5517-ac11-8933ba3f9684 |  | note | Reference - Site Sampling & Testing Procedure
label | 7d73eb57-fb64-5159-88df-80d323f22cb0 |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | 506370cb-f8c9-5893-8cda-63ad276d4051 |  | note | ○ Record: Required information on the Concrete Pour Record.
label | 263d4651-89cc-5ce7-8a8a-a75911d8ed76 |  | note | Method - Testing
label | c05ecc31-ffac-592a-ad8e-f7c58137ffe2 |  | note | Frequency - Each sample
label | f3833984-7026-5642-9b30-a984a2b99b57 |  | note | Category - IP
label | fdfd1b4b-8c3f-576b-b160-577824fb79e6 |  | note | Responsibility - Concrete Tester/SE
label | 21929ddd-f350-50f2-8e1e-75e9bc6fac2c |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.19 - Supply & Discharge Rates - Base
label | 7765e00d-f314-5fa4-ac98-3d03f74cd3fe |  | note | Reference - Section 610.13 (a) & (f)
label | a6d7580c-c703-5f14-87e8-ac7ed1005a4d |  | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | e51207c7-b770-5016-b411-edf750097df7 |  | note | ○ No water is to be added once discharge commences.
label | 208be9fd-d1e6-5699-99fd-457fd79d139b |  | note | ○ Maximum time between batching trucks is 25 minutes.
label | e1a307b1-4197-5f81-967b-90e43f26442a |  | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | ea7346e5-468a-54e1-b001-015278744176 |  | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | efbacd5d-83bc-56d9-823b-be1e245e22f5 |  | note | ○ Record required information on the Concrete Pour Record.
label | c1661ea2-9a18-5267-ba43-25b15c69a323 |  | note | Method - Measure, Visual
label | a35586b3-9c8f-5416-b1d5-e2b6bc1be65f |  | note | Frequency - Each load
label | 857e62b9-b881-53a2-9b05-28fab3f06319 |  | note | Category - IP
label | 12652a5c-b679-5271-a595-e87e8b4b841b |  | note | Responsibility - Foreman, SE/PE/SPE
label | 567e8383-ccb3-575a-8124-7b5913249f5a |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.20 - Placement & Compaction - Base
label | dda55b0a-5ac0-51ee-8013-0813cc3bb7a0 |  | note | Reference - Section 610.18 (a) & (b)
label | fd909993-80f6-5b78-baf7-392240928ee6 |  | note | ○ Section 610.18 (d) (i)
label | 5483a4a4-4196-5b57-99a9-8d3235c66e3b |  | note | Acceptance Criteria - All concrete batches are traceable.
label | a2e66e68-48b3-521e-8af3-8cb2ccd8c38b |  | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 86b1c074-3e6f-5ab5-964d-13028369cb27 |  | note | ○ Concrete is not dropped freely from a height exceeding 2m.
label | f537f6ce-0f02-5045-a81e-74a4c2173f43 |  | note | ○ Concrete is not moved horizontally by use of vibrators.
label | 72338c08-67ef-54ed-9ae4-417fa8765436 |  | note | ○ Adequate compaction is ensured
label | fa67ce1a-a5ae-5a8b-9819-2bbd99666268 |  | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | 60023424-591b-5939-a95f-2d996c9b98ca |  | note | ○ Concrete layers are not more than 350mm
label | 54fc84e0-4d78-502b-8721-cf680e495487 |  | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | 3ffe9ea3-b656-5760-8561-75586a70f707 |  | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | afc9dc01-ef3a-5b27-926a-0aef966611df |  | note | ○ Record: Required information on the Concrete Pour Record.
label | 1c92950b-9583-5bab-b398-1364a9e0bf2d |  | note | ○ Attach: Concrete Pour Record
label | 7f405dbb-cfad-5ec2-ab60-bbaff8b3b2d8 |  | note | ○ Attach: Concrete Dockets
label | 60a1b87f-aed2-56fa-890d-dced2573ae43 |  | note | Method - Visual
label | 4cf5b9a3-0cf9-5699-86ce-636e86136f8c |  | note | Frequency - Each load
label | 48d22fba-aac1-5a04-9145-9a908dfdd1cb |  | note | Category - IP
label | a2f50d53-cf88-5313-9813-c354ccb57691 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 6864a1a7-3682-5d40-a852-f89d5f4dd3a9 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.21 - Surface Finishes - Base
label | a528f7ce-cc44-5e54-810d-0f2cd6a262dd |  | note | Reference - IFC Drawings
label | ca4c567b-790b-594e-8528-57df1dd33c4e |  | note | ○ Section 610.31
label | f923951d-8f97-5d03-bd35-161cdfd132de |  | note | ○ Section 610.20
label | 12173215-14c2-5b52-91db-2b496e30b8f3 |  | note | Acceptance Criteria - Surface finish as per IFC drawings.
label | 3bba3c90-7a8d-5b65-8ab2-99fe8859840d |  | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 117dc360-4e00-50fc-b497-3ac67f1927ee |  | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 49ea6395-d9bf-5fec-90a3-7e077844382b |  | note | Method - Visual
label | 92433ff8-5ad9-5938-97d1-ed26ec0ff1cc |  | note | Frequency - Each element
label | 5bd1c430-498e-5fa3-9f8f-1e8e562e1966 |  | note | Category - IP
label | 93c7c50b-78a5-546e-a305-317bb9a07d69 |  | note | Responsibility - Foreman, SE/PE/SPE
label | fb31029b-a91c-5ab9-9552-781613cdceb0 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.22 - Curing - Base
label | d9b58ab2-1ff9-5a9b-ae77-ceb4c09f5ea4 |  | note | Reference - Curing Methodology
label | b881c6fc-f625-558d-9c64-49848e88a668 |  | note | ○ Section 610.23
label | e0d69eb6-0ab2-5ef3-9b40-ad4ba8431e9a |  | note | ○ Table 610.231
label | 1dd114fd-ef70-507f-94b0-96f6132c806a |  | note | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | 325a795a-587a-5a9f-9aa0-0aa08a6c6014 |  | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | 8054a731-b4fc-5d64-8409-ffca3a34aadb |  | note | Method - Visual
label | 78aa4486-169e-5c15-ad2b-a3ec9d7f41a9 |  | note | Frequency - Each element
label | 49c18bbb-e24b-5804-80dc-0bf8f6821543 |  | note | Category - IP
label | 0b419ffe-ab4d-508c-83dc-8d2fb7f8f6fb |  | note | Responsibility - Foreman, SE/PE/SPE
label | 1c49a50c-998d-5b58-8b81-e09c87e7df0a |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 6. Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Survey Conformance - Subgrade Prep
label | 1f460ff3-fb91-5148-909c-8d8cb239b346 |  | note | Reference - VicRoads Section 204.03f,g and h
label | 16f6a8aa-8f2d-512d-92b8-be397795cd77 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 7d8fcab7-c159-539f-9a2c-74d71ac23674 |  | note | ○ Level tolerances (Scale A):
label | 8c8a52af-a907-5bcc-bed4-75ceaf6c43f3 |  | note | • Range x = +5, -15mm
label | 068a6e8c-c6f1-5c61-87f3-8913068dc448 |  | note | • Max S = 12 mm
label | cec24779-165b-58d7-91a3-8341f52753ed |  | note | • 80 measurements per lot
label | cef49d7d-94e7-59ce-a5fa-f33c69e8e286 |  | note | ○ Level tolerances (Scale B):
label | 7cc7d0b3-90f4-5619-b330-6dd25f1c24ed |  | note | • Range x = +5, -25mm
label | 384b398d-6c4c-5126-b64c-45052411f263 |  | note | • Max S = 15 mm
label | 5d704266-42cb-5f1e-ab98-3b0220ea8db7 |  | note | • 40 measurements per lot
label | 593a1a25-dcf3-533c-a84d-352f722c0a5e |  | note | ○ Level tolerances (Scale C):
label | 397ca26d-2aca-5cfc-91a4-cdd7a87bc4da |  | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | b62dacb7-ee24-5812-9202-cf40b043cdfb |  | note | ○ Attach: Survey Conformance Report/Data
label | ad44e58b-eb36-573d-9b81-4641ec4bb8f5 |  | note | Method - Review Document
label | 63549c1d-b0eb-5193-abf9-a7ff02c1a7ca |  | note | Frequency - Each lot
label | b7d97d94-3311-557d-8e8e-893f8f10793e |  | note | Category - HP*
label | 34d68fd9-2d85-5d19-8439-eec3fa19b984 |  | note | Responsibility - SE/Surveyor
label | e344b488-6059-54e4-9d80-e074f9224975 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 6.2 - Survey Conformance - Subbase
label | 5c61ebdc-a250-5e86-b9d7-14b37b9b783c |  | note | Reference - VicRoads Section 306.03
label | 7171dba5-a434-5b3d-8d4d-80968e373e40 |  | note | Acceptance Criteria - Level tolerances Scale A:
label | e7f864ed-a8d9-5643-9f62-773bc8794b9d |  | note | • Range x = +4, -8mm
label | 19b09fc7-3435-5535-814e-24c8979c2e27 |  | note | • Max S = 8 mm
label | a938fad8-accd-5dd7-b9e0-affac9b8699e |  | note | • 80 measurements per lot
label | 4bbb25f7-f1a3-517e-8980-8f61dd2bdd4d |  | note | ○ Level tolerances Scale B:
label | b577c215-124a-579a-81e6-83cfbc8cc91d |  | note | • Range x = +6, -12mm
label | 71ccbfc4-23cf-532d-aed0-e8f0fc2e3af4 |  | note | • Max S = 13 mm
label | abca4921-df1c-5efd-a38a-4970ed6f0277 |  | note | • 40 measurements per lot
label | 3a9349d4-0def-5947-be63-65586ef63a55 |  | note | ○ Level tolerances Scale C:
label | 7d8dd630-9429-51f5-a71e-e76504c79bc7 |  | note | • No point on the subbase surface shall be more than 10 mm above or 25 mm below the specified level.
label | 88214201-e46e-57b3-91b7-782afda4f87e |  | note | ○ Attach: Survey Conformance Report/Data
label | 551fd600-8c00-553d-973f-35d0a43d969e |  | note | Method - Document Review
label | 8bd32c52-f438-51fc-bb80-3503fb3cb734 |  | note | Frequency - Each lot
label | 25bfe88d-0778-5982-adad-4310e4916dc5 |  | note | Category - HP*
label | 3dc77001-95eb-5700-87f9-c9557129ba0c |  | note | Responsibility - SE/Surveyor
label | 6f5a577c-4dc3-5da1-9c38-e0bd3100b7d6 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 883d7109-fd3c-5a9d-91cf-317127f4eb20 |  | note | Reference - MRPA Quality Management Plan
label | d75d29e3-a7b9-5761-b983-959b5e0aabae |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
label | 027c7a79-ff4e-51a9-b03e-b19b42eb53b1 |  | note | Method - Document Review
label | 16eb7c17-efe1-5ad0-82dd-0136a4761b54 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 92c21fce-1dc3-5a1b-8cad-9f6310b494e8 |  | note | Category - HP*
label | 0e4aee27-fcaa-5250-8953-b747772b0696 |  | note | Responsibility - SE/PE/SPE
label | 87ae1cfd-fbf5-5834-9983-21fa91459970 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 6.4 - Surface Inspection - Cracks (Concrete Base)
label | 8700f7dd-2292-5250-b75d-cd68c1ac7f27 |  | note | Reference - Section 610.24
label | a8d92ecd-12f6-5049-a18a-412af24cc16f |  | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
label | 5881ddfa-e240-50f1-9206-02634702de2e |  | note | Method - Visual, Measure
label | 9285caf2-2da1-5537-95d9-e1a694d44852 |  | note | Frequency - Each element
label | 2d2eca1b-8b8d-54c9-9975-201e2f4f13f3 |  | note | Category - IP
label | 9bdd13a1-418b-5fff-93e2-d6c6aa8bff5e |  | note | Responsibility - SE/PE/SPE
label | eed839b6-3f87-5a8a-8568-37cae59db177 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 6.5 - Surface Inspection - Surface Finish
label | f67f9754-e07f-5754-ba79-4dbd7bbd1bb2 |  | note | Reference - IFC Drawings
label | 545c572e-3dae-565d-bb56-68f186604278 |  | note | ○ Section 610.31 (a) - (n)
label | d050bd7a-9656-5132-b975-f58eefea106c |  | note | ○ Section 610.32
label | e4cd17ca-7de9-5c8b-bf09-72f7dd93fbba |  | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
label | 37266cf6-ec08-5381-aa4a-31065ad026e6 |  | note | Method - Visual
label | 4f3168ff-fc06-55eb-b9a9-07b521585533 |  | note | Frequency - Each element
label | 7669a9c3-9384-5d5b-bb24-6313785edf4c |  | note | Category - IP
label | 04cab9a1-9de3-5655-bc91-2845423f5a90 |  | note | Responsibility - SE/PE/SPE
label | 60c3db65-63a2-597c-bc07-6bcfe359ed95 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 6.6 - Measurement of Concrete Cover
label | 227cfd5d-0687-591f-9f71-6feeb9751113 |  | note | Reference - Section 610.34
label | 1e84bd84-ba49-5035-97ca-d63b7ca06fe9 |  | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | 8a3adc6d-b2e3-591e-8949-f5985b57ed72 |  | note | ○ Minimum 10 no. measurements recorded in each area.
label | d55f8a5d-8029-581a-9885-60ea84930fd9 |  | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | 94ea4c2c-7be9-548b-873a-b3abea6a32f8 |  | note | ○ Attach: Covermeter Check Record
label | f69ddaac-ac96-57d3-83df-af9c0cf80517 |  | note | Method - Measure
label | da5d7cda-9165-5812-899b-843a83a58c30 |  | note | Frequency - Each element
label | 982a9050-650a-51cc-9c58-6a946276218f |  | note | Category - IP
label | 7f988c66-b9a0-5738-b5b2-c88b458363e9 |  | note | Responsibility - SE/PE/SPE
label | 8754e88e-8506-5c0d-8773-870f4aa805b9 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 6.7 - Compressive Strength & VPV Test Results
label | 8315ab84-c22c-5d15-88bd-c924f68a8631 |  | note | Reference - IFC Drawings
label | 7a4cbe18-3d68-5cdb-be1e-030b03ec22f5 |  | note | ○ Table 610.051
label | 2eba627b-25d4-56b8-b12e-f5fafdc3a1cc |  | note | ○ Table 610.061
label | baad0e74-2451-5e77-a20f-befeef22b795 |  | note | ○ Section 610.16 (g)
label | 848338a5-a889-59ce-b563-5d7b2a521a46 |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 5fed2ad6-ce71-5a96-b514-a5536c608974 |  | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength and VPV results comply with table 610.061.
label | d9476344-2d41-5895-96dd-320a713d844f |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 31759d6d-b6ed-56ae-b2b0-a9940ef2b8b2 |  | note | Attach: Compressive Strength Test Results
label | f00bca8a-9865-5fa6-83b6-51462bd46a0d |  | note | Method - Document Review
label | 5477df40-c573-5a1b-a574-8891195d80ca |  | note | Frequency - Each cylinder
label | 13267daf-d60d-5adc-a6da-39490483c9e0 |  | note | Category - HP*
label | cdf1be92-c65d-5616-8f6b-5f385b4315b1 |  | note | Responsibility - SE/PE/SPE
label | 691c8a71-a32d-52f5-9ff9-ad33a0df1c21 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 6.8 - As-built Survey
label | 10422342-97d2-56d5-a144-1ae200e531c4 |  | note | Reference - IFC Drawings
label | 01165553-f8a9-55dd-83e0-1eee042564dc |  | note | ○ Section 610.46
label | 0026d87a-6fa2-5ee2-b113-93296788b249 |  | note | ○ Table 610.462
label | 90b788ed-8c8e-55dc-b3ae-aacb73dea5fa |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | b598a992-672c-5769-855c-0782c2d5fcb7 |  | note | ○ Attach: Survey As-builts / Survey Report
label | 7ca5d50d-b32d-564d-ab9c-eb3ac2ded0b3 |  | note | Method - Document Review
label | 0e8f30dd-f993-5486-a2d2-dbb8564b2dc6 |  | note | Frequency - Each element
label | c96a8c36-19b8-561d-a8f1-2c6f8988b2a9 |  | note | Category - HP*
label | a16a9d03-44fe-521a-a7ab-e5dc238affc9 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | b0ae07c6-3e97-5582-b066-db57532df8e9 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | Final Inspection
label | f4fc45bc-2812-51c7-aeef-4d330c90b5d9 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 193573d6-f80f-5f79-9510-ca8d1fbd4cd2 |  | textbox | Name:
text | fb762a41-ef5c-5468-9d65-ba5c3ce1aae9 |  | textbox | Position:
text | 026b5584-561c-5a57-9665-32cf20b67fad |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-038-RAIL-Brunt-OHLE Wire Regrading | itp |  |  |  | Yes | ITP-038-RAIL-Brunt-OHLE Wire Regrading | 7cc87bbd-e73b-4f28-ac06-a447742d9afb
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 0de47312-507d-5ed3-9788-ea6c5c2d4da6 |  | note | Document Title: ITP-038-RAIL-Brunt-OHLE Wire Regrading
label | 3c7f90e2-8980-5d9c-8a18-eac590d0cc42 |  | note | ITP Description: OHLE Wire Regrading
label | 2b58d7d9-d139-5b10-9f2e-01d5073c77eb |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | be489d5b-9540-5aef-b609-28ea07e93919 |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | faf86eaf-fe46-591f-92f3-4a2f2b64d99a |  | note | Revision Number: 0
label | 51491dca-fd5f-5100-b381-bb3662bf3c31 |  | note | Revision Date: 16/05/2023
label | d0f4a1df-8361-59ef-ad1e-e96a10b4b016 |  | note | ITP created by: Nikhil Siram
label | 64753031-4ba2-5cd2-911d-306a0ac3ff60 |  | note | ITP approved for use by: Kevin Liang
checkpoint-status |  |  | checkpoint | 1.1 - Overhead Line Electrification
label | 7c6cc7eb-3837-53a2-b9d5-3b2a0edaaeda |  | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint-status |  |  | checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 753988f1-ce1f-5c9e-8693-5628f562c419 |  | note | Reference - VRIOGS 001 AS 4100
checkpoint-status |  |  | checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | 07e93314-1f55-537c-9203-4e1cdc8cffe2 |  | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Procurement Materials delivered/collected to stores/Site.
label | 7202f173-3c3e-5f40-9fd4-ea93d8d97c0a |  | note | Reference - Contractor - Site Material Control procedure.
label | 4a173b72-4131-5292-9e42-5c3eb3e5190f |  | note | • Cat5 Material received - Brunt and Camms Tracking sheet
label | e0ff0d10-b6c0-5fce-99f0-817725aeb9c4 |  | note | Acceptance Criteria - Ensure materials are delivered/collected as required.
label | 39059d4e-8f70-56a3-a692-4e9bbaf2cc56 |  | note | • Certificates of Conformity provided by MRPA
label | 91e03e61-97b7-5301-b561-3840a860025f |  | note | Method - Document Review
label | c723753d-62cd-5cf2-9876-9080f8c9595c |  | note | Frequency - Once for each supplier, prior to works start
label | da2927b8-8963-53ac-ae64-193b21e36b22 |  | note | Category - IP
label | 2a0f34f3-498b-5b47-be95-d19b2aaf1036 |  | note | Responsible person - MRPA Engineer
label | c171e223-f382-5675-9318-242641a742da |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Produce Work Package Plan
label | 00271e6d-79b3-5ec3-b207-80d8aca140a0 |  | note | Reference - Work Package Plan WAP_BR_184
label | 1abde248-d5dd-5ad6-8657-6ed508d50247 |  | note | Acceptance Criteria - Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
label | e8972752-28fa-59d0-b3b9-3aef27665867 |  | note | Method - Document Review
label | 52216cc2-83e1-5ad5-b939-ba7458623be6 |  | note | Frequency - Prior to Works Start, TBC in accordance with MTM Standards
label | ba4a677b-35db-5a0b-93da-dc32b19ac5a5 |  | note | Category - HP
label | 326247ea-3f1b-51f5-9b28-7cf381de16c9 |  | note | Responsible person - MRPA/CAT5 Engineer
label | f7e6f9a1-b9e5-59ae-be39-e884a5cbb825 |  | note | Verifying Documents - This ITP Signed Off
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Approval of IFC drawings
label | 1a8a870a-6829-55b1-88c9-ce0abb0c294d |  | note | Reference - Contractor Design Management procedure. MRP-DPK-089-00-ETN
label | 553366c3-d6dc-526f-bc81-0c0b65a5fd96 |  | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 25da1b89-68a1-54d1-8dec-fe01c23aee36 |  | note | Method - Document/Drawings Review
label | bc730528-aac9-5e7d-9d84-c041356744d1 |  | note | Frequency - Prior to Works and at regular intervals. TBC in accordance with MTM Standards
label | 8b34c9bd-300f-55eb-afed-5335b4dea4cd |  | note | Category - HP
label | 75689d22-5b58-5f53-9330-5630ed16ed44 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 63143b2c-551e-5a8f-acfb-867939ed19c7 |  | note | Verifying Documents - This ITP Signed Off
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Task Specific Permits
label | 55d44a38-c9c9-51ae-95b7-c26482a6f80c |  | note | Reference - Working at height permit. Hot works Permit, Permit to dig. OHLE SWMS
label | 1c38b6f5-8cda-5b58-bded-cdf9c833bb85 |  | note | Acceptance Criteria - Ensure all task and activities have relevant permits issued and received.
label | 7f32e4be-b37d-57e5-aa09-ea49131d87e5 |  | note | • Task Permits to be generated and signed off by appointed person.
label | c246c46d-b4c7-5ef3-82cd-849c5eb85e47 |  | note | • Task specific documents - MTM to issue permit to enter/Isolation permits etc.
label | dda9e8f7-77a1-533d-9426-f750b3f74376 |  | note | Method - Visual, Document Review
label | 5c819c1b-59dc-5541-b719-79eb0d580c05 |  | note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards
label | 48245370-9101-59c9-981e-3389d89b2f60 |  | note | Category - IP
label | a72b1b45-6bf8-5b3b-a3d7-b72494200c6d |  | note | Responsible person - MRPA/CAT5 Engineer
label | db7308f4-05a9-5ea8-9eda-4674270e0f70 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.3 - Cantilever assembled.
label | ca84a1fb-4cb0-5a70-bd0b-9d3ca5fe8d69 |  | note | Reference - Cantilever assembled as per IFC design.
label | 7d50ef61-5de5-5a63-9987-c8dccbfe1c60 |  | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | 2ab2fc8f-4a1a-5644-b249-a6364fd1ba4b |  | note | Method - Visual, Document Review
label | 46cefae2-86c4-5d23-8cef-a68edcb7ff10 |  | note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards
label | 4abb2602-439c-51d6-92bf-0b6ad6c1c7f6 |  | note | Category - IP
label | 2394a8a7-b0cc-5aa7-8035-d1b77d5b3d54 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 8b081b4e-c8bd-5c93-8562-7912579e0233 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.4 - Pre-Installation check
label | 12eeca52-3c46-5e61-a93d-053ef20e3b20 |  | note | Reference - IFC wiring layouts, IFC cross sections and BOQ. Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
label | fe0e7c5d-f09d-5969-9e7f-380b0225d9f8 |  | note | Acceptance Criteria - Ensure that locations matches most relevant IFC drawings
label | ae467d31-12c4-5d17-9ecf-c2da1632fcf9 |  | note | Method - Visual, Document Review
label | 75043ee9-219c-57c0-be3b-084c3a3f9132 |  | note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards
label | 05f3b3dc-0dda-55a3-a1e8-4612895fbe93 |  | note | Category - IP
label | e26f5e7c-6a17-57d4-9249-d79c3e3add7d |  | note | Responsible person - MRPA/CAT5 Engineer
label | b1553a9a-e57e-5ca1-8361-914884546dd6 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Cantilever installed.
label | bf11e6e1-2a73-51d7-a588-f38d5dea66fe |  | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | 5df2179e-76df-5461-89f7-8651140ed22a |  | note | Acceptance Criteria - Work instructions in accordance to IFC design
label | 1e1c9b1d-0363-5ac1-afe2-eb8ffa961d06 |  | note | Method - Measure, Visual
label | 2c76d2c3-2c64-5761-bc7e-2e20b90fddb8 |  | note | Frequency - Each OHLE Structure
label | c7b167bb-a6b0-5bc1-9266-304216a1307d |  | note | Category - IP
label | 9ee53310-b1a1-5093-a742-b028ff09b54a |  | note | Responsible person - MRPA/CAT5 Engineer
label | 3b119a73-4366-5f35-b77a-463c906d951f |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.2 - Install SPS to correct height / position relative to track
label | 246b499c-5e2d-50cb-a1bf-afc5232d08ce |  | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 991d03a2-f3f7-5a47-9796-03ee4863e3eb |  | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range.
label | 4c15efab-a234-50cb-a4a2-3acd0ebb81d4 |  | note | • Supervision / checking to ensure that equipment is installed correctly.
label | 74cc6f13-761c-55eb-a717-3f16a4f07281 |  | note | Method - Measure, Visual
label | b20b7925-b652-5fa6-a351-155c08f3e6a0 |  | note | Frequency - Each OHLE Structure
label | d3205a6c-17cf-556e-8a2e-04700037e9d2 |  | note | Category - IP
label | 7a593682-05dd-5f7b-b797-c660527ab432 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 0cc332cf-11e0-516c-beec-136636aff87d |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.3 - Cantilever checked once installed.
label | c0025b36-90bb-5128-a5b5-400f28c437aa |  | note | Reference - Cantilever checked as per IFC design drawings/MTM design range.
label | a4dba3e0-d66e-5267-94d2-5d48fa47dc9d |  | note | • Completed check sheet. CAT5/OHLE/CHK002
label | 5413d3fc-ebf3-518b-978f-d18d511b73df |  | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
label | 397b9682-7eb3-547a-8c86-70aaf6100dc9 |  | note | Method - Measure, Visual
label | 72c7db37-a5c4-552d-8458-261cd5895049 |  | note | Frequency - Each OHLE Structure
label | 65822c87-5b92-5efb-9a96-8937c724ad26 |  | note | Category - IP
label | 2ba2ee78-5265-51ee-ab3b-50a55d22261f |  | note | Responsible person - MRPA/CAT5 Engineer
label | bb448425-d995-56c1-8983-7e79023abbc7 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.4 - Installation of wire supports at the correct height and stagger.
label | 746443a0-cbe7-58dd-bd6f-cc74b4c36b28 |  | note | Reference - Install as per design drawings.
label | 71c05836-df10-562d-94d2-cd9b689e8bfd |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | 1848125a-9ab8-56c7-8105-d38210155edf |  | note | Method - Visual
label | d980bbf6-b711-5924-af9d-1a8f0791646e |  | note | Frequency - Each OHLE BWA structure
label | ed9cf684-cedc-503f-a6ba-bff2f2459f8a |  | note | Category - IP
label | 238da381-7d45-5f94-ac26-486af50135bf |  | note | Responsible person - MRPA/CAT5 Engineer
label | 9e596ae9-4ef8-52e2-9aaf-a707d53d4026 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.5 - Installation of small parts
label | 205ef441-5a5c-5b3e-91e4-0e604289dc0a |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | 4423e5f5-8380-514a-8cc6-227db2359a4a |  | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | efb9ba0e-1894-5da3-a6d6-51fdfe220796 |  | note | Method - Measure, Visual
label | ebfc7377-d480-5ceb-bacb-5da4f937d487 |  | note | Frequency - Prior termination
label | 08dd5aff-c8ed-5b95-b7fc-28c787705f49 |  | note | Category - IP
label | f9064340-2834-5865-94a7-b9582e1e2d2e |  | note | Responsible person - MRPA/CAT5 Engineer
label | 5dd56a71-8fd5-5a96-8fcd-24a75d588a8e |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.6 - Complete Clearance Checks
label | fb56f735-2b38-5790-94de-e61ec67a13e1 |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | d0d1c656-650c-5dfb-b95a-cfa8d2ab3fc3 |  | note | Acceptance Criteria - Visual inspection for clearance and wire staging from Hirail EWP
label | 05e10a61-aa61-58b3-b2a1-d6f6780d020a |  | note | Method - Measure, Visual
label | 7c6ca83c-c794-5ed6-bfa1-c7c355f4cb08 |  | note | Frequency - Prior termination
label | 86aaa4a7-6ff3-5bdd-bf11-b856526617f5 |  | note | Category - IP
label | 674fc628-7c15-5e3e-b13b-cea98914339e |  | note | Responsible person - MRPA/CAT5 Engineer
label | 5e65eef1-27f2-57c3-a42c-2664de6bee22 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.7 - Complete Pan Run Test
label | 3f1362f1-9c04-5417-ba2a-bf94b9a0d940 |  | note | Reference - Install as per design, use span/ambient temp. tension charts.
label | 58aed145-9fe7-5ccc-b0a2-b0c237649e59 |  | note | Acceptance Criteria - Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
label | a5872029-2871-5e8a-85ad-6e15dc885a3c |  | note | Method - Measure, Visual
label | b4a51d72-ba11-5ccc-8845-cf7e4cd1171a |  | note | Frequency - Prior termination
label | 01c8c2be-b28f-5165-a986-b305946de7e9 |  | note | Category - IP
label | 4e2ec300-1568-581f-a41e-32223be3140a |  | note | Responsible person - MRPA/CAT5 Engineer
label | 90124b4d-280b-5977-9f0c-e7df9ed6b4f9 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Defects/Temporary Works
label | f170923b-d7e2-5e37-a98b-6ea0740a4dbf |  | note | Reference - IFC wiring layouts, cross sections and design drawings.
label | 31f97a90-5ef4-58be-8f4d-7137ce337568 |  | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
label | 89365b30-6360-50da-8d95-8840cc80dc84 |  | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | 76dc76b5-c250-5f64-9d12-859e0616f063 |  | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | b42e09e0-e2ce-5624-83d7-7d597ab32e1b |  | note | Method - Document Review, Visual
label | 052a8f92-e608-5a16-890b-5d5c28735a25 |  | note | Frequency - Each OHLE Structure
label | 3902bf27-2db6-5f2d-a04c-7a1c0afed6c0 |  | note | Category - IP
label | 6f19a318-59ce-5127-8a6f-3d684451f970 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 5cb0a103-b4b7-5774-ab38-8d23f39de1a7 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
label | 7c5dcc2f-54bf-5ff1-bf81-59f0bd483c57 |  | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
label | 29b7b095-278e-533f-b458-ab70e5cb492e |  | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
label | 11b4fc20-41f1-53bb-b500-7a5988c8a93a |  | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | 4b83be60-75c0-5b13-be31-8806f75a0b8c |  | note | Method - Document Review, Visual
label | da08ec12-ac2e-5b0d-9c67-6fcf8afcc3f3 |  | note | Frequency - Each OHLE Structure
label | c236780e-771e-5ff2-b976-4b335614688c |  | note | Category - IP
label | 2ac64e0a-adb2-5593-909d-3512b0bde8b2 |  | note | Responsible person - MRPA/CAT5 Engineer
label | f84011ea-74bc-5d32-a6c1-d9c08b980ea1 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 2c36b3e8-bb8f-59f5-89ad-e93da7181fab |  | note | Reference - MTM Quality Management Plan
label | 2f949301-71ac-51a1-94b5-f293a1307a6a |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | dd435533-64db-59d0-9272-2f2df24a2b61 |  | note | Method - Document Review
label | 6e6573be-d8a8-5d3f-8507-bd262580f250 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | f1b535c4-ac93-596b-998f-6c939863ee89 |  | note | Category - HP
label | c02290c6-9c2c-58e8-9a8c-0ee822470a49 |  | note | Responsible person - MRPA/CAT5 Engineer
label | 1ebf1882-4eb5-5ac2-95c4-db5bd4562cd1 |  | note | Verifying Documents - This ITP Signed Off
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 445b13e1-680a-520a-92d3-5f677bdf993f |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2dde5716-4b43-58d4-a576-b43028bba46e |  | textbox | Name:
text | 8b6b65cf-5e02-594d-b1af-c3e4d1626d6a |  | textbox | Position:
text | 8dbd467d-7286-580f-9210-5a96cea5ceb7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-022-CIV-BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS | itp |  |  |  | Yes | ITP-022-CIV-BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS | 8b3c83f4-9492-4b34-974e-01c36b4b52b5
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | bb58bdfa-4120-5ad2-9c3c-ea12decbd2c2 |  | note | Document Title: ITP-CIV-BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS
label | 508d739b-0428-5786-b6a2-2324fdf08065 |  | note | ITP Description: BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS
label | b5d53ed2-76de-5868-a604-34ba51eed229 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | af41fadf-b378-5b72-a6b3-d74b37e4a522 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 593917a4-bd96-5872-b49e-e55615ac2fb7 |  | note | Revision Number: 0
label | 12864ece-51e4-531d-af25-dea021f6cec7 |  | note | Revision Date: 28/02/2023
label | 3112fbd5-2352-524a-94fa-fa07363b3ef5 |  | note | ITP created by: Jason Lee
label | 6a158d1b-553a-5d68-9e18-fa57deb033c2 |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 3d626682-501e-5091-b26a-f911b15d9d6a |  | note | Reference - VicRoads Section 204
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | b6c9a89a-d9e2-5fce-87b6-3e9b8b4ce26a |  | note | Reference - VicRoads Section 173
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | c3f1a1c5-fdc2-51ad-8238-48311eade7dd |  | note | Reference - IFC Drawings
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Non Dependent
label | a7738ac7-d205-596c-96cf-be00246c449c |  | note | Reference - N/A
label | 2b875782-377d-5ece-9af8-5ea21e0ec665 |  | note | Acceptance Criteria - N/A
label | 7ea0bdeb-5398-55fb-9a93-3bbe5ffdb8cf |  | note | Method - N/A
label | fb5210b6-82a1-5837-8eef-3c8bb4b0c1b0 |  | note | Frequency - N/A
label | 9faa04f5-ce46-5a4f-a43b-932195a47531 |  | note | Category - N/A
label | deef606b-1d3a-599b-b842-17cf36010848 |  | note | Responsibility - N/A
label | 36478e73-3df7-5da8-81b5-90b82a60fb48 |  | note | Verifying Documents - N/A
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Non Dependent
label | 226b6ad5-c3d5-55f9-9b5d-0b8ecc0ff33d |  | note | Reference - N/A
label | f1dba21b-817a-538c-b918-11d3af342ead |  | note | Acceptance Criteria - N/A
label | 1db13ed2-e1e4-5a6b-beec-d0661d29ffdb |  | note | Method - N/A
label | 6f232d0a-cc0c-5858-96b0-2d33c4b26ceb |  | note | Frequency - N/A
label | 53730b95-bb82-5365-ba16-f1fd2e1dddcc |  | note | Category - N/A
label | 8dd23b29-48ea-584d-b3b8-6bc292b82369 |  | note | Responsibility - N/A
label | b454a5f6-bd6c-58c3-9ef8-e5407d586335 |  | note | Verifying Documents - N/A
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out
label | 018e5cc8-29a6-5f1d-9e0f-acd0d655ba97 |  | note | Reference - IFC Drawings
label | a55e3b75-c1d1-5062-b183-47c5367293a1 |  | note | Acceptance Criteria - The Area of Excavation has been set out in accordance with the drawings.
label | 621a270d-f986-56c8-8c7a-f4dd7c4409de |  | note | ○ IFC Drawings with work lots marked-up attachment required
label | 5c346335-e18c-527c-a008-b713b518bab8 |  | note | Method - Verify
label | cc42a24e-630e-5a47-897d-61bde68a2e06 |  | note | Frequency - Prior to Commencement of Excavation
label | 0abd0a1e-5de1-5772-b643-e84f9eb53569 |  | note | Category - IP
label | 3c1c2e6e-5869-509b-8129-0117e8a1097d |  | note | Responsibility - SE/Surveyor
label | 66be2e1f-4be7-5514-bb08-1611b690e9e3 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 4.2 - Material Classified as Silt
label | bfea54f4-2e2c-5b2e-8a32-c0dd4f9c854b |  | note | Reference - Section 204.04 (b) - Table 204.041
label | 169a9f7c-a3de-5fd1-ac7d-c159df3b2294 |  | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
label | 92d28415-883f-5f38-9b97-325360126453 |  | note | ○ Type A Material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | 93819912-66fa-5767-aa18-4f90c0bb46f5 |  | note | ○ Superintendent satisfied with stabilisation
label | ff91152b-af6c-555f-af68-110d95eec4db |  | note | ○ Attach: TeamBinder Material Approval Ref No.
label | 31fc819c-6119-57ce-9277-e34836ccb198 |  | note | Method - Document Review
label | 906bb5c9-ebc9-5f33-87b4-bf9854484eb0 |  | note | Frequency - Prior to Commencing
label | 7f4f2d70-a8d5-5425-9193-6af766f21d83 |  | note | Category - HP
label | dddf4b23-986e-5a8f-8021-141969ec1b73 |  | note | Responsibility - Nominated Authority
label | 2a302808-5e46-524e-b371-0dfa0ca6495b |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Subgrade Material Properties Inspection
label | 38d53059-0d3c-5ceb-81ed-fe01858e15a2 |  | note | Reference - IFC Drawings
label | caf337eb-314d-527b-bb51-5f9b41e79ed4 |  | note | ○ Section 204.06 (c)
label | cbb97342-52a6-527c-9ed3-5ec5266c2f3a |  | note | ○ Section 204.06 (e)
label | 452a6488-adee-53b5-846c-dd10e6662501 |  | note | Acceptance Criteria - Section 204.06 (c)
label | df98b1b1-fc91-5461-9667-1d8db9b9b69b |  | note | • Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04 and Table 204.041
label | 1ba5b4ff-1574-5cc4-8e6f-a5f2b50eb04a |  | note | ○ Section 204.06 (e)
label | 7e15d369-7f79-5238-a8eb-9cecfce0b782 |  | note | • In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | 96eda9c3-e9f9-5b83-adb4-e86ec0695a0f |  | note | • Assigned CBR not less than Type A material and shall have swell less than 2.5%.
label | 81cf8b92-ee12-5903-8bc1-7d78684ec20b |  | note | • If parameters are met, rip and re-compact to a depth of 150mm.
label | fbca6f52-1ed7-5f9f-81e1-843c862839be |  | note | • If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | 0f901ee5-1773-5f9c-bf1e-ce694967d78f |  | note | ○ Attach: Laboratory testing Verification
text | a72ee641-a577-52fe-a643-d3d9578d7c9d |  | textbox | Type A fill Lot Number:
label | 4b9201b6-36fb-5e5a-a028-8bc4d78bcb18 |  | note | Method - Verify - Document Review
label | ec28dde2-7951-5d6a-b88c-bbd6eb179f88 |  | note | Frequency - Each Lot
label | 8095a172-4686-5ed0-91fc-f1070b6b5eb4 |  | note | Category - HP
label | 003adcd5-59e8-53d9-9c13-838b275237d4 |  | note | Responsibility - Nominated Authority
label | 39df3f2e-d91c-5bd3-ab63-bfe593ff9381 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Acceptance of Rock Subgrade (where applicable)
label | 6a0a4cb7-ed15-5f7f-a7ed-f3782f3df3f9 |  | note | Reference - Section 204.06 (f)
label | 32c27b42-5910-5dbc-aa8e-d16fa43a8b05 |  | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | bd7faa9e-9b02-59dc-ad6b-55edaac511e7 |  | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | 430ad468-549a-541b-b591-73867db082c9 |  | note | Method - Site Inspection/Document Review
label | 1c0c28d3-17c7-520a-a958-d9096327cef7 |  | note | Frequency - Prior Construction of the regulating layer
label | 814a6aa6-f9ec-5740-b5f0-4f98c11cc1fd |  | note | Category - HP
label | 26026df9-c2ec-54c7-93e1-5f32e7c22ed9 |  | note | Responsibility - Nominated Authority
label | 835727b7-4b5b-58a8-9e7d-992e98687822 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Unsuitable Material
label | f4f939a8-f393-5b4a-87ce-3f91f2a81625 |  | note | Reference - Section 204.07 (d)
label | 9e4c172b-77e8-5ebb-b943-db064194afb8 |  | note | Acceptance Criteria - Where unsuitable material is encountered, proposed in-situ treatment or extent of excavation must be submitted to the Superintendent for review.
label | 1d38bc96-e3ff-576d-8874-d7cbdd9915b0 |  | note | Method - Visual Inspection
label | 25e7240b-78bf-577a-8391-cab566c7e3f3 |  | note | Frequency - Each Lot
label | 0f4f5aff-c9fa-5975-b1ef-4f0c0a23f6b7 |  | note | Category - HP
label | 92b89906-ea5f-5c60-8190-4d26fd00f105 |  | note | Responsibility - PE/Nominated Authority
label | 819efa65-3d19-57f1-9b4d-ea5bbc86b83f |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Groundwater
label | 5f49dc32-5c38-53de-b78d-686e4249d762 |  | note | Reference - Section 204.06 (h)
label | 2689c2cf-2c26-5fed-b881-9d5414ac1e95 |  | note | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
label | 068b5009-657d-51c7-841c-3490dee3a522 |  | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | 038e5479-ebe9-5d18-a38b-ce3e77e13873 |  | note | Method - Visual Inspection
label | 111315cf-6439-5d73-aa4e-764b23decb2a |  | note | Frequency - Each Lot
label | ecc354eb-2a66-5887-8502-0a8439342048 |  | note | Category - HP
label | e23c5ebd-b4ad-521b-8b59-3c36178b8794 |  | note | Responsibility - SE/Nominated Authority
label | c00642c7-1e3a-563a-8027-bb5e1ca6f8b4 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Fill Construction
label | 1f03cb93-5d27-583e-a28a-bf97b50b5c9d |  | note | Reference - IFC Drawings
label | 104fe3d6-9103-5002-a637-f5fabee7bc99 |  | note | ○ Section 204.10 (b)
label | 4a078569-e599-5359-8ced-eadc2f6b59b0 |  | note | ○ Section 204.11 (b)
label | b42272fe-cc6b-5252-a227-e59fa3c585e1 |  | note | Acceptance Criteria - No Fill to be commenced on prepared areas until area has been reviewed by the Superintendent.
label | 3a692930-f7eb-51b7-a611-ccb8612d6c9f |  | note | ○ As per the notes in the IFC drawings, excavation is required until natural clay is exposed with a minimum shear strength of 75 kPa, to be inspected by CMW prior to fill placement.
label | 5917022e-0d86-5ecb-90d5-2373144b605f |  | note | ○ No Fill placed against or within 3m of a structure until the foundation for fill has been reviewed by the Superintendent.
label | 0f9ed091-ec96-55c9-aaee-20e5f2587a6a |  | note | Method - Site Inspection
label | 8e763716-9b72-5435-a6bc-4fac98f23801 |  | note | Frequency - Each Lot
label | ae9397c4-998b-5cb1-b503-7ca9cf83b026 |  | note | Category - HP
label | 267df310-71a2-512a-830b-7f7cbf76bcfc |  | note | Responsibility - SE/Nominated Authority
label | 92fa1a6c-5b73-506e-abf5-8737007b68e8 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Proof Roll
label | b7b3de7f-c4da-52c1-9382-a52720fe4077 |  | note | Reference - Section 173
label | 1e261148-f865-57d2-8ba8-58c7659216ff |  | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | 0724e991-95f6-54fd-b0b1-2adeca5f7775 |  | note | Method - Visual inspection
label | 67f8df28-1dbc-50cf-9e74-7fe44e12a1cf |  | note | Frequency - Each lot
label | 83f94572-fff0-57d8-8d11-c9fc4db9eff6 |  | note | Category - HP
label | eee07f6d-a388-5f5e-ab47-a2b5a361a1dd |  | note | Responsibility - SE/Nominated Authority
label | 1c09f2a6-db38-533e-9e33-e2c68b2b6d2d |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 - Compaction Testing
label | df5b77a0-205c-535f-86ad-583915132b87 |  | note | Reference - Table 204.131 IFC Drawings
label | 08c687c5-7744-5cdc-a8a4-b7dbd2c614b4 |  | note | Acceptance Criteria - As per IFC Drawings Notes:
label | ad4074fb-fe91-5507-b9d0-72a5e9dabf6c |  | note | 7. SCALE A MAY BE ASSUMED FOR THE PURPOSES OF ALL MATERIAL TESTING EXCEPT WHERE APPROVED BY THE DESIGNER
label | e86e0963-9c8a-5214-af39-37e9209bd344 |  | note | ○ Attach: Compaction Test Result:
label | be38ab00-07a4-53be-9616-1b7927119e5f |  | note | Method - Document Review
label | 0434e82f-77bd-57dd-b7f6-e9c069b0a3c8 |  | note | Frequency - Each lot
label | 8ac35dab-ad09-5e52-a380-6555a87447a8 |  | note | Category - IP
label | 0a55771f-1676-563a-bf78-25a84d15a4ad |  | note | Responsibility - PE/SE
label | 15dc585b-8005-57d7-b1de-c76f930f1091 |  | note | Verifying Documents - Test Records, Lot Register
checkpoint-status |  |  | checkpoint | 5.8 - Post Compaction Material Property Testing
label | 6dd0a750-e3de-50ed-b116-0b0fd3c96aa2 |  | note | Reference - Table 204,041
label | b6ed6fb1-6867-5088-bdd3-d4d4df254f36 |  | note | ○ Table 204.141
label | 9626f4f7-1268-548e-a519-55828be10a97 |  | note | ○ Section 204.14 a) or b)
label | 5c0132a3-d6f5-530c-9242-3fe96527f86e |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | 7a8e1914-3e5a-504c-bf87-233f1722b1af |  | note | • CBR ≥ 8% and Swell ≤ 1%
label | 79db980d-e003-55a7-8dc0-da11e82bafe2 |  | note | • Max Permeability = N/A
label | 60d2f918-b20b-5cc4-b53c-9fc3e09fdbd9 |  | note | ○ Grading: 75.0mm 100%
label | acf7aea1-2dfd-584f-b7e0-f53fbc519a21 |  | note | • 37.5mm 50-100%
label | 0bece197-1cf1-5cf6-90e5-330598b3fa17 |  | note | • 4.75mm 25-65%
label | d16f8f35-5d1a-52c7-8084-f66adf833546 |  | note | • 0.425mm 10-25%
label | 439bc086-27ac-5be3-91f8-14af50b65ee5 |  | note | • 0.075mm <20%
label | 1013d625-6deb-55eb-8574-239aba8df32d |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = <25
label | 675286be-728e-5a6f-a529-189818654323 |  | note | ○ Scale A:
label | 1b382757-34c3-585b-a3b0-442b32f3be6c |  | note | • CBR & Swell
label | 1537e2df-ac62-55fe-b395-92bc2312f4df |  | note | Initial - 1 Lot Test to determine Assigned CBR and swell
label | b22a1f59-ff3f-549a-b53b-4eaf8926d2d3 |  | note | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | 7e69a118-7821-5611-b49b-13cd4ccc8dc5 |  | note | • Max Permeability
label | 7bc57646-1cea-52bf-b515-372f8371246a |  | note | Initial - 1 test per 2 lots
label | 6daed1e1-351d-5fce-abd7-f2147ce0d7ba |  | note | Reduced - 1 test per 4 lots
label | 2ee2489a-bee7-506f-a772-8685461cbe6b |  | note | • Grading:
label | 3ef0f00a-5fec-50c2-9cdf-cd843030d934 |  | note | Initial - 1 test for each lot tested for compaction
label | a1025dc4-c69e-5479-b88c-ce212e5f3034 |  | note | Reduced - 1 test for every second lot tested for compaction
label | 767436af-f0f5-5e18-b753-55a079ded349 |  | note | • Max. PI x%Passing 0.425mm & PI
label | aa203ed5-4213-515c-b840-7422511ae6d4 |  | note | Initial - 1 test per 2 lots
label | 306aaa67-cef6-5af5-b2e8-578ccb8c8f2d |  | note | Reduced - 1 test per 4 lots
label | decadef9-4e0a-5a54-92fd-db2b75219a60 |  | note | ○ Scale B:
label | c5aef63b-4ddf-5276-af1f-c3362f7b4ec4 |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | c4f6a6fa-9f95-5a0c-a619-b84c35420bb1 |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | e2572cf0-3ed5-55ff-85bf-7d57df2c1241 |  | note | • Attach: Post compaction test results:
label | a7c9f43e-2ea4-5d44-ab5d-ed2736781de4 |  | note | Method - Review Document
label | 52cf5482-7497-555c-bfd7-14ba9f84815f |  | note | Frequency - Refer to Section 204
label | 01ae599e-c39d-5846-8724-b10d10c69097 |  | note | Category - IP
label | 8bd04083-d02e-5cf6-98c3-1bce2c4c94dc |  | note | Responsibility - PE/SE
label | 8d7ed096-5e5a-5783-90dc-684dfe99188b |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Survey Conformance
label | 639b8b28-543c-5a27-b002-755cd2e8ecf5 |  | note | Reference - VicRoads 204.03 (f,g,h) Section 173.05
label | e5ff157e-2237-5b44-8390-35c8b81b1e44 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | f3d5ef07-7f2c-5bf8-b769-cde02820b7c4 |  | note | ○ Level tolerances (Scale A):
label | 0884ddd0-741c-5694-812b-ac8f70444503 |  | note | • Range x = +5, -15mm
label | faadcbf9-43dc-5357-8437-46ab6ab892ae |  | note | • Max S = 12 mm
label | 0c013f8b-feef-5679-9b0e-990f0b37fd17 |  | note | • 80 measurements per lot
label | 40481a8b-e1e5-5a6a-9407-000f04948d79 |  | note | ○ Level tolerances (Scale B):
label | 2feb8781-f69b-5180-932c-62ab1238c583 |  | note | • Range x = +5, -25mm
label | 511be02c-b280-58c4-b46b-6acfee0a60ac |  | note | • Max S = 15 mm
label | dfb56a20-886a-53d6-a065-56a0621217bb |  | note | • 40 measurements per lot
label | 64afcb48-f94d-5085-809c-19548db004b5 |  | note | ○ Level tolerances (Scale C):
label | 73152944-e379-5e04-9380-41f83374d79a |  | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | b74359e9-e0eb-5556-b2c6-73bde0dd0ccf |  | note | Method - Review Document
label | 0d7e4661-e80b-5ef1-8fef-aec9c991cbfd |  | note | Frequency - Each lot
label | 2109a2b5-f4ba-59bb-b382-72552342dd15 |  | note | Category - SP
label | 2609fa1c-81f7-5c11-b3d2-0f941e22ac35 |  | note | Responsibility - SE/Surveyor
label | f2e96422-a2be-5d03-992f-bfd98a94b8fc |  | note | Verifying Documents - Sign ITP, Attach Survey Report
checkpoint-status |  |  | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | fe91746c-aeb1-5262-b60c-88bf03bb401a |  | note | Reference - MRPA Quality Management Plan
label | bddcdcc2-d079-590b-b2da-96a3d38d68a0 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | aa6969ef-d785-5257-8608-95abac88d2d6 |  | note | Method - Document Review
label | 2a33830a-62a8-50be-afac-8e1c994ac66d |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | a7de5295-c614-5b98-98ad-52aa5c30a428 |  | note | Category - HP*
label | 67ce426b-ee5a-562b-838f-efd0828c8661 |  | note | Responsibility - SE/PE/SPE
label | a8651c65-cf7c-5725-b89c-5be35921a7b5 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | 5babc2b5-1b08-5d59-8e3f-4f2e2b2a3c5c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 830072d9-d6c7-5c42-a146-4234f092c816 |  | textbox | Name:
text | fc6d4cc6-0dd8-556d-92e0-651de3ef3960 |  | textbox | Position:
text | dc8ce6b4-b90f-5251-9bed-bd1cf6a71329 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | CHK-001-CIV-Stormwater Drainage Pipes Installation | itp |  |  |  | Yes | CHK-001-CIV-Stormwater Drainage Pipes Installation | 8ea17dce-31d4-4a13-80ce-b333bace6f1e
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 9606f886-735c-5a77-b1cc-39eb08fcf281 |  | note | Document Title: CHK-001-CIV-Stormwater Drainage Pipes Installation
label | 9085515f-c8a7-5f88-8182-6aaefc246de0 |  | note | ITP Description: Stormwater Drainage Pipes Installation Checklist
label | 25d13b2b-e7dc-5f0f-ad53-a1d994db777d |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 2c084acb-7f74-5acd-8cf7-3febc9620061 |  | note | Revision Number: 0
label | b4adb168-eba8-5e1c-8f27-5576c0a52e02 |  | note | Revision Date: 20/06/2023
label | 9f9221a8-8f19-5dd1-ad90-5e22ca24428e |  | note | ITP created by: Kamel Alshobaki
label | c705680d-43f9-529e-bd52-f7ea58f1ec99 |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 570725ac-0b3d-5329-9e3a-4049bbde88f0 |  | note | Reference - VR Section 701
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 6c797f0e-d8c9-54e7-a01a-137ce07388ed |  | note | Reference - VR Section 705
checkpoint-status |  |  | checkpoint | 1.3 - Main ITP
label | 131222df-4944-57f5-a6b9-3e4d709dbec9 |  | note | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
label | e2bfa6ec-ea00-56c3-8540-a0406d05f622 |  | note | Acceptance Criteria - This Checklist should be used in conjunction with ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
text | bb043660-7b8b-59be-b45b-428e5cfdfc73 |  | textbox | Enter: Main ITP Lot Number
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Bedding
label | 75f4f975-eca2-5dfe-937c-d6438a11fa6e |  | note | Reference - VR Section 701
label | 9b47376a-fe08-5d98-8ab8-bd3b3bef293a |  | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
label | 72a7817a-b175-52a6-84a1-d35967def897 |  | note | • ATTACH: Bedding Material Delivery Docket
label | 10689a10-dda8-58eb-9f0b-1ab77ec9b0e4 |  | note | Method - Document Review
label | 1cbf99d2-38ef-59d4-bd71-095bed18b14f |  | note | Frequency - Each Lot
label | d2779326-7dba-5051-bdd6-3066a738c2e4 |  | note | Category - HP*
label | 53c245ed-340a-5a18-ba8f-251cda226f29 |  | note | Responsible person - SE
label | bf8385ad-cc72-5984-957c-4344647a3be9 |  | note | Verifying Documents - This Checklist Signed-Off
label | de163a89-097a-5b49-b9dd-7023c1c75f91 |  | note | • Material Delivery Docket
checkpoint-status |  |  | checkpoint | 2.2 - Backfill Material
label | ed7b938f-f145-57a6-97c7-6e1da5b88eba |  | note | Reference - VR Section 701
label | 3b515b37-c532-592d-8838-1952620fbf33 |  | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | 5df750a7-3a3d-5e24-b259-4f40290699ef |  | note | • ATTACH: Backfill Material Delivery Docket
label | 6e7be390-7d4c-52ea-ba79-798092c32ca2 |  | note | Method - Document Review
label | 1e3b4d41-dab4-560c-8b55-225ec2fa3bbd |  | note | Frequency - Each Lot
label | 432e4edf-52ed-5b27-8834-49810191a285 |  | note | Category - HP*
label | 91a38553-84b7-5906-a1f9-60e7d4e9707a |  | note | Responsible person - SE
label | 071568e4-9e91-5cd1-ac6d-bbfc2ca1b175 |  | note | Verifying Documents - This Checklist Signed-Off
label | f2421219-d8e8-5ea0-92ad-6797001d91cf |  | note | • Material Delivery Docket
checkpoint-status |  |  | checkpoint | 2.3 - Stabilized Sand
label | 9e0c1574-a3f1-58c9-a671-67bac827b197 |  | note | Reference - VR Section 701
label | d8a19c7a-94a2-541c-b895-d9e765d758a0 |  | note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
label | 04899235-29bc-5b5d-a85d-1b7df2799daf |  | note | • ATTACH: Selected Backfill Material Delivery Docket
label | b67cf58c-5bd1-5f77-827d-ac824aca9de3 |  | note | Method - Document Review
label | 7a5d6521-9d67-562a-b2ea-14473a55cf47 |  | note | Frequency - Each Lot
label | 5041558e-bca6-5b11-8b6e-1518c9b5f909 |  | note | Category - HP*
label | b0397f2b-7d09-5da6-8612-a037895ee547 |  | note | Responsible person - SE
label | bfd0e44c-d7c0-557b-9e4b-3b1cd1ef4a48 |  | note | Verifying Documents - This Checklist Signed-Off
label | 85b052ee-a658-5aea-a769-460e471c360e |  | note | • Material Delivery Docket
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Subcontractor QA Submissions and Approved ITP
label | 94aa007c-b6da-5ef8-8e7d-ded8ffa56bb4 |  | note | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
label | 82b6a721-ecc4-5fcc-a681-4cc02fcfacb7 |  | note | Acceptance Criteria - Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
label | 4767e7dc-c79c-59cb-bab9-9416bae6f662 |  | note | • ATTACH: Subcontractor Signed ITP
label | 8d051671-df00-5680-9ff5-c26d6bd1773c |  | note | Method - Document Review
label | a2d2de44-0182-51c7-9ea7-0385a1820aaa |  | note | Frequency - Each Lot (in case undertaken by subcontractor)
label | 54612012-a363-5efd-bb40-d9b1317f9e47 |  | note | Category - HP*
label | 3f149ea6-abb7-53b2-9fd4-1162ce3b9c60 |  | note | Responsible person - SE
label | 1c2d598c-ca00-5a23-84e9-078c4c73ebf0 |  | note | Verifying Documents - ConQA Hold Point Release
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out
label | 23c189ea-52f3-5cab-8155-fc171aba7c2d |  | note | Reference - VR Section 701.10
label | 5d776ac9-cb07-54aa-a425-eedf4c14f4b8 |  | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | f9828b13-a6a6-534c-a7dc-4f47dc40ef97 |  | note | • The culverts constructed shall be constructed true to line and level.
label | b56476d4-55e8-5418-bd7e-dd5911e4f545 |  | note | • MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
label | 10dafc57-e13b-5a88-aa32-80e8fc1d9101 |  | note | Method - Survey, Measure
label | 9916ffdc-b960-5cf2-aa31-b2d5e054f88b |  | note | Frequency - Each Lot
label | d9197a34-9591-5aea-975d-7283efc3856d |  | note | Category - HP*
label | 165dde9d-318b-5344-bbbd-62fb51a4a5ff |  | note | Responsible person - SE
label | efd66298-5acb-50a8-be24-12c7457651fb |  | note | Verifying Documents - This Checklist Signed-Off
label | 6e73409e-7ffa-5354-a84d-385bab2ab3eb |  | note | • Attach Main Lot Map
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Trench Excavation
label | 5b2b2eb7-86e1-548f-b84d-f35359b6dca7 |  | note | Reference - VR Section 701.15
label | c5ad33b6-322f-5ee0-9f83-c5357d50759c |  | note | Acceptance Criteria - For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
label | 8fa6b910-720d-57e2-9f65-78a0e905c64b |  | note | • Horizontal Clearance to wall of trench
label | dfc8ebe7-66f7-5e10-a2eb-9eee5164da4b |  | note | ○ Pipe Culverts:
label | a5dbaf05-d04d-5653-b618-a9297c13a04f |  | note | • 300mm<Horizontal clearance for corrugated metal culverts<1000mm
label | c1299120-2fcf-5fd6-9249-6dd758235dbf |  | note | • 300mm<Horizontal clearance for other Pipe culverts<600mm
label | 0df6eb03-1ca1-5bd3-88bc-a3e5a6e8cca1 |  | note | ○ Box Culverts:
label | 4961334e-a762-5bc9-8c7b-ac028d716df2 |  | note | • 0.5 times the height of the culvert<Horizontal clearance<overall height of the culvert
label | 4b61aa72-2685-568d-a25a-edb1ff871872 |  | note | Method - Visual Inspection, Measure
label | d5b7480a-ea3e-5e7c-b034-707a34d7073e |  | note | Frequency - Each Lot
label | 78f4226d-460f-5874-9d81-4de12cbdbc06 |  | note | Category - IP
label | 84372a68-aebe-5fe9-82e7-79c999d6114a |  | note | Responsible person - SE
label | ea01c666-fa43-5345-a9ef-2974f063c3ff |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.2 - Trench Base
label | 963dd88a-629d-5698-8f36-f9c465bf3c2a |  | note | Reference - VR Section 701.15
label | 31bc0da9-7312-51ea-bbb8-f2ce66db1a7b |  | note | Acceptance Criteria - The base of the trench shall be compacted to refusal using mechanical plant.
label | fbda3065-1f55-5d8e-8750-0dbf05fb5905 |  | note | Method - Visual
label | f4205396-3a5a-5e6a-9d42-25d104e44423 |  | note | Frequency - Each Lot
label | 40f0cfb7-756d-55b2-92a3-05be6f241d89 |  | note | Category - SP
label | d7f54698-eea3-573a-82a7-a8fbfbc0958c |  | note | Responsible person - SE
label | 9aac5b35-0df4-5111-9cac-cebab8491798 |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.3 - Bedding-Placement and compaction
label | 0914069e-a7bf-5df3-b999-7ccd58f06613 |  | note | Reference - VR Section 701.16, VR Section 701.20 (a)
label | 29767ac6-022d-5c55-a2e1-7e307d4ef7c0 |  | note | Acceptance Criteria - Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
label | 2478666f-c7d7-5482-acbf-944f75ba648e |  | note | – 100 mm where D < 1500 mm
label | 946708df-1a1f-5e8f-913b-08e5b3e6e33c |  | note | – 200 mm where D ≥ 1500 mm
label | f16371d9-2c97-585e-8d10-c65ef1ecced1 |  | note | • Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | 00ae06f1-f24c-5d9d-bfc3-d041040cb6de |  | note | Method - Visual, Measure
label | f1cd1bd8-b5a8-5151-a6ab-92558e8b1892 |  | note | Frequency - Each Lot
label | 5b5263c2-1b5c-5f6e-9bbb-9e8f70ec0cdc |  | note | Category - HP*
label | 8d975cee-54e0-577c-89ce-0728ad050a4f |  | note | Responsible person - SE
label | 163dddda-0e18-55dc-a7d4-12a583c13c2f |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.4 - Laying pipes-Bedding conformity
label | df26f6fd-e48c-5acd-bc27-cd3cffb35cc1 |  | note | Reference - VR Section 701.17
label | b1efe20c-e47f-51af-b3fb-86e666b2db0f |  | note | Acceptance Criteria - Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
label | eb23f495-9281-54f8-8d49-3ad3953f6f8d |  | note | • Laying of pipes or box culverts shall commence from the downstream end.
label | e406d8b5-d39c-599b-a51c-7a3cb29cbb5f |  | note | Method - Visual
label | 90fe179b-0765-554c-b2e7-43c6c9c113db |  | note | Frequency - Each Lot
label | ff1cd743-7e95-5ac9-8418-330b594e6c73 |  | note | Category - HP*
label | 401f50d1-b66c-5314-b132-55a4e8161fbc |  | note | Responsible person - SE
label | 033d5dd4-7d4a-563e-98f8-6b94391bf411 |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.5 - Pipe Laying
label | 0cf6d844-a9ef-5bb0-a6c2-35d775367940 |  | note | Reference - VR Section 701.16, VR Section 701.17
label | 24fd5913-d844-5b4b-8d2b-546ed3940ba5 |  | note | Acceptance Criteria - Laying of pipes or box culverts shall commence from the downstream end.
label | 72a50dc2-8871-56d0-9eb6-7bef738fe72d |  | note | – Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
label | 6e492bd4-8028-5377-8c82-5c9214f458db |  | note | – The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
label | 018651b0-d806-5cf8-9a97-181dfba3b2c4 |  | note | – The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | 98cd1c37-413a-5bed-becb-00dc7bb5271f |  | note | – When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
label | 140f1f68-9dde-5817-b821-f96f3c70916b |  | note | Method - Visual
label | 491a255d-a322-5073-8121-44615d669c38 |  | note | Frequency - Each Pipe
label | b074fa79-b006-58d1-918d-b0c77ec955ee |  | note | Category - SP
label | da5998ce-6cff-5898-be0e-dfc1598d2e17 |  | note | Responsible person - SE
label | 0a46b02e-7d06-518f-9f86-67a2d6ffeb45 |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.6 - Pipe Joints and rotation
label | 81721ed7-b94e-5f82-832f-3fbbc2ddcaa2 |  | note | Reference - VR Section 701.18
label | b93cfed2-5388-599b-be86-e642f49bb614 |  | note | Acceptance Criteria - All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
label | 86ac7324-d0ed-5580-83ec-1232d385c040 |  | note | – Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
label | a849b464-4906-5afd-b005-00712dfff637 |  | note | Method - Visual
label | b9c5b291-93f6-5ad2-8923-c76e72682ff3 |  | note | Frequency - Each Pipe
label | 4d76ea64-86db-50c5-84a0-31939f1acc6e |  | note | Category - SP
label | 7b0d64a2-fb2b-5232-8593-5b4e39007781 |  | note | Responsible person - SE
label | 67b6e2cb-d327-5a7e-9e93-e963a1493935 |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.7 - Conformity with drawings
label | 3446fb44-2f2f-5b5c-be71-70eecc37a307 |  | note | Reference - VR Section 701.10
label | 6ec33e2a-70d4-5135-a457-ca85a4dc9127 |  | note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | bba3f7cd-f3e6-5123-9686-b9bdad909a6c |  | note | • Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | daa51087-6530-5676-ae0c-6b85dab098eb |  | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | d71d1aef-32d8-51d5-8e14-7de8fe75b7cf |  | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | 0d522301-fd7e-5722-90f1-25aed1881242 |  | note | (c) invert level of pipes at pits ±50 mm
label | df7152d5-1758-55b2-8b3e-642760aa9ee2 |  | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | cb27e881-f25d-5619-8d47-1411549e673d |  | note | • ATTACH: Survey Report
label | a842843e-f263-5a76-9364-ca1f5625e483 |  | note | Method - Measure
label | f9b8a8cd-0241-57ef-9df9-2427a1080082 |  | note | Frequency - Each Lot
label | 594d2c7a-9346-5b74-ad7d-4aead200415f |  | note | Category - HP*
label | 6557317e-9a99-5233-8fff-fbcd4c003de3 |  | note | Responsible person - SE
label | 61c0e53a-c697-5759-9bce-d9958d83901a |  | note | Verifying Documents - This Checklist Signed-Off
label | 17bcd92e-5064-5a55-95a5-11cb0bfd7c36 |  | note | • Survey Report
checkpoint-status |  |  | checkpoint | 5.8 - Backfill-Under area to be paved
label | 9986d4b7-b064-589c-b1b3-e2a02d3472bf |  | note | Reference - VR Section 701.19 (a) i
label | 6ce9a8c0-5666-53fc-899c-5bea263f8ca4 |  | note | Acceptance Criteria - Culvert under area to be paved
label | 56a37cd4-c13b-5412-b314-bc62d4cd5587 |  | note | – Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
label | 3fe9e562-7344-560c-aee0-ba791184968c |  | note | – Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
label | 0f25a3c8-01a3-56b0-a812-eee8283d72ad |  | note | Method - Visual
label | bd804190-8511-503d-a39b-e8990f5ac9a5 |  | note | Frequency - Each Lot
label | da4fb769-fc92-50fd-a09d-03417870346e |  | note | Category - SP
label | 7c84510f-8fe2-5e8b-abab-932db9a063c4 |  | note | Responsible person - SE
label | ff35041b-9935-5445-9d2d-5ffc9a170570 |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.9 - Backfill-Under area not to be paved
label | d3c78002-8c9a-59e7-9daa-508972f23950 |  | note | Reference - VR Section 701.19 (a) ii
label | 8af641fd-1fda-597b-b813-2a5226a4e238 |  | note | Acceptance Criteria - The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
label | de84b64b-9026-5cee-992a-7b013a973b94 |  | note | Method - Visual
label | 412b5cc2-0718-5eab-a377-a054207a6a76 |  | note | Frequency - Each Lot
label | a9c43f0c-daef-5277-a49d-7ec38b0946ea |  | note | Category - SP
label | 7a38a625-369f-5770-b35d-20fce2c96de0 |  | note | Responsible person - SE
label | 67845464-c69f-5baf-91de-be3258311d05 |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.10 - Backfilling with cement stabilised sand
label | ba881519-3ba4-5a77-876f-0d4aedc2faea |  | note | Reference - VR Section 701.19 (c)
label | 2e34911f-e716-52f4-aec4-ebfd4e84cdb0 |  | note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height.
label | 06f6c3f3-0f4e-5a21-8a38-fa8a144519c0 |  | note | Method - Visual
label | ba61c2f1-2137-5bd6-8787-2bc9524fa39a |  | note | Frequency - Each Lot
label | 0a199f0e-677b-5b85-8231-11fb744c8bce |  | note | Category - SP
label | cd3aea3a-a12a-5cd4-8df9-066b022e8e8c |  | note | Responsible person - SE
label | 31050f64-9359-5a4e-b904-f3bd9dd4c23c |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.11 - Backfill Placement
label | 579ea0ce-44d6-558c-b890-6da5fe47bab5 |  | note | Reference - VR Section 701.20
label | 86ce0d1f-82ce-5c3b-9778-b1c803d4ba67 |  | note | Acceptance Criteria - backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | b9d8e8be-4929-58ef-8a4f-b84a928cee0d |  | note | Method - Visual
label | 3cde6f2c-2800-53a7-ac00-306bfb32190d |  | note | Frequency - Each Lot
label | a6703015-fdec-529a-b991-9d1c8e763d6f |  | note | Category - SP
label | b427c085-9b47-51fa-99fe-c93b1a2b319c |  | note | Responsible person - SE
label | 2eceac5f-06d0-5160-a08a-5ac1ae050460 |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | 5.12 - Backfill Compaction
label | c5a32cbe-5230-5785-889f-959986f9101b |  | note | Reference - VR Section 701.20 (b)
label | 13bf021e-9323-5215-9436-5a5742886f44 |  | note | Acceptance Criteria - 20% of all bedding/Backfill layers for each culvert shall be tested.
label | 2c52073e-5ea2-581e-9245-de5b08e613a2 |  | note | – Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
label | 7fdcb984-c725-5e7c-8345-b01f3f9c3eb8 |  | note | – Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | fbcb7ad8-358d-59ce-9b66-cc80801e37b3 |  | note | Method - Test
label | 669e4b01-823a-59c0-bb8a-6bf0a4891919 |  | note | Frequency - Each Lot
label | 755a42bb-0ecd-506c-a0b4-b8e1db31f1c2 |  | note | Category - HP*
label | d5160f74-0976-5700-9c8b-3b42caab0dad |  | note | Responsible person - PE
label | 4a87bbd6-2243-5d60-9f68-402626817961 |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Compaction and Moisture content tests
label | 53daef47-5f04-5d2a-aa52-666b3f310e96 |  | note | Reference - VR Section 701.20
label | 0ca32cb2-abf4-5a6b-aa53-0b1aa7cae807 |  | note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
label | 7abf9a95-a6b7-5bb2-8719-a12bb98bda8a |  | note | • ATTACH: Compaction and Moisture content test results:
label | e1ec9efc-d34e-5ee7-a2e9-430e62a2fde7 |  | note | Method - Document Review
label | ba29cebf-3403-5931-9785-f90a52fe53f2 |  | note | Frequency - Each Lot
label | 309df2a0-9210-5e19-a306-891b9024ec45 |  | note | Category - IP
label | d73a6a6f-ec7c-57d4-b704-cc243f62f46b |  | note | Responsible person - SE/PE
label | 1e6337e9-6996-53a0-8541-26e1c1738bd1 |  | note | Verifying Documents - This Checklist Signed-Off
label | a237437a-7d93-560c-8368-1a3ca7ac882c |  | note | • Attach Test Results
checkpoint-status |  |  | checkpoint | 6.2 - CCTV Inspection
label | 4204d85c-3122-5c24-9ead-455387507840 |  | note | Reference - VR Section 701.30
label | c7e55f01-5b1e-5412-bbf6-6a5199ee6609 |  | note | Acceptance Criteria - All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | 534affc0-3c6d-5bea-8dc9-2005ae0fbbec |  | note | • ATTACH: CCTV Report (PDF)
label | 931c2d3d-0e3b-5dad-8f67-e68d1fdd42f0 |  | note | Method - Document Review
label | 0c6bd963-f85e-5d20-8c37-1352cc20bd08 |  | note | Frequency - Each Lot
label | 00f4e48e-9af7-5c7e-9ee4-944a85eeae3b |  | note | Category - HP
label | ee58b695-f292-599b-b319-35c35833ca64 |  | note | Responsible person - Nominated Authority
label | 737bc00d-6d8e-5afd-8b05-4368f350a533 |  | note | Verifying Documents - ConQA HP Release
label | ddebd2e8-da05-5192-a341-0ad54af13437 |  | note | • Attach CCTV Reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 19e88502-33ee-55df-8d6e-62cf37895e68 |  | note | Reference - MRPA Quality Management Plan
label | f38364ae-3f30-5906-b39e-2098e27bd0c9 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | 8970a0cb-f6c5-55f4-983c-7f4891888966 |  | note | Method - Document Review
label | 90c95c4e-864a-50f8-8f8b-fde2664b21fb |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | d409339d-7dfa-58ce-8a68-a42352a2adbe |  | note | Category - HP*
label | 1b2e97f7-2498-584d-a23a-96217de73369 |  | note | Responsible person - PE
label | f2ccecb7-ff22-51c5-8293-4c696f94d65a |  | note | Verifying Documents - This Checklist Signed-Off
checkpoint-status |  |  | checkpoint | Final Inspection
label | 496fd5a6-ee80-5024-966f-622e9435eb5b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 07efe473-6fa8-5a4f-97eb-1e2f343ba5e0 |  | textbox | Name:
text | dfe414ca-ef6e-5840-ba07-e02dd379dd94 |  | textbox | Position:
text | b32ddedd-a1ef-5266-b966-228f8fbf2d43 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-025-CIV-Brunt-Kerb & Channel (Supply and Install) |  |  |  |  | Yes | ITP-025-CIV-Brunt-Kerb & Channel (Supply and Install) | 8fc93039-3f87-4784-a7a7-dc13bd43a9cc
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 6b9720fd-7c54-5cf8-83b5-464feaa8ed6e |  | note | Document Title: ITP-CIV-Brunt-Kerb and Channel (Supply and Install)
label | 0e6587bf-f846-5421-80a0-baa41fcc578a |  | note | ITP Description: Brunt-Kerb and Channel (Supply and Install)
label | c0cd8cbd-1654-548d-972a-a5adcdcc076b |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 155c011c-e213-55f1-bc6d-8285ae2f5a7a |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 6e06a300-6840-55bb-a8d6-9c8089ea14ed |  | note | Revision Number: 0
label | 6db6d066-fdaf-520a-aec1-17f0af044566 |  | note | Revision Date: 28/02/2023
label | a89e24cb-4456-5db4-b9d9-eb494cbe8408 |  | note | ITP created by: Jason Lee
label | 3916dd72-2ab0-547b-bc3e-cb7775ca8d4e |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 6c8075d5-ea12-5e1a-9e79-550a7e944716 |  | note | Reference - VicRoads Section 703 (August 2021)
label | c475052b-a0f9-5e66-ae25-7a671d3b24d1 |  | note | VR SD2001
label | 18db27d2-f917-5068-bfe3-43b91b47943f |  | note | VR SD2102
label | f355ee05-bd4e-573f-87c6-52c77c66161d |  | note | AS 2876
label | b5bb447e-3292-529a-9deb-efd6f8224243 |  | note | AS1379
checkpoint-group |  |  | section | 2. Preliminary - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Mix design
label | af5dd723-16cf-5e62-ae6b-0f6ce6c2f02f |  | note | Reference - SD2001 AS1379
label | d3edf9c4-cd78-5a54-811a-0bff1da73bd7 |  | note | ○ Section 703.05, 703.06, 703.07
label | 7c5d059b-f2cb-516f-8d9b-3f130990f9fb |  | note | Acceptance Criteria - Approved VR mix design to be used.
label | c58ee228-b282-518c-9576-d8fb2c20fb84 |  | note | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
label | fdf3945e-5cfe-5c79-9737-e1e436c9270f |  | note | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
label | e59bc8b5-c96b-51e2-b16b-4226b571ab3e |  | note | ○ Attach: TeamBinder Material Approval Ref No.
label | 1fae6b38-55f6-58af-b1d1-edd124d72e84 |  | note | Method - Verify, Document Review
label | 7c3bbe00-7308-5622-8594-91bd7279e957 |  | note | Frequency - Prior to commencing any activity
label | 1ade6834-1d61-5e19-b039-4249962c160e |  | note | Category - HP
label | afebfdec-685f-5d94-a848-d40dba43b376 |  | note | Responsibility - Nominated Authority
label | 130fc6f8-d4d4-57f8-be5b-f5c30f6378bb |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Bedding Material
label | 05f9e601-2f17-507b-a49c-02dbf4b5d43c |  | note | Reference - Section 703.21 IFC Drawings
label | 57be8a0e-b490-5b5c-b724-56b92d93412d |  | note | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | 0366bb4d-fde1-573a-975e-fba83ea93aa0 |  | note | ○ Attach: TeamBinder Material Approval Ref No.
label | b4d4092b-9061-5068-9373-09928b763e2c |  | note | Method - Verify, Document Review
label | 52470324-1bb1-5c80-8165-effb7fb0379e |  | note | Frequency - Prior to commencing any activity
label | 8f45bf6b-336f-55f6-a2e0-e9c126aa4007 |  | note | Category - HP
label | bbfca76e-ef3e-52cb-90a6-59c47ca91211 |  | note | Responsibility - Nominated Authority
label | 1ec7da20-a739-50d5-8e00-db593a62666d |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Curing Compound
label | e490f7e7-8245-5a91-ba2c-944e0149e45a |  | note | Reference - Section 703.10
label | 14f15093-1e14-52cc-89bc-7c490305ef6d |  | note | Acceptance Criteria - Curing compound shall comply with AS3799
label | 9249160f-5008-5b13-bb07-df126a394131 |  | note | ○ Attach: TeamBinder Material Approval Ref No.
label | 52ca43d2-042a-5b0f-afc8-c064ee68420b |  | note | Method - Verify
label | 258e3006-017b-56fa-9f62-3443442f6641 |  | note | Frequency - Prior to commencing any activity
label | 873555ee-c52f-578f-8290-8feaa4f82eb1 |  | note | Category - HP
label | fad85ce0-dbe9-519d-a1ff-73594efafef0 |  | note | Responsibility - Nominated Authority
label | ab43aa48-62bf-5a36-884b-aa6fa78ff91e |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminary - Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Check for correct documentation
label | 021ba59a-a9fd-56d5-987c-591c9d347ca6 |  | note | Reference - IFC Drawings
label | 10280ead-9431-599c-81b4-0043d9a45b4c |  | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
label | 45a172bd-7165-5125-ba17-777a46f5c67d |  | note | – Using the correct and complete set of drawings
label | 65913086-8170-5273-9b4f-a88ac1aabc59 |  | note | – All drawings are the latest version
label | fdfc4b06-15b7-5e1c-8359-4f084e9fab7a |  | note | Method - Visual inspection
label | 1d61fac2-9d46-5cee-83f0-5ab550e2a9d0 |  | note | Frequency - Prior to commencing any activity
label | 80ec6a66-a9cb-5140-949f-049a2cebafb6 |  | note | Category - HP*
label | 339fd17f-24b3-5cc4-97aa-ffb38e2c576c |  | note | Responsibility - SE/Site Supervisor
label | abc6f78c-8477-56fe-9b83-8d8cb8b240ce |  | note | Verifying Documents - ITP Signed
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Setting out
label | a16289eb-b911-5576-b5f4-97ab64853d2e |  | note | Reference - Section 703.17 IFC Drawings
label | 163cf5fe-2cee-50fe-8ac6-a9f2357ee805 |  | note | Acceptance Criteria - Set out work in accordance with IFC Drawings.
label | 318f09fd-1dbc-5304-b643-29a200a1d09a |  | note | ○ The superintendent will review and confirm set out.
label | 5cff4dbb-db92-584b-b7db-baadd3b93c4f |  | note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | b90ae5f1-9223-5f33-9394-843291c46aa0 |  | note | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
label | 96557c43-533c-5adf-bbf1-290da2e7ec92 |  | note | Method - Verify
label | c95a16dc-18b6-55da-a01e-69cbb7b2376b |  | note | Frequency - Prior to start
label | db982897-f4d9-58f1-9d0f-51972e5a4e13 |  | note | Category - HP
label | 70b9bb77-7bec-54f6-b44c-089f578ab7b5 |  | note | Responsibility - Surveyor/Nominated Authority
label | c68f5a4e-717d-5735-b6f1-5b1e16ec61e5 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Temporary drainage provisions
label | e3db48db-005b-5112-9fef-68db22f8c28d |  | note | Reference - Section 703.18 CEMP
label | 883813aa-aa9e-5112-abd1-87d00aee34a0 |  | note | Acceptance Criteria - If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
label | a9423001-6490-58fa-9635-b31af6f4bf4e |  | note | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | 26a276b8-ca94-5c0b-abb7-05bebe9d566c |  | note | ○ Attach: relevant written approval from relevant stakeholder.
label | e84aa963-a2ce-5a52-85f7-1e2a4cd17492 |  | note | Method - Visual inspection, Document Review
label | 84a6249b-53d6-54d2-85ff-43ab75497cd1 |  | note | Frequency - Prior to start (where required)
label | 201831f5-5fce-58a2-8b0d-d81df58a5d82 |  | note | Category - HP*
label | f73cdbc9-7822-57a5-89bd-49351af30360 |  | note | Responsibility - SE/PE/Site Supervisor
label | 5445c107-3686-54e5-ad7e-b9b8c175ec1e |  | note | Verifying Documents - ITP Signed
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Bedding
label | d33f54e9-ca24-54eb-8d17-67f50f53ad6e |  | note | Reference - Section 703.21
label | a3850de6-27ea-56bd-8325-f3d0757d7b33 |  | note | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | be93843e-19ae-5001-94c8-b0af77e51825 |  | note | Method - Visual inspection
label | c774239a-caa8-57d0-be9f-a446ebaf28d2 |  | note | Frequency - Each lot
label | 137c745f-6de6-5a97-883f-00048936622f |  | note | Category - WP
label | bf02cbfe-592e-50f3-8b4f-46eec034330d |  | note | Responsibility - SE/Site Supervisor
label | 93bb4ebb-a596-5cae-a687-dcde82574aeb |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.2 - Formwork
label | 6b899e08-2249-5a8c-9be7-f6de9651379c |  | note | Reference - Section 703.12 AS3610
label | a5ed3721-86eb-54b2-a77a-47e14accd765 |  | note | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
label | 47ed9196-a856-5a7d-9819-d408cd01a922 |  | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | c925cada-b3cd-5a2e-b634-d4b9a5e65e84 |  | note | Method - Visual inspection
label | 4ad2d805-bd9c-522a-8c1e-c39739b52ddf |  | note | Frequency - Each lot
label | b46fb4d1-33c2-5cd2-b1e4-24525bd27401 |  | note | Category - WP
label | 45e4fa9c-fd67-5580-9870-6de32a7e3827 |  | note | Responsibility - SE/Site Supervisor
label | 2030e67b-3ac4-50b6-aa12-d9e169f8cee0 |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.3 - Pre Pour Check
label | b07207af-c798-552b-b88a-ecd4486890f8 |  | note | Reference - Section 703.09
label | c559e05c-fa9f-5976-8a4d-5865485b5fc1 |  | note | ○ Section 703.2
label | 52a0c6f0-3b03-57dd-9269-aa0d404eaea4 |  | note | ○ Section 610.17 (a,b,c)
label | 28926b95-32f4-5386-bf1e-bc963d960e1b |  | note | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface.
label | 75949ddf-e97d-54d0-9ddc-5d1dd0755144 |  | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
label | ecdbf081-7f57-5809-99d1-6ad38d7c8221 |  | note | ○ Attach: Pre-pour Inspection Record
label | bd9b9228-6841-5843-8a03-fff4ee2587cb |  | note | Method - Verify
label | 45e82ca2-3cb2-5081-ba37-f01b680f20b2 |  | note | Frequency - Each lot
label | cd348c05-4398-54d9-9637-b99e41a83599 |  | note | Category - HP*
label | e831c4bc-a3d5-5a26-9a4d-8bdfa433dc1b |  | note | Responsibility - SE/Nominated Authority
label | 61944123-9a5d-5287-809a-ca141e84a5f2 |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.4 - Concrete placement
label | c18ed478-280d-5ca5-ba6b-90bbe6afbd76 |  | note | Reference - Section 703.08
label | 746fbf47-aca2-5616-8b66-5c2d5becb861 |  | note | ○ Section 703.23
label | 82891dc7-8a75-58a5-b7d2-3f8d0c9a02d7 |  | note | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
label | a23e5753-4753-524e-a70a-128183a1c077 |  | note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
label | 12df94d1-ba31-597c-af7d-95a03c25583e |  | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | e3e891a6-398e-5f34-a8d7-32956094ab3a |  | note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | e3f5f4de-5daa-52a9-b77c-d9fbe7bf1d1d |  | note | ○ Attach: Concrete Pour Records
label | 06aca65e-b1be-5d8a-9f16-a97bb2144a94 |  | note | Method - Site inspection
label | 7d32eb90-eecd-569c-9d17-50d9a67103ff |  | note | Frequency - Each lot
label | 43c60e2d-e654-5b2a-ac5b-13f668cad2b0 |  | note | Category - IP
label | 0d715546-0588-5581-aa95-a17703c06449 |  | note | Responsibility - SE
label | 425ee9d5-51fa-5554-877a-ead7513cfd24 |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.5 - Transitions
label | 74710bbd-79c4-534f-85f4-d5af53e4e955 |  | note | Reference - Section 703.24
label | cafe4aec-8191-524d-8a43-b4e95c2fac65 |  | note | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | b305fc0c-53b3-5f32-81c3-1edf46d2eda0 |  | note | Method - Site inspection
label | 5c79c742-c283-59de-8b77-b07aac651bf8 |  | note | Frequency - Each lot
label | e765d43e-147d-5545-b419-321e198decee |  | note | Category - IP
label | e33bb3a8-1608-5056-9d6f-3f7b7833792f |  | note | Responsibility - SE
label | c62b3c98-18fa-5519-a1a6-d2358ceede85 |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.6 - Surface Finish
label | 8c4ece4a-7a68-5462-928e-4c8e336719d5 |  | note | Reference - Section 703.25
label | b9873d0a-957b-50fd-9011-967da43e742d |  | note | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
label | 2a790de8-bdb6-5a20-9636-c2db00f0cff4 |  | note | ○ Renderings shall be applied within 30 minutes of extrusion.
label | bb8be37c-f451-5be2-a7f8-c99311bbcecd |  | note | ○ Concrete to have a neat appearance and uniform colour.
label | 711b7d8e-8bc0-589e-ae54-99d9ed953e4c |  | note | ○ Class 3 finish required for external surfaces.
label | 2a3302ef-a81b-51f0-8b31-54111b93a6e4 |  | note | ○ Class 4 finish required for permanently hidden surfaces.
label | 19196b76-0f10-547a-a57a-793dcff16523 |  | note | Method - Visual inspection
label | f40cde76-09e9-5f91-b2f2-c4900654519b |  | note | Frequency - Each lot
label | 5c5cb985-469c-543c-bd81-43f365d0b94e |  | note | Category - IP
label | 370f11ef-b472-53a0-80c4-79d7b1ff0b44 |  | note | Responsibility - SE/Site Supervisor
label | 47835453-5089-539a-adf6-67f86166eff4 |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.7 - Formwork Stripping
label | c13892db-3821-5cf0-8394-4cc7e24e33f3 |  | note | Reference - Section 703.12 AS3610
label | adaefd91-8d45-5845-94c7-52f213adf185 |  | note | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
label | 9c58dda6-5cc7-5071-8cf1-b5613dcf0dd4 |  | note | – External faces 2 days
label | 172f0c76-8027-54be-9e43-8055421d5966 |  | note | – Permanently hidden faces 1 day
label | 75201602-c629-5aac-9aed-562f0fc51ab0 |  | note | Method - Visual inspection
label | 2cbe73db-08d8-5c37-9449-d0f2809be82e |  | note | Frequency - Each lot
label | 54608081-a238-5289-bc13-dc356ea17919 |  | note | Category - HP*
label | 0a676042-e1b5-5b05-a1d3-9c87590a8b6a |  | note | Responsibility - SE/Site Supervisor
label | 99d6866c-f9ea-53a6-9dbc-aa4b5eac9a98 |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.8 - Tolerance
label | f9da69dc-4a2f-5e22-ac86-a264fc97add6 |  | note | Reference - Section 703.15
label | 313cfe39-2a69-5084-8944-a8808c8f5025 |  | note | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
label | 19d13dd4-9508-569d-a170-b3ba81d4e4a0 |  | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
label | ec146257-a2d6-559e-ac99-02d5a57b154e |  | note | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
label | 1d786647-6e24-575e-83dd-af9cfd67714c |  | note | ○ Attach: Post-pour Inspection Records
label | e3a31006-2992-5bd3-9ee2-9bfe0ffd0cd0 |  | note | Method - Verify
label | ab0deb0a-927e-5e4f-b819-4fc0419a22db |  | note | Frequency - Each lot
label | 524ecabe-ef33-5a82-90c6-a53cb78a57bd |  | note | Category - IP
label | 75d4ee7f-df08-55f5-9836-24481554391c |  | note | Responsibility - SE/Surveyor
label | 020d7643-23a4-568e-8902-41694cbfd16a |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.9 - Curing
label | e95ae1e9-7d58-58ef-8412-459cbb679961 |  | note | Reference - Section 703.10
label | d5e7fcdf-3082-5428-a67a-13bef639cf58 |  | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
label | fa88f4ff-d9e1-59ae-a193-3d6ad488a8f0 |  | note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
label | 2f2d1947-c68a-5627-ad3f-31dff96ef14c |  | note | Method - Visual inspection
label | bf5a4477-b469-5418-9c69-6afaf1a9652e |  | note | Frequency - Each lot
label | 00b3cfa8-dc43-574c-a99b-86e3b38b2e3e |  | note | Category - IP
label | c66f8918-c2c7-5749-9365-a5c1bfad44d8 |  | note | Responsibility - SE/Site Supervisor
label | e748b495-8b0d-5748-ac16-f42c7de73b41 |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.10 - Joints
label | a779896f-6899-5b0b-a16d-75fdedcc2424 |  | note | Reference - Section 703.26
label | 80c5b5e2-4dc0-5228-9e4d-6eb7570cb3de |  | note | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
label | 92ac0610-2d6e-5e8b-84bb-8b8fb76364f6 |  | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
label | 358da6d6-6b6d-5b82-8de5-2424eef44aa0 |  | note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | 9ee4f16e-0cdc-5b46-8fa0-151f075ed77e |  | note | Method - Verify
label | 6fa3aceb-1d56-5ea1-a757-87db0a9a617e |  | note | Frequency - Each joint
label | b7f5f983-5f27-5ea2-8851-fe9eb21e6387 |  | note | Category - IP
label | f96b1b58-ee0c-563c-a8dd-df87e2aa0d2c |  | note | Responsibility - SE / Site Supervisor
label | cef9a541-6501-5fed-87cc-b16ee5d91b61 |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.11 - Protection of Concrete
label | cbdb2031-8efe-5e6b-bc52-6174c1a15bd7 |  | note | Reference - Section 703.27
label | 59522271-cc56-5128-b3dc-ce6977ed1620 |  | note | Acceptance Criteria - All concrete shall be protected from damage from early loading.
label | 3aa7ded0-b8db-58a7-a209-25268905e03b |  | note | Method - Visual inspection
label | dac70034-3a05-5663-a2a5-92ea895aa3e0 |  | note | Frequency - Each lot
label | 6b6211e9-97fe-5e94-b659-cc54b5cd217f |  | note | Category - IP
label | d68c4a23-dc36-5670-9b7e-cbe94e67442e |  | note | Responsibility - SE
label | 663475ed-44f6-5f6d-869b-197d6888c915 |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 5.12 - Bus Stop Kerb Height
label | 9d5cf70f-8ab8-5026-86d4-46eb9f0c31c2 |  | note | Reference - DoT Handover Process
label | a6eeae5d-4b98-51fc-b63d-66f0f294a588 |  | note | Acceptance Criteria - Height of the Bus Stop Barrier Kerb to be between 150mm and 180mm.
label | bedd2986-6812-5f5a-9563-75345dc3df84 |  | note | ○ Note: Capture this in pre-pour checks i.e. formwork and post-pour checks
label | 1263cc7e-18a8-54b4-9a95-361c699414b9 |  | note | Method - Visual Inspection
label | dfd2da32-317d-5d3c-a645-05d1f5afbd27 |  | note | Frequency - Each lot
label | 75a9d908-535b-52da-a507-20f3004162f1 |  | note | Category - HP*
label | a8f252f3-91e4-5dee-a2fa-d8508b1894fc |  | note | Responsibility - SE
label | 1fe5290b-1871-581b-8703-c5548a6bb2af |  | note | Verifying Documents - ITP Signed
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Backfilling
label | b53a095f-d246-51aa-b082-fa1667060f13 |  | note | Reference - Section 703.29
label | 2f2595ad-bda7-5f53-b802-56149cd55fb2 |  | note | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | 6f13a1d2-052c-5999-9fdc-da59caeb91bf |  | note | Method - Verify
label | 5f50916e-2e10-527a-92dc-7e9b825acac5 |  | note | Frequency - Each lot
label | 90529844-08a4-5186-a013-97adc13b6c11 |  | note | Category - IP
label | 48163269-4f49-5333-8d97-c7431153a201 |  | note | Responsibility - SE
label | d4304b2b-66fd-5a51-b531-2cefd9a446ff |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 6.2 - Cracking of Concrete
label | 6532b6b1-cdd8-5d96-9633-323b28aed103 |  | note | Reference - Section 703.30
label | 9ee5caf9-429b-52ad-a2fd-e5fbe3c38c6c |  | note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | 9b6c0d10-c759-578d-bddf-2c4d89c74dcc |  | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | 9c6ea6b3-2429-5293-a530-0b401d77f5c1 |  | note | ○ Attach: Pot-pour Inspection Record
label | cf748b34-40af-5488-820b-28ba86a53986 |  | note | Method - Visual inspection
label | 608e97c3-88ab-5916-a1b4-0ca02e0c3410 |  | note | Frequency - Each lot
label | 5cc82f4f-ec72-5858-b19e-5863be1b2b9f |  | note | Category - IP
label | 976a12d1-72d1-5a9a-aa7c-562eabe003f8 |  | note | Responsibility - SE
label | 654837d4-0bd8-5d3e-b4b2-12b2804e4ce4 |  | note | Verifying Documents - ITP Signed
checkpoint-status |  |  | checkpoint | 6.3 - Survey Conformance
label | faf20553-d8b0-51d1-896a-11e959a693ef |  | note | Reference - Section 703.15
label | 3f8f4fda-5f51-5dea-a591-5c00ebf1c477 |  | note | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
label | b40b1afa-7d83-5424-b680-ee268c0b5f7f |  | note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
label | 5fd732f4-152a-5cce-9896-376d353cd52f |  | note | Method - Document Review
label | 5793e36b-b360-5651-be76-27cda0844adf |  | note | Frequency - Completion of each lot
label | ce84a221-4ebb-5ce0-8e39-4c8cde130f10 |  | note | Category - WP
label | 9e81b46a-917e-540c-9d22-f4bc9905cdad |  | note | Responsibility - Project Engineer/ Surveyor
label | 31e95b2e-e34f-5228-b2a5-97b7b354a406 |  | note | Verifying Documents - As-built survey records
checkpoint-status |  |  | checkpoint | 6.4 - Non-conSupervisorce Report (NCR) Closure
label | 8f3dd12a-ec56-5da9-8788-7d0b5101f828 |  | note | Reference - MRPA Quality Management Plan
label | d11a228e-8117-5a4d-a3a6-d9cf1cf5fa79 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 093ead3d-53f8-565d-9578-7161d9dc6c52 |  | note | Method - Document Review
label | dad69e78-a114-5212-b553-d791ce7a3ee3 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 577b29ef-7a28-5160-807f-e4ace71b2f39 |  | note | Category - HP*
label | 40da50e2-ad7e-5d50-90e6-82ba3f8790e4 |  | note | Responsibility - SE/PE/SPE
label | e8799b54-b047-5cc2-943c-0ca609aab3b2 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | e42d15d7-cb37-5c1d-9154-ff1c1a6636ae |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | a6870f92-e3ae-5500-8f3f-1defed728f9d |  | textbox | Name:
text | 57ddebda-7818-52a3-a53b-027cbc5a9598 |  | textbox | Position:
text | 48bbf3cb-ac40-5ef5-b208-56f7de9559d7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-026-CIV-Brunt-Subsurface Drainage (Supply and Install) |  |  |  |  | Yes | ITP-026-CIV-Brunt-Subsurface Drainage (Supply and Install) | 9e1d4f1f-3efd-4ca3-b032-7fdf366f8f87
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | b3395565-3a0b-5911-a9e3-5463ac5c62b6 |  | note | Document Title: ITP-CIV-Brunt-Bus Stop-Subsurface Drainage (Supply and Install)
label | f474b4e6-6883-5a4c-ac86-89dc729be028 |  | note | ITP Description: Brunt-Bus Stop-Subsurface Drainage (Supply and Install)
label | e9db8c05-8c92-5ebf-bad2-060132f07712 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | d8205acd-1d62-5c0b-80f6-5fcc03993ca7 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 2c1a8b98-56bc-5776-9ad8-ea305f307eac |  | note | Revision Number: 0
label | 8ce9b793-bb01-56dc-bf07-c6a4fccfd7b4 |  | note | Revision Date: 28/02/2023
label | 1949e694-0142-5d3b-b7fe-eab4674b0e49 |  | note | ITP created by: Jason Lee
label | 8a7cad72-a57e-5fd9-b6df-349ef0c2875a |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 2400a9f6-05f1-549a-9fe8-3dc749147088 |  | note | Reference - VicRoads Section 702 (May 2019)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | c29098b3-51f9-5447-ab53-fa7b04206d50 |  | note | Reference - VicRoads Section 204 (Dec 2015)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 8033d78b-3768-5675-895c-8cdda97777f7 |  | note | Reference - VicRoads SD1611
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 4545ab06-1079-5596-9028-f9c0c525ad33 |  | note | Reference - VicRoads SD1051
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 0f76ee56-4c4c-5bec-ae17-d13fbd88fcc9 |  | note | Reference - VicRoads SD1631
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Drainage Pipes
label | 04b0f4ee-072f-5267-8071-8773c006eb03 |  | note | Reference - IFC Drawings Section 702.04
label | e1c8f5b4-8f95-5575-87c8-badc56584bfd |  | note | Acceptance Criteria - Subsurface drainage pipes:
label | 3704b23a-8c79-52d1-b54c-9fd85fb02795 |  | note | ○ Category 1, 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | bfd78149-374f-5553-9603-df9f7e5182dc |  | note | ○ Attach: Material Approval Ref Nos
label | 0f1e3c36-0bbd-5e35-8c9c-477090b75b89 |  | note | Method - Verify, Document Review
label | bb4c30ae-77c3-5f42-9b00-963ee71c2996 |  | note | Frequency - Each Lot prior to work start
label | e12c95c9-27c1-56f3-816e-9b8b8b3439a0 |  | note | Category - HP
label | 54d26d63-98e1-547b-9594-1fb763b6337c |  | note | Responsibility - Nominated Authority
label | 735604ed-8094-5e1a-8d75-85647e05acbd |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Granular Filter Material
label | 633f1e8c-7381-5606-8218-c47efb980413 |  | note | Reference - IFC Drawings Section 702.05 Table 702.051
label | d64cd33c-890d-5d77-80c1-3716aedaba49 |  | note | Acceptance Criteria - Granular filter material:
label | e6d241a5-0698-5b3d-9c53-0550e76ea3c2 |  | note | ○ Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
label | e71474ff-cbb5-5258-81f9-1b6336791c67 |  | note | ○ Attach: Material Approval Ref Nos
label | 0e206454-c20f-5f21-9d53-8dddd5d17eff |  | note | Method - Verify, Document Review
label | f1e078d5-94b4-5b21-a9f1-53d2f1ac4dbd |  | note | Frequency - Each Lot prior to work start
label | cf7fecfb-c43f-5e67-bc18-f0b9498343bf |  | note | Category - HP
label | b70c9767-bb45-5fa0-ad6d-ee9411c81967 |  | note | Responsibility - Nominated Authority
label | 00252c3e-25f0-56f4-ab5a-5ef755433199 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - No Fines Concrete
label | 8960fe11-dcf6-59da-8182-1e1e3374e5dc |  | note | Reference - IFC Drawings Section 702.05
label | 7215b38c-473b-506c-a33a-c6f5ffd6aa41 |  | note | Acceptance Criteria - No Fines Concrete:
label | eba097b4-5988-5213-8ec0-ae3abe5fcfe0 |  | note | ○ Shall comply with 702.05 (e)
label | 8d82463a-e1c8-5fb6-95ba-4661d2567a19 |  | note | ○ Attach: Material Approval Ref Nos
label | ebec0b73-4d6f-5f10-84bd-a45584111603 |  | note | Method - Verify, Document Review
label | f154c029-3188-5c3c-bcc6-b2e07169cc17 |  | note | Frequency - Each Lot prior to work start
label | e2bc0348-3a15-5a4a-b0ea-f61a671910f2 |  | note | Category - HP
label | dd64800e-c706-5471-b78a-3cdde818b8e0 |  | note | Responsibility - Nominated Authority
label | 2de116d6-d7c3-50b4-9270-77f96ce079a0 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Geotextile Filter
label | dacd7574-fcf8-5603-bc1c-f9c3892819a7 |  | note | Reference - IFC Drawings Section 702.06 Table 702.061
label | 4751d3d1-f4a2-5cca-8aae-dbc22bdab569 |  | note | Acceptance Criteria - Geotextiles:
label | 0a4bdc81-db90-5f23-99f2-35639cbc4764 |  | note | ○ Shall comply with 702.06
label | f595cbef-7b94-54d8-8dbf-d9a54df14539 |  | note | ○ Attach: Material Approval Ref Nos
label | 0669068d-736e-5fe4-914e-430829da2d65 |  | note | Method - Verify, Document Review
label | d25939c8-a39d-5b6f-b1fe-992c28f5ff13 |  | note | Frequency - Each Lot prior to work start
label | d9102875-d8e7-5288-9ad6-831ebba392c8 |  | note | Category - HP
label | 2aa41455-3ae6-57c2-ab3b-97bbd3979162 |  | note | Responsibility - Nominated Authority
label | e10ad554-3a80-5489-9347-bf38e24c7ee5 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - SSD Pits, Pit Lids, Flushout Risers
label | 959f8a2c-0edc-57e9-9a62-75f9d4ad250e |  | note | Reference - IFC Drawings
label | 8e3015b5-a62a-5332-8f61-056382e5816d |  | note | ○ SD-1051
label | f755239e-d27c-51d0-be53-194a6d72ce8e |  | note | ○ SD-1611
label | 796e55ad-96e2-5680-8b44-deb8c26b8f7c |  | note | ○ SD-1631
label | a4df8900-3c6a-53b9-8304-b2ef5c5464cf |  | note | Acceptance Criteria - Subsurface drain pits: shall be Type S1 (as per SD 1611).
label | 2dfaafab-2b45-56b0-9c83-c04e3b5560a6 |  | note | ○ Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit.
label | 370484e0-bc3b-52f4-8c11-0658028fd51f |  | note | ○ Flushout risers: As per SD 1631
label | a5603778-f5d7-5b8d-b757-c92cf82bbf26 |  | note | ○ Attach: Material Approval Ref Nos
label | 1ce29ec8-b67d-51cb-a5d5-88109b838e96 |  | note | Method - Verify, Document Review
label | e99d77b9-bb2c-5dbd-8a64-675b307095e9 |  | note | Frequency - Each Lot prior to work start
label | 73a2e2c4-430c-5971-915e-6b2bcb82afa8 |  | note | Category - HP
label | df8d4cff-1247-5f11-a093-279ac368ad1a |  | note | Responsibility - Nominated Authority
label | 878afe15-c3d9-5547-b3e6-dc0a60ecf269 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Check for correct documentation
label | 4394027f-5cb7-5eff-bcaa-525563181bed |  | note | Reference - IFC Drawings
label | e3165533-413b-586b-8e02-eafa3bd47138 |  | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | 416f5b1f-508f-5f83-a29e-0842dd5fc66f |  | note | – using the correct and complete set of drawings
label | 49dbbb7b-aa81-5eee-923e-5742c4f988cd |  | note | – all drawings are the latest revision
label | dd9a92bb-22db-5dd9-be1f-ada5f924de40 |  | note | Method - Visual inspection
label | ce5887c7-cabb-5e67-bff8-b82987cca048 |  | note | Frequency - Prior to commencing any activity
label | 21cab3ba-a4ce-5539-ace4-8860721ac7ac |  | note | Category - WP
label | 4e595c86-6e51-5921-9db5-525de900ad8e |  | note | Responsibility - SE/Site Supervisor
label | b2bc93f9-91d3-54af-a03c-2bf2a553aede |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 3.2 - Methodology for compaction of Granular Filter Material as Backfill (where applicable)
label | 1d7bd6e7-8da0-5dd8-b3b2-1f4ef5a33296 |  | note | Reference - WAP-252
label | b5db7353-790e-57e4-92c2-95abe6ed9acf |  | note | Acceptance Criteria - Ensure that all workers/subcontractors understand the correct method for the compaction of the granular filter material.
label | a667863b-b5df-5145-b28e-adcc7ec480ab |  | note | Method - Verify, Document Review
label | f8d68acf-bd0f-5c7b-a2b2-3b41a0ad37bc |  | note | Frequency - Prior to commencing any activity
label | f870b312-7292-5aa6-b047-72cc5d4bfb1b |  | note | Category - HP
label | 290afb04-a008-56a3-938b-0b2e01909f06 |  | note | Responsibility - Nominated Authority
label | e442cce2-9424-5798-ac4c-5ef39da35403 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Methodology for placemnt of No-Fines concrete as Backfill (where applicable)
label | 7b135730-aead-5c07-92f2-ef33378d9f6c |  | note | Reference - WAP-252
label | 874e59f2-34f8-58c1-8cd6-a4744e368513 |  | note | Acceptance Criteria - Ensure that all workders/subcontractors understand the correct method for placing no-fines concrete to prevent segregation and slurry formation at concrete surface that may block water passage into filter material.
label | 0de0f051-cca1-5596-96c5-221f466ba865 |  | note | Method - Verify, Document Review
label | 2aa14198-f017-5f56-940b-0e398b676c84 |  | note | Frequency - Prior to commencing any activity
label | 2bd6c79a-e5c8-5600-924a-376166450bf7 |  | note | Category - HP
label | 0a1e9426-34d3-5f80-9926-b945ae66e593 |  | note | Responsibility - Nominated Authority
label | 0c72b873-bea1-5c9b-a3dd-57979a9cbd47 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out
label | 7bf0abe4-9d9d-5810-b1cf-06221f9c9aa9 |  | note | Reference - IFC Drawings Section 702.03
label | 02f7fa51-6554-5d05-bbe8-b7648994b96a |  | note | Acceptance Criteria - Survey to set out Subsurface Drainage line.
label | 535943b5-cbba-5f70-88ea-94861f682599 |  | note | Method - Visual inspection
label | c9e7bbbd-e725-5501-a1ea-d5af04c080b5 |  | note | Frequency - Each Lot
label | e4a85799-1a52-5455-9b57-23331ac7a6f5 |  | note | Category - IP
label | 0f5759ce-8fb8-5680-a7fe-f9e8bf7cc5c5 |  | note | Responsibility - SE/Site Supervisor Surveyor
label | 79b9b1ca-5431-50ba-8647-5c5338691dbe |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Trench Excavation
label | 021723f2-237d-52e8-b07d-84016718cade |  | note | Reference - Section 702.08
label | f7115049-5ace-5548-a512-cb4c44b77d65 |  | note | Acceptance Criteria - The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
label | ca22ed6b-818d-5b23-ab3b-82f9757b1df2 |  | note | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | 7aea9e49-ae94-56a3-a636-29e9813404af |  | note | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | c70e20e2-5dd3-5c48-90d2-1af9596ff686 |  | note | ○ The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations.
label | 56d60bef-3f99-5d96-898d-1019a40e49dc |  | note | Method - Visual Inspection
label | b2c47000-caaf-5134-895f-28d28b835e8c |  | note | Frequency - Each lot
label | f76b9329-1dd2-5512-9347-5571f0372e4b |  | note | Category - HP
label | 72f437ad-938f-566f-955a-84275adde39d |  | note | Responsibility - SE, NA (Nominated Authority)
label | d6c37153-40f3-53bb-8e9c-b74292d2c5d7 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Placement of bedding
label | 4ed05d57-0dcb-5d93-bbfc-8d9278cde37d |  | note | Reference - Section 702.09 c)
label | 5c8de953-8862-51b2-b848-6fa1e9393e64 |  | note | Acceptance Criteria - Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level.
label | a9ad2c87-3844-50bd-98e0-023e8cb42257 |  | note | ○ Attach bedding material delivery dockets
label | f6771e2a-4100-5df4-a5b9-3b15665c6a49 |  | note | Method - Visual inspection
label | e7128135-a4fb-542d-b41b-84f5131a80fb |  | note | Frequency - Each lot
label | 5ac40b52-4ebb-5411-9007-3ccc92ced2e2 |  | note | Category - IP
label | 323b117a-20a3-58a9-95a3-7311c0627e2d |  | note | Responsibility - SE/Site Supervisor
label | 5565e797-0161-56ad-9b2d-15e75789a656 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.3 - Pipe and Geotextile Installation (if required)
label | b4d9fca6-72ad-5a07-a3cf-9fcf2a87e036 |  | note | Reference - Section 702.03 Section 702.09
label | 0b9d3de2-86fd-5797-ba25-ce2ac2621dcb |  | note | Acceptance Criteria - Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
label | 91c6a304-c9aa-566b-b6c8-001710c3d38b |  | note | ○ Attach Suburface pipe and geotextile delievery dockets (if applicable)
label | 86c3b1c1-77b6-5278-82cf-05f87fd98734 |  | note | Method - Visual inspection
label | 96f42b24-de96-52b2-9af2-00937d531614 |  | note | Frequency - Each lot
label | 1ed7cd32-1e83-51b4-b989-843ee8106312 |  | note | Category - IP
label | 17f65d6c-ec78-5fa8-b467-3a495406f903 |  | note | Responsibility - SE/Site Supervisor
label | f41aedfc-f159-542f-bc11-13af9b64a879 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.4 - Backfill Installation (Granular Filter Material)
label | 215f28a9-8aa1-5116-ac68-d6a8532a6570 |  | note | Reference - Section 702.09 (g)
label | ff9a1bdd-23ab-533c-8c7a-1380c8834165 |  | note | Acceptance Criteria - Material shall be placed moist and compacted in layers not exceeding 300mm.
label | 0cc74d39-f944-5b2a-9eea-d5d5e1c4ebf5 |  | note | ○ The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | 3162047d-8353-535b-9b9c-4d9ad3cbe610 |  | note | ○ Attach Backfill Delivery Dockets
label | 43fa7c4a-db78-54e0-a411-25f406317606 |  | note | Method - Visual
label | 8f402814-4f8f-5f5d-a584-47efca6ed81b |  | note | Frequency - Each lot
label | 65a0f132-6ffb-554b-b126-d736e2921120 |  | note | Category - HP*
label | 53fe7a00-9ce3-5c62-95f5-5e9c3e5a658c |  | note | Responsibility - SE, NA
label | 602c2602-1bb2-5b1f-a054-79eed78c5776 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.5 - Backfill Installation (No Fines)
label | 3df65192-1619-5dce-a460-3d88ce4af660 |  | note | Reference - Section 702.09 (g)
label | d4c88d80-3611-5aa9-8700-8ab94534cf04 |  | note | Acceptance Criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
label | ff27146d-1111-59a9-a0b8-5fa96862b78e |  | note | ○ Attach Backfill Delivery Dockets
label | 9407dd1f-76d7-56e7-b52c-31e0618ddf2a |  | note | Method - Visual
label | 5f3237ff-8b90-515a-9d8e-9c2b5f84a69a |  | note | Frequency - Each lot
label | 4982544e-0de7-5d8e-b98e-0a85ed98e0df |  | note | Category - HP*
label | 681c7c21-d3e2-5f1a-a5be-64d14bb79ae1 |  | note | Responsibility - SE, NA
label | 67e674e8-529a-53ee-bf7f-c2a87ce5b820 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.6 - Install Pits and Flushouts
label | 85a8e825-e267-5d14-bc27-6cfd6ac53734 |  | note | Reference - Section 702.10
label | 95908e9f-3939-5d31-b8ed-08f3eb26f577 |  | note | Acceptance Criteria - Subsurface drains shall have access points at the start and finish of each run.
label | 47c658b6-49fb-5d42-b3af-7be761791416 |  | note | ○ Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings.
label | 8f0ac1b6-9e5c-5918-a1d4-0627bcc9e8c1 |  | note | ○ Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
label | 1077798d-908f-58e1-9ac5-b7e3d21af43b |  | note | ○ Attach Pit and Flushout Delivery Dockets
label | d6d94ab4-bda0-5e14-a200-5a063ab5d8d2 |  | note | Method - Visual
label | 90cfe745-16ca-5419-af29-75dbafcf93c5 |  | note | Frequency - Each lot
label | 23824176-d99b-59d8-ad54-530df8b0dfb1 |  | note | Category - WP
label | e1af612d-d5e5-52ff-9a69-316ffce0459f |  | note | Responsibility - SE/Site Supervisor
label | 7ef9892c-5cfd-5e18-ad6e-66a5f0cba26d |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.7 - Marker Points
label | aff4db2e-8870-594a-bec2-2779c4e5d6da |  | note | Reference - Section 702.11
label | e0a83e99-a752-5b02-9cc7-994a63b8be5b |  | note | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
label | e9c6528d-ee2e-5968-bddc-e00d174c99b4 |  | note | ○ Attach Marker Post Delivery Dockets
label | 2af24377-9e06-56ee-8e5f-1d688b684f3f |  | note | Method - Visual
label | 3146938d-0f4c-5e75-87dc-b5b35aef08ef |  | note | Frequency - Each outlet
label | 7d69c59d-0e25-5afb-ab50-540215c69aa4 |  | note | Category - IP
label | da54708b-a4b5-5ac0-9019-85f769b34816 |  | note | Responsibility - Supervisor
label | 4db1bf5a-691c-514a-b035-090dd28affd1 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As Built Information
label | 4fe74e23-00f4-5f26-87cb-9c7c60d83a97 |  | note | Reference - Section 702.03
label | dc7df969-9d9d-5b5d-a90d-2b9bc9466768 |  | note | Acceptance Criteria - The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
label | 8d1a693e-6cad-5e08-be1e-ff7a8bdd7150 |  | note | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length.
label | 15987b07-0456-57d8-8802-e248495faf41 |  | note | ○ Attach Survey Conformance Report
label | 36afaf3a-bd12-5acd-8c52-c9e863e53083 |  | note | Method - Document Review
label | cc018ce2-60bb-56a3-aafd-7bb35bdd7bbe |  | note | Frequency - Each lot
label | c8ff3d80-e905-58c8-b525-7fbb7a416d44 |  | note | Category - IP
label | bfd13f01-3592-5caf-a2eb-2908bc18280b |  | note | Responsibility - Surveyor, SE/PE/SPE
label | d05d0c39-a5a7-5552-8487-ade48b18290a |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 6.2 - Flushing
label | 43fbfa24-c70b-537a-8108-eb7042d41e1b |  | note | Reference - Section 702.09 (h)
label | 5bae2049-4aea-5700-995f-9d0bc57ee7bf |  | note | Acceptance Criteria - Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
label | 9759caea-6ca6-5835-adc9-bd3457e14cda |  | note | ○ Attach Flushing Tests Records
label | f04646e8-086f-580b-a24a-9b01118575d4 |  | note | Method - Document Review
label | b55ade86-34be-54ec-b69a-864c3d879820 |  | note | Frequency - Each lot
label | 53a8451b-55ad-577d-b9fa-6c9ce060b801 |  | note | Category - HP
label | 864b7fb1-77c8-5414-b316-d74146969ae9 |  | note | Responsibility - SE, NA
label | c337baf6-510a-5830-8ed3-7f8e69f994e3 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 - Inspection of Subsurface Drainage - CCTV
label | 391b1bba-9b7a-5b60-a823-644a0b6f2660 |  | note | Reference - Section 702.09 (i)
label | f71d4619-8c45-5006-abdf-5a2f6caa3ba2 |  | note | Acceptance Criteria - All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects.
label | 0afd8870-bae6-558b-9aa4-27419dbd8c27 |  | note | ○ Attach CCTV Inspection Record
label | 5dc9be2b-ad70-5bd0-baa8-638a379d46bb |  | note | Method - Document Review
label | ab0121d1-0039-519d-9d44-265722e5826e |  | note | Frequency - Each lot
label | 7683439a-10df-5bca-831b-9eb82c453d3f |  | note | Category - HP
label | 2b4b2c5a-6217-576f-9dfa-3bf2894d9b33 |  | note | Responsibility - SE, NA
label | af8e374f-627a-51fc-ba3a-ec0c6fc1782c |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | 64f3495d-e591-592a-9618-e621541cb5e2 |  | note | Reference - MRPA Quality Management Plan
label | 828fc54c-f2ec-5a8c-9670-8070921e6cdb |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs.
label | 62ed4e9c-54d8-5ee8-a10d-f292a9a739f3 |  | note | Method - Document Review
label | d914075e-6666-5eea-be30-9dd549f257d7 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 6719151b-73ec-5c47-af9c-64457f350a68 |  | note | Category - HP*
label | 312e563e-d80f-5648-80aa-5e7ebebf6146 |  | note | Responsibility - SE/PE/SPE
label | 14639952-de68-5044-bbb6-10f933df6824 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | Final Inspection
label | 393652fa-f944-5342-9df3-8a6a486083e0 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | b2fe1be0-83ee-5221-8eea-1706ab485015 |  | textbox | Name:
text | 7b4eae08-0075-5469-b3c3-ffe5c078fcee |  | textbox | Position:
text | 9071c45f-3936-57b0-a08f-2fdb6371fb58 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-036-STR-Brunt-Pile Caps |  |  |  |  | Yes | ITP-036-STR-Brunt-Pile Caps | b4ffdd33-2c24-49db-b77e-bd3ab0e19a58
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix
label | 098f8cbb-b16f-5ba5-a8c5-0e5a8d868e20 |  | note | Reference - 610.07 Table 610.071 IFC Drawings
label | 440d584f-7572-595a-97e9-b83a5b05a947 |  | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Enter: Teambinder Material Approval number [free text box]
label | f8d85f64-1ee3-537a-a109-5047e709ffae |  | note | Method - Document Review
label | f712a817-1f1c-5b4a-a2ad-a3ed366995f1 |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | f3295a30-cb1c-5c8a-8f5e-2319fd53674f |  | note | Category - HP
label | 018b73a2-4f89-5fe6-93a1-239bb3ee38fc |  | note | Responsibility - Nominated Authority
label | 812f2c64-f726-57dc-833b-ed35a7a29248 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | 9a5b8ae8-c176-5aca-9db8-87b7ac923590 |  | note | Reference - 611.05 (a)
label | e3baaa8c-50d9-50c4-91b8-7b87f3b485a1 |  | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Hold Point Ref Number [free text box]
label | 4ba8642b-ac29-59a8-a6ab-467c0a25f67d |  | note | Method - Document Review
label | bbe1050b-ec9a-5f44-a700-6c8b688d325f |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | abcc6bdf-65c5-50cc-8c51-83a6cc015630 |  | note | Category - HP
label | 56da5718-0146-56f8-8335-f5855f68a6f4 |  | note | Responsibility - Nominated Authority
label | 542b40b0-a3a8-5f1c-a021-bf8c439dbe37 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Bar Chairs/Aspros Certification
label | f5182306-a9ca-5b9f-8f5e-0ac52757a04a |  | note | Reference - 610.26 (a)
label | ffd3b82b-7c1f-5593-a9ea-c5ba4469c020 |  | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require testing to demonstrate suitability to prevent excessive deformation under loads. Concrete aspros require annual compressive strength and soluble salt testing is required. Concrete bar chairs and spacers shall have a maximum VPV value at 28 days of 12%. Bar chairs and spacers made of wood, metal, plastic coated metal and site made concrete shall not be used. Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 47585ae9-b0ee-5416-a604-c69472db9b43 |  | note | Method - Document Review
label | 23bab01d-7137-5ee9-885c-1185ee2cc45d |  | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | 53482a8b-5f0f-5456-a4f2-a1e19dd7fa1c |  | note | Category - HP
label | 86e9b33c-3476-59f8-943b-211d8d4b60b1 |  | note | Responsibility - Nominated Authority
label | d8f08528-5738-5b7d-a954-ed0c0766dbe0 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Evaporative Retardant
label | aa1b76ec-f6bc-5e63-86ff-a2870dc469e4 |  | note | Reference - 610.17 (f)
label | 7dc00732-e762-5209-9cca-d6f9bacdcf55 |  | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 6227f7f6-86c6-5e45-8397-3c17c1bb10ff |  | note | Method - Document Review
label | dfd4bd8e-e9fe-5d3c-a67e-e75bebd406a3 |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | a7664b82-b560-52e5-b646-ad326e356aca |  | note | Category - HP
label | 69133545-15b9-560d-9019-c64cbbed397d |  | note | Responsibility - Nominated Authority
label | 9995aa5a-bed7-5a10-8f0d-866cec3f2cbc |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Curing Compound
label | df343d77-5a91-5b13-95f8-c2fe8c58aa45 |  | note | Reference - 610.23 (d)
label | 2c88a27b-4e5b-5fca-8627-710b811e524c |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 838e7672-9cce-576f-87f2-1f141ac3bd0c |  | note | Method - Document Review
label | f7831b20-bf6b-5497-93d4-b4f46577bda0 |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | 191471df-abeb-5335-865c-86930d6d0e76 |  | note | Category - HP
label | 7452cfdb-26c8-523c-95d8-444f871ab536 |  | note | Responsibility - Nominated Authority
label | 3d05fec2-a235-570d-bbbf-68bd0b026389 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
label | 02553d14-aca3-5cb0-9494-a9736db49898 |  | note | Reference - 610.18 (a) (i)
label | d6049262-2162-527d-8b49-604bee995860 |  | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | a7cc3dd7-7a23-5494-b7f3-d30eeb9233b5 |  | note | Method - Document Review
label | 412f0b13-ab6f-5c17-b327-d8357d75cc0c |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | f616ea0e-6475-5512-879d-73ccf3846a89 |  | note | Category - HP
label | 5806d0c6-fdd4-53fc-81cd-0c2f85598d27 |  | note | Responsibility - Nominated Authority
label | 8a3965d8-0e9f-561b-9f71-9de3563c6c18 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Concrete Sampling and Testing Procedure
label | 11e93264-5ea7-5b67-91bc-1be690858dde |  | note | Reference - 610.18 (a) (v)
label | 7cfe810e-fa8e-5e0b-9e4b-11de6b945037 |  | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 12ee03ca-8ccb-5ecc-a49b-565390d39d9d |  | note | Method - Document Review
label | 39c93cd6-f5f5-53fe-bfc5-c61861bd22b4 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | a4d29fb3-ee9a-5cda-9919-1d079f6e5901 |  | note | Category - HP
label | 83db0f00-1350-5e74-8a88-88ba3da9a1ec |  | note | Responsibility - Nominated Authority
label | 355b3673-881f-52d5-b0e2-0de81210f696 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
label | 51fd7a40-6c56-5aa8-a4e1-5b7b7120741c |  | note | Reference - 610.18 (a) (iv)
label | f1caeba5-c0e3-53f4-a2eb-54f4d556cdde |  | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements. Minutes of this meeting to be submitted to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 6edb911d-be2d-5fa6-93b8-9c27ca6f5b17 |  | note | Method - Document Review
label | f14b4117-34d6-54b2-980e-f766cfa389f4 |  | note | Frequency - Once, 1 week prior to placement of concrete
label | 9e3d0734-9472-52ef-8dbc-b68333b2376d |  | note | Category - HP
label | af1aed21-bbeb-513c-80e4-f68e01ad4922 |  | note | Responsibility - Nominated Authority
label | 7662a40d-3c79-5789-9b86-daaf5597fded |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
label | a44284f2-d9f7-505d-9119-2446530b58ad |  | note | Reference - 610.17 (a)
label | bd78e9e5-92cb-52cb-a848-ba5928132145 |  | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 34b66f28-d37e-55f3-865b-470702efdbb0 |  | note | Method - Document Review
label | c16a2413-0475-5677-9160-d50a63e06da9 |  | note | Frequency - Once, 2 weeks prior to placement of concrete
label | 5767eb76-8d4e-5918-9f94-2d99c7d8129f |  | note | Category - HP
label | b0e1274d-2c7b-5a85-80ff-f81d67e7cbdd |  | note | Responsibility - Nominated Authority
label | ea74d491-7d10-5bb8-be26-85e062d1a404 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
label | 85014965-373a-57f7-84a4-265b306c89fd |  | note | Reference - 610.23 (a)
label | 243fcd1c-dfcd-59f6-9314-5a1af354cb71 |  | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 3a78b946-4ae4-56b3-9cfd-fcd0668f9d37 |  | note | Method - Document Review
label | 4531e6be-1ce7-55d9-86f7-0047868056d1 |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | ce397625-3a26-5014-94e5-f7926460cc6b |  | note | Category - HP
label | ccdd4086-9409-5d30-a79f-ae31eb840d65 |  | note | Responsibility - Nominated Authority
label | a080db56-cb10-54b7-9824-73251cd09552 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Concrete Drilling Procedure
label | d02111c9-3663-5578-8608-f9d3ae273b4e |  | note | Reference - 610.46
label | f4b068aa-2fbf-549c-8a11-359a5d71f800 |  | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services. The planned locations and drilling procedure shall be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
label | 51f971b6-34d5-5d26-98cb-3a6e9f3a8f01 |  | note | Method - Document Review
label | f1c7e833-e86d-54e2-aa3a-0dd508d7545e |  | note | Frequency - Where applicable, once, 2 days prior to drilling
label | 6bc4e780-2ec1-5d14-bea6-94e16d881333 |  | note | Category - HP
label | 3ce4a568-d872-56be-867b-5cf24b920bbf |  | note | Responsibility - Nominated Authority
label | be6bee66-a562-5651-bd79-596652f10e89 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Temprature difference measuring-Calibration
label | a0454849-f6dd-5880-b529-5a866b601461 |  | note | Reference - MRPA Quality Management Plan
label | 0df6f689-124b-5494-954f-8f27ebdae715 |  | note | Acceptance Criteria - Calibration records for Themocouples are valid and up to date. Attach: Calibration certificate
label | 77e08991-58ff-56f6-a6c9-297e709d3590 |  | note | Method - Document review
label | 61c897b8-4d76-5955-b7cd-18358574c9bd |  | note | Frequency - Where applicable
label | 8696ea57-93a3-5729-be50-acf2129a9355 |  | note | Category - HP*
label | 539d1f40-283d-5d07-8dac-0e639cd8eff3 |  | note | Responsibility - PE
label | 3b17d02e-81ec-54f4-b07f-4b1f76a4a277 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
label | 3209893c-c0cf-5f8d-84a9-2f97032316d5 |  | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
label | d14f2fcf-3297-5b7c-99a4-7f13f087bd96 |  | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
label | d4f66754-849b-5b28-b0af-9a914436e9d9 |  | note | Method - Document Review
label | d0252a74-d461-5a2a-b342-ad52c2ec3c61 |  | note | Frequency - Where applicable, once, prior to welding
label | b6bc1b00-4974-508f-9bcc-de90da54004e |  | note | Category - HP
label | 48e9b073-eb69-5d6c-9ffc-382c55c0a56d |  | note | Responsibility - Nominated Authority
label | 4a32f467-83b1-5176-ba3d-dc1335617445 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | e388ce43-9895-510f-a339-aa447144bc7b |  | note | Reference - MRPA Quality Management Plan
label | a9dc8304-d5ea-58e3-94a6-ae026935d1d8 |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 5ca144d6-20b3-5461-87b4-56eecaec5d0b |  | note | Method - Document Review
label | f2b50cce-7042-5016-8e03-4617c7f4ecd6 |  | note | Frequency - Prior to starting Works and at regular intervals
label | 21805050-d3e5-5d0b-a67e-84f4d3411997 |  | note | Category - HP*
label | cdf5209f-15e6-58e1-a23c-a2b5bea1346d |  | note | Responsibility - All
label | 09642fee-c2fa-541d-a206-6529bad3a30b |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out
label | ce15e68b-50ea-5c65-8508-11a7105c71d5 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472
label | cf484311-050b-5b76-8297-13304e5422ac |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element. Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | f3665e28-0538-53be-9e2b-0164b26c77c4 |  | note | Method - Measure Visual
label | f000f582-cd35-59f7-ad04-b6609b40fbbf |  | note | Frequency - Each element
label | e98a011a-199f-588e-adc2-2b54a63c4ce8 |  | note | Category - IP
label | 916b6110-d987-582b-a435-887e27ccddc9 |  | note | Responsibility - Surveyor SE/PE
label | 8bd8aab1-dfe7-5f87-bb3e-d09bd793c183 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.3 - Piles - Completed Prior to Construction of Pile Caps
label | c61bb648-eb1d-505f-9817-a9e10720d44c |  | note | Reference - IFC Drawing
label | c57d8280-e42b-51c3-a6fd-509758e4c329 |  | note | Acceptance Criteria - Related piling Lots are closed. - Pile design strength is achieved - Integrity and Dynamic tests performed and interpreted (if applicable) - Pile is broken back to the design level - As-Built Survey performed - Related piling NCMs are closed Enter: Relevant Piling Lot Numbers: [FREE TEXT]
label | 5e6cfee2-ba05-5a8a-bee4-733674f62998 |  | note | Method - Doument Check
label | c456396b-2b4f-5787-b834-a83ffc4ab3f5 |  | note | Frequency - Each Element
label | 54267abf-b229-5597-b058-4a688f307b14 |  | note | Category - HP*
label | 419d6b2d-4f47-506f-9a60-5f837e41f514 |  | note | Responsibility - PE
label | e95aa341-c3e4-5444-bd6e-3f98b1a701a3 |  | note | Verifying Documents - This ITP Signed Off Piling Lots Closed-Out
checkpoint-status |  |  | checkpoint | 4.4 - Excavation support
label | 4ea0c2c0-769f-565d-8442-5b5ce579f9f5 |  | note | Reference - 602.02
label | 58d25467-8960-526f-b4c6-ea4d4d30addb |  | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal. Where applicable, a PTDT approved for use. Enter: PTDT Ref No. [free text box]
label | 44eef87f-4d1b-5160-964d-b36e7f13aa90 |  | note | Method - Document Review
label | 485751f4-4486-50ff-9493-4281e361347c |  | note | Frequency - Where applicable, not less than 10 business days prior to excavation
label | 7edb9410-5a16-57e8-be9b-ab1fe8f55c38 |  | note | Category - WP
label | bcfd5a4e-16fd-5f5c-9744-8c9202278145 |  | note | Responsibility - SE/PE/SPE
label | b912b57c-58ed-5c75-96cc-30c2502005df |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.5 - Excavation Inspection
label | 7a998f3c-a6b4-50ea-a8ec-b9b8f0cd26c5 |  | note | Reference - 602.03
label | e2b1a4df-5e84-550a-ab32-9566289ad1f0 |  | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | 4db0caa9-82ef-5bd8-a39b-00d7f5ffa12a |  | note | Method - Visual
label | 82f60e4b-cd65-5567-864d-6baaafa60506 |  | note | Frequency - Where applicable, prior to placing blinding concrete
label | 9c85cb4c-db68-5cbe-ae52-822617255102 |  | note | Category - HP
label | 3245ec29-4f9b-5c0b-9e99-b5f2239b840b |  | note | Responsibility - Nominated Authority
label | 75f39ccf-44be-588a-adb6-90021ebdd9ab |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Formwork Design and Construction
label | a4839947-0c63-5e62-acf3-c5aec3417913 |  | note | Reference - IFC Drawings 614.04 614.05 614.06
label | d761bcee-ca5d-508d-b3da-b038cea48dea |  | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected.
label | dde44b48-b786-5b73-a1f8-72fc75482562 |  | note | Method - Document Review Visual Measure
label | 345d8b74-72b1-50ad-a8ff-7e3e4b4794e9 |  | note | Frequency - Each type of element
label | a8ecfc0d-0698-574c-8fc6-34f6127695cf |  | note | Category - IP
label | f31825ed-3262-5942-8adb-6ee7b529cba7 |  | note | Responsibility - Temporary Works Designer Proof Engineer SE/PE/SPE
label | 6f6f4e75-40fa-5392-98ad-e900c66b1d49 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | 25ea7377-8e9b-5f64-8930-a90f52c9dc94 |  | note | Reference - 614.08
label | 4aa95979-26b0-5687-841b-8a8e5ac59a8d |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Pile caps with heights greater than 2.0 metres Any member for which self-compacting concrete is proposed. Attach: Attachment A Attach: Attachment B
label | abdab0c3-ee7d-5653-b58a-07c260e22436 |  | note | Method - Document Review Visual Measure
label | 5e1d66f9-07d3-5413-9cdf-0b75f90bc163 |  | note | Frequency - Each element (where greater than 2m)
label | 9056429c-a03b-5ec1-9c50-5e93296dbd28 |  | note | Category - HP
label | 2a809e8d-d10b-5692-89af-9df1e9994827 |  | note | Responsibility - Temporary Works Designer Proof Engineer
label | ed93240b-c595-5089-ba26-0cc5f50d070e |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | b969eda7-182d-5517-9ed6-7dd5395dd4de |  | note | Reference - 614.08
label | 4429d295-0d32-5954-b55c-7c6a1d1ea8ca |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Pile caps,with heights less than 2.0 metres Attach: Attachment C
label | 29e85043-0873-520c-9e0b-ae284f2ca9b1 |  | note | Method - Document Review Visual Measure
label | 82ef2331-da67-5c8e-bb4e-67823690c818 |  | note | Frequency - Each element (where 2m or less)
label | 3880e2ee-6beb-51ca-a094-3921ba29b5ec |  | note | Category - HP
label | 4d87cdb7-2b58-5408-b11e-4d6e893c136b |  | note | Responsibility - Temporary Works Designer Proof Engineer
label | 52d4b6c6-297a-5807-a010-c0f1135bbc6c |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Pre-pour Survey
label | a756eefa-5fc4-532f-970e-24f60fcda23e |  | note | Reference - 610.47 (a) Table 610.472
label | 4c3c6924-b846-56e5-b2ed-1d3804e9a136 |  | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | 892170e0-eec9-5d2f-9513-6a01433abcfc |  | note | Method - Measure Visual
label | 533bae3b-893b-5c55-bc12-b1aa09ea202e |  | note | Frequency - Each element
label | 58ab9f30-d3dc-54ae-b1d7-27c1dfde181f |  | note | Category - HP*
label | f92249e5-0f58-52e2-b8cf-eec1b1443ffc |  | note | Responsibility - Surveyor SE/PE/SPE
label | e67159f0-57e6-5836-9bfe-4fd93f33027e |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.5 - Reinforcement Placement
label | e8cf548b-4a76-5604-88f6-5af7249f61ac |  | note | Reference - IFC Drawings 611.06 611.09 611.10 611.11 611.12
label | f935207c-3926-5ada-a018-1191b97e86d0 |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings. Projecting reinforcement is the correct length and location. Splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour. Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | 5f959ebb-bb8e-58a3-8928-0871cadf5fa4 |  | note | Method - Measure Visual
label | 999ca954-48a7-544d-80ef-e06447150c6a |  | note | Frequency - Each element
label | 6bcefbad-0866-53f7-ac92-660412f1b9db |  | note | Category - IP
label | f31eccae-8815-51a4-9690-d6d0274d2484 |  | note | Responsibility - Foreman SE/PE/SPE
label | b8d6d75c-fd2b-552a-b848-3b25009e5389 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.6 - Cast-in Items
label | 74032e67-0a68-5ac5-a62e-4430d341fa43 |  | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | 19eff7aa-b5e2-5175-be09-119875dd996c |  | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement. Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress. Tack welding of any cast-in items shall be performed by someone pre-qualified to do so. Grout tubes shall be fastened at regular intervals to prevent kinking. Placement tolerances to comply with the IFC drawings, if not specified, use the following: i. Bolts, ferrules, projecting bars & couplers = ±3mm ii. Running dimensions of a group of the above = ±6mm iii. Ducts and conduit location = ±12mm iv. Diameter of ducts and conduits = ±3mm
label | 07bae29a-ab97-53a6-95e5-079116261330 |  | note | Method - Measure Visual
label | 10c99e81-0598-5305-87a4-0dcb25b72bf5 |  | note | Frequency - Where applicable, each element
label | 5b5cd102-82be-51da-af46-d500cebfe5f5 |  | note | Category - IP
label | b7b13819-5351-59e5-a634-0b06a207bfb0 |  | note | Responsibility - Foreman SE/PE/SPE
label | 518f4944-6da8-5e27-a327-b032fc5156cc |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.7 - Thermal Differential Monitoring
label | b3dbe9ee-97a3-52e0-bbc4-562e6ebe8f33 |  | note | Reference - 610.22
label | 43b37f9d-ed19-5286-99c7-dde0352682ac |  | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | 1824cc2e-619b-5fa8-a9a6-ef7ae0205b30 |  | note | Method - Measure
label | 10e6ae45-50fc-5fc2-9f9c-944d23e2eb1b |  | note | Frequency - Where applicable, each element
label | 92ee9284-1a01-5f1e-bb32-1c50ae9dbd00 |  | note | Category - IP
label | 68505c5a-4573-58f6-a9f8-4ee5407859f2 |  | note | Responsibility - Foreman SE/PE/SPE
label | 59066a98-70c4-5c2f-b3da-91094bf775bb |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.8 - Pre-pour Inspection
label | a8418297-a8db-5adc-b9f4-834705652d17 |  | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | 2a670680-9925-5b26-9f6b-efc981610529 |  | note | Acceptance Criteria - Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority All foreign material has been completely removed from the forms.
label | f6442cdc-a37a-5464-922b-e3725801d92f |  | note | Method - Measure Visual
label | 0d033ef3-9c0a-5e3e-be91-4bf4e8aee380 |  | note | Frequency - Each element
label | 2e66489e-4e71-5094-8a1e-0bde763030d4 |  | note | Category - HP
label | a9a01ec2-6180-5e0a-8767-d59429059993 |  | note | Responsibility - Nominated Authority
label | 1935b835-6d91-54e1-8d02-bbcf732855de |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.9 - Weather Conditions & Evaporation Limits
label | 52d2349c-307e-551d-b120-6f5dc3623c04 |  | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
label | e019b690-805f-5104-9f29-7d5012ef03c7 |  | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record.
label | 861237e2-651c-56c4-a4d1-2de5a89ce4f0 |  | note | Method - Measure Visual
label | f5f08055-dd6d-5b1e-88a4-c1a3be708423 |  | note | Frequency - Each element
label | feee0e70-eef7-5d1e-ad70-9b4a8ad524cc |  | note | Category - IP
label | 95b32c73-613c-53a0-bfd7-279a58006522 |  | note | Responsibility - Foreman SE/PE/SPE
label | a2c513c3-6ac8-5ca7-a982-987f97e867f1 |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.1 - Concrete Testing - Sampling Frequency
label | 49628ef9-9b11-569f-83f5-aa2141365d2d |  | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
label | cbd55bc6-cbf6-5cb5-bc04-6343ada4578c |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing). Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork. Record: Required information on the Concrete Pour Record.
label | c36f7e20-5697-545d-80f2-d8acd21fbb80 |  | note | Method - Test
label | 894c0213-360e-51c8-a157-99bdfa938bca |  | note | Frequency - Each element
label | 88b84979-b791-5889-ab83-7add31bef937 |  | note | Category - IP
label | 4757910e-e230-5800-88ef-1215b8b323bc |  | note | Responsibility - Concrete Tester Foreman SE/PE/SPE
label | dce900ae-6e0e-56a6-8fb6-31e3cbb8e82e |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.11 - Concrete Testing - Slump
label | adbe7890-fdbf-5c2c-a067-2eecdd318fdf |  | note | Reference - 610.16 (c)
label | 7c757053-1731-5391-b78d-86b406c6ce79 |  | note | Acceptance Criteria - Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record.
label | d3cb471a-9cba-557b-8543-a98346f2488d |  | note | Method - Test
label | 19d2de68-c9ef-5c6e-852c-fca524efb403 |  | note | Frequency - Each sample of Standard or Superplasticised Concrete
label | a52de42d-dc1e-5a4e-8166-15cd8b4f9fbf |  | note | Category - IP
label | 894fe283-17cf-5666-a2e5-9f8296973af7 |  | note | Responsibility - Concrete Tester
label | 6d31fab1-8b11-5f40-96d3-45035d9229a8 |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
label | 059938be-7222-59d3-84dd-d4e3101c0eb1 |  | note | Reference - 610.13 (b)
label | 21c16234-0814-5e54-8d5d-bcee18e0aba4 |  | note | Acceptance Criteria - Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record.
label | 07ddf00c-2422-599b-9e61-5871eef2e8f7 |  | note | Method - Test
label | 470a573c-84e7-5aee-8440-524fdbaac5e9 |  | note | Frequency - Each sample of Self-compacting Concrete
label | f7dfdddf-4c64-5a28-93e6-96ab498d3240 |  | note | Category - IP
label | 72a4aeb1-a877-5339-8bbf-dc11f48586a8 |  | note | Responsibility - Concrete Tester
label | 8d393093-43a0-5420-b944-23209e44acfa |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
label | 784217b2-cd71-5d98-92a4-9561a48f4bbc |  | note | Reference - Site Sampling & Testing Procedure
label | b71cc5db-dc01-5ff2-b149-32174bed1bf3 |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record.
label | 65b49233-8e98-55cb-a313-6f0a9a2aae36 |  | note | Method - Test
label | 2ebfe147-c255-5ec0-a115-0ce9b7c7edbf |  | note | Frequency - Each sample
label | ca4113c2-b1cd-5294-9817-90339ff156fc |  | note | Category - IP
label | 3355880a-5d21-5d36-a0de-257c41e22b77 |  | note | Responsibility - Concrete Tester
label | 36e91db3-a563-5f66-a905-1c57eb6d4fbd |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.14 - Supply & Discharge Rates
label | d6d41efa-8e54-5e3e-99b2-640a36825c0d |  | note | Reference - 610.13 (a) & (f)
label | 9304e8a3-f9f8-5b1b-aba7-43c2988c7693 |  | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed. No water is to be added once discharge commences. Maximum time between batching trucks is 25 minutes. Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants. Concrete that stiffens or is showing signs of stiffening shall not be used. Record: Required information on the Concrete Pour Record.
label | a7eb4195-110b-5d2a-965c-2dc8a174cb51 |  | note | Method - Measure Visual
label | ece1186d-ae13-5ed7-b0e8-94f8223ca23c |  | note | Frequency - Each load
label | 6af35a40-7fee-5573-8e89-566a34f6666e |  | note | Category - IP
label | 31700686-168a-5811-9808-c26a924f8c36 |  | note | Responsibility - Foreman SE/PE/SPE
label | 5a191b49-e06d-5c11-bdbb-b4f83cb5d3fe |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.15 - Placement & Compaction
label | 1d9cefca-7f2c-5239-9b40-1dfcd720f1b0 |  | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b) 610.18 (d) (i)
label | 6d4ae2b9-5fde-57a1-9a6d-0776ac97d12c |  | note | Acceptance Criteria - All concrete batches are traceable. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Concrete is not dropped freely from a height exceeding 2m. Concrete is not moved horizontally by use of vibrators. Adequate compaction is ensured Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments. Concrete layers are not more than 350mm Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence. Vibration continued at each point until air bubbles cease to emerge from the concrete. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets
label | f936e992-53fe-5bb0-b51a-45f88403bd62 |  | note | Method - Visual
label | 20ac63c1-21d2-5c9d-8220-12cbe0173a65 |  | note | Frequency - Each load
label | e797608e-9e37-5d61-82c6-42a8b0f9205b |  | note | Category - SP
label | 2097c9bc-d0ae-5b1c-9532-cf1c3639b103 |  | note | Responsibility - Foreman SE/PE/SPE
label | 3be2b370-367f-5f39-87f8-b2d44f2ee641 |  | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
checkpoint-status |  |  | checkpoint | 5.16 - Surface Finishes
label | d24d3199-f298-5213-9ec1-7d7931425e70 |  | note | Reference - IFC Drawings 610.31 610.20
label | 86002295-ed83-516b-8aa8-41d5c81b937d |  | note | Acceptance Criteria - Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 22bf0399-bfe3-5bdb-862f-7a4c2cb3cfd4 |  | note | Method - Visual
label | d77dd1df-4f54-5d4c-ae84-71b48acf2c22 |  | note | Frequency - Each element
label | 2ef4dbee-e43f-5e4b-adcd-955980b26c22 |  | note | Category - IP
label | bfa48b61-403e-51aa-8931-e9851827efda |  | note | Responsibility - Foreman SE/PE/SPE
label | cce04cbd-e8be-50f9-8b5b-8e143e927bb5 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.17 - Curing-Top Surface
label | 21106287-c6c9-5dfd-923b-f8c69a96c9f6 |  | note | Reference - IFC Drawings
label | db24251e-7158-56ae-b5e3-79ab765ffd06 |  | note | Acceptance Criteria - Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | a8c3717c-33f1-557f-8205-e8f6042a6bf2 |  | note | Method - Visual
label | dd81ecf0-79c0-5369-8945-a416b99ee15f |  | note | Frequency - Each element
label | c19d6163-e362-561b-a4ea-290694eb23a5 |  | note | Category - IP
label | 6949eefa-03e7-57b6-a949-6ea8057f1a69 |  | note | Responsibility - Foreman SE/PE/SPE
label | a3ced9e4-0561-510e-b599-778f6ac3a749 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.18 - Curing after formwork removal
label | 1177183c-8c8a-537f-8c4a-8ca7b9cda6e2 |  | note | Reference - IFC Drawings
label | bfd61cc5-7b35-5ab3-9798-5f3b6996b73e |  | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | 6916ef18-d578-50fa-afd5-25751c66017b |  | note | Method - Visual
label | 5a946f86-3d4c-5bb0-b88f-35e1c0b5acb2 |  | note | Frequency - Each element
label | c2ae9517-a300-5f31-aaf1-20c5dfa786da |  | note | Category - IP
label | fe1a2b81-8fe3-5a42-b718-ef536ec1efa5 |  | note | Responsibility - SE
label | d739062c-1955-519d-9660-76e375af4ef8 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Thermal Differential Monitoring
label | 180f3af9-db14-5361-97f9-552ab465d6eb |  | note | Reference - 610.22
label | e9c16f31-2d63-5c0b-b033-440ca8d6aa36 |  | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints. Attach: Thermal Monitoring Report
label | 397aee8b-0cca-5789-b7d5-3b89e2722d9e |  | note | Method - Document Review
label | d69cb643-31fd-52a1-9fa9-7429ea02ad73 |  | note | Frequency - Where applicable, each element
label | d56c6635-96ee-5d35-bcc8-f72c250f09ef |  | note | Category - IP
label | 6337281c-953e-51a5-88b8-74e9182e22bd |  | note | Responsibility - Foreman SE/PE/SPE
label | 3bc3103d-8daf-59c4-aa40-062bf039f9e8 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
label | d7d92cdf-7538-5a99-887f-4263b9077cb0 |  | note | Reference - IFC Drawings
label | e0a02ec8-5468-5aaf-b12d-61e9561d7a1e |  | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | c5134ead-afd7-511c-9428-a6f68cc2f97d |  | note | Method - Document Review
label | 9f503083-889b-53c1-a38a-06928eaced2b |  | note | Frequency - Where applicable, each element
label | 7da1fb81-ed75-5f83-b5da-ba43b4386943 |  | note | Category - IP
label | 7b0d1eb5-d8ed-5458-a188-98a50acac138 |  | note | Responsibility - Foreman SE/PE/SPE
label | 6f276df5-bd3c-5f6d-a5b3-80fde98c3bb1 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.3 - Surface Inspection - Cracks
label | 8135bdb3-3f5b-5c02-a5a1-611791b02ca3 |  | note | Reference - 610.24
label | 671c3703-6228-51cd-9f4d-42a4b89ca8ba |  | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1) If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | e56636d0-b71e-5196-a56a-6427c4da5d50 |  | note | Method - Visual Measure
label | a8a83e94-bdd5-5fcf-8885-9772f90403b4 |  | note | Frequency - Each element
label | 2f4e73ad-7a09-553c-bd73-fa04d8dddf5e |  | note | Category - IP
label | 58a84b2a-4317-51ee-b803-6d827c9d0530 |  | note | Responsibility - SE/PE/SPE
label | 017c7c26-b0d4-571d-bf49-4e416de2ea74 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.4 - Surface Inspection - Surface Finish
label | e338adb1-c2c6-5f21-b13a-93617fb156f5 |  | note | Reference - IFC Drawings 610.31 (a) - (n) 610.32
label | 2732711f-abb4-5929-8d78-d0159f97b4ac |  | note | Acceptance Criteria - Comply with the IFC drawings and specifications. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | 0a2c0c57-2c8e-5690-aacf-2c26294f50d0 |  | note | Method - Visual
label | 505f59db-423d-58d6-9a00-b9436aa219dc |  | note | Frequency - Each element
label | 50cb94fc-5c3a-5fb0-a6dc-9a2f7a9f41bf |  | note | Category - IP
label | b6f07abc-b362-5c19-a91e-4d8f549561ed |  | note | Responsibility - SE/PE/SPE
label | 18d89ee0-1eff-5033-b9e7-328ea8894424 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.5 - Measurement of Concrete Cover
label | 9c04e3e0-47ec-5c78-9d7a-88683570dddb |  | note | Reference - 610.34
label | 274c1769-1da8-5123-8448-d801b4d0c376 |  | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area. Minimum 10 no. measurements recorded in each area. Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority. Attach: Covermeter Check Record
label | 9cd3f90b-1132-5e50-82b7-3584757cdbaa |  | note | Method - Measure
label | 565212a3-3f9a-52f9-8ff0-f96d0b8030c1 |  | note | Frequency - Each element
label | 79e6f8f0-dc6f-5e30-bce2-6eed0e444c52 |  | note | Category - IP
label | fbeb93bc-13e8-582c-a824-a7a8c0be6448 |  | note | Responsibility - SE/PE/SPE
label | 6d441370-0c64-59fb-b1a6-285300ed16f6 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | 3ae1967f-7536-58e9-831d-6cb6f3bec996 |  | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
label | ce716b6b-c005-5d03-aa7b-174c644cd372 |  | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour. Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure. Attach: Concrete Test Results or Maturity Test Results
label | 2a478ee0-8c9d-5937-aa30-c976ef70df12 |  | note | Method - Document Review
label | 5024904e-fd6c-54c2-ac7a-88083c407e4c |  | note | Frequency - Where applicable, each substructure element
label | 76141904-b90b-5645-b555-d1149325e74a |  | note | Category - SP
label | 79ac799c-26fe-535c-8569-b8e41383db16 |  | note | Responsibility - Foreman SE/PE/SPE
label | 5dc8cd0c-6c6d-5a80-910e-ae04c0bba17b |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.7 - Compressive Strength Test Results
label | 49b05607-c868-5f9e-a4ff-b2f17444e919 |  | note | Reference - IFC Drawings Table 610.05.051 610.16 (g)
label | 7019dc92-4d64-58eb-9b20-96f1ecedee0f |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results
label | 91f9378e-7d6b-5b3f-8de3-054ef2f4151e |  | note | Method - Document Review
label | e7447507-9e95-5994-803b-99ee192cefe3 |  | note | Frequency - Each cylinder
label | 5a063d64-0095-59d9-b590-642d3a3fc8f2 |  | note | Category - IP
label | f78635f8-b362-5bca-8cd3-867093b9298c |  | note | Responsibility - SE/PE/SPE
label | aabdd767-7979-5168-8e07-12f403eaf0fa |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.8 - As-built Survey
label | 4e787d84-d422-57b9-87fa-a4574e74bf81 |  | note | Reference - IFC Drawings 610.47 Table 610.472
label | 962cdbb0-781c-54a2-beeb-94d0a523b697 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element. Attach: Survey As-builts / Survey Report
label | 5b975817-1518-573c-8f41-0a7016b9d07d |  | note | Method - Document Review
label | 765bb70a-b6e9-570e-9716-13a64ea836a0 |  | note | Frequency - Each element
label | d5c19e56-f3e0-57a1-b37b-605b35871e84 |  | note | Category - IP
label | 92612b34-43ab-5aa7-8161-a063acf24b74 |  | note | Responsibility - Surveyor SE/PE/SPE
label | 6b39aee2-7915-5ae9-b374-bbaeb333ac89 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
label | 6a4afbfe-1b73-575f-b113-932a5654c0f9 |  | note | Reference - MRPA Quality Management Plan
label | 4522cd81-a806-539f-8fcf-188d6c7462d8 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | f016c3da-ccb4-5fb0-a86d-104b8bac0380 |  | note | Method - Document Review
label | d9f9b507-14f0-5884-b597-9ad21ce95c55 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | d0b4a905-4103-575e-aaf7-f7a5c4f2f428 |  | note | Category - HP*
label | 102165b4-8eb2-51ad-acf8-cfef477a884a |  | note | Responsibility - SE/PE/SPE
label | 6001f37b-89fd-56e1-8d62-e505adc23557 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | Final Inspection
label | e68c1839-171a-5fc5-9e3f-fc66ae4fb0e3 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
label | 817ce759-d9f5-5c9e-8bf7-b580ad3cad02 |  | note | FH Environmental Team
label | afe8fcbe-1e68-5e0e-ade5-7f30bd2dcda5 |  | note | Name:
label | a41be08b-b9c0-58f5-a862-f0a70144a852 |  | note | Position:
text | 2fb7352c-ca95-5352-8ef6-b45d0f69e3f5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-035-STR-Brunt-CFA Piling | itp |  |  |  | Yes | ITP-035-STR-Brunt-CFA Piling | b61f8fec-a5d5-4184-a4ff-0bbf1c503723
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 0aa960c2-e638-5872-aa47-dbadda66f16d |  | note | Document Title: ITP-035-STR-Brunt-CFA Piling
label | f9c2bf03-6063-5f79-b7ae-cb49968bc48b |  | note | ITP Description: CFA Piling
label | 91b5e611-c235-5c96-a7c8-8ed00acd3ca8 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | d0d4aed7-b66d-5dec-be2a-1c85ce0314ff |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 5fd47d5f-b1b0-5a64-a1df-b4c862bfc5ed |  | note | Revision Number: 0
label | 081f5b39-e865-58f7-8e44-6d5c50f75a46 |  | note | Revision Date: 5/05/2023
label | ae9751c9-bf32-5399-a1dc-b670b7814f7c |  | note | ITP created by: Yasna Naicker
label | bc737d5c-fa2c-5651-a507-b41c1d4fea6a |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | c1e55f20-2d9f-57b7-8203-0c51e766d5b2 |  | note | Reference - VicRoads Section 607 March 2015
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 22a5fd19-e18c-545f-9695-927bbb11be8f |  | note | Reference - VicRoads Section 610 June 2019
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | cfba98d1-6992-53fc-a685-eac8b646be78 |  | note | Reference - VicRoads Section 611 November 2018
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | b5bc179c-f0bb-5513-80bf-e85ac73d5c53 |  | note | Reference - AS2159-2009
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | c1ae77b6-4ffb-586d-8197-7432ebf42623 |  | note | Reference - AS3810.1-2015
checkpoint-status |  |  | checkpoint | 1.6 - Non Dependent
label | 01ec5812-6224-54cd-986e-4d8e78bc4be7 |  | note | Reference - AS5100.3-2017
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix
label | 61fff819-1753-5ec3-8359-99ecbd4f84be |  | note | Reference - 610.07, Table 610.071
label | 5675c286-19c8-560f-9362-c68423319d7e |  | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | c60d1012-9917-58fc-81dc-ba8beeaa8ad1 |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 04fae702-0112-5fe1-a8b2-105487c0adeb |  | textbox | Enter: Teambinder Material Approval number
label | 43e9672b-aab9-53e6-af0c-e0db817db98d |  | note | Method - Document Review
label | f0411c03-a63b-5476-9b40-fd3c3e9d3438 |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | 7c034814-067e-50c5-93a7-8d94f9e6c325 |  | note | Category - HP
label | a4d62623-2ef5-580b-971f-67241c2893a4 |  | note | Responsibility - Nominated Authority
label | 7166a5e4-2ddb-57f5-8469-136b586aa805 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | fd46d9de-df7a-54fa-80a0-0220f5568809 |  | note | Reference - 611.05 (a)
label | 197357fe-355a-5da7-8385-dcf3c2832123 |  | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
label | 42f31bfc-b7cd-53b8-ac3c-d7302de1a2b9 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 739bfb7b-368e-5160-9d1a-56d91111df41 |  | textbox | Enter: Teambinder Material Approval number
label | 576478af-b335-5f54-9f5d-df81f59da018 |  | note | Method - Document Review
label | 99991d44-c451-5c21-bad1-e01183cde786 |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | 045e11f0-27f5-52d9-a43c-8b55bbaf3711 |  | note | Category - HP
label | 153f2f98-e6f0-5444-a1b7-e859ae6896a1 |  | note | Responsibility - Nominated Authority
label | e9af8e13-551b-5556-b048-b65de482af4f |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Bar Chairs/Aspros Certification
label | 2ec36ef9-6f09-5f32-8d83-dd4b69215502 |  | note | Reference - 610.26 (a)
label | 872de1c1-522e-5102-ac60-257cda23adc0 |  | note | Acceptance Criteria - Wheels, and spacers require testing to demonstrate suitability to prevent excessive deformation under loads.
text | 2eef4d22-1a56-516c-9528-6e8c6a67dcfb |  | textbox | Enter: Teambinder Material Approval number
label | b4f2ea8a-f740-51d8-9815-987481080ce8 |  | note | Method - Document Review
label | 9dff2b56-8480-5113-854f-1dd599bb558e |  | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | a13589ed-c3b8-511c-b28a-2261bb3df2c6 |  | note | Category - HP
label | b90cc05b-20fa-5ce4-b2dc-31ccb076450e |  | note | Responsibility - Nominated Authority
label | fd976820-a9b8-5744-be65-16db7f905b6e |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Working Platform certification
label | 18193ce2-9108-593c-94fa-dfd9787bfee9 |  | note | Reference - Piling platform design
label | ac073311-34c9-5ea0-9de1-a902cda543bd |  | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement.
label | e015bbaf-e19a-52b6-a1c0-178db552aef9 |  | note | ATTACH: Piiling Platform Certificate
label | 6262479f-4570-5533-9920-712e3b797ae3 |  | note | Method - Document Review
label | 849f7800-378e-5603-a5b6-6eefe00491b6 |  | note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | cbe10d9c-c85b-58f8-81f8-91ce069577ae |  | note | Category - HP
label | 83a1d080-0c0e-5f85-a919-f93fcfd49baa |  | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | e4868708-efc7-5e7a-b7d6-7d0c8cd2f8c1 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Concrete CFA Pile Design
label | 4ad5053f-6e67-5b6e-ae2a-b072afb4c33a |  | note | Reference - 607.01, IFC Drawings
label | 09240cbe-a7c8-52a5-a69d-116b94f6fc43 |  | note | Acceptance Criteria - Concrete CFA piles shall not be used in foundations for bridges and other structures on or over roads without the approval of the Superintendent.
text | 28301354-041f-5079-b2b8-e4daf0ce03de |  | textbox | Enter: Teambinder Approval number
label | 8472fd42-c3ea-5a06-9f5f-49f422ca6c6e |  | note | Method - Document Review
label | f5f374b7-11bd-5401-8917-2e6f53ec78b6 |  | note | Frequency - Where applicable, once, 4 weeks prior to the commencement of piling
label | 45f9a7eb-eee9-51eb-90d1-433f4871c9c3 |  | note | Category - HP
label | 9aa99a41-f1e7-55bc-b3bb-9cde323bd8c0 |  | note | Responsibility - Nominated Authority
label | 58536aee-4be6-5d73-863b-ad06357aa892 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Piling Operations Work Procedure
label | 2e4ecb90-dfe8-5db6-b9f1-3c9306d34c91 |  | note | Reference - 606.03 (a)
label | 69a93ec0-f990-561f-9f52-3b1180a35ea6 |  | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
text | e8210c62-2a73-5a27-9d59-7a010b01ab58 |  | textbox | Enter: Teambinder Approval number
label | 07fc85fb-c6ed-5529-82b2-cb87b23df484 |  | note | Method - Document Review
label | d7c4dec6-34ae-5846-9407-6e25f893ec59 |  | note | Frequency - Once, 4 weeks prior to the commencement of piling
label | 9ab2cfb6-2588-5ace-ab3e-203c540dbd24 |  | note | Category - HP
label | ad532b41-6b9f-5cd8-bfe3-ac39efceeb46 |  | note | Responsibility - Nominated Authority
label | 4f0df4e5-82f7-5c62-a0ca-e0d7ab5cc820 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Casting Under Water Procedure
label | 9cf1162d-79f2-59b3-92c0-95f0d04ea05c |  | note | Reference - 607.04
label | 2c1b9b44-fbfb-56c0-a50f-d71784221a7f |  | note | Acceptance Criteria - Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
text | 5f833e8d-158a-56d8-a275-536e6b481685 |  | textbox | Enter: Teambinder Approval number
label | d80ceae5-889a-514b-a9f5-f31b458a8c9b |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 8ed89d73-7b82-593f-877e-631e684ce762 |  | note | Method - Document Review
label | 899879f7-78ef-52df-a02e-ec7117e4e516 |  | note | Frequency - Where applicable, once, prior to placement of concrete
label | 364025c4-ab98-5fcb-8c65-f5364aceef31 |  | note | Category - HP
label | 7b7e50da-f9c8-5cee-aad0-a84d6ee52d25 |  | note | Responsibility - Nominated Authority
label | f65a4fa4-35b1-5c3a-9cdc-b7045ffa40b0 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Dynamic Pile Testing Procedure
label | edd3aab1-cefd-5ad1-b5d8-078f886809cb |  | note | Reference - 607.07
label | 8ee3bf09-700e-5c14-9435-6836952ec79b |  | note | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | 7c1c8737-5710-5cc8-9b88-7cc0702cc60c |  | textbox | Enter: Teambinder Approval number
label | a8f8ec6f-66c2-511d-a9ca-6940dc3d4ac2 |  | note | Note: Attach Superintendent Dispensation/Approval if not undertaking this test.
label | a93b50aa-5240-5769-88cc-2eb29db6f48d |  | note | Method - Document Review
label | 580c6004-3a3c-59ac-a22e-53f241eba7c2 |  | note | Frequency - Once, prior to testing
label | 7d66b00c-996a-5ad3-b6ba-781d21ea5e02 |  | note | Category - HP
label | c62b6032-8e1d-5927-8287-5ac3bc13fbe8 |  | note | Responsibility - Nominated Authority
label | ad2f7672-6a79-5692-8cc9-8ba3c99b3e5b |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Pre-qualified Pile Testing Consultant
label | 256f5573-bbc4-5975-b7d7-a1726f2a7890 |  | note | Reference - 607.07
label | 0c2c3d9b-afac-588f-85cf-87e9b92b7439 |  | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | 9bc73370-b743-5cad-b350-a8093ad28baa |  | note | Details of the consultant to be submitted for review to the Nominated Authority.
text | 7ec44a5e-0c90-5871-9acc-d854515d4d8b |  | textbox | Enter: Teambinder Approval number
label | 59e4b968-2d58-5bad-9d7e-d62d84e62b46 |  | note | Method - Document Review
label | 31f3a859-ffd0-5c98-b236-654f3c5e4a83 |  | note | Frequency - Once, 2 weeks prior to testing
label | 7b54256c-7621-5ad1-b355-fd8835ee392d |  | note | Category - HP
label | f1ebb6f2-bb55-51d5-9c7f-476a06c70165 |  | note | Responsibility - Nominated Authority
label | c59ff1a3-3625-51ed-a149-1d006670df32 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Reinforcement Welding Specifications & Qualifications
label | 76c7b424-3d19-5010-a0d5-ae88821db508 |  | note | Reference - 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
label | 93426112-fc27-51e6-8cfd-3f81f30ac2b7 |  | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
text | 9566ec70-5a53-508b-a502-a94f87402045 |  | textbox | Enter: Teambinder Approval number
label | 960110e8-e88a-5365-9219-42500a6a9d71 |  | note | Method - Document Review
label | acd0683a-6c15-5fe1-834c-6883989c5310 |  | note | Frequency - Where applicable, once, prior to welding
label | 68add482-d74b-5335-a288-839ce03790ca |  | note | Category - HP
label | a96a6cfc-cb35-51c3-9859-ca2b4ef63fe1 |  | note | Responsibility - Nominated Authority
label | 881a921f-fce2-599b-8e91-285cc2f73dbc |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | ec6a2c09-fb6e-5c29-816e-d7ae28548d9c |  | note | Reference - MRPA Quality Management Plan
label | 7cc34870-5907-5e61-99c2-86aa5581708a |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 2aa6c8ef-e2ab-5f01-9b5d-295b41e54f2c |  | note | Method - Document Review
label | e972c1c8-d7f9-54ba-908d-b152cd45e114 |  | note | Frequency - Prior to starting Works and at regular intervals
label | a24f43fb-22ef-5424-acf9-1fac12da10a4 |  | note | Category - HP*
label | 3fd06e54-517c-50a7-a0c9-6572b88571f5 |  | note | Responsibility - All
label | 976cfc1d-a942-5563-b53b-85ff4c54e429 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out / Set-out of Piles
label | 8750bee5-7c62-57fa-a162-b25902d5d749 |  | note | Reference - IFC Drawings 607.06 (a)
label | 2c41c2b8-3de5-5869-82d7-a5d56dbbc58e |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | 089ca947-5d55-5c57-91c8-22bb0f33da04 |  | note | • Ensure Pile Set-out is correct and working area is clear.
label | c3749257-33cb-5940-b876-ff51b69090dd |  | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | 84e3b278-29a2-5164-b7f1-85255f094a58 |  | note | Method - Measure, Visual
label | d747b0ce-56bc-5c92-841a-f72f957ec76c |  | note | Frequency - Each pile
label | 567f59cf-2b69-5a36-98a0-d3d091f4280f |  | note | Category - IP
label | c4eb5a53-aab8-5d3f-87a4-99ef1860077b |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 5299ebf9-5242-5c97-a59c-4cf5b1b728fb |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 4.3 - Protection of Adjacent Piles
label | 5a1b9bb3-b292-577e-a9cf-31b2a82b4420 |  | note | Reference - 607.05
label | 7b54e630-577f-5b7b-b92a-66aab5290895 |  | note | Acceptance Criteria - Pile construction shall not result in damage to adjacent newly cast piles due to ground vibration.
label | fe5b7f0b-4859-50b3-bbcb-c140e936b6bb |  | note | • Pile excavation shall not commence within 2 metres or three pile diameters (whichever is the greater) of a newly cast pile until the concrete in the newly cast pile has attained a strength of 15 MPa.
label | ade4e829-b6a7-5402-99aa-9633bab87384 |  | note | Attach: concrete compressive strength test results, and Lot maps to show pile strength, locations and sequence of piling works to ensure pile protection requirements are met in accordance with VR 607.05
label | a993aa98-891e-5c9d-b837-145a2e07af8f |  | note | Method - Measure, Visual
label | 06d00eb7-34e7-5ad6-a88c-abf4efd706a4 |  | note | Frequency - Each pile
label | 363ea986-3b17-5f78-b651-752a1e459589 |  | note | Category - HP*
label | 5ca95659-bb17-565a-844e-b93ee0454818 |  | note | Responsibility - SPE/PE
label | f67e3490-89ab-507c-921b-c7a8f62bc38b |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Reinforcement - Inspection
label | 90b5255e-370f-5e44-93e9-cfc61c225570 |  | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | 9c1882bf-8111-5b2b-a59d-a92272dfec67 |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 2c2802f5-1a33-5aa6-b8c4-06ecf369a943 |  | note | • Projecting reinforcement is the correct length and location.
label | 5924312e-76a6-5159-82f5-026018370a1f |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | 836b6004-482f-58d3-8c69-5aa0e130a5bb |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | 3d35cb49-b438-5dd9-b626-b4accdb2184d |  | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 2ab7b32b-4ed5-5e6a-a3e7-9ddc7e047d19 |  | note | • The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
label | 4c18b7c6-ed74-516f-9307-58a6344ef842 |  | note | Attach: Prepour Inspection Checklist
label | ae51b4c0-55a2-516f-a508-39729517802f |  | note | Attach: Steel delivery dockets, checked if correct to steel / cage design, fabrication checked as acceptable, cage/splice lengths matches design.
label | 8958a577-eb89-55ec-be46-63d15cc806b2 |  | note | Method - Measure, Visual, Document Review
label | b4cf6b91-ae5e-5492-955d-3eb47c7ba0c6 |  | note | Frequency - Each pile
label | b87b2c1b-ea7c-5c34-9d29-7619c4aa200a |  | note | Category - IP
label | 17565e47-428c-521a-a5dd-1e71eacd0f92 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 39f49942-27c6-5b54-8e76-524906a75095 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.2 - Reinforcement - Electrical Continuity
label | 5c5dafec-aef9-5b7e-ad7d-336bbdca139b |  | note | Reference - IFC Drawings 610.29 (d), 610.43
label | 07196ca3-8053-5e94-806a-3bdeb853f188 |  | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
label | 0d15d2b2-575e-517a-800c-607c4be36f4e |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | f75fe682-6b9c-52b0-a1ec-341aa8ad56ec |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | 64c35a9e-f4f9-5673-9916-86f1283bf120 |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 45ee079f-c0ac-5206-a4e1-cbb67ced3b7e |  | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 3dba28f4-9e48-5bf6-857f-d9ee1337797c |  | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage, and Prepour Inspection Checklist.
label | a2b7bbca-e01b-50a5-8c20-2b26d688cc35 |  | note | Method - Measure, Visual
label | 20e7dc73-e228-5910-980d-33abde5b1737 |  | note | Frequency - Where applicable, each pile
label | 9396d32c-d342-5a27-b9ee-696925eaa128 |  | note | Category - IP
label | fa676bf3-c194-5bff-85f0-43662fbbbafa |  | note | Responsibility - Earthing Engineer, SE/PE/SPE
label | 02cce1d1-3f7a-5eef-b9bc-9933318573f9 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.3 - Augering Operations
label | c589cdde-24bd-5fe6-b9d4-201c71ad3d41 |  | note | Reference - IFC Drawings 607.04
label | 4d3a9fab-e126-5e3e-a1fe-a88e73db204c |  | note | Acceptance Criteria - Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | 702e52bb-4b95-5677-93e8-95db835138dc |  | note | • The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process.
label | 2a0102c2-5c14-57f9-83f4-ad396a10673f |  | note | • Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
label | 37cf969a-8d00-5ad5-b69a-16618446d6da |  | note | Method - Measure, Visual
label | d5eab16d-a068-546f-99cb-c197764b0fee |  | note | Frequency - Each pile
label | 7387cf89-db8e-5d14-9a98-5bec8e8f928d |  | note | Category - IP
label | 22664e86-f9ee-5575-9f3c-22794e7e66dd |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 2fc65949-4740-5e7a-a3a6-bd636f94ce07 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.4 - Inspection of Excavated Material
label | 6176eb11-0554-56e0-85b4-363a58b1ad45 |  | note | Reference - 607.04
label | 02bf8312-a1b0-5862-b08b-b57d4ef13197 |  | note | Acceptance Criteria - Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | c1fbd861-5733-510d-b602-662b110b1138 |  | note | Attach: Geotechnical Field Sheet or Report
label | 151c352a-bdc3-5c30-986a-7298d24254fc |  | note | Method - Measure, Visual
label | f24f4c37-8ab7-507c-bccc-93c70f7d194a |  | note | Frequency - Each pile
label | 44174ff0-f1a2-55f1-bd12-298f00babea2 |  | note | Category - HP
label | 8de12356-fa73-5965-b741-eecc42823bde |  | note | Responsibility - Geotechnical Engineer
label | a01ca903-644c-5541-a42e-add00cb8bee8 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Increase in Depth Beyond Design
label | de499ebc-bb00-5382-8c98-2d03c1f9fd15 |  | note | Reference - 607.04 (a - d), Piling Operations Work Procedure
label | 8efd0d88-778b-5e71-a081-92ca0d5f6542 |  | note | Acceptance Criteria - Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity.
label | 459ec03a-9a80-5909-a38d-e11cae305d11 |  | note | • A full account of the changes shall be submitted for approval to the Nominated Authority:
label | bcd6b1c4-0bf3-56ef-ab4e-c078d6af71a4 |  | note | Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
label | f0139d5c-4716-5e91-a22d-0ea098e6dcc4 |  | note | Method - Measure, Document Review
label | 5ae8bef4-3e81-5941-8067-8228b211037c |  | note | Frequency - Where applicable
label | cc5940fc-4ebb-5459-a51c-0d2feb56556d |  | note | Category - HP
label | 31ced675-4ad3-5413-9cf6-da94b0afd3da |  | note | Responsibility - Geotechnical Engineer
label | ec990ccd-e27f-5843-82a0-fdb97180b16f |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Weather Conditions & Evaporation Limits
label | 0cd12fbf-eae6-5dff-b250-d4bdeba79fb1 |  | note | Reference - Hot and/or Cold Weather Concreting Procedure, 610.17, 610.17 (a) & (e), Table 610.171
label | 313a061c-2adb-55f5-8191-a9285c321e59 |  | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | f4e127ba-4532-545a-9d3b-e90ca9d9742c |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 13f8d3a4-f782-5965-8d5b-78f433f2bb7b |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 94c3b8a9-b6c5-5005-8dbf-826e8e8a2bd6 |  | note | Record: Required information on the Concrete Pour Record.
label | acf3e947-0d25-5f6a-9980-8ec5fdc55763 |  | note | Method - Measure, Visual
label | 777c2318-8b33-5d8e-b1a8-a7339715a2e7 |  | note | Frequency - Each pile
label | 02389c6d-783c-50ad-95ff-c04d9920636a |  | note | Category - IP
label | 6355464b-9ae6-5c42-9d9f-a5d054ac00e4 |  | note | Responsibility - Foreman, SE/PE/SPE
label | d1712511-2c20-5ecb-baec-70a15e761c02 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.7 - Concrete Testing - Sampling Frequency
label | 724a044f-36e5-5a17-afec-f10dac0fac86 |  | note | Reference - Site Sampling & Testing Procedure 610.16 (b), Table 610.161
label | 8c0a9c8e-0bca-5473-9eca-c372cee673c8 |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | ff87ea71-f0c1-5e97-9a62-c846cefd80c6 |  | note | • 0m³ to 10m³ = 1 sample
label | 3605c8ff-e29c-5890-ba22-9182d16b803b |  | note | • 10m³ to 25m³ = 2 samples
label | e5339f0e-23fc-5ad6-ac31-bc5e8758141e |  | note | • 25m³ to 50m³ = 3 samples
label | d1b4ff75-108d-5bec-8923-d31d879c1e14 |  | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 7b47c896-72a9-567d-bf35-b7841254d1f8 |  | note | • For each additional 50m³ and additional sample shall be taken.
label | 06d686ac-0ba3-53d7-ae76-4259a549ff97 |  | note | • where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | d116f5fc-831e-5055-b6d5-618f6be2fc74 |  | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | a2215a73-bd5b-5994-85e2-b5da16ce9aba |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | e6b25e08-8cc9-54c0-83c3-aab586782b19 |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 1207547b-e641-5c0a-a2fc-c490d8b2e5c0 |  | note | Attach: Concrete Pour Record
label | df804b9b-05bc-52c4-975d-714a9ef5e85c |  | note | Attach: Concrete Dockets
label | ed41d273-5244-537a-a2f9-156a859f93df |  | note | Method - Test
label | 1840d52a-1ce6-5488-b441-b36463f010a1 |  | note | Frequency - Each pile
label | d299b58b-f6ad-53f4-a887-e4b0acf55265 |  | note | Category - IP
label | 2f8f2bef-e4a4-5d53-a11f-331c0ab7ddc0 |  | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | e4129f3b-cbc0-512b-bfa3-4389ef7313bf |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.8 - Concrete Testing - Spread, Passability & Viscosity
label | f6e478a6-d64f-5712-889f-7d54a59f9f8e |  | note | Reference - 610.13 (b)
label | 4f146275-01ae-5fe4-94b0-934a96e9e130 |  | note | Acceptance Criteria - Spread range = 550mm to 750mm
label | 0e76f407-c748-5bde-ade7-584a25a8d4a3 |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 67ae64be-6584-5845-a4cb-f34345fe6be2 |  | note | • Passability = ≤10mm (aggregate height differential)
label | dbc2d120-5a09-5891-806e-40700db67d90 |  | note | Attach: Concrete Pour Record
label | 49e214af-1886-51c9-b2b6-b4505f0a0f29 |  | note | Attach: Concrete Dockets
label | 245a54d7-79f1-59e5-abba-aea25eda9685 |  | note | Method - Test
label | 87f9bf45-3f4b-5a43-9c84-cf1d537c450a |  | note | Frequency - Each sample of Self-compacting Concrete
label | e53b91dd-a183-5e6b-bdbb-0527b7c0a761 |  | note | Category - IP
label | 01c68b91-57b5-59b5-9afe-a366712db270 |  | note | Responsibility - Concrete Tester
label | a8532648-89e8-55c5-8043-3eaedabb39f2 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.9 - Concrete Testing - Compressive Strength Cylinders
label | c62af0cd-d7ea-5e2a-b93b-a606c039874a |  | note | Reference - Site Sampling & Testing Procedure 610.16
label | 1a4d2db6-ef58-5b38-ac16-d4327427e8fb |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample in accordance with VR 610.16.
label | 21eead5b-08a0-5089-8c7e-eabca07e3211 |  | note | Attach: Concrete Pour Record
label | bae6ae17-979f-5f4f-a1fb-704267d5bac9 |  | note | Attach: Concrete Dockets
label | 264accb4-469c-544d-908b-13b9b227a5d0 |  | note | Method - Test
label | 2dfcf173-d627-5d28-a1f4-ebf3bcc3e47e |  | note | Frequency - Each sample
label | 44a966bb-78ea-57fe-b3dc-6779a357f72a |  | note | Category - IP
label | 66915a1a-73ce-5a45-b7b7-5ba351418534 |  | note | Responsibility - Concrete Tester
label | 1f94d9c7-26c1-5c5e-bd2b-420f7c5eb505 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.10 - Concrete Placement & Compaction
label | 775fd08b-d4bf-5487-b529-f02ed40c3679 |  | note | Reference - Piling Operations Work Procedure 610.18 (a) & (b), 610.18 (d) (i), 607.04
label | b54271a3-1c36-5a6d-998c-e4714c27b0bc |  | note | Acceptance Criteria - All concrete batches are traceable.
label | 680e06a8-c42e-5d09-aaa9-304f22e23290 |  | note | • The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
label | 10e67b12-d505-5fe1-98b6-7ba4c79fb93c |  | note | • The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
label | 3f0cd7ba-d47e-5752-90fe-014320e63802 |  | note | • Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
label | fe86878a-89b1-5d50-81b3-8e7db06b0668 |  | note | • Concrete shall not be dropped freely from a height exceeding two metres
label | c7db1aaa-5354-5703-8112-1f1ad90b4c02 |  | note | Record: Required information on the Concrete Pour Record.
label | 332191ee-7a22-5428-8f4e-fe636040bc43 |  | note | Attach: Concrete Pour Record
label | e5d829c2-d1be-5a17-89ac-0704121c4b9b |  | note | Attach: Concrete Dockets
label | 8cd48764-ccd3-59db-be1d-2916c2528418 |  | note | Method - Visual
label | 1b60ac25-8c66-5800-9f0f-b2e963d48025 |  | note | Frequency - Each load
label | c9bc8f04-340f-5263-a6bd-6003b34fdfdd |  | note | Category - SP
label | b8443c96-e362-57d3-a7f6-41632bdf465c |  | note | Responsibility - Foreman, SE/PE/SPE
label | a06d9733-e8a5-5876-8f21-5dba858bbecb |  | note | Verifying Documents - Foreman, SE/PE/SPE
checkpoint-status |  |  | checkpoint | 5.11 - Reinforcement - Placement
label | d5b50a5b-63e9-5fd3-9583-93bdca1389a7 |  | note | Reference - IFC Drawings 607.04
label | af90d0b3-80c8-5f33-ab3c-325aad1153a7 |  | note | Acceptance Criteria - The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
label | 84b70667-a4c5-5b1b-b79e-e5dbac27c41e |  | note | Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
label | 9beac68c-b274-5868-bc9b-7a8cef9c7811 |  | note | • If the cage cannot be positioned into its final level, the pile shall be rejected.
label | a25a40b8-7667-5cdc-a74c-ae9d51065d0a |  | note | Method - Measure, Visual
label | a12fae45-dc95-5ddc-9aef-22ee3b6c7fb5 |  | note | Frequency - Each pile
label | 8cfc98f4-ac2b-5067-bfac-142187e9419e |  | note | Category - IP
label | ef5b02e3-d19c-55ce-b7c8-78579864161f |  | note | Responsibility - Foreman, SE/PE/SPE
label | fef82a69-eb18-5d8c-858a-9bac81cf49f3 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.12 - Cast-in Items
label | 2a6283e8-4c17-5f34-a76e-ae0ca78d1080 |  | note | Reference - IFC Drawings
label | efae13c5-2ef6-55f6-a2e1-e9f60876d972 |  | note | • 610.46 (a), Table 610.462 (November 2018)
label | 61e6f95d-86b5-57d9-b657-a11ff2446326 |  | note | • 610.47 (a), Table 610.472 (March/June 2019)
label | d763eebd-2d11-5e52-85af-734f751f51e1 |  | note | • AS3810.1 Table 3.3.6.2
label | 730e9f1e-c900-55d0-95a8-3d03f9bce244 |  | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement.
label | ae2512a8-52cd-5b95-8299-af6acbfb2889 |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 4ad0bf9b-d4cd-5f67-b5fc-b2dfcf10d472 |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 8780252b-bdfa-5874-9916-7d83892e94db |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | d331e6ee-fedf-5bf5-bf7e-b2e0deeb2106 |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 3a6a10b0-37a2-5a76-9938-5ad2a3506c2b |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 43964141-8381-55fd-b651-56cb4f8c27e4 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 501fdcad-b4a9-51fe-9245-6ea9a4bff4ad |  | note | iii. Ducts and conduit location = ±12mm
label | 8f0e2b56-e4d7-5f26-9d7e-433e93b33074 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 6acc8164-a0e2-56ff-9df9-263c53bf103f |  | note | Method - Measure, Visual
label | 71f1e1a8-ce48-583c-ad09-bdfd06198734 |  | note | Frequency - Where applicable, each pile
label | 73b67de9-f086-57fb-924e-3b63112597dc |  | note | Category - IP
label | cc41d956-7d8d-507b-b64e-47b24e650f73 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 423480be-3135-552a-95c3-bfed6fcf59c1 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Pile Trimming
label | 651659f6-4071-509a-a028-9a4e481fa681 |  | note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 607.04
label | 0874bf55-bc8b-5c31-ab05-bbe4db9468fc |  | note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | 3db87bc7-e555-5827-82fe-850f89e4007c |  | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | 902b6ffa-ec9e-5b75-a814-18a9d855528c |  | note | • Any weak or damaged concrete shall be removed back to sound concrete.
label | d7ae451a-50f3-599d-9065-53eb762526e2 |  | note | Method - Measure, Visual
label | c237e938-dc11-541b-93c8-cecab930a8cc |  | note | Frequency - Where applicable, each pile
label | d69090fb-b133-5b2f-ac8b-492cbf2e076e |  | note | Category - IP
label | e49dfbb7-3857-590a-bc9f-c185292e6976 |  | note | Responsibility - SE/PE/SPE
label | 4494a7f3-c2d2-5d7e-9972-bd1899d12f4d |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.2 - Compressive Strength Test Results
label | d15ad762-e826-56d7-a4bf-a7e19f634473 |  | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
label | 43df1580-ce2e-5ba6-a441-daeab583cf61 |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | e8fc75c0-45dc-5320-bf3b-e8c822702886 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | d4512cad-9c34-5f36-b9c1-25bbdad12017 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 70203cdb-d772-50eb-a688-58617aa2beb0 |  | note | Attach: Compressive Strength Test Results
label | 4502c68e-81bb-5c66-904f-8e506031a7ac |  | note | Method - Document Review
label | e9fe83bc-da66-5a92-b316-8ce3577ce6ec |  | note | Frequency - Each cylinder
label | 58755d29-43e9-5b9e-8b68-70ed83b17291 |  | note | Category - IP
label | bce13450-e9ae-58df-8e97-0c9afe6190c7 |  | note | Responsibility - SE/PE/SPE
label | 7442624b-4735-52e9-b984-fed1c804d24a |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.3 - Pile Integrity Testing
label | 7ff63f61-dd13-5093-b954-2e13eadc80ac |  | note | Reference - 607.07, AS2159 Clause 8.8
label | 4467728d-acca-5b6e-a384-87473cb6d451 |  | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | 618e7e64-e609-5f6b-8af6-aaba1d5789d8 |  | note | • Cross-sectional area = ≥90%
label | 280ac7bb-131b-52ab-884b-42b412bb6424 |  | note | Note: To help ensure the Pile Integrity Testing is done properly, proper planning on site activities are to be considered, i.e. plan for PIT to be undertaken with minimal works around the area to avoid induced vibrations that may affect testing results.
label | 311ce2f6-05ed-5f40-b7ed-93b57310b465 |  | note | Attach: Pile Integrity Test Report
label | fed01780-15ad-57cf-99b3-50bba918e984 |  | note | Method - Document Review
label | cb280dbf-4298-50a9-880b-694f017f495b |  | note | Frequency - Each pile
label | 3694a9aa-2969-5817-b65e-3db6929c2475 |  | note | Category - IP
label | 8bc3219d-c1f5-5bde-92dd-35213ba03277 |  | note | Responsibility - Testing Consultant, SE/PE/SPE
label | a10e8c15-83c3-5a37-a85e-90e9d4ba38d3 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.4 - Dynamic Pile Testing
label | 661d8995-283f-5577-8ec8-b69649d04a49 |  | note | Reference - 607.07 (b), AS2159 Clause 8.7
label | a6aa5a3a-720b-5daa-9d34-4ff05ec4bfc4 |  | note | Acceptance Criteria - Where applicable, Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | da1c4900-9fa8-548e-955d-496df4df7d55 |  | note | • Measured Ultimate capacity = ≥ values on IFC drawings
label | 1c12ca18-d35d-59d8-987f-e852843442fe |  | note | Attach: Dynamic Pile Test Report
label | 13132dd3-84ec-5c9d-b5da-f242e8799927 |  | note | Method - Document Review
label | 8c04da0a-b056-56ce-bc58-74d7efeea9e9 |  | note | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
label | 86bf9df6-d816-5de1-a6ae-d4bf06c2e3ed |  | note | Category - IP
label | 363c927c-a311-5ab5-9b58-17c4ad6d0ca9 |  | note | Responsibility - Testing Consultant, SE/PE/SPE
label | 943c1f47-79aa-5f4b-ae06-5922e21ca7d7 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.5 - As-built Survey
label | 4fb1dcc6-5e95-547a-adf6-507977be6322 |  | note | Reference - IFC Drawings 607.06 (a & b), AS2159 Clause 7.2.2
label | 82e7e41f-5d07-52dd-9d83-474b2055004a |  | note | Acceptance Criteria - The following tolerances apply to piles:
label | 82fe87a6-38d1-5b06-86d0-a9fee5fc13de |  | note | i. Centre of pile head plan location = ±75mm
label | b233b546-0509-5538-b39a-ba639c894892 |  | note | ii. Variance from vertical or rake = 1:50
label | 3262c4ba-6308-53cf-b3b5-f3520f209171 |  | note | iii. Irregularities in straightness = 1:100
label | 887184cf-a4c0-5ffb-ae67-69271fb7b04a |  | note | iv. RL = ±25mm
label | 67fc6ad7-37d7-5b95-ab25-50cae1996b2a |  | note | Attach: Survey As-builts / Survey Report
label | 180fa052-dcfd-5945-914d-c5929eae4fa5 |  | note | Method - Document Review
label | 242073dd-f787-52d9-96fc-0144684fc018 |  | note | Frequency - Each pile
label | 9e3c0d01-a976-5b4c-b50d-8d034b304169 |  | note | Category - IP
label | 4c2474d9-9e83-541b-b490-aa45af04e81f |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 94ad3d89-653c-56c1-9394-c87b943c784a |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.6 - Non-conformance Report (NCR) Closure
label | 2aa97275-b16c-53cb-8fd6-7d1f821cb847 |  | note | Reference - MRPA Quality Management Plan
label | 004a505e-d85f-517e-a609-4d027731ddd6 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 1afc7120-8fdd-5853-b286-048a0b17d13d |  | note | Method - Document Review
label | af22082b-9447-53f3-8c35-71136a90d8b6 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 680b5883-f204-53a0-b50d-0289f37263ec |  | note | Category - HP*
label | b6b9e98a-d2e0-5e6b-94aa-138dc0091736 |  | note | Responsibility - SE/PE/SPE
label | 713af050-3b7c-512b-997f-fbfb92820536 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | Final Inspection
label | 28c9c095-1d3a-530a-8e77-2815ee15e916 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d986f432-74a5-56e9-964d-36757bb156a9 |  | textbox | Name:
text | 5281f24e-9b97-59c0-86c8-b6bc9512399a |  | textbox | Position:
text | 1ee3060a-fcad-5108-8e53-eaf8f9cf1bac |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-030-CIV-Brunt-Clearing and Grubbing |  |  |  |  | Yes | ITP-030-CIV-Brunt-Clearing and Grubbing | ba5f7183-5cb7-4850-8f9e-16a2b3e2d0de
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 8e159dce-c0fc-5a2f-99cf-3f63a72657cf |  | note | Document Title: ITP-CIV-Brunt-Site Clearing and Grubbing
label | a88f30c3-1c99-5145-bf25-935e107a813c |  | note | ITP Description: Brunt-Site Clearing and Grubbing
label | 8aaf5de8-344d-5041-b605-e15f7d3e74a5 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | e27646ab-89b8-53d1-a6d6-29edd40984ae |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 920ca111-04bd-54e4-90da-30818ef50777 |  | note | Revision Number: 0
label | 532cc76d-d04e-57e1-a6ea-f45a16479ab1 |  | note | Revision Date: 28/02/2023
label | 82e97086-0839-5ddb-b3fb-7b539c347600 |  | note | ITP created by: Jason Lee
label | 59706888-a445-5ece-bec2-9fb019c0a56b |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 41274045-7e03-5cfc-bfe9-519c34f415db |  | note | Reference - VicRoads Section 201 (Feb 2023)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | bd9820d7-64f4-532d-8fee-fa48fbb1f7b0 |  | note | Reference - VicRoads Section 204 (Dec 2015)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | ff055742-db8b-5e13-9cfd-f637d6ead5a2 |  | note | Reference - IFC Drawings
checkpoint-group |  |  | section | 3. Preliminaries - Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Environmental Controls
label | f96b350f-03ea-545f-864a-b38eb5881247 |  | note | Reference - MRPA Environmental Management Plan
label | af3fc118-cf64-5be5-99c9-ba02ba6f89f0 |  | note | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified.
label | 6dbbfc26-8422-55e1-affa-048b5ef04591 |  | note | Method - Visual
label | cda550b9-7fe3-5102-91de-7bc7888505a8 |  | note | Frequency - Where applicable, prior to starting Works
label | bcedc756-769f-5605-ab22-005225a0a0b0 |  | note | Category - WP
label | 56a46289-ed66-5e8a-90a2-ddfcf63bad92 |  | note | Responsibility - Supervisor, SE/PE/SPE
label | 5e538427-cb74-57a6-8a11-a991ccf2655a |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 3.2 - Vegetation Removal Permit
label | 9ac1f8ab-382c-56d7-bdf2-a6a62e73b6a1 |  | note | Reference - MRPA Environmental Management Plan
label | 0db262ae-7bf8-5837-80aa-6630a51c9ca4 |  | note | Acceptance Criteria - Prior to removing any vegetation or habitat:
label | cbd48a4a-b007-5686-8470-97831c088414 |  | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
label | bf7cecb2-352e-50d4-9efd-35dae4f666cc |  | note | ○ A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
label | 41fd6293-8d9e-54b2-8a78-3147950d66fc |  | note | ii. fence and sign all sites nominated as No-Go Zones.
label | 06ad73c1-e049-5a6f-a7d9-bf5706f9abdc |  | note | ○ Attach: Vegetation Removal Permit
label | 6154d21a-0e38-585e-9761-c6e8e3d87ac7 |  | note | ○ Attach: Ecologist's Report
label | b1e4490d-b2eb-5217-bc2e-cc3742bfb6a7 |  | note | Method - Document Review, Visual
label | 4d492a62-16a9-5588-af10-9405b8518f6e |  | note | Frequency - Where applicable, prior to starting Works
label | a9796e06-dcb1-587f-9ed6-8548d229a497 |  | note | Category - HP*
label | e3369c96-49a0-5435-8ac7-21428db73f04 |  | note | Responsibility - Supervisor, SE/PE/SPE
label | 1a3fbe70-7c5d-51de-8dec-da1ca3a57604 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out / Limits of Work
label | 7033a169-8831-5f24-97a6-c236517ea004 |  | note | Reference - IFC Drawings Section 201.03
label | 8537a109-996f-587a-8a85-2b37f9bf097c |  | note | Acceptance Criteria - The limits of clearing and grubbing shall be:
label | 8a8dfa2b-fc13-5b6e-8042-1fc9299951a9 |  | note | a. the limits defined on the IFC drawings
label | a05ff1a4-0d08-5019-85b1-ca32ad2a75b5 |  | note | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
label | e2ba3099-74e1-5dd8-b68d-ec21ff8b0c07 |  | note | c. no more than the width required for completion of the Work under the Contract.
label | 15fba5b9-eccb-5e77-8b1e-f35d7dd9283b |  | note | Method - Measure, Visual
label | 2e69f213-391a-5e11-bf2b-5d037f0da46c |  | note | Frequency - Once, prior to starting Works
label | 2c6f3110-4df5-5948-932c-184ec1c58a77 |  | note | Category - IP
label | c728fe2f-29ec-5b6e-acee-5dc637679bdf |  | note | Responsibility - Surveyor, SE/PE/SPE
label | ef0a2d88-5065-5813-9079-0feb05cd53d8 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 4.2 - Cultural Heritage and Areas of Significance
label | 01235c33-bb64-5172-a9e0-4e097adc940e |  | note | Reference - MRPA Environmental Management Plan Section 201.10
label | bfb6425d-21bc-516b-8e81-4e2a4d14282f |  | note | Acceptance Criteria - Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | c1720823-2141-5b0d-a8c1-5e881087a3f9 |  | note | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
label | e5eb9ee8-59fa-5b38-a9fe-440bad117d04 |  | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | e0cba92b-b4c0-5b00-b9de-64c0afda7fd4 |  | note | ○ Attach: Cultural Heritage Report
label | 73fe8de0-13fb-5600-b67e-b0a5a76614d5 |  | note | Method - Document Review, Visual
label | e08f5c86-2a8b-5b0b-bdd1-2e5dcd6213ff |  | note | Frequency - Where applicable, prior to starting Works
label | 456c2ead-ba45-51e7-b0e7-7854231b1b03 |  | note | Category - HP*
label | cf49de65-7951-56fb-8dc0-14998e7e2fe1 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | f82c6fb5-98c5-526e-b6fc-e066f807f40b |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Stripping of Topsoil
label | 940aa0bb-8a1b-5f02-bf75-7f530cbbb63a |  | note | Reference - IFC Drawings Section 204.05
label | 2baf29db-b6e8-55cc-8eb0-3ccdf1360e2b |  | note | Acceptance Criteria - Topsoil shall be stripped for the full width of the formation.
label | e3b65fa1-d8c7-5c4f-9974-499305deae73 |  | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | 6903c3bf-7231-5e09-9912-7a512f32e506 |  | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | eab16182-d4bb-509f-ab26-89c45189cc4a |  | note | Method - Visual
label | 62a58451-9947-5141-a966-224431207035 |  | note | Frequency - Each Site
label | 37fc8206-75c8-5787-929f-8c027933db69 |  | note | Category - IP
label | a45ac57f-cdc0-55ca-9b42-cbb403be9a0a |  | note | Responsibility - Supervisor, SE/PE/SPE
label | c6e72ae6-4f2e-554d-8ef7-1c0774f1888d |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.2 - Stockpiling
label | b661b657-c5f7-5782-bec4-54e5f0c8ab0a |  | note | Reference - MRPA Environmental Management Plan Section 204.05
label | 081fa4de-7415-5bfc-b7db-ccd28d0d30a0 |  | note | Acceptance Criteria - Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
label | db375597-8e73-5ce8-8808-e72e87dd760f |  | note | ○ If this clearance is not possible,additional protection shall be provided.
label | f3c0f298-03b4-5e3b-b1a3-5a8556e111b9 |  | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
label | 271dcf4b-62b2-55f7-b78c-b683e81ed91e |  | note | ○ Topsoil shall be re-spread as soon as practicable.
label | c5d68771-e5be-5c94-9855-212452342383 |  | note | Method - Visual
label | 7d8c706c-0aca-59f6-87b9-3246decde5ea |  | note | Frequency - Where applicable, each Site
label | 0b9e2cc3-3ac9-57fb-84fc-b7a16e81e2f5 |  | note | Category - IP
label | c0550552-c38a-5d41-9907-bc0f5224933b |  | note | Responsibility - Supervisor, SE/PE/SPE
label | cc9218f7-a511-5c3a-af0c-7843ac923cef |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.3 - Abandoned Services
label | ae39f2e0-e89b-5aa3-ae50-a9ec03a179f8 |  | note | Reference - IFC Drawings
label | 6c26e770-2873-56e8-ae4c-60dd370f20df |  | note | ○ Excavation Permit Section 201.05
label | 34a64120-1ebb-5b90-bc23-51ce4f37f07c |  | note | Acceptance Criteria - Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
label | 6ba6291e-d66a-59a2-8db2-e0dfa48132dd |  | note | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
label | fd996bba-5400-5f03-aa9c-6dee2d5d5623 |  | note | ○ Decommissioned services to be disposed of in a suitable manner.
label | 0e0275b4-7eab-5239-b65e-38fa022bb502 |  | note | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
label | 23950f11-c3a0-5908-b3b8-77dee2632d4e |  | note | Method - Visual
label | 27965389-0054-5019-934f-e50c32c1e0e1 |  | note | Frequency - Where applicable, each Site
label | 5ca8853f-122a-5188-b5e6-b75c41b9c0b5 |  | note | Category - IP
label | 6c76dd7b-7d4e-57b0-bf27-99c258c9413b |  | note | Responsibility - Supervisor, SE/PE/SPE
label | ebd33d17-7447-51f5-b7b4-1fe5f554afbb |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.4 - Clearing of Trees and Vegetation
label | 7b3d7c5c-d918-5f57-9e5a-0cd3f7e8e4d3 |  | note | Reference - IFC Drawings Section 201.04
label | fd3faa39-c3ce-59b5-84b2-f655485e413d |  | note | Acceptance Criteria - Clearing work shall not be undertaken outside of the specified limits of work.
label | 38a15f72-6519-5920-b85a-ecbdec9b76e1 |  | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | 09e4c152-87a4-5be0-9535-4e8b2f6a0eeb |  | note | Method - Visual
label | 52bc273a-82e6-5491-b15e-31030df188f6 |  | note | Frequency - Where applicable, each Site
label | 8084b753-1945-5149-888b-d9d8b0c93398 |  | note | Category - IP
label | b12484da-fc0c-5506-9109-d8e11a14924c |  | note | Responsibility - Supervisor, SE/PE/SPE
label | 012c3e38-2b70-579e-a478-5586ea5adfaa |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.5 - Grubbing of Vegetation
label | 0b28bc1c-dfe9-57da-bf01-ac77c1004816 |  | note | Reference - IFC Drawings
label | 596b9fa2-9fed-5afb-addb-1c05a03a3f85 |  | note | ○ Section 201.05
label | b88e69dd-988a-5091-9e7e-6435abeb4a3a |  | note | ○ Section 201.06
label | ce4a36f0-5e1d-5ca0-ac66-6816148dbe0c |  | note | Acceptance Criteria - In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
label | 19edc6d4-7c89-59e8-b85f-83ebddf2d349 |  | note | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
label | 30081dc4-c9d1-5b17-a466-b273981ca391 |  | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
label | fe4211e4-e3b1-59d5-9420-be89cea4db7c |  | note | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
label | eefc6cd6-1740-565c-b23d-4f8a63bade8a |  | note | Method - Visual
label | b15fe6d7-2385-59a7-9292-b45542e3adbd |  | note | Frequency - Where applicable, each Site
label | f7421ccd-c37a-5d30-a1ae-3b2c0249b7a2 |  | note | Category - IP
label | 65f09293-0563-5db4-8098-29ab822c2d07 |  | note | Responsibility - Supervisor, SE/PE/SPE
label | d5d225c9-52ab-5c43-9d62-d587899aefe9 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Disposal of Materials & Vegetation
label | 0af8ef14-2062-53c9-a8e0-47277ac9636b |  | note | Reference - Section 201.07
label | 7e7fc2b5-3739-5c64-ad6d-ed6b7ab38d48 |  | note | Acceptance Criteria - Salvagable material to be used wherever possible, the remainder is to be remove from site.
label | f882d4cf-9eda-5112-9f43-ba707575596d |  | note | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
label | 669ece55-b78f-5055-9032-9ad6d2132985 |  | note | ○ Tree trunks and large branches shall be removed from the site.
label | 9fde0a91-fec6-528c-9c45-113e89062d93 |  | note | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
label | cedd56a7-ccbd-5362-8e90-13e001535037 |  | note | ○ Attach: Delivery Dockets (for Items sent off Site)
label | 0f07b41a-5f5b-593f-82da-24db428dbac2 |  | note | Method - Visual
label | d6e4dcec-b5b4-5954-b853-60381a53828c |  | note | Frequency - Where applicable, each Site
label | ba120b6a-8953-5045-81c0-19efd39162a0 |  | note | Category - IP
label | d7f6fa1e-19fb-525c-a844-9bdb7fe4d1ec |  | note | Responsibility - Supervisor, SE/PE/SPE
label | f978476b-5824-53a0-8ba3-3dec9af342b7 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | Final Inspection
label | 481bc89d-e15c-5e38-9fc0-31567aadafd5 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 69aa806c-5b45-5302-adda-fbeb74558e23 |  | textbox | Name:
text | e8eadce0-323e-557d-b656-35c9b1ea2954 |  | textbox | Position:
text | f18bfb61-9d5b-5479-a614-7395a4212482 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-024-CIV-Brunt-Footpaths & Shared Use Paths |  |  |  |  | Yes | ITP-024-CIV-Brunt-Footpaths & Shared Use Paths | c67bdbe9-c439-46db-a9ae-14ceeee91984
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 1bfe8e83-fcaa-521c-a0f6-03748aed1f1d |  | note | Document Title: ITP-024-CIV-Brunt-Footpaths & Shared Use Paths
label | 83f1348c-d3bf-5d37-b50e-9ae469c2011b |  | note | ITP Description: Footpaths & Shared Use Paths
label | 99a77119-57fd-5991-82ca-002bf3a0db99 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | d18f0a10-c2fa-5f87-82a9-7ae8aa57b661 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 46e3c69c-9bc0-5fcf-87eb-7884fc71f0ee |  | note | Revision Number: 0
label | dd57b9f5-60a5-562b-8f89-c9253d53348d |  | note | Revision Date: 28/02/2023
label | 85bea7e8-52ad-522a-b754-b1984c88e218 |  | note | ITP created by: Jason Lee
label | 0ca26cee-2e75-57be-84ae-9dc54b060efe |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | b4185d05-6796-54fe-9536-ef7a84fd8319 |  | note | Reference - VicRoads Section 304 August 2013
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | f56cb33c-e1ab-589a-8598-833742baa360 |  | note | Reference - VicRoads Section 703 August 2021
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 3d2bd5b3-8546-54fd-a1c5-819732001739 |  | note | Reference - Council EDCM 401
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | fc13dd62-317f-59d5-aae6-87308671a8c9 |  | note | Reference - AS4586
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 20b5ac4b-144b-546a-a83f-0f756eb7a6ee |  | note | Reference - VicRoads Section 812 July 2016
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Bedding Material Placement & Compaction
label | 3c9e193d-a994-59d1-b8d8-9b897d457d17 |  | note | Reference - IFC Drawings
label | 403c7dc7-d5cc-5257-9d92-67136deedfc7 |  | note | ○ MRP-089-C-ACD-DRG-14-BFD-CPT-2211 and MRP-089-C-ACD-DRG-14-BFD-CPT-2221
label | 53530aa6-4907-5f50-9ce2-90cbadef0314 |  | note | ○ Section 812.04
label | a3a05144-2137-502e-8f32-ee1f80e5c1e6 |  | note | ○ Secton 703.21
label | ac7ac269-562d-5302-a825-be2fca2cf8a3 |  | note | Acceptance Criteria - Footpaths: 20mm CLASS 3 CRUSHED ROCK
label | 659e10b9-31f9-5eee-b0fa-ab3654a1e572 |  | note | ○ SUP: 20mm CLASS 3 CRUSHED ROCK
label | 50a1284c-9d55-506f-a789-e5a0dc499f7f |  | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
text | c08ead8c-a7e8-541a-87c5-e563bf69ab46 |  | textbox | Enter: Teambinder Material Approval number
label | 508be8a8-48d8-560a-be5c-22e85bbd111a |  | note | Method - Document Review
label | 52cdaf99-f78b-57a5-a7c1-42c892b8073c |  | note | Frequency - Each Lot
label | db7dd89e-9240-577b-b06d-edc27fa5ac99 |  | note | Category - HP
label | d2175564-5c0d-5ee8-87fe-6971950be314 |  | note | Responsibility - Nominated Authority
label | 163ee965-c4a6-5754-ab2d-3322637b231f |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix
label | e65580d6-41cc-50ab-9ad7-e58f3ae5d00f |  | note | Reference - IFC Drawings
label | cb02efa8-27d7-58ed-a6ed-8b92925d4646 |  | note | ○ MRP-089-C-ACD-DRG-14-BFD-CPT-2211 and MRP-089-C-ACD-DRG-14-BFD-CPT-2221
label | 0738f9ca-1707-5da2-a523-afa4e07ca7dd |  | note | ○ Section 703.05 (a)
label | c7d13439-98ab-590d-9aee-ac8b383011ef |  | note | ○ Section 703.07
label | c43cf9ab-2392-56e8-9326-45a08afafb2e |  | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
label | eee8797b-b11e-5017-ab69-7e8842a72e42 |  | note | ○ Footpaths: 25MPa CONCRETE WITH eMESH FIBRES APPLIED AT 5.6kg/m AT 100mm SLUMP
label | 09d6f886-f50e-59ba-93aa-bff4081b9f89 |  | note | ○ SUP: 32MPa CONCRETE WITH eMESH FIBRES APPLIED AT 5.6kg/m AT 100mm SLUMP
label | 7813cedd-ecfa-5cbe-bbab-d722c687367d |  | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
text | 27ba6be8-0b83-59de-a612-8ef04a123fbe |  | textbox | Enter: Teambinder Material Approval number
label | 74e03b57-1fc3-59b8-9232-171f684a2ec8 |  | note | Method - Document Review
label | f3da797f-1ee9-5c5f-bc6d-7a4876084555 |  | note | Frequency - Each Lot
label | 19118bdf-a36e-5749-b4c2-37e45418dadd |  | note | Category - HP
label | b807dffa-2ce0-55ba-bd77-e2458b188ad4 |  | note | Responsibility - Nominated Authority
label | 9816e9f2-966d-5559-a80f-084d1cedeeb3 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Reinforcement
label | d782bd31-762e-58f1-a2a0-b6faccd893e3 |  | note | Reference - IFC Drawings
label | 1740775c-4ee6-5799-91b0-c738da4a78d8 |  | note | ○ MRP-089-C-ACD-DRG-14-BFD-CPT-2211 and MRP-089-C-ACD-DRG-14-BFD-CPT-2221
label | 43cd447d-c08e-59dc-9f9c-1eb9f03afd86 |  | note | ○ Section 703.16
label | 1d43267b-789d-5772-934d-dccf3d562865 |  | note | Acceptance Criteria - Reinforcement shall comply with AS4671.
label | 6906fbd4-e7cd-5072-92cd-0e6d38694193 |  | note | ○ Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification) following steel mesh requirements shall apply as per IFC Drawings:
label | 4107958f-b97c-5972-bcbc-0fa6869aa752 |  | note | – Footpaths, Residential driveways and Median islands infills: SL72
label | 71ffbd86-aa42-5725-858a-d01ffc1d563d |  | note | – Industrial Crossovers: SL82
label | 93e4efb9-4243-557b-86f4-b06cfd4f3bb0 |  | note | – Traffic Islands: SL82
label | 9c80e0e0-b24a-5a63-8584-a3ff67e7927d |  | note | – SUP: SL92
label | cc48533f-7bd3-5c72-8f7d-81c6e26a2e73 |  | note | ○ Refer to drawing MRP-089-C-ACD-DRG-14-BFD-CPT-2221 - Pavement Composition. PT04 Footpath and PT05 SUP - it states the use of 25MPa & 32MPa Concrete with EMesh Fibres - can you please double check if you're going to use the conventional SL72 and SL82?
text | 90d751b7-3a7a-5fcf-a8c4-adb56a189e0b |  | textbox | Enter: Teambinder Material Approval number
label | 1422087c-62bf-5f72-a685-bc7e067d16c3 |  | note | Method - Document Review
label | 14b219da-ed59-5682-b007-d8500fad6c16 |  | note | Frequency - Each Lot
label | 61af9c47-93fc-587e-8e81-012eebafdd7b |  | note | Category - HP
label | 82b90322-96de-5ea2-a3a8-59845319a923 |  | note | Responsibility - Nominated Authority
label | b10cf40b-4248-5d42-9318-533d1bd48272 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Evaporative Retardant (if required)
label | a4a77a56-c136-56a4-a542-7d08a33cfb7c |  | note | Reference - Section 703.09
label | 91d7748d-c3a4-5da6-bbe3-c5326f80749c |  | note | ○ Section 610.17 (f)
label | 3f70f723-5987-521c-bca8-453e03280194 |  | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | b7e40042-3c88-567e-9614-0f3a9ade65b3 |  | textbox | Enter: Teambinder Material Approval number
label | 199ba761-65d4-5d3c-85b4-27a6636f1af5 |  | note | Method - Document Review
label | 5ffa9297-23bd-58c9-8296-2aa568405b4f |  | note | Frequency - Once, for each product, prior to placement of concrete
label | 94dec77e-775b-51d0-8e34-bcddc79f378e |  | note | Category - HP
label | c14b8f9e-39fc-5ede-9eb8-95ed09ee67c6 |  | note | Responsibility - Nominated Authority
label | 2c0b4624-e945-5c1a-bb03-abe76a28b0a3 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Curing Compound (if required)
label | 02cf34bc-ff92-5e3e-9c2a-51f1ee2586c5 |  | note | Reference - Section 703.10 (a)
label | 7993bcd0-d512-5d64-b21f-d06336e700f2 |  | note | ○ Section 610.23 (d)
label | 8d0ab502-91f4-5224-8a8c-b182bfd2aea4 |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 6100d778-5a1f-5a4e-9a93-a8d0b4fae32c |  | textbox | Enter: Teambinder Material Approval number
label | f842ee45-2268-5e56-abfe-4bf6ce1f9e86 |  | note | Method - Document Review
label | ef194e5a-4761-53bb-897e-ad1055018a9e |  | note | Frequency - Once, for each product, prior to placement of concrete
label | a572726d-3431-5025-98fb-b55e66e22296 |  | note | Category - HP
label | 6ece0f71-a980-5f9b-a89e-421dfb630925 |  | note | Responsibility - Nominated Authority
label | 858d3b39-0120-597e-9be2-380fb25c030d |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Documents
checkpoint-status |  |  | checkpoint | 3.1 - Survey Set-out
label | 23552379-9db0-55be-be99-f329fe36964a |  | note | Reference - IFC Drawings Section 703.17
label | 6e6e4c00-9d5a-58cc-970a-e694f76a4dd6 |  | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | e097952b-8963-5f3e-86ff-d25035a43226 |  | note | ○ The Nominated Authority will review and confirm the set out.
label | ed91dd9b-5218-5050-8b0f-85d28b3899b7 |  | note | ○ Attach: Survey Report
label | d3c4acec-0094-5caf-9819-8cc38459af23 |  | note | Method - Document Review, Measure, Visual
label | 37c11418-aa49-553e-9227-59f3bf09d9f8 |  | note | Frequency - Each lot
label | b82bb3a0-f0a2-50cc-8f9a-a672c165f0f8 |  | note | Category - HP*
label | c6d8090a-6ca9-5612-9f41-9a9e58a920be |  | note | Responsibility - SE/PE, Surveyor
label | 16c77218-742f-5b1f-87f2-8e48792d2506 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 4. Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Site Clearing & Grubbing
label | dce0c0dc-2a60-50a5-b079-3befeceb55ea |  | note | Reference - IFC Drawings
label | 766b58c8-140a-5c40-ad42-e7868acfd475 |  | note | Acceptance Criteria - If not completed during the site establishment, the work area needs to be cleared and grubbed.
label | 8bf14aee-cf44-5650-b6c8-15e825cf6e00 |  | note | Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
label | d3e5ff87-2687-544d-b5d3-4082268f051b |  | note | Method - Visual
label | 432d4b2b-bed4-57a1-abcc-ed0d59abb340 |  | note | Frequency - Each Area
label | 91f8a77e-42f8-5c1b-9240-77f2e5fdd3a2 |  | note | Category - IP
label | eb78ef41-a85b-5e38-b3fa-dc282687e5c6 |  | note | Responsibility - SE/PE/SPE
label | bc5c0b70-c43e-51aa-a3c3-0bc5e919c448 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 4.2 - IFC Drawings
label | 334d439a-674e-5856-9177-51462443ec23 |  | note | Reference - MRPA Quality Management Plan
label | 40158f54-70d5-5e54-bf3f-21fb8531a7de |  | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
label | 266016d6-e78c-5713-ab43-0c450d6ad7f8 |  | note | – Using the correct and complete set of drawings
label | f027216b-538b-5e9d-b2e5-3d45b5f8c2f1 |  | note | Method - Document Review
label | 1906192d-eab2-57d0-a83f-a3f981406535 |  | note | Frequency - Prior to starting Works and at regular intervals
label | f2df83b9-df0f-5595-80a1-63295fc61438 |  | note | Category - HP*
label | e96420a0-52c7-5caf-b0d9-4f1846a8db32 |  | note | Responsibility - SE/PE/SPE
label | 57105e39-4000-57ff-9706-45985c3ee694 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Excavation
label | 23d74e3f-b76c-5b86-a3db-c9a7429c28af |  | note | Reference - Section 703.20 IFC Drawings
label | a04bb207-3e3e-5783-ac15-725670e2f9dd |  | note | Acceptance Criteria - Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
label | 136535c1-bd65-53b4-9c79-b6ed827ba2fb |  | note | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
label | d0507c72-f1b9-5824-b1af-345eb0e3fb9c |  | note | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
label | 15d21de3-318b-5012-b7ce-ff3986fb00cb |  | note | Method - Visual, Measure
label | 5bfd6748-c576-56c7-b417-eb172d8dad6c |  | note | Frequency - Each lot
label | 0de846aa-ad28-5242-9b7e-c778c655e2f8 |  | note | Category - IP
label | b8f42c38-22ad-5dc8-8439-b9994531d4c8 |  | note | Responsibility - SE/PE/SPE
label | 52a6c132-cfb7-5e28-a83c-a95fe6eae0e6 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.2 - Excavation-Pavement Thickness Increases for Crossings
label | 5f665620-c20a-5199-907a-9da0fdb9a3c5 |  | note | Reference - IFC Drawings
label | db0a0375-db2e-571b-8606-0e6c2cd2cbb9 |  | note | ○ MRP-089-C-ACD-DRG-14-BFD-CPT-2211 and MRP-089-C-ACD-DRG-14-BFD-CPT-2221
label | 0216784c-272a-5f62-a408-dbac354c582a |  | note | ○ Relevant Council drawings
label | a8d5867c-ef3c-5b8b-9787-254a229719ec |  | note | Acceptance Criteria - Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
label | fde0df83-aa37-5390-8ed1-fd42253e1b59 |  | note | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | 795c3bd2-74df-5b5c-97a7-1c04053cb3a4 |  | note | Method - Visual, Measure
label | be6b6283-dc83-50b8-b2dd-af0a78d4be68 |  | note | Frequency - Each lot
label | 3dbdcac0-bd2c-5c5a-a0d6-2ab010a1124a |  | note | Category - IP
label | 5df83bd9-2f6a-53c7-97e4-9464bbaf6507 |  | note | Responsibility - SE/PE/SPE
label | 93d7b90a-4092-5592-bc17-20f86b0cb110 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.3 - Bedding Material Placement & Compaction
label | 1dd74886-62e1-529c-88d5-96ccb23c06df |  | note | Reference - Section 703.21 IFC Drawings
label | 7850a8a5-542d-59ae-b5a8-f8dd0be7314e |  | note | ○ Relevant Council drawings: EDCM 401
label | daecca66-1383-5374-934f-3e6350e83a63 |  | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings :
label | 05425642-21ed-513a-a853-f78f108be84a |  | note | ○ Footpath: Bedding shall be 100mm as per drawings
label | 6a933b88-c5bf-5a08-84bd-7edfe0601ccb |  | note | ○ SUP: Bedding shall be 150mm as per drawings
label | 5b356e25-506a-5111-a85c-a8866a89d722 |  | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
label | dc1c7186-dd99-5d09-9e65-88e86b632db2 |  | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | cde5f769-d200-521f-91df-b29d2a7110fc |  | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
label | 4197b55f-4a49-53a5-8f11-1935ff5fca60 |  | note | ○ Attach: Bedding Material Delivery Dockets
label | 7c78d2f2-5376-506f-b38f-176a34269f75 |  | note | Method - Visual, Measure
label | 100158ef-d415-5ffe-96cf-0645bfcb1b5e |  | note | Frequency - Each lot
label | cb8b95d7-9ff5-527e-aab4-f07fee289393 |  | note | Category - IP
label | 5a714991-7256-5bf9-aaf2-968ceab5371f |  | note | Responsibility - SE/PE/SPE
label | 41f9b44f-14b7-587a-9dd8-92d64891d458 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.4 - Shared User Path - Compaction Testing
label | a7bf7dd6-dfb0-5ac2-b7a9-fd63b0ecc28b |  | note | Reference - Section 703.21
label | d0426a53-8729-5854-93b2-2486b8b5d3a3 |  | note | ○ Section 304.08 (a), (b)
label | 024c4105-7f39-5463-8aa2-77148b857bb4 |  | note | ○ Section 304.11 (a)
label | acf8a5b1-f7c6-5de9-804e-74ff15621eca |  | note | Acceptance Criteria - Compaction shall meet the following requirements:
label | 729256dc-189c-543f-93e9-ae2673f0d404 |  | note | ○ Scale of Surface Level Measurement = Scale C
label | 94bd9e4f-10e7-550e-870c-d2a64656932b |  | note | ○ Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
label | 79dd5e38-a695-5f26-b0e1-bd7498c433b9 |  | note | ○ Mean Value of Density Ratio % (3 tests) not less than 100%
label | 85c875a1-74c6-505f-9688-fa5d096e6883 |  | note | ○ Attach: Moisture Content Test Results
label | 2753deb8-1053-5260-ae4b-1c1859d498ca |  | note | ○ Attach: Mean Value of Density Ratio
label | 3936d40e-25c8-5e2b-865b-f90f225c28a0 |  | note | Method - Document Review, Visual
label | 487c656e-9b07-5ea7-b524-dc8569d1a889 |  | note | Frequency - Where applicable, each lot
label | 2bbe7e98-a9d2-5748-9e8a-3e9a444f73ee |  | note | Category - HP*
label | 18ddea85-f0d4-53f7-ba38-dae84f5bef83 |  | note | Responsibility - SE/PE/SPE
label | 4f67672e-2722-5e3e-b4e7-1ec5de0d49c4 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.5 - Shared User Path - Proof-rolling
label | 790608ff-ba4c-579d-8b0f-2afca76bb14f |  | note | Reference - 703.21 304.08 (b)
label | 50c979e4-be68-5c77-bf63-b7250d41033a |  | note | Acceptance Criteria - Bedding material to be compacted and proof rolled before any construction. Withstands Test rolling without visible deformation or springing.
label | dd79b33c-d7ba-5894-aa2b-eb0d3ae324cd |  | note | Method - Visual
label | c57607fc-5b14-5e6c-ae65-cc0823a19f6d |  | note | Frequency - Where applicable, each lot
label | 1ed96d8a-7519-502f-a713-6304f788979a |  | note | Category - HP
label | b5613905-df2f-5604-b0f5-69b784ed94ec |  | note | Responsibility - Nominated Authority
label | 94586081-5033-57b8-995e-57c23d86630d |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Formwork Construction & Placement
label | bf029538-5b4c-5e0b-b44b-04edeba50558 |  | note | Reference - IFC Drawings Section 703.12
label | 0506b54f-3891-53bd-9c56-8f615223dca2 |  | note | Acceptance Criteria - Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
label | 6442ee48-118d-5a56-8913-c2ce5650e2e3 |  | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
label | f622b089-1910-5827-95f6-7f63317e1dc6 |  | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ae3a2a0b-e04c-5cd5-904c-a29be156f3ae |  | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | a8f91009-0137-5f10-aa20-8979dc868d5f |  | note | Method - Visual, Measure
label | 46b35e7c-562c-5a32-af61-bd2b5af038e8 |  | note | Frequency - Each lot
label | 9491556f-4e5d-5e2d-9017-0bf95c17d7fa |  | note | Category - IP
label | d1adcb82-f191-5d97-9f05-62bcca1af07f |  | note | Responsibility - SE/PE/SPE
label | 7a5d53f6-ae28-5808-a325-40464a11d73f |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.7 - Construction Joints & Matching Existing Surfaces
label | 624ceb25-de14-534a-a00d-b5d713062ee0 |  | note | Reference - IFC Drawings Section 703.24
label | 9777f599-61de-555a-a16f-c57f0feee942 |  | note | ○ Relevant Council Standard Drawings
label | 35c8d37a-0d83-5eaf-b61e-a2d2a1d8f23a |  | note | ○ Relevant Council drawings: EDCM 401
label | 7b6c0a9a-6192-538f-ab71-33193d1895b0 |  | note | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | f3d8e0e6-eede-5f29-ab12-73ea2e2a3359 |  | note | ○ Consult the relevant Council Standard drawings for the joint detail, these may require:
label | 5fe2b618-676b-567c-b9f5-d6b86013e12a |  | note | i. Concrete cutting of a shear-key
label | 9ce650cc-c4ee-5cd1-96e5-4f8ba971087e |  | note | ii. Surface roughening
label | c875bae8-3cb5-5039-aa1d-062de08cc364 |  | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | 5d769cb2-4c6a-5729-a4f4-c21a87509ea6 |  | note | iv. Cutting a groove for sealant
label | 26208c2c-3759-5ab2-85a5-5333de722cc1 |  | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | a5ee7ee5-0a58-557c-9c01-14527dd38b1d |  | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
label | 7948fa8c-325f-5c33-9d54-cc6df501aacb |  | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | e2bb95d0-b191-5706-959b-d417f23e6117 |  | note | Method - Visual, Measure
label | 5e29ec3c-5974-5cc4-b9fe-5a36302ae52d |  | note | Frequency - Where applicable, each lot
label | f75cb5de-5e3f-556f-996a-3efae6ea392e |  | note | Category - IP
label | b48c94d0-74b6-5f5a-a250-68e3e7491df3 |  | note | Responsibility - SE/PE/SPE
label | 14f17ab1-734c-5625-a6fd-c0b8a77a7984 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.8 - Isolation Joints
label | ebd1aa27-a2ad-5a01-8a8e-fb65cf624428 |  | note | Reference - IFC Drawings Section 703.26 (c)
label | 3b4fb2fc-0170-5895-aaa0-7ee86a6917a5 |  | note | ○ Relevant Council Standard Drawings EDCM 401
label | dad58fa9-124e-597f-a291-c4ed33f09882 |  | note | Acceptance Criteria - Where applicable, isolation joints shall be placed:
label | ccdd4c11-0847-5f31-87b0-749ed4a30712 |  | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | c785baf1-4d0e-5bd5-b465-d84477a0b6cf |  | note | ii. at any location marked on the drawings
label | 050b2b3b-046e-50d3-91d4-ba3d7da384ec |  | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 63adb08f-a1b1-5b7c-8c91-e2e7c349b6fc |  | note | Method - Visual, Measure
label | 42f21996-dbb3-5702-a310-b33f6a3f8a58 |  | note | Frequency - Where applicable, each lot
label | c3bf70ac-4b90-5f5f-9a36-99a382320509 |  | note | Category - IP
label | 1875394d-7b9d-57b3-97cb-4cbc83ae9e7a |  | note | Responsibility - SE/PE/SPE
label | be496ad5-1185-5290-af09-79b8e17364d7 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.9 - Expansion Joints
label | 88853a16-0cf8-500e-a057-e0bf53de4e79 |  | note | Reference - IFC Drawings Section 703.26 (a) (ii) & (b) (i)
label | 2d489bfe-2267-5fee-b557-837a5dae730e |  | note | ○ Relevant Council Standard Drawings EDCM 401
label | 04d54f34-6f7b-5427-96cd-2b0eeaf0f94a |  | note | Acceptance Criteria - Where applicable, expansion joints shall be placed:
label | 60486ae0-2d31-5aaa-a68f-e57122fbaf25 |  | note | i. on either side of vehicle crossings
label | 6da1226d-6a1f-5594-821a-657400544723 |  | note | ii. at junctions with existing footpaths and shared use paths
label | d7700fb9-d85f-5013-9a74-4b69a368bbb1 |  | note | iii. at junctions with bridges
label | e737b7f2-4fe9-5a19-a4cb-4290bf65d5c6 |  | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
label | 5ab1f4af-a725-55d5-abdb-5d3665a7e30b |  | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 539178e8-7b09-52e2-9912-46e04930dce5 |  | note | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
label | c3d3d4a2-8cd1-5eba-afad-7301c6a65517 |  | note | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
label | c477e726-fa74-5b5b-9978-e156465e52f7 |  | note | Method - Visual, Measure
label | 73c3e26c-1029-510d-b30a-3c05a47c77c2 |  | note | Frequency - Where applicable, each lot
label | c7d867fe-dff4-5eec-8f97-fab40d41a54b |  | note | Category - IP
label | 7c73570b-107c-503b-96fa-8eb88ae3ccee |  | note | Responsibility - SE/PE/SPE
label | 274cd5f4-551a-5784-b87b-2a2555e867ae |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.10 - Reinforcement Placement
label | 2932a363-30fa-5b94-bbdf-178714eb018e |  | note | Reference - IFC Drawings Section 703.13
label | cabf76ee-dfeb-5c08-8350-19d6e22f0227 |  | note | ○ EDCM 401
label | 90b1acfc-88fc-5448-aa28-da43673418a9 |  | note | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
label | 8e9583ea-ebf9-5564-9621-0d87f209e6ed |  | note | – Footpaths & SUP: SL72
label | c054a8e6-c127-5cea-8997-9f5fc1f75e5a |  | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | 3704b4e4-c65c-5e59-b072-eb6747121d96 |  | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
label | 6fb30326-9231-5d90-8eaf-a134ea16e382 |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | 97663c1f-e59f-5681-bd1d-a4b2cb11aa4b |  | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | 165d7fe5-1012-58fd-a458-63bcccead258 |  | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
label | b38cc4d7-cb82-505c-b493-e220a20020fe |  | note | Method - Measure, Visual
label | 47afba04-a44b-5523-af51-06a886aabf44 |  | note | Frequency - Each element
label | 169b1163-9d4b-5683-aa20-e857398cc8c7 |  | note | Category - IP
label | fc95cb4e-d905-593b-9c10-2ba78a2ef1f8 |  | note | Responsibility - Supervisor, SE/PE/SPE
label | 64949b2a-95d0-5fa3-b98a-f34624691701 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.11 - Pre-pour Survey
label | 9737515c-d48c-5a4f-820d-b335501cfdc4 |  | note | Reference - IFC Drawings Section 703.15
label | 68b88916-88b3-5107-9a41-5680182e3fb8 |  | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
label | 640e6ae4-d9bf-50e0-8a81-621f95c0cbaf |  | note | ○ Erected formwork and base layer within the tolerances below:
label | 8db6129e-314f-50ba-9bf3-bf1ab071cb80 |  | note | ○ Departure from RL = ±10mm
label | 3592b375-7a20-54f1-94bc-d6ef6b8b2db6 |  | note | ○ Departure from alignment = ±10mm
label | c99dc229-6edf-5ed3-9e4b-90680b95159e |  | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
label | 8399daf9-38ea-5075-96a5-9a4f18b69137 |  | note | ○ Irregularities in alignment = 5mm in 3m
label | 7b5e026d-4379-57a6-a58e-bbb7ae8a930a |  | note | ○ Section dimensions = ±5mm
label | 822e81be-2097-5466-839f-cb7e14b93608 |  | note | ○ Section dimensions (less than 25mm) = ±3mm
label | c6ae5b7a-eec3-5354-a6d4-483969b953eb |  | note | ○ Width of pavement = -5mm, +15mm
label | 80ca98a6-1a0e-5f17-a1c2-cc89068811b9 |  | note | Method - Measure, Visual
label | f1c48168-ba15-5a08-afd5-15e895d1c7ab |  | note | Frequency - Each lot
label | d9ce8ffe-1c28-55a1-936a-9eb2a5726876 |  | note | Category - HP*
label | 5854c554-cf42-5102-b6b1-2c17f157ed7b |  | note | Responsibility - Surveyor, SE/PE/SPE
label | fabf2964-f5fe-5f7b-997d-69c52a69135e |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.12 - Pre-pour Inspection
label | 73b8e100-caf3-5daf-abc4-9295d2248f91 |  | note | Reference - Section 703.09
label | 28014ba8-efdb-58e3-89c3-df4fc4489cf2 |  | note | ○ Section 703.21
label | 0855f46d-e713-5658-a762-71cc73de0adb |  | note | ○ Section 610.17a), b) & c)
label | 6f4a1a99-f4c6-537f-81f9-2db82ef3e2ae |  | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
label | 1d7268c8-9b66-5543-988b-31af62a853e3 |  | note | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | 7e96e282-61f5-5e3a-a915-d5ed31a4303e |  | note | ○ Attach prepour inspection sheet
label | b1950bba-89ee-52ee-8e0e-91feb45645c2 |  | note | Method - Measure, Visual
label | 6fd3c247-0667-5089-b69f-4463d0933212 |  | note | Frequency - Each lot
label | a14dc190-6154-511e-94ed-59d6bc233710 |  | note | Category - HP*
label | ae7a85e2-1df1-5f44-9a30-9371ac29f6d7 |  | note | Responsibility - SE/PE/SPE
label | e5fd0350-7bc3-520b-9bce-7ce159271cc0 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.13 - Weather Conditions & Evaporation Limits
label | dedc2506-f32d-5686-be19-8901492cb05c |  | note | Reference - 703.09 610.17 (a - f) Table 610.171
label | 6411a4e8-5435-57ec-8fff-62fa2a8c8ca0 |  | note | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | b84c4aa1-c02a-5b48-83cf-294080328760 |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 8aa98db9-593e-5b29-942b-d37ee282dee2 |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 8f33b661-0006-5122-9458-0d7c51cd6f4f |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 56b1a495-0331-5b56-87f9-9fc6fa2525f6 |  | note | ○ Record: Required information on the Concrete Pour Record.
label | 1fa0424b-a999-5a78-b6cc-8ca03f9e88e5 |  | note | Method - Measure, Visual
label | 3c026aa1-2d77-5299-bd7a-c588b43735c7 |  | note | Frequency - Each lot
label | 8739f88a-da74-5e13-96f8-8d43c5747051 |  | note | Category - IP
label | 96c35f67-4fa6-5a0e-b116-50f26d976b1a |  | note | Responsibility - Foreman, SE/PE/SPE
label | f5e24c58-660f-52d9-bbee-c1d8e305a69c |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.14 - Concrete Testing - Sampling Frequencies-Footpath
label | acec883f-cbdc-5605-b2cb-83aa8a0d89af |  | note | Reference - 703.11 AS 1379-2007 Cluse 6.2
label | 43072fc8-1f70-5b99-be6a-bb035e005489 |  | note | Acceptance Criteria - The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
label | d9fed927-3461-58ca-8a17-7bd4b642234f |  | note | ○ Correct quantity of cylinders manufactured per sample.
label | 7c34f844-ccbd-5185-829e-deb22424a2bb |  | note | ○ Record: Required information on the Concrete Pour Record.
label | 326c6148-bf27-53aa-a9e2-776b483a535a |  | note | Method - Test
label | 4a75e29f-9efd-526d-ae1a-7ecf637b485a |  | note | Frequency - Each lot
label | 99b1f650-7836-546a-9996-8166ef536252 |  | note | Category - IP
label | 793ac5bd-f846-5814-ab8a-ee14a578116b |  | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | 19ef0d23-2da3-52d2-b8de-0b94a5c9f624 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.15 - Concrete Testing - Sampling Frequencies - SUP
label | 660c318a-5879-5323-894f-b18fc767f434 |  | note | Reference - 703.11 610.16 (b)
label | bd2d8a31-9dfa-5999-afc4-e934d430e501 |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 6d9ee38a-e887-5a8c-aefb-6c9f7fe253ad |  | note | ○ Shared User Path:
label | 99ffaede-984f-5afb-bc44-c53e920b2778 |  | note | • 0m³ to 10m³ = 1 sample
label | 99fa58de-9b29-5f6c-8f78-6a2c55c2fb39 |  | note | • 10m³ to 25m³ = 2 samples
label | 61328106-662a-58f1-a19c-f360b3211416 |  | note | • 25m³ to 50m³ = 3 samples
label | 720558e9-e151-5c9b-a13b-390cb91dd355 |  | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | c411f79e-0828-5573-a80a-aa1cbf8de176 |  | note | • For each additional 50m³ and additional sample shall be taken.
label | b920758e-9219-5e7f-b7b5-bf25dadd919b |  | note | • Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
label | 74d4bd2e-a162-588f-b942-23ce79b89f98 |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | fdfa37ec-e54a-5107-9a28-c9c8ded649f9 |  | note | ○ Footpaths:
label | ca4f1aad-6c5f-5f1d-b9cd-33a9b54369cb |  | note | • 0m³ to 50m³ = 1 sample
label | f14b9756-ae2e-5763-91f7-1a60b5e7fab3 |  | note | • Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | 5acfbe51-f4de-57b4-ad1b-f31290553f61 |  | note | • Compressive strength cylinders = 2 no. 28 day strength.
label | 71f06185-4f2b-5b9c-9e07-854563474bc3 |  | note | • Correct quantity of cylinders manufactured per sample.
label | b170fd60-7ee8-5f7a-9654-0eccf69318f2 |  | note | ○ Record: Required information on the Concrete Pour Record.
label | 7d9cb691-9b37-5fa2-bb01-839a1988d989 |  | note | Method - Test
label | 274d136f-b46f-5f83-b1f6-ab0d3c9dade4 |  | note | Frequency - Each lot
label | 6807d940-131d-505a-aacd-d117bd60744d |  | note | Category - IP
label | 87db886a-c66a-55a5-af0a-4d72fc2fb4fe |  | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | a1ea0eb5-1d59-5eb8-87f6-1c47eebae1c7 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.16 - Concrete Testing - Slump
label | 3b6eed49-a15d-5228-a5f4-8e2329a7625c |  | note | Reference - 703.11 610.16 (c)
label | e81392c2-392b-5b1c-8f3b-5dc5899c1e11 |  | note | Acceptance Criteria - Slump testing tolerances =
label | aefea509-04b2-5849-9003-bd364ed9d901 |  | note | • <60mm = ±10mm
label | 1df6be63-2589-59d6-867e-b6a7666cd4b0 |  | note | • ≥60mm to ≤80mm = ±15mm
label | 36846dca-331c-5e6a-bf44-367ac6329535 |  | note | • >80mm to ≤110mm = ±20mm
label | da910f43-2c05-5d82-811e-26164d45dafd |  | note | • >110mm to ≤150mm = ±30mm
label | 6ba2c7fe-2f35-58f1-8d58-de404bc048e5 |  | note | • >150mm = ±40mm
label | 56899129-a9a0-5965-9cd5-1affae27133d |  | note | ○ Record: Required information on the Concrete Pour Record.
label | 964cba56-bfcf-5a93-b3b1-59dcd7790e3e |  | note | Method - Test
label | 44e5451d-4479-517c-a81a-90c96bb5f8a2 |  | note | Frequency - Each sample
label | 8bf99059-3aed-5569-a6f9-968629dd0028 |  | note | Category - IP
label | f8a351d5-3477-5815-8b42-f1ebbc3bd7c1 |  | note | Responsibility - Concrete Tester
label | 67b50d1d-8418-54e9-bf2e-aa648b5a79a1 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.17 - Placement & Compaction
label | 959ebf63-8c16-59b1-9788-01c1124656a6 |  | note | Reference - 703.08
label | c46ac046-54c4-54fc-a8c9-06719d566fb2 |  | note | Acceptance Criteria - All concrete batches are traceable.
label | 27f9e586-eec0-524c-8e6e-862b7404bf44 |  | note | ○ Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | 3745f32d-9019-5a1c-af53-e7e9c6a674c5 |  | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 487641fa-1063-5abd-9664-ff9cfd64e29b |  | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | aec2ce2c-bc12-55c4-a073-32334d3005b3 |  | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | dd23c0cb-f618-57b8-9393-27230fd4d225 |  | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | 3a132827-bc66-5e8d-ba8b-5680e40d95c4 |  | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | b6d21852-a419-506b-b115-59c5943d180f |  | note | ○ Record: Required information on the Concrete Pour Record.
label | dc89a6a0-d62f-5dd2-ac7f-95c26374d400 |  | note | ○ Attach: Concrete Pour Record
label | 66f5a412-28d2-5031-bd77-37c2e02cd069 |  | note | ○ Attach: Concrete Dockets
label | 03be6649-e3d8-5e5f-8ba9-3875a04091b1 |  | note | Method - Visual
label | 84005c09-2179-55a4-b986-def392f59412 |  | note | Frequency - Each load
label | 6b4a7bfb-c423-5b3d-9e13-8d9c66cb1385 |  | note | Category - IP
label | 006320f1-aacb-584a-bf0b-12b7c2e7ae89 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 5d7da57e-ef4e-55b8-abe9-27ea757bc22f |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.18 - Surface Finishes
label | 200ab523-38a7-5dc0-8428-da72317f83dd |  | note | Reference - IFC Drawings
label | a055cb51-73d4-5784-b1f3-0227c6cd0645 |  | note | ○ Relevant Council Drawings 703.25
label | a110c910-fb72-5b23-a43c-0611f9162556 |  | note | Acceptance Criteria - Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | ebe0a5e5-3d9f-5b81-857d-3c55a7587c34 |  | note | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
label | 5bbc0fcf-10c5-5b87-a734-c7086ef5dd75 |  | note | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
label | 4fd6b4e5-96bb-545a-8d63-b23781ae80f4 |  | note | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
label | f4137f06-2325-59f9-91ab-c8b3c73f3a87 |  | note | Method - Visual
label | d31135e6-cc60-5ade-80d6-7d7c91c61063 |  | note | Frequency - Each lot
label | e2229baa-1019-5e79-b39a-ed01e953e665 |  | note | Category - IP
label | 090a0be2-f9cc-5883-8a86-9aa7a974536a |  | note | Responsibility - Foreman, SE/PE/SPE
label | 456b4490-bbb1-5ca9-a7b9-94e9f9c7305a |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.19 - Footpaths - Crack-control Joints / Weaken Plane Joints
label | fc900d1b-995f-5399-b66a-89e700e6fb5a |  | note | Reference - IFC Drawings
label | 15091f6c-44f3-5f33-90d7-bf86a0c2f40a |  | note | ○ Relevant Council Drawings Section 703.26 (b) (ii)
label | d8ff3e2b-ccde-5875-b291-e8dc6fe18f2d |  | note | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | 747d76da-2482-54c4-826c-2c232f90e8c7 |  | note | Method - Visual
label | 04be7279-008e-5566-bd16-4c3efbf121d9 |  | note | Frequency - Where applicable, each lot
label | e5a5065a-21a9-5028-9ac7-35129e4fd7e7 |  | note | Category - IP
label | 3cef4468-a3fb-5396-999f-bcda193081d7 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 04082cea-d009-5cef-9b10-426c62f930e0 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.20 - Curing
label | 1d28e45d-0301-53cc-ba49-a1b0c7425f47 |  | note | Reference - Section 703.10
label | 613bbd23-93ea-564d-90b8-a1df53ff97d7 |  | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | 2746efe2-c129-56f1-9c43-bb30cb8a197c |  | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | 243c2fc6-533d-5477-a031-a53616f42d70 |  | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | 73f68001-4dd7-581f-92e2-df34d1c256ab |  | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | 1ff83b1a-3775-58c8-98cd-5713dc02ebf2 |  | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | fbc386ce-16d7-5331-848b-af97704d2c80 |  | note | Method - Visual
label | 5dec4180-01bf-5a72-b207-0fd9439613a5 |  | note | Frequency - Each lot
label | 2f2d4c7e-403a-538c-b398-58d48f68f285 |  | note | Category - IP
label | d1ce4522-2c47-531d-a6d1-77c98d36b1f5 |  | note | Responsibility - Foreman, SE/PE/SPE
label | e276d436-c975-5eac-a698-929d2aa4f74e |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.21 - Hardstand Grade
label | b8303995-a1e4-591a-9d6a-2357ae9890dd |  | note | Reference - STD S0075
label | 7466a273-6379-5a67-a2aa-166fbfa4fa48 |  | note | Acceptance Criteria - Hardstand that are connected to the Bus stop must have a grade between 1% to 2.5%
label | f8ffd8b5-8dd6-58b6-87d0-d44c811b663e |  | note | ○ Attach: Survey As-built
label | 5eaa3d41-f591-5117-b29e-c8676f882ca5 |  | note | Method - Visual
label | a4ce2971-1e48-52d3-a391-acb77806bee6 |  | note | Frequency - Each lot
label | bf53f6a6-7657-5335-aab6-bb3e6f2f6e82 |  | note | Category - HP*
label | aa5c27cf-30c7-5670-837d-95973a7d4525 |  | note | Responsibility - Foreman, Surveyor, SE/PE/SPE
label | 425f24ca-5d40-52f6-bcc1-4f55050b28c9 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Shared User Paths - Crack-control Joints / Weaken Plane Joints
label | c01b8d6a-e215-5041-9d14-b19a8911d6a4 |  | note | Reference - IFC Drawings
label | 28169128-4cf2-5cd8-b3b5-9be9fb0e94cd |  | note | ○ Relevant Council Drawings Section 703.26 (b) (ii)
label | fae4453f-7aa3-5196-9f4e-46429a811608 |  | note | Acceptance Criteria - Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
label | 279e59e8-9b2d-5b0a-9791-c0c31dc6a7a1 |  | note | • <20°C = within 24 hours of finishing operations
label | 98519f4a-9190-5788-a5fe-7004859cf885 |  | note | • ≥20°C - 35°C = within 4 hours of finishing operations
label | e88c45ac-57ae-5fc2-b819-8a779f3ede81 |  | note | Method - Visual
label | 128b9809-909c-5bff-84fc-c2357ef4a074 |  | note | Frequency - Where applicable, each lot
label | bc2efbd7-0089-51d0-a473-22212b5a80b6 |  | note | Category - IP
label | 6111eab7-de5c-5ef4-afd9-cb71739a456f |  | note | Responsibility - Foreman, SE/PE/SPE
label | 3e78f426-15c6-5e52-8d54-c219bf337ea3 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.2 - Protection of Newly Poured Concrete
label | a3a27ce1-1ded-598a-9809-0f818a1272fc |  | note | Reference - Section 703.27
label | f19246c9-4296-5e1d-ab6b-3ccd7dacf7a2 |  | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | f9190d4c-adbb-5c55-8001-7bf24d2fbd48 |  | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | 726e025c-9409-5019-bef9-2b54622c7d41 |  | note | Method - Visual
label | df390c42-10f3-5d13-a8a2-a78e69200257 |  | note | Frequency - Where applicable, each lot
label | 1e601bf5-e30c-5757-8987-df87fb89cbb9 |  | note | Category - IP
label | a09d244d-d04a-54dc-8747-f8b464fe3d0f |  | note | Responsibility - Foreman, SE/PE/SPE
label | a0aa58db-ed4b-53e3-a763-067d51413c95 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.3 - Stripping Formwork
label | 2d5ef642-ead3-58fb-88ba-387ffddb3080 |  | note | Reference - Section 703.12 AS3610 Table C2
label | ec0c5c2f-942d-53d8-a236-0e8e365da5a7 |  | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | 58032c71-5c8f-5c18-852d-92f310535d15 |  | note | i. 2 days for vertical formwork on external surfaces; and
label | 70470727-1cd0-5800-a898-a20908665029 |  | note | ii. 1 day for vertical forms on permanently hidden surfaces
label | e01a005c-4fff-5dc5-b0d8-0515a584fa53 |  | note | Method - Visual
label | 12b7c2a8-4e03-549b-b7f1-46541af4a1e4 |  | note | Frequency - Each lot
label | 7bdc520a-95c5-579c-a3bc-9b90ac6cce3f |  | note | Category - IP
label | 6329c288-92d3-5c07-beb1-83b62778dc9c |  | note | Responsibility - Foreman, SE/PE/SPE
label | 6778ffb5-7b4c-57c1-ae72-6810fe09daa4 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.4 - Backfilling & Pavement Restoration
label | f2f5d9f0-a031-5133-8c6e-9fd1ed59eb00 |  | note | Reference - Section 703.29
label | 646a108a-dd82-5d9c-abf6-c5738a315b76 |  | note | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | c0b4ee79-e6dc-5daf-8cee-0b4d237cee87 |  | note | Method - Visual, Measure
label | fb16859c-aac3-598a-b8d2-50c5c9d0e7cc |  | note | Frequency - Each lot
label | 94dec536-2e23-5ca4-9658-d0d7d584fcca |  | note | Category - IP
label | e2714db8-a359-54fb-872e-5a5c7e04bd13 |  | note | Responsibility - Foreman, SE/PE/SPE
label | b8f8b1ee-2fb0-55cf-b0fe-832da324e92a |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.5 - Surface Inspection - Cracks
label | 6c4c5e96-a3bc-54a5-85d9-7777964c4730 |  | note | Reference - Section 703.3
label | bb67248d-0d40-5211-8604-7add019c5945 |  | note | Acceptance Criteria - No cracks greater than 0.2mm. If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 618f8dfb-a791-5ff0-8652-665563da8763 |  | note | Method - Visual, Measure
label | ff4fdae0-b01b-5ec6-83fb-5587aeffb66b |  | note | Frequency - Where applicable, each lot
label | f6de8df7-4f68-5de4-a496-465715bda13d |  | note | Category - IP
label | 71b05d15-390c-50c1-8e91-a7a5588507dd |  | note | Responsibility - SE/PE/SPE
label | 05da6a71-cd84-5963-b488-0ebda3b456cc |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.6 - Surface Inspection - Surface Finish
label | 685e4933-e28f-51be-9960-1da29d3e80b8 |  | note | Reference - IFC Drawings
label | c8fac977-dee3-512b-97fc-75bb0ee6088f |  | note | ○ Relevant Council Drawings
label | b275786f-6158-538a-afef-90f5f28ce7f1 |  | note | ○ Section 703.25
label | 6cd1ff9f-d9ff-5997-ae4a-d6ec8bb58330 |  | note | ○ Section 703.10 (a)
label | 9e21130b-ee36-579f-b0f3-2b8d791dbb90 |  | note | ○ AS4586
label | dc8df539-d676-5bb6-b552-9b8ab4788059 |  | note | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
label | 3a0369a0-a701-5b4d-8077-eec9aca7f468 |  | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
label | ba9829bb-afc0-5060-b706-bc3af8f23b2e |  | note | ○ All Finished Surfaces to comply with AS 4586 Slip Resistant Classification of New Pedestrian Surface Material
label | d1421787-d530-531a-9f8b-5919d91823eb |  | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
label | 92dfeaa8-53e9-5f9d-899e-8ea81a70a351 |  | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | 070d58cc-6aa5-58b4-8cf1-ddc4a7154cf8 |  | note | Method - Visual
label | 56f93c12-5891-5938-ab4f-99a8d7456af3 |  | note | Frequency - Each lot
label | 8f604336-58f3-573f-94e5-66e9f010e22d |  | note | Category - IP
label | c07d6a91-37ca-58e8-bc1b-7dd0c04d83ee |  | note | Responsibility - SE/PE/SPE
label | c01809ef-6e0e-5966-9ffe-5d6dedd8e137 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.7 - Compressive Strength Test Results
label | 5bf53eaf-e73e-5827-bd19-02c81d210770 |  | note | Reference - IFC Drawings
label | 25a100cd-0277-5886-8a2f-c312a5b012e2 |  | note | ○ Relevant Council Drawings
label | 47ac36d8-a978-5303-b371-d683cff276f0 |  | note | ○ Section 703.11
label | e0f5a26c-43e7-5fa1-bb49-aa5c23b92b4a |  | note | ○ Table 703.111
label | b31b683f-9394-5895-b4d8-4ddf4dab38f4 |  | note | ○ Table 610.05.051
label | 65940027-13e4-5089-aae2-fe5fab242b24 |  | note | ○ Section 610.16 (g)
label | e1c70621-8803-52d1-ba3c-c36f49aa2090 |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 7d2a54fa-1132-5c46-8f31-dceae759106e |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 9c93fa42-a7a8-5165-953d-d51a78549bfa |  | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 4e37af95-7b72-54a4-89d4-58a29e588322 |  | note | ○ Attach: Compressive Strength Test Results
label | c84cde45-b574-5725-bddf-9be287c6a38f |  | note | Method - Document Review
label | 80c3c37f-fa89-5565-8b77-3dbf3594eda1 |  | note | Frequency - Each cylinder
label | 68043d6e-60ff-5096-a0fe-736d768bdab2 |  | note | Category - IP
label | 60d55850-211b-5cc3-a2cd-d99bd070a380 |  | note | Responsibility - SE/PE/SPE
label | ec8c2d00-4d4e-5c8a-91ec-37c352351ac3 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.8 - As-built Survey
label | 66811eaf-ec3b-53de-a401-78064624bed1 |  | note | Reference - IFC Drawings Section 703.15
label | 2195c9df-4a7c-5652-8c83-e956fbc88043 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | e9d912eb-8b23-54a7-851e-eef08ee70964 |  | note | ○ Departure from RL = ±10mm
label | 64f713d0-e2bb-541a-bfac-757c0d00b08a |  | note | ○ Departure from alignment = ±10mm
label | 15463c75-64a7-57b0-ab9e-187ac75c23ae |  | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
label | c17ffaf0-04de-5d66-a340-9002e2fc95f6 |  | note | ○ Irregularities in alignment = 5mm in 3m
label | 50e5ea19-d89f-5bc4-8237-f250b5150eb4 |  | note | ○ Section dimensions = ±5mm
label | 547c84f7-b7aa-5914-ad10-1f17c5655dc1 |  | note | ○ Section dimensions (less than 25mm) = ±3mm
label | 6ee551dd-33c8-5a43-a583-bd9da615e97d |  | note | ○ Width of pavement = -5mm, +15mm
label | bc16c36c-b4b3-5b5e-a226-0f30d9674a6c |  | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
label | 8a8ee913-fc89-5471-a26e-3dea275f291c |  | note | ○ Attach: Survey As-builts / Survey Report
label | f4ea1b28-4fab-5bfd-9bd0-58f383f4dfbc |  | note | Method - Document Review
label | 9331e090-49de-5d5d-9c9c-4f44710dd867 |  | note | Frequency - Each lot
label | d036f617-47f3-5206-bfde-ae8c2c7acd41 |  | note | Category - IP
label | 7a541f26-757a-540e-88a6-470875a95e73 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | a972e9b2-d9e7-5891-ada3-c38a6d9a9e19 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
label | 1c5fe5cd-88de-567b-994d-a26b4050fa89 |  | note | Reference - MRPA Quality Management Plan
label | 659a8b6d-28ae-559b-9732-adbac5909987 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 6c25391f-7cc0-55b4-8130-020bb18fe9a0 |  | note | Method - Document Review
label | 7d04c6ce-42c9-5beb-b9ea-d65ad6485c15 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 054abc32-5b4f-5193-be72-2d28be2b6760 |  | note | Category - HP*
label | 316242c0-8958-520c-9f6d-b386c33ee6a0 |  | note | Responsibility - SE/PE/SPE
label | d6250411-1f6a-5291-8cdb-ac2bdb6c5abe |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | 5153d69d-b63d-54b7-8149-1d64ce4aeab5 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 92e136a6-3aca-5bc4-a9cc-66592e8a79d1 |  | textbox | Name:
text | 3c962548-ed6f-5443-97f7-9593a73f63cb |  | textbox | Position:
text | 7de713f1-a553-56be-8290-a2fd0656dd84 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-027-CIV-Brunt-Signage (Supply and Install) |  |  |  |  | Yes | ITP-027-CIV-Brunt-Signage (Supply and Install) | cbe034e6-3d34-47dd-939a-093ede516809
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | bfeef2f0-bca8-51d4-89a0-0c41fd27baca |  | note | Document Title: ITP-CIV-Brunt-Signage (Supply and Install)
label | c1621b2b-7c66-571d-ac26-e9eee2c231fa |  | note | ITP Description: Brunt-Signage (Supply and Install)
label | 076c1bc3-5618-5b2c-a5e4-d57a8425a33a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | dc099d8b-36a0-5323-a1b5-1917f513b7ec |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 7f71c04d-b0dd-5417-84af-53202e7780c1 |  | note | Revision Number: 0
label | 355e4ddb-bea2-5b61-b7c4-5760da31dce2 |  | note | Revision Date: 28/02/2023
label | 655a326f-582e-525a-96f5-db3230626464 |  | note | ITP created by: Jason Lee
label | fb918bda-1e6d-5c7b-87e2-42f41c6013b6 |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | b74c2cf6-e90a-52c1-9664-963d716ecb13 |  | note | Reference - VicRoads Section 860 (Feb 2023)
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | aa063e7e-0d66-5124-803b-59e1075e63b1 |  | note | Reference - VicRoads Section 714 (Feb 2023)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | df42a309-3bed-52a0-a30d-4dbb28142daa |  | note | Reference - VicRoads Section 703 (Aug 2021)
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | b705eb3e-c163-553d-bf70-3e8a2eba60ce |  | note | Reference - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | 85bdbd9f-6220-5a99-86d0-3e66852ac8a8 |  | note | Reference - AS 1742.2:2009
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Manufacture & Supply of Signages and Posts
label | 7cec4bbb-ef4a-50c1-b13d-d28f5d3289bc |  | note | Reference - Section 860
label | a67fe110-11b4-51a7-b260-0026b76c034b |  | note | ○ Section 860.06
label | fafaaf18-fb39-5958-88d6-e21ce810e582 |  | note | ○ Section 860.07
label | 69ee7ff5-b238-5ae4-9cf7-5806d00a2307 |  | note | ○ Table 860.071
label | e847a3fe-32e8-5baf-93b9-2fcedc47dec0 |  | note | ○ Section 714.03
label | fda09eb7-f78f-53ff-be39-fab14d65e5cc |  | note | ○ Section 714.06
label | 88810b92-45ce-567d-8afe-c7c7db6324b5 |  | note | ○ IFC Drawings
label | 20c49c9c-e780-5aeb-a991-7a9bb03fce2f |  | note | Acceptance Criteria - Signs are to be manufactured in accordance with Section 860 and IFC Drawings
label | 20d23df5-7400-5cdb-896b-76f8ac559289 |  | note | ○ Warranties for the Signboard and Components, Sign Face Material, Giving of the Warranty and warranty Claims to be in accordance with Specification 860.07 and Table 860.071.
label | a6b87b97-487b-5749-b42b-8c4852842e67 |  | note | ○ Packaging and Storage of Sign to be in accordance with Specification 860.06.
label | 9cceac4f-40f5-571b-b980-2a3dd57f41c1 |  | note | ○ Signs and components shall be handled and transported so as to prevent damage.
label | c119eab5-6b59-55ef-a8b7-54571a8852e7 |  | note | ○ Signs shall be stored vertically in such a manner to prevent damage to the sign face, edges or components, taking into account any recommendations of the sheeting manufacturer.
label | 9bbe5a09-b455-583d-ab27-729e9bb9de9f |  | note | ○ Post details shall be as shown on the Sign and Post Schedule and in accordance with the VicRoads Traffic Engineering Manual Volume 2. Steel posts shall be either:
label | 94f62c2f-4657-5908-9a9e-1d58cbd9f7c9 |  | note | – Hot dipped galvanised; or
label | 04f0d2f6-b4fe-5706-9925-962235cb6d4c |  | note | – Pre-galvanised prior to forming
label | 71e2e54b-5241-5987-81ed-69743fee6186 |  | note | ○ Attach: TeamBinder Material Approval Ref No
label | 48a56d57-3694-57ab-a323-90b734d53b10 |  | note | Method - Document Review
label | c4e44512-d428-5466-8adb-dbc697274271 |  | note | Frequency - Prior to works start
label | b635fe1c-e337-5929-b550-97a033431668 |  | note | Category - HP
label | e55c9c93-97b4-50a4-9b43-16087623ca7c |  | note | Responsibility - Nominated Authority
label | e4a3dc92-c560-54d3-beb8-4bef2a0ae355 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Check for correct documentation
label | 7f47e098-3ea7-56be-97df-c02df4bba0c9 |  | note | Reference - IFC Drawings
label | 368b94ef-3188-571e-8875-0289577d3810 |  | note | Acceptance Criteria - Ensure that all employees and sub contractors are:
label | 747f9daa-7fb6-5ba6-9a17-1fd8bf521a2d |  | note | – Using the correct and complete set of drawings
label | b944ee0e-1499-543d-b1cb-084f5656fd96 |  | note | – All drawings are the latest version
label | 3344164b-9516-5ce0-b7cc-bd03ec34796b |  | note | Method - Visual inspection
label | cfed2639-5142-525a-bb5a-475396e193f5 |  | note | Frequency - Prior to commencing any activity
label | 3f02c1c5-f604-5c36-90b1-c17099fc635a |  | note | Category - HP*
label | 8c9c732a-7d74-538c-81cb-269d710b2196 |  | note | Responsibility - SE/Site Supervisor
label | c4fe3b8a-56a0-5791-9da8-9765f6a2fe84 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Setting Out - Position of Posts and Signs
label | 427eb93c-6bb1-5a54-b44a-c3c017b1e27a |  | note | Reference - Section 714.06 IFC Drawings
label | 7784acbe-af4b-5ce2-b371-a98e540c66f0 |  | note | Acceptance Criteria - Set out work in accordance with IFC Drawings. The required positions of all posts and signs shall be checked and confirmed by the Superintendent before the erection of posts
label | ac42b444-e9b7-5529-8e7c-da15058dc25b |  | note | Method - Verify
label | 344c7924-14db-554c-ad6a-d907152071cc |  | note | Frequency - Prior to start
label | fe1f8cd0-13dd-5c14-adb0-9267db537d2b |  | note | Category - HP*
label | 42e44d2f-549e-5c6c-9526-765401335920 |  | note | Responsibility - Surveyor, SE/PE, Nominated Authority
label | 7389a70d-22da-5b4e-87ac-8bf3116c3c84 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 4. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Foundation
label | 5dd9840e-45da-5bd9-92c8-6cf35b665479 |  | note | Reference - Section 714.06 (c) Section 703
label | 96a19468-e452-59a0-a76b-3ae6c5db53a7 |  | note | Acceptance Criteria - All posts shall be set in concrete foundations to depths shown in the Sign and post Schedule and have hole diameters as per the below:
label | 88e3e050-277a-57be-93c6-8f19af2feb9e |  | note | ○ Post sizes 32mm and 50mm nominal bore steel = 225mm diameter
label | c4a77849-0ac7-5534-a3d2-15f9e1eb49da |  | note | ○ Post sizes 80mm to 150mm nominal bore steel = 300mm diameter
label | 422545f7-fd93-50f3-9ae2-73431d2fc52a |  | note | ○ Frangible hardwood posts 180mm x 100mm = 300mm diameter
label | 843bfbf5-8bd6-579d-a208-7e842757f96c |  | note | ○ Concrete shall be 20MPa and complying with requirements in Section 703.
label | c98abbf2-b88c-507c-9e54-3425d18aca4e |  | note | ○ Attach: Concrete Delivery Docket
label | 11e5f0a0-0a3a-5547-b81b-53983548a6ac |  | note | Method - Measure, Visual
label | 68dce87b-5685-5e1d-880a-f35068389a4e |  | note | Frequency - Per Lot
label | 43548a84-58aa-5c37-88b0-5b8b64745a86 |  | note | Category - HP*
label | 5678d170-60fe-578f-9a08-3cab5d12e47b |  | note | Responsibility - SE/PE, Nominated Authority
label | ee70e2ea-f524-525c-80df-5a592b981723 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 4.2 - Post Installation in Sockets
label | 9dede390-23ff-5810-b0b7-3b40344becc6 |  | note | Reference - Section 714.06 (d) Table 22 of AS 1742.2:2009
label | 157aa50a-739b-51e1-80dc-c34b7fddce65 |  | note | Acceptance Criteria - For Post Size 32mm Socket size to be 50mm Nominal Bore Tube
label | cd81a36b-ee34-5f02-9186-df9831b10854 |  | note | ○ For Post Size 50mm Socket size to be 65mm Nominal Bore Tube
label | a54ad967-7dee-5db8-9b7a-52c15417d6f0 |  | note | ○ The socket should protrude 50 mm above an earth surface or 25 mm above a paved surface.
label | 08b6ab0d-e432-5b36-a6ce-bb1d32aea5db |  | note | ○ The sign post must penetrate a minimum 450 mm into the socket.
label | 50ef56b5-bbcf-5ee2-a65b-6524c9ad2630 |  | note | ○ Depth of the socket should be as per Table 22 of AS 1742.2:2009.
label | e9a149dd-035d-5487-a815-c84172b0fd88 |  | note | ○ The sign post should be securely fixed into the socket by an approved vandal-proof method.
label | 35b4a040-775d-5707-956d-6da6ce082610 |  | note | Method - Measure, Visual
label | a772a573-2735-5d72-b69c-e21dd848bfff |  | note | Frequency - Per Lot
label | 0c189354-6885-5c58-a855-c0f0fd56b405 |  | note | Category - IP
label | a83cb3c9-7140-55d7-ad55-e85a0245379c |  | note | Responsibility - SE/PE
label | 2c4e8b1b-f2c5-56fc-9221-30ff7a2dcd8d |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 4.3 - Backfilling of Post Holes
label | 1f517259-97eb-5509-97d8-ff01fc86291f |  | note | Reference - Section 714.06 e
label | 1fdacb4a-f599-583e-942f-12683cf42946 |  | note | Acceptance Criteria - 32 and 50 mm Nominal Bore Steel Posts
label | 538af8f3-4022-5d1f-aaaf-0d7a5e01e027 |  | note | ○ Posts holes shall be back-filled with concrete with a nominal strength of 10 MPa.
label | 4f92b166-46e9-5ad5-b0cb-74dc5aebcf04 |  | note | ○ 180 mm x 100 mm Frangible Hardwood Timber Posts
label | 2151b9c7-37ab-5bff-9372-63ed3d44db30 |  | note | – frangible Hardwood Posts shall be erected in accordance with the drawings;
label | 5aaaa807-a337-5a90-bcd1-56df8962ec20 |  | note | – post-holes for frangible hardwood posts shall be filled with a mixture of gravel and cement (4% by weight)
label | 906b72c1-d70e-550d-8847-114a6528357e |  | note | ○ Attach: Delivery Dockets
label | 4c9f7dc3-611b-5eb7-bcd9-ea320139420f |  | note | Method - Verify
label | e100148b-64d8-56d1-9d74-cf48a884b7e9 |  | note | Frequency - Per Lot
label | 5fab3570-9edb-5fe5-aae4-a1f991baa42e |  | note | Category - IP
label | 24ffe9b8-91ae-5ef9-a7c4-5bd1fc15bf58 |  | note | Responsibility - SE/PE
label | fe160453-4165-5837-b3db-9c688da327b9 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 4.4 - Sign Fitting
label | ecd41049-35e2-5906-8cd1-3721cd81721c |  | note | Reference - Section 714.07
label | fd9d8c3e-0039-5e0b-b329-3fb249a036ad |  | note | Acceptance Criteria - Signs shall be attached to the post or structure using the type and number of fittings as specified in the Sign and Post Schedule, or as follows:
label | 7e4b02c7-9bd8-5822-a158-4b85a39e3325 |  | note | – Signs up to 200mm in depth – one fitting per post
label | a6477a7d-d139-557e-9c79-5e06114844bd |  | note | – Signs 201 to 900mm in depth – two fittings per post
label | 4cbe527c-e325-5c1c-bf16-d54450d0b96c |  | note | – Signs 901 to 1200mm in depth – three fittings per post
label | dd78d408-e5bc-572a-bc6c-5c02af48f32a |  | note | ○ One extra fitting provided per post for each 400mm increment or part thereof above 1200mm.
label | 6ffc6e10-c657-50d4-a116-ab95f8c89041 |  | note | Method - Measure, Visual
label | 6f990118-da00-5cd6-b015-ac5abc01546e |  | note | Frequency - Per Lot
label | ee0a9e94-99f1-54d6-8edf-a0afd1a0953f |  | note | Category - IP
label | 4b9cae86-fb96-5a25-ba85-bff30d349095 |  | note | Responsibility - SE/PE
label | a3324cba-db44-5f38-ac65-5aa901478073 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 4.5 - Mounting of Signs
label | 7f09b195-a1b5-544a-9055-8fba4ff32ef0 |  | note | Reference - Section 714.07 (d,e,i) IFC Drawings
label | a2e2afbf-654b-5cf3-8f93-ec2a8c949c1f |  | note | Acceptance Criteria - Nominal Mounting Height for all signs in 2m from Road level to bottom edge of sign except keep left signs (R2-3) located in median islands, which are mounted 0.5m above ground
label | 5f411997-cfe3-5cbc-86d2-0a31e78dff5c |  | note | ○ Signs shall be positioned in accordance with the following tolerances:
label | 983672af-ab36-51a8-8208-d90c56a89677 |  | note | (i) +/-40 mm of the height specified in the Sign and Post Schedule measured from the bottom of the sign or sign assembly to the lip of the kerb or edge of shoulder nearest the sign;
label | ba2f2b13-fcae-587f-9b7c-a864b5565eab |  | note | (ii) +/-100 mm of the pegged sign location or specified location.
label | 13591091-99f7-5c2c-931b-cc2fa8d716bf |  | note | ○ When a sign is to be mounted on frangible posts on a cut batter having a slope steeper than or equal to 2:1, the mounting height at the shorter post may be reduced providing that:
label | 6913b740-f478-5c09-990d-df5ba8e9c09b |  | note | (i) the uphill corner of the sign is a minimum of 800 mm above the ground;
label | 73de89ae-d70e-5a39-a419-06fe9441ce63 |  | note | (ii) the sign at the longer post is 2200 mm minimum above the ground.
label | 95a5ddc3-00ad-5451-ad3e-b505e62a85bb |  | note | ○ Sign shall be installed such that the sign face is rotated away from the approaching traffic to avoid direct reflection (approximately 5⁰)
label | 17fee63b-08bb-5bc9-90ea-e0f47e44991f |  | note | ○ After erection of each sign, all stiffening bars are to be removed.
label | 3c018456-e3da-5181-a0e6-d44ff5571c2f |  | note | Method - Measure, Visual
label | 22f8fe07-c7e0-5707-85aa-9a66a7f72eab |  | note | Frequency - Per Lot
label | 887670af-c03d-505f-b2b6-d5720d662eb7 |  | note | Category - IP
label | 10e9052e-8ed6-576c-af9c-b2bf3be1e7f6 |  | note | Responsibility - SE/PE
label | 6a3a994e-6e4e-5a3f-b993-3830d8c90339 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 4.6 - Masking of Signs
label | b6d183cf-4718-5bda-b294-33b4954e4877 |  | note | Reference - Section 714.08
label | 2f3beb93-7fe8-59af-bd4f-75bbbdb203f8 |  | note | Acceptance Criteria - Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign.
label | e12a82c0-d3aa-58eb-8dde-e2b7d29b643f |  | note | ○ Adhesive material shall only be applied to the masking material and not be applied to either the front or rear face of the signboard.
label | fbcd658d-0d93-527f-b308-bb6f93915840 |  | note | Method - Measure, Visual
label | 2b786447-a02f-5842-bc3e-19da575c58c7 |  | note | Frequency - Per Lot
label | b6503b80-b926-5bca-a194-f6d062cc66d1 |  | note | Category - IP
label | bb0a577c-8f1f-5829-befa-0b15d87efc68 |  | note | Responsibility - SE/PE
label | 2266c127-d4d2-5750-929f-021bb3aaaf9b |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 5. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - As-built Survey
label | 49ee943e-d0c4-5be6-b68c-a4794d74f353 |  | note | Reference - Section 714.05, IFC Drawings
label | d84640b6-965e-5f7d-9955-adbe16d453b8 |  | note | Acceptance Criteria - Survey activities carried out to validate correct construction of signs, components and posts as per IFC Drawings and Section 714.
label | b94c3bd2-2d19-5b83-b187-bfe7a36eefa1 |  | note | ○ Attach: Survey Conformance Data/Report
label | 36add929-d674-5969-8494-4c3a30b613f0 |  | note | Method - Document Review
label | b93a3999-5c78-584f-89fd-c16c6e12deec |  | note | Frequency - Per Lot
label | a8869624-b472-5afc-8a62-8ae9d7a8659b |  | note | Category - IP
label | fbb72c22-4a11-53e8-9624-b170f3cd4712 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | a8943292-22a5-55b3-9529-8cf3017ae918 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.2 - Non-conformance Report (NCR) Closure
label | f5361328-afa5-575c-9b8b-bf39a6a879d2 |  | note | Reference - MRPA Quality Management Plan
label | 067cab8e-c8e7-5893-aea9-5c066a1be848 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
label | 0f349fd4-e496-51eb-bf72-eeef3e23e635 |  | note | Method - Document Review
label | edac4b90-5f86-5818-a66e-b70f55a3b44d |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | b5fa9945-7b73-598f-aee3-badb44939395 |  | note | Category - HP*
label | be999e6a-08ff-58ac-b276-7a913ab73c2c |  | note | Responsibility - SE/PE/SPE
label | 9f3b2427-9b18-57f2-bbf0-77480454e22b |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | Final Inspection
label | 70502c38-226e-5b91-85b0-4a649945ae17 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d0b3ebed-1144-5550-82cc-5f10be65d9a0 |  | textbox | Name:
text | f8ab2061-aec1-5209-83c6-46b0ea2611ef |  | textbox | Position:
text | 5ba1a661-9098-5438-9ea0-624ba5ec1313 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-043-CIV-Brunt-Type A Embankment Fill | itp |  |  |  | Yes | ITP-043-CIV-Brunt-Type A Embankment Fill | d587068f-6e9c-462b-9791-e947cd646e96
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 9aa55048-26ab-546d-8619-9c6b8b68c2ef |  | note | Document Title: ITP-043-CIV-Brunt-Type A Embankment Fill
label | 43e9ff87-10b3-5968-8758-3f44b01697aa |  | note | ITP Description: Type A Embankment Fill
label | 36ece767-8d0e-5d2f-9f0b-3a6c52bbd015 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 4e32b7b3-ed6e-50e3-8867-e38abaa08646 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | accb5953-fb53-5d3e-b951-23c6c706e729 |  | note | Revision Number: 0
label | c3ea72d0-6b1c-53e1-b4cb-79c619e43c6a |  | note | Revision Date: 7/07/2023
label | 686a49f8-1755-59f8-b82e-7418da17616c |  | note | ITP created by: Jason Lee
label | 5efad249-b68f-57a8-8a51-23dcaef254f2 |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | f919786e-93bf-5516-8851-ce7244ae514d |  | note | Reference - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | bf02a6c9-7303-5f4a-af97-43f658689ea2 |  | note | Reference - VicRoads Section 173 (Oct 2008)
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | efebf337-a13e-5ab6-a59b-58c0ff2d56c2 |  | note | Reference - VicRoads Section 204 (Dec 2015)
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 5bed3cdd-8674-55e7-8022-d12b46dde596 |  | note | Reference - Code of Practice RC500.20, RC500.5
checkpoint-group |  |  | section | 2. Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance
label | 88dcac63-f324-5d72-89f0-4c885ffa1349 |  | note | Reference - IFC Drawings (MRP-089-C-ACD-DRG-30-BFD-CBR-2848) Section 204.04 b) Table 204.041
label | f29d7ee4-40ae-59dd-bffc-1d4f2571d985 |  | note | Acceptance Criteria - CBR ≥ 8% and Swell ≤ 1.5%
label | fd7cf5d4-f274-582c-9dd1-2fe63f0efc7d |  | note | • Max Permeability = 5E-9 m/s
label | 539a90ea-350e-5d24-8461-3f7d3d621138 |  | note | ○ Grading:
label | 51e5f53f-b89f-51bd-b27d-e174f6c8a090 |  | note | • 75.0mm 100%
label | 6d005c35-b4f1-5d68-b3da-f4ff10eed3de |  | note | • 4.75mm 40-80%
label | 0808cdae-106c-5a38-be64-e6fd11eae3e8 |  | note | • 0.075mm 10-40%
label | adc5867e-2664-5496-bb56-db870f027e6c |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
text | e19f6309-5a79-59ac-82b2-392ebda9a293 |  | textbox | Reference: TeamBinder Material Approval Ref No.
label | 127f3655-6c52-5133-a0b9-eb24cad6e49e |  | note | Method - Document Review
label | 1ad04910-d814-5aba-88b9-fdae40f8b1b8 |  | note | Frequency - Once, for each material type
label | 0c7b95be-68e8-54ec-8f11-4ba166aa5b5f |  | note | Category - HP
label | 8d487b84-da11-5640-8e7c-af99593bdb57 |  | note | Responsible person - Nominated Authority
label | 70800ead-253f-5036-9c11-a88932fa6ce3 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Pre-Commencement of Fill Works
label | 1adfa66b-5a70-5d37-bc87-c6522b746beb |  | note | Reference - Section 204.10 (b)
label | 399a9acf-09aa-5f68-9519-a33427e7cf9d |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | c71f6ec2-93ce-54f8-b491-b4360a1cdd4d |  | note | • The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | 56399c4e-e92d-5a33-872e-3171443c3b0d |  | note | • No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
text | d716d2de-85c5-5c95-8366-67cd3ab71342 |  | textbox | Reference: Subgrade Preparation / Previous Layer Lot Number
label | b3d074ad-98d4-5db8-9b1e-f70e7446980a |  | note | • Attach: Lot Maps
label | 09f8555d-fb66-5ae8-adfd-ec04e62ee90b |  | note | Method - Visual Inspection
label | 20121d86-6888-5ba8-ae7b-da8982af3d08 |  | note | Frequency - Prior to commencement of fill works
label | 21f67fb4-b66e-51a3-84d8-c9dcd11ad107 |  | note | Category - HP
label | ca6d9d19-5a9b-57da-8052-4726a0af1773 |  | note | Responsible person - Nominated Authority
label | 82dfc764-14d2-51fe-87e8-9d0013c59182 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out
label | ba167167-4b3f-5f95-8d61-30b8b1e9bc6b |  | note | Reference - IFC Drawings
label | 1e0b8012-2fbd-50b8-a95a-b25381982cdd |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | 59998471-80e6-5ebc-8493-148a91add776 |  | note | • Attach: Lot Maps
label | 0f9c6ae5-179d-5d0f-ac92-bf04a5414bc3 |  | note | Method - Visual Inspection
label | c00200fe-9434-5fab-83cf-c3f4e6bcc876 |  | note | Frequency - Prior to commencement of fill works
label | 39e5933c-edea-51b9-a725-5582fbb7d5e8 |  | note | Category - HP*
label | 333eaab0-2035-5161-90d5-b94654ac5aa2 |  | note | Responsible person - SE/PE/SPE
label | cc277183-d770-5beb-95aa-f0258c80d242 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 5. Type A Fill Activities
checkpoint-status |  |  | checkpoint | 5.1 - Placing of Fill
label | c7573a08-a2c8-5efa-ba32-0e147da60507 |  | note | Reference - Section 204.10 (d)
label | ec0ce410-0432-5c3c-a8f6-ba9aec8537d0 |  | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | 99ea1d7a-da0f-55e9-bc88-3ca692fae5f1 |  | note | Method - Visual Inspection
label | 981392ed-e0ea-5333-b1af-44b5fea98e9b |  | note | Frequency - Each Lot
label | 2788e3f1-bb23-5f0a-9337-7a3298f393f0 |  | note | Category - WP
label | 59ee80dd-2532-53f6-9e7a-05d4171092f8 |  | note | Responsible person - PE/SE/Site Supervisor
label | 8708c1c5-4f45-5abe-9dfd-c778c595f221 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.2 - Fill at Structures (where applicable)
label | e5b20d1e-1f9a-56e0-b24c-9af1625bdd7d |  | note | Reference - Section 204.11 (b)
label | 90993620-1182-5f1c-8341-71f717fbc8e9 |  | note | Acceptance Criteria - No Fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent
label | 05017d59-32d0-5487-bc00-2bd87be08af9 |  | note | • In addition to the placement of Type A material at bridge abutments as structural material, embankment material or backfilling within 3 metres of retaining walls, wing walls, all crown units, and culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
label | ea443de8-79b4-5c88-aca7-7d59718ba12e |  | note | Method - Site Inspection
label | f2f837a3-7161-575a-85d6-cbe9ee7ea842 |  | note | Frequency - Each Lot
label | 8434919f-2b7c-5cc8-bc2e-343844026317 |  | note | Category - HP*
label | d97c73c7-3cd2-5ced-89ea-60671b1fc677 |  | note | Responsible person - PE/SE/Site Supervisor
label | 044bd8a6-be71-5c8f-a72e-dc2e2f1819e3 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.3 - Test Roll / Proof Roll
label | ee28546c-5542-57d7-98be-459401076ec2 |  | note | Reference - Section 173.03, Section 204.12
label | fbf75c18-9ca2-588a-8fbf-a6eb62cbf33f |  | note | Acceptance Criteria - Each Layer shall be proof rolled with a superintendent present. Compliance with the proof rolling requirements shall be when an area withstands proof rolling without visible deformation or springing.
label | ee9750c1-bf05-50cf-b195-47fa1a745b1c |  | note | • The plant for use in proof roll to comply with the following requirements:
label | c62d8753-2237-5e86-8459-eb2d42b61634 |  | note | (i) Static smooth steel wheeled rollers shall have a mass of not less than 12 tonnes and a load intensity under either the front or rear wheels of not less than 6 tonnes per metre width of wheel.
label | 356bc8ae-7e18-5b5a-9755-eb5409712b64 |  | note | (ii) Pneumatic tyred plant shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre. The area over which this ground contact pressure shall be applied shall not be less than 0.035 m2 per tyre.
label | c6201fc9-083d-5f3a-8a9c-12293e57f63a |  | note | Method - Visual Inspection, Test Roll as per 173.03
label | 6b1b573e-e910-58a6-a8f7-ac8ad52c3804 |  | note | Frequency - Each Lot/Layer
label | 5a0755d2-63e5-563f-bb7b-85027b1bb7da |  | note | Category - HP
label | c1475976-afd3-5275-a9d2-cb2494b08e50 |  | note | Responsible person - Nominated Authority
label | 7dcd1ded-1ebd-5e74-8418-db5274a3a1f1 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Compaction and Moisture Content Testing
label | 7b039dd0-e48c-552c-a84b-40cb7028debb |  | note | Reference - Table 204.131, Table 204.142
label | aed782ec-1978-5c57-b6e4-4f197f7c5fa2 |  | note | Acceptance Criteria - Compaction Requirement to be Scale B: Characteristic Density Ratio 98%. (6 tests per lot)
label | 69015c4d-4967-5e3f-910d-132ef9026a5f |  | note | • Once three consecutive lots of like material have achieved the requirements in the first test, minimum testing frequency can be seek with the Superintendent agreement.
label | 50d223fe-7a52-55c9-946b-1609df420add |  | note | • Minimum Testing Frequency: Every second lot
label | dbd6bbbc-9def-509d-a575-7229c6ddf909 |  | note | ○ Lot size
label | 6452aaee-75a9-5601-bc79-398f9341eece |  | note | • Type A Material - the lesser of one day's production or 5000sqm
label | 2be5dab4-f391-5348-b1d9-2f4ab3e8ced8 |  | note | • Attach: Compaction & Moisture Content Test Results
label | d4efd88d-242e-5696-a8a5-ae4381fc5c12 |  | note | Method - Review Document
label | 0ecd2bbe-fd9b-5513-86c4-39c8695ba4de |  | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | f1227353-e17d-5ff2-afd4-29e6fce510a7 |  | note | Category - IP
label | 91d1ea23-179f-5cde-be2d-73af1e551511 |  | note | Responsible person - SE/PE/SPE
label | 7cf22cd9-4913-50fb-abeb-d8aca7a9639c |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 5.5 - Post Compaction Material Property Testing
label | 9a300b30-d43f-5178-8cc2-915f36084656 |  | note | Reference - Table 204,041, Table 204.141 Section 204.14 (a)
label | 9f1f5a16-9c4c-59c1-9dce-75ac044cd7bb |  | note | Acceptance Criteria - Material Properties:
label | 99a410e9-6277-5e7e-994e-4d21782b2a43 |  | note | • CBR ≥ 8% and Swell ≤ 1.5%
label | 92a48768-784e-569d-a689-ca25b408e1ff |  | note | • Max Permeability = 5E-9 m/s
label | 170e728d-3ba3-5ec8-84d5-78992bd26163 |  | note | ○ Grading:
label | 2a51e371-c1b7-5121-a75c-62a6dad0271f |  | note | • 75.0mm 100%
label | 37fe420a-4cc6-52e4-b256-cbd783363bdc |  | note | • 4.75mm 40-80%
label | b14542cc-c88d-52a7-a206-862d49f0fc03 |  | note | • 0.075mm 10-40%
label | 1ad4538a-a274-5835-9b92-d6919c780922 |  | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 9b09d95b-886f-5590-a108-1c4a03c90811 |  | note | ○ Scale B:
label | e4af1178-2ab6-5b80-9e81-a4ed03214621 |  | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 7bc49269-67e7-5969-a52f-4c7d2f3416a2 |  | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 08d74956-ef93-5727-9d5c-5c073a3049d7 |  | note | • Attach: Post Compaction Material Property Test Results
label | 3050d655-0921-5e13-ad32-edfcdb78f0cd |  | note | Method - Review Document
label | 1a0ffd8e-aa96-5d25-af13-66a63adc21de |  | note | Frequency - Each Lot/Reduced Testing Frequency, Refer to Section 204
label | bf12c3ff-4ed2-5614-9425-0c5b52c7b6f5 |  | note | Category - IP
label | 660570cf-8a99-562b-9a68-9dbbb0417b29 |  | note | Responsible person - SE/PE/SPE
label | 2225651d-d6d1-5070-be06-97b5a09642f3 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Survey Conformance
label | 1d850ac2-524f-5588-981b-347680562794 |  | note | Reference - Table 204.031
label | f235a8ae-cefd-5308-95aa-5fef5f140a60 |  | note | Acceptance Criteria - Level tolerances (Scale B):
label | b807d4e0-cab2-5d60-a189-9c58eccf854c |  | note | • Range Mean = +5, -25mm
label | 31953c40-5abd-56b2-9d19-6dfe69574d4c |  | note | • Max Standard Deviation = 15 mm
label | 59a66fb4-cdc7-522d-9911-61e0015389ce |  | note | • 40 measurements per lot
label | d1c866e8-f826-5ce2-81a8-2ff45739d6f4 |  | note | • Attach: Survey Conformance Report
label | 581200a9-b430-5ba0-ab95-4e6083a79f11 |  | note | Method - Review Document
label | 98489305-b5a0-50d3-a23e-fae7cba6c4e0 |  | note | Frequency - Top of Type A
label | 0e1586a3-e675-5067-8888-a4433af6429f |  | note | Category - IP
label | ef51a104-4441-5f5a-b1cb-41b367f0c708 |  | note | Responsible person - SE/PE/Surveyor
label | 83daa6d4-bf06-5add-99e2-eb198622a2ae |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | 6.1 - Non-conformance Report (NCR) Closure
label | 27a1fd7d-d646-590a-837c-c11033d1e9c6 |  | note | Reference - MRPA Quality Management Plan
label | e057b7d9-2bb4-53c9-90b6-d69f42a4a266 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | e76558c4-c114-5ba3-9715-b7e4bad6d9c1 |  | note | Method - Document Review
label | 31a945fc-4aee-551d-88c0-722ffb7d9ea7 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 92842a2f-6e49-5d32-ade0-03b2d7287e38 |  | note | Category - HP*
label | 8cdca31f-d408-5a75-b54d-6cf90ae13037 |  | note | Responsible person - SE/PE/SPE
label | 517c4c8f-3a6d-576e-8ac0-4d69afb18277 |  | note | Verifying Documents - This ITP Signed Off
checkpoint-status |  |  | checkpoint | Final Inspection
label | f474439c-08f9-5a32-a9dd-11bb2ad9d958 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c46bad7b-ae2f-5c35-90f7-958975836b05 |  | textbox | Name:
text | 1d1c94d9-3273-5bbf-9956-9d8dd488dd53 |  | textbox | Position:
text | 0bda0a6d-67b6-568b-968b-b3e0d90c459a |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-018-CIV - Rail Delineation Temporary Fencing |  |  |  |  | Yes | ITP-018-CIV - Rail Delineation Temporary Fencing | d5893295-6f23-44df-9977-9016088197db
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 49a60d57-6123-55aa-b7be-8a3ac319df20 |  | note | ITP-018-CIV-Brunt - Rail Delineation Temporary Fencing
label | 004e7bf7-04cc-5797-a0c8-f77b5bfeb28a |  | note | Rail Delineation Temporary Fencing
label | 05937d5e-05eb-503f-8173-a4a5afb41186 |  | note | CIV
label | 39b8aecc-a924-52bd-a916-1d3d6d511c72 |  | note | B
label | 26157d17-12a8-5451-88c0-67dabf0e4bf4 |  | note | 12/01/2023
label | f5e170dd-c3cd-5fc0-97c5-ad2808e9b949 |  | note | Casey Knowles
label | 71fbd623-fa48-56fa-b525-8b5ecacdeccf |  | note | Jon De Castro
label | 42a58549-c3ab-5734-92f9-4aca1ffce1dd |  | note | ITP for Brunt Rd only
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 2a8dffb2-68f4-56ab-8267-6b79039a65a2 |  | note | Reference - IFC Drawings L1-CHE-STD-005 L1-CHE-STD-025
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix
label | 47a88c6d-99ce-56d9-b81c-4296f94a7690 |  | note | Reference - IFC Drawings
label | 1f8f3773-4552-5da2-8fca-4e45f9ea0688 |  | note | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings. Attach concrete delivery docket.
label | fad838b6-117d-5c25-8bfa-8f3fec182da1 |  | note | Method - Document Review
label | 465f6575-e2da-5ee4-b4a4-17b91c139182 |  | note | Frequency - Each Mix
label | c65899e4-f70a-5dd7-b994-f192d1f1d8e2 |  | note | Category - HP
label | 37647053-5974-590b-86c9-32fcf9a52e62 |  | note | Responsibility - SE/Site Supervisor
label | f50fafae-c8a3-53d1-9a60-d87721ed1afe |  | note | Verifying Documents - Supplier Certificate of Compliance Deivery Docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Steel components
label | 43f5e242-67a4-53d0-9f15-d42f95ea2531 |  | note | Reference - IFC Drawings AS41000 AS1163
label | aad9508b-99cd-5949-a2a6-c0879564fce3 |  | note | Acceptance Criteria - All Steel must comply with Australian Standards. All dimensions relevant to setting out and site work are to be checked on site by the project engineer prior to works commencing. Erection and fabrication tolerances for structural steelwork as per AS4100. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250.
label | 68e38571-4c53-55f4-9706-1b5e67fee084 |  | note | Method - Document review Visual and Measure Order Acceptance Checklist
label | 7e5e872f-74be-5056-b114-360a394a55a1 |  | note | Frequency - All elements
label | d9013d35-bae3-5ab0-ae7d-18c7c680d90c |  | note | Category - IP
label | 8b909d21-7bfa-5c6b-81bc-ec20c9e003c0 |  | note | Responsibility - SE/Site Supervisor
label | 31969b90-b953-5ff5-9610-ddd905d0d0c7 |  | note | Verifying Documents - Supplier Certificate of Compliance
checkpoint-group |  |  | section | 3. Preliminaries - Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Excavation works
label | 746f05a8-9cb3-5aef-99a8-97e1b6741361 |  | note | Reference - IFC Drawings L1-CHE-STD-005
label | 0b971038-b61c-5974-ac75-f8b8416c5882 |  | note | Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements. Follow asset owners guidelines for work around their service. Where posts are within 1m of an underground service, or whereelse nominated, post footing installation shall be via Non Destructive Digging. Direct driven installation method to be used for all other posts.
label | 13dbafa5-7241-5964-8836-36c8a07348c5 |  | note | Method - Document Review Visual
label | 13176b84-2181-5f95-9bdd-4dd04ea67f58 |  | note | Frequency - Each Post
label | 3a345071-3c5c-55e4-bcd9-dbaf004afc52 |  | note | Category - IP
label | f7b83b8e-1327-527a-bef4-e217b1ff5d9c |  | note | Responsibility - SE/Site Supervisor
label | 51ec3f16-acc9-5089-886e-3423c124400f |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | 4354b5ad-148a-5feb-b0c5-a4fd6827327a |  | note | Reference - IFC Drawings
label | 8b11fcad-069d-5452-bb6f-51152ab69e64 |  | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays, gate locations, tie in points. Offset checked against the running edge prior to installation of posts. Up track & Down track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | e3a55277-3c60-5aaf-a95f-8d2993c5c464 |  | note | Method - Measure Visual inspect
label | 85f06c05-df5a-5869-8e77-1177888cb636 |  | note | Frequency - Each element
label | 6e26e5a2-dc02-59e2-b5f4-1ccb78c62dd3 |  | note | Category - IP
label | ed5ece6c-530e-5cab-ab49-ddfa30530145 |  | note | Responsibility - Surveyor SE/PE/SPE
label | 2c880b13-ccda-526d-aa13-f4f4dad1ba24 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Ground Conditions
label | 23486828-33da-5083-a2c5-d4e1dd7d80b7 |  | note | Reference - IFC Drawings
label | ef49b2f3-119a-56ef-908e-0324f4e85a7b |  | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | a78e4402-7058-5d25-bec6-1baae39cad42 |  | note | Method - Visual
label | 89f204c9-bd12-5f35-9504-48cc4fa9f1f6 |  | note | Frequency - Each post
label | 2bb05fad-3eba-56be-9338-60100d6af1de |  | note | Category - IP
label | 71baf2cf-e7a8-59f9-b6ec-ab5cb7e8f375 |  | note | Responsibility - SE/Site Supervisor
label | 8fafa8f8-3cff-5286-9bd5-177d8174624f |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.2 - Post Foundation
label | 1f6c1322-3b7f-5fa6-b463-6c4ae1a99851 |  | note | Reference - IFC Drawings
label | 4ca189e9-92c6-5c08-b722-e6f4381ff4c3 |  | note | Acceptance Criteria - Post into 101.6x4 CHS Sleeve - 300mm Dia - 1300mm Depth - 2700mm Typical Spacing
label | 8b83fb41-283f-5030-91bb-70f89dea38be |  | note | Concrete Footing (for Steel & Timber Posts) - 300mm Dia - 700mm Depth - 2700mm Typical Spacing - 600mm Post Embedment
label | f7bc3401-a5dd-51de-8928-fce8d4965834 |  | note | Direct Driven 88.9x4CHS Posts - 300mm Dia - 1500mm Depth - 2700mm Typical Spacing
label | cfffcb64-04df-5ccf-867a-040ac64c6489 |  | note | Gates - 350mm Dia - 1100mm Depth - 1000mm embedment depth - 1350mm end span spacing
label | e6d1c2f2-e6b6-56d2-a2b0-0abf480a0fd9 |  | note | Where post is installed through a slope/embankment, increase the depth of embedment by 600mm from the above requirements.
label | 1a67751d-98eb-50a0-8524-78039394ee95 |  | note | Section 610.161 Concrete testing at frequency as per 610.161. Minimum of 2 samples per truck.
label | 4e960bab-f889-5d87-b090-e541877b7d70 |  | note | Method - Measure
label | d604e622-e325-54e6-a093-1541c34e78d7 |  | note | Method for Section 610.161 - Concrete Testing
label | 9636d6a0-6913-5b7a-9dd4-fad18142c44e |  | note | Frequency - Each footing
label | 4ea90bdb-d70d-5df3-9851-505be07bc053 |  | note | Frequency as per 610.161
label | 7fc7ce7b-7c2c-5c96-9090-179e3b6b6ad9 |  | note | Category - IP
label | b10326f6-3ce3-56ea-a6e0-828a4a18dff1 |  | note | Responsibility - SE/Site Supervisor
label | 4bfec945-e638-560f-aff6-14088bd969b9 |  | note | Responsibility for Section 610.161 - Testing Report
label | 3e3fcdb0-146f-5c53-83d8-2ff6f1c3708e |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.3 - Post Installation
label | cf971ca5-ad2c-5529-83ad-b513cef13a2f |  | note | Reference - IFC Drawings L1-CHE-STD-005
label | e532c69b-3dc0-5a93-8961-159cacc277ab |  | note | Acceptance Criteria - Up track & Down track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | f001543d-2005-514a-a4c0-fef2cc86b2fc |  | note | Maximum post spacing to be 3.1m to avoid clashes (localised only).
label | 5afe9b53-8275-5ada-aa78-904369e93aa3 |  | note | Two spans at 1350CTRS at the end and at Refuge bays.
label | c548d363-c92a-5aa4-a9ac-d5ef9d0e6305 |  | note | Max. post height 1800mm above ground level.
label | 5dd8fac0-9455-5edc-9a6b-afad0faab199 |  | note | Vertical Tolerance: ±20mm from the design line.
label | 6fe7376b-c944-59b7-976c-93b69f877b12 |  | note | Timber Post to be installed directly either side of OHLE footings (existing and future).
label | d784857a-6fd5-5f4f-a8fc-545c410ebfbb |  | note | Method - Measure
label | 211b8e04-a859-5287-a305-6f5bd032cce1 |  | note | Frequency - Each post
label | 8796a8d0-5340-57fa-8672-12aae4ddd175 |  | note | Category - IP
label | 2794f13c-ae4f-52fd-8c38-df1ad9f798e9 |  | note | Responsibility - SE/Site Supervisor
label | edb3e090-070e-50b1-b86c-78253cbe27c3 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.4 - Chain Wire Mesh Installation
label | 6d38b241-4e87-5069-9878-e5af856b25ba |  | note | Reference - IFC Drawings
label | 5678344b-dcfa-5ad0-8707-fed1bd27e053 |  | note | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with 1.57mm tie wires.
label | 9193df3b-210d-5e64-8eac-5f52ef496631 |  | note | Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tie wire or approved clips.
label | 9688de5d-4bfa-59b4-b9fd-a422901f0a09 |  | note | PVC coated mesh and tie wire to be installed for 2m extent either side of OHLE footings (existing and future).
label | 49f21903-d3f4-55cd-88b1-b229b0fb1df7 |  | note | Distance between ground and bottom of chain mesh and ground to be 50mm.
label | e22a3857-59eb-5150-bc72-631cb139a45c |  | note | Method - Visual
label | 77ba1fda-0dc5-51e4-9d45-38feaa67d47b |  | note | Frequency - Each element
label | 81b8af1d-342e-5835-bfd0-ae5a1c4fdfb8 |  | note | Category - IP
label | fc72415e-c29a-54dd-816b-e6ff69a3ba6b |  | note | Responsibility - SE/Site Supervisor
label | c2ba6288-f9ae-5341-98a2-22d7d7800fd6 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.5 - Bracing
label | e285804e-4544-5d5d-9831-6d345a5e4c1c |  | note | Reference - IFC Drawings
label | 04aeb4a0-044a-558f-8cda-8daa90cd63ff |  | note | Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | 0d2055fc-371a-5e89-bb13-10119de679cd |  | note | Bracing to be installed on both sides of the fence at the fence corners
label | ab353d7a-98ba-5b9b-86ea-ac8498c7c7b0 |  | note | LVL Brace to be used between timber and steel posts either side of OHLE footings (existing and future).
label | 5cbedd33-eb2c-5564-8040-45785cec9eeb |  | note | Method - Visual
label | a0a30cc2-6f4e-5294-8f21-6e6c3505d6cb |  | note | Frequency - Each element
label | 9ff30c8b-b87c-55d9-8b2c-3478781e9e00 |  | note | Category - IP
label | 8de83fba-2a21-5502-9f27-e4ef089e1801 |  | note | Responsibility - SE/Site Supervisor
label | f3669e03-cf21-560f-baee-b0825ee65f31 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.6 - Refuge Installation
label | 0be0407d-2057-54df-8164-da8777a31d32 |  | note | Reference - IFC Drawings
label | 9826e0e2-62f2-5c02-9232-b5e98c6c7ceb |  | note | Acceptance Criteria - Refuge Access to only open from track side.
label | e580def4-c676-566f-8ebc-71c06b91e480 |  | note | No chain wire mesh to be installed at refuge access.
label | 91b6cf41-f7ca-552f-b589-bea179eb35be |  | note | Refuges at southern fence shall be staggered in relation to the northern fence refuges. Refuges to be at maximum 20m c/c spacing.
label | 777a0624-bc31-5ba4-a541-f578a8a342ca |  | note | 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | c488423c-2815-5386-801c-0060493cb192 |  | note | Method - Visual
label | 54cc27cf-531c-5349-a92a-9e14bb54ed2e |  | note | Frequency - Each element
label | e7e5bf24-af5f-5779-8b11-f1dd7253171c |  | note | Category - IP
label | 37f5601d-984d-5029-bda6-1c8cd3d1c816 |  | note | Responsibility - SE/Site Supervisor
label | abb6bb21-04d9-5cb3-a619-bde27e5129ba |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.7 - Refuge Signage
label | 5e62ca1f-ed75-5861-a660-b11a7afcd564 |  | note | Reference - IFC Drawings
label | 5784ab9b-c4db-5195-bd3a-ad8942d3b413 |  | note | Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
label | 64208897-0291-5a5d-8c81-2d79384a80c6 |  | note | Method - Visual
label | fd13c10c-5c46-52a1-a655-937897db63e6 |  | note | Frequency - Each element
label | 9b3d222e-7fb4-5487-8885-8df0da101902 |  | note | Category - IP
label | 77f57202-29f3-53f1-a6b0-e60ba98262ea |  | note | Responsibility - SE/Site Supervisor
label | 8005ca26-59e4-5a78-ba8a-52c61864b319 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.8 - Fence Tie In
label | 8c9bc60a-c6d7-5afa-b50e-8540dfc89cd2 |  | note | Reference - IFC Drawings
label | 0ab05ce6-09ba-5ee1-8652-3c775917ee7c |  | note | Acceptance Criteria - 200mm Air Gap to be provided to existing fence to provide electrical discontinuity.
label | 797b4484-ed2f-5765-a4ba-9a5eb07215e2 |  | note | Method - Measurement
label | b7636286-e696-5a1b-9e0a-6f0080041231 |  | note | Frequency - Each Tie In
label | d92fa36a-aa5e-5b74-9cbd-fb024a05789a |  | note | Category - IP
label | d0aaf000-801e-5163-9aff-3bba0499ee90 |  | note | Responsibility - SE
label | 223e1f94-4634-57b0-b2fb-e12555c90ac9 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.9 - Gates
label | 9aeb0f06-0da3-5114-bf79-80593abcdda9 |  | note | Reference - IFC Drawings
label | e4f35f63-2865-52b8-8731-cd212c8841ee |  | note | Acceptance Criteria - Gates to be installed as per IFC drawings. Location may be moved nominally to avoid service clashes.
label | 0fcf76bb-bc05-5aaf-9ee6-864ebcecef9f |  | note | Method - Inspection
label | 704048f5-3aca-50f1-9c3e-b34dda0158ec |  | note | Frequency - Each element
label | 9d4a3491-a19e-55cf-b7b9-170ef9dc1653 |  | note | Category - IP
label | 7b2c7f3a-5328-572e-9cc1-5f116b2da8fd |  | note | Responsibility - SE
label | 7bcfc6b9-7795-5569-a402-6fadf7936430 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Fence Height and Track Clearance
label | cf442c4e-c33d-5cef-aa37-a000215ef6de |  | note | Reference - IFC Drawings
label | d7dbecd1-e4f7-551a-b5a5-d85ea510f3f0 |  | note | Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. Attach as-built survey.
label | ba894dc1-d999-57d8-b7b2-7dc7c4b0b016 |  | note | Method - Survey / Measure
label | 391efbbc-fb16-56c4-8b1c-a71ed9d76952 |  | note | Frequency - Each lot
label | f0d79ab1-2a5b-535b-ab43-c9b09e3ce516 |  | note | Category - IP
label | 5b6ca6e8-8518-5231-91b6-1d5f62f87ebd |  | note | Responsibility - Surveyor SE/Site Supervisor
label | ade9378e-84ef-564f-ab93-88b1339d7aa7 |  | note | Verifying Documents - As-built survey
checkpoint-status |  |  | checkpoint | 6.2 - Compressive Strength Test Results
label | c9093542-6ed3-54b3-aa62-17ef9dab268a |  | note | Reference - IFC Drawings Table 610.05.051 610.16 (g)
label | 6874aee7-3030-527f-9c9a-3bede66730bb |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 1468fd3c-5f67-5ee6-8ace-40cb9bb08173 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength
label | d972ca36-b0d2-53e5-8fc7-1805498efb8d |  | note | Attach: Compressive Strength Test Results
label | 0a9644b9-5a87-5eb6-aaf8-422b17750f14 |  | note | Method - Document Review
label | f8217460-d5e0-5c0e-9508-cba33f895b43 |  | note | Frequency - Each cylinder
label | 62c960da-f1b9-5e61-b25f-56bc1abe4abf |  | note | Category - IP
label | eaf7232a-fb89-5a48-825a-b5e7976d0b08 |  | note | Responsibility - SE/PE/SPE
label | 20fe5757-37dd-59f0-b6a8-a9fe0c090f7a |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | f0af6660-3bba-5898-b888-8be70ed9bc64 |  | note | Reference - MRPA Quality Management Plan
label | 73d8010c-9604-53b0-aeb0-feb9c5b536cd |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 295d5bf7-383b-5205-bb6c-ca4fa06fa177 |  | note | Method - Document Review
label | 59e3d294-acfa-5f1e-97cf-ef9315d54327 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 8f32cf8f-7c6d-5da9-a4d4-44447eaf85a5 |  | note | Category - HP*
label | 3a82e2e4-cfdd-59ac-840b-591962fba7b9 |  | note | Responsibility - SE/PE/SPE
label | 55c1dbc2-4996-5ab3-8198-4ea381913302 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | f8699205-a213-5aa7-a73a-06b8836c5969 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | aed79ae8-abf3-5f0e-bc61-ab0724ab1db6 |  | textbox | Name:
text | 6a91607d-f6d8-5917-8f37-c45d98e89380 |  | textbox | Position:
text | 09b6037e-8554-5bf4-80df-69f833451586 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-016-STR - OHW Structures Pilling |  |  |  |  | Yes | ITP-016-STR - OHW Structures Piling | eef7af09-66b8-47db-9512-9d23c3787642
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-status |  |  | checkpoint | 1. Referenced Documentation
label | 6d75905b-07b8-5e13-b390-d11b52066b1b |  | note | Document Title: ITP-016-STR-Brunt - Overhead Wiring Structures Piles
label | 25fc532b-3682-55cf-8499-c43ab2276bec |  | note | ITP Description: OHW Structures Piling
label | 25f42d5f-087c-5edb-9bdc-6e244c2dab6c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 6e5019be-b9b4-5917-8341-bac778d9966b |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | e611855a-68fa-5e12-85cc-9cbfe4ed46cf |  | note | Revision Number: 0
label | d703875b-2d08-5fb5-a938-e288c1f8f377 |  | note | Revision Date: 21/12/2022
label | ae7103d2-f4e4-5eed-925a-8e91636519df |  | note | ITP created by: Casey Knowles
label | ef2f780b-b06e-5605-b8c6-12f6ef21e186 |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | d75bbc7f-4a0b-506c-a2a7-14e5386b2ce0 |  | note | Reference - VicRoads Section 606 July 2017
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | ae8bff4a-42a3-580a-8c4e-5d2db5b84c2a |  | note | Reference - VicRoads Section 610 Feb 2020
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | a02fdeab-9f5b-5d5d-81ea-26c0aab6147d |  | note | Reference - VicRoads Section 611 November 2018
checkpoint-status |  |  | checkpoint | 1.4 - Non Dependent
label | 66967e35-84fb-5140-aaa3-5236e5c02ecf |  | note | Reference - AS2159-2009
checkpoint-status |  |  | checkpoint | 1.5 - Non Dependent
label | b0041dd5-f7b8-5f68-9993-f16305955c57 |  | note | Reference - AS3810.1 2018
checkpoint-status |  |  | checkpoint | 1.6 - Non Dependent
label | aec856d6-1d8c-5b81-a21e-f95b5607e407 |  | note | Reference - AS5100.3-2017
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix
label | b3844d19-3c04-5d51-9153-9eaef57490d0 |  | note | Reference - 610.07 Table 610.071
label | 3b58881b-b880-57e0-bc65-93161972d7cd |  | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 7bc36f21-1387-53c1-a6c9-3cd8381e56b8 |  | textbox | Enter: Teambinder Material Approval number
label | cae957aa-ec28-5707-830c-951a66807c95 |  | note | Method - Document Review
label | 54867dfb-1bf6-527a-aebb-ffb609a51ff2 |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | a35ac1d4-8c4f-5505-a7d0-f5cf5226c96a |  | note | Category - HP
label | ff9f2d3e-3042-5355-8299-2eba33557146 |  | note | Responsibility - Nominated Authority
label | f91e9f3a-4fc7-5b99-add8-129ec4899d03 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | 3951fa93-0e36-5cc5-9512-c64256ec59b9 |  | note | Reference - 611.05 (a)
label | 4e563028-aa74-57d0-8cf5-1d231baddb84 |  | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | e5c17641-b10e-56e7-a3fd-6babac3f47d7 |  | textbox | Enter: Teambinder Material Approval number
label | b059eb69-2ee5-5787-92b5-46c6011ae554 |  | note | Method - Document Review
label | 26edb014-e6ac-53ee-9b53-c99cb3c01737 |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | 7a2e238a-171b-5ea2-baae-e816551a3309 |  | note | Category - HP
label | c036e448-4623-53ae-89d8-07d2ab9e7964 |  | note | Responsibility - Nominated Authority
label | 7a70db95-6141-56f8-b2e9-cfa8a58ce0bc |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
label | ad53c4fe-946f-5c1a-b009-4c481f63bb47 |  | note | Reference - 610.26 (a)
label | 3fcb2cf7-c4b8-5ae1-b71f-2f30139c1499 |  | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require testing to demostrate suitablity to prevent excessive deformation under loads.
label | 3931cec5-fc17-5887-ab73-836a16ace267 |  | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 10967ddb-2832-50ee-a39b-b07e8bd085d8 |  | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority
text | ae0bf16a-90a3-5cd4-b427-23e5c8240b7a |  | textbox | Enter: Teambinder Material Approval number
label | 135a68e9-98ef-5a64-b577-debc40a2a9a0 |  | note | Method - Document Review
label | 769fa397-44e1-5937-a464-3faea5466b1b |  | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | 23c2a5a6-4060-5441-bf79-d731328abc4e |  | note | Category - HP
label | 21cad5ab-4012-5ff6-b2ae-cdafaded3557 |  | note | Responsibility - Nominated Authority
label | 4780be35-f84f-5694-af4b-8701c5c86e5c |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Cast-in Bolts, nuts washers
label | c684f3a8-fec4-5cb2-8a12-6a45b83e5f4c |  | note | Reference - IFC Drawings
label | a3bd4659-a516-5a1f-bf12-88b97f9801eb |  | note | Acceptance Criteria - Unless the drawings note otherwise all bolts, nuts and washers shall be 8.8/TB galvanised components to AS 4291.1 & AS/NZS 4291.2
label | c2156da2-3fa6-524a-b245-fb0863d8bd40 |  | note | • Washers installed under bolt head and nut. Tapered washers used as required.
label | 775b07cd-813e-5473-830a-a149338c7acc |  | note | • Slotted holes and required hardened or plate washers in accordance with AS4100 and AS 5100.6
label | ff967c5e-9397-5f05-899b-f04438a746a9 |  | note | • If HDG, a certificate is required. HDG thickness should be as per designs.
text | f86c57ba-2cde-5b7a-af58-17c27aea07f2 |  | textbox | Enter: Teambinder Material Approval number
label | abcfa52e-971d-5bf4-b437-6c794dc1d448 |  | note | Method - Document Review
label | 1f449ea9-8364-5da1-b0ad-3ba5e62e44d2 |  | note | Frequency - Once for each supplier, 14 days prior to placement of hold-down bolts
label | f9744f86-c2a3-501a-8ce0-0725d178ce20 |  | note | Category - HP
label | b58ca47c-a231-5933-81c4-992cd3695315 |  | note | Responsibility - Nominated Authority
label | 629212cd-3668-5ba2-8ec7-68ddcb24faaa |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 - Working Platform Certification
label | c4064d7c-2e71-5411-8642-78fc796483cd |  | note | Reference - Temp Works Design
label | 6ce5a0bb-569a-59ea-9819-9989a30a30dc |  | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement
label | 7b3570a1-1fbd-5a1b-9364-e51fa70d9262 |  | note | Method - Document Review
label | cfed4fe6-be1b-524d-895b-246dc3213c98 |  | note | Frequency - 14 days Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | c490ab29-b37c-5e48-92fa-e8b5de83b2f9 |  | note | Category - HP
label | 805ea187-20c6-59c8-a2d9-3a33d90b0fec |  | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | 71baafbc-37a1-53a8-afd1-44758c98ad85 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Piling Operations Work Procedure
label | 899849f2-25ee-50d8-a354-a8ee8889b31e |  | note | Reference - 606.03 (a)
label | f257c195-c370-5c2e-b34b-41d590265d40 |  | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
text | c28edede-10ee-5512-8edc-e591c5bef884 |  | textbox | Enter: Teambinder Approval number
label | 03456f31-ed63-52f3-9558-76c0fa815b73 |  | note | Method - Document Review
label | c285a223-ebeb-5151-bc96-d30db01b34c7 |  | note | Frequency - Once, 4 weeks prior to the commencement of piling
label | 581df56f-0f4e-5ec0-8ae1-cc72ecadcb10 |  | note | Category - HP
label | 421cd6fe-c986-5e61-af82-6b18e6aa4753 |  | note | Responsibility - Nominated Authority
label | 7f4d58be-55c4-5431-bb22-ccd17fe71925 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Temporary Steel Casings
label | 85cf63ea-e7c9-5586-a215-683eacb69e5c |  | note | Reference - 606.03 (b)
label | 7e6626e3-ab70-5b34-ae6d-d9fe0ca70913 |  | note | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | 2debd97c-9da6-5b97-8307-f72ccacffa55 |  | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | 9eb06191-6953-5f1c-a939-acf85c70eab4 |  | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | eda654c3-765d-595d-a894-9e43d18575a9 |  | textbox | Enter: Teambinder Approval number
label | 9ebb7cf7-8a0b-59bc-8057-a74d862ad8ee |  | note | Method - Document Review
label | 1f8c3bb8-af4b-552c-97f7-92a231d51977 |  | note | Frequency - Where applicable, once, 14 days prior to use
label | 25cb5f79-e074-574c-829a-4bb8806e081a |  | note | Category - HP
label | 29071cf4-1fe0-5357-b0be-0dfcc1bd84ca |  | note | Responsibility - Nominated Authority
label | 85640938-bbe4-508a-a6ba-87a8af35948d |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Casting Under Water Procedure
label | 3201180a-6520-54ab-a780-637d1e424d7e |  | note | Reference - 606.06 (a)
label | e49f44f0-04e1-5744-9dad-0b6ea366841e |  | note | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | 11622133-9d38-5390-b84d-a5715104f124 |  | textbox | Enter: Teambinder Approval number
label | 87ab2ae2-a7f8-5438-8cfb-f6d4528f7717 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 0bb2389b-1a8a-51fd-a81a-c56ec9872faf |  | note | Method - Document Review
label | 120d7443-5ab7-5cce-8ae8-7b7ee9277d1b |  | note | Frequency - Once, 4 weeks prior to the commencement of piling
label | 0d69acdb-a7ad-5300-90f0-59f3b8c06600 |  | note | Category - HP
label | c882b95f-bc90-5b94-93e6-b327d283e917 |  | note | Responsibility - Nominated Authority
label | 0b44b29e-2c32-51d5-aa19-b2a8fb952358 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Pre-qualified Pile Testing Consultant
label | fdb83e28-2359-51cc-bd96-2a3ce3c182a4 |  | note | Reference - 606.07
label | 1336b521-30ea-56af-b331-545c22e78345 |  | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor. Details of the consultant to be submitted for review to the Nominated Authority.
text | a4803dc4-d65d-5b6f-b611-36d9f119897e |  | textbox | Enter: Teambinder Approval number
label | 0811d0ee-d3c8-5f41-9370-c4d0cc2669d0 |  | note | Method - Document Review
label | 3cf03bd7-cab2-5308-92cc-aee931bf8263 |  | note | Frequency - Once, 14 days prior to testing
label | ea707cef-b7fe-5e08-9916-4f254a234819 |  | note | Category - HP
label | e23afe74-40f1-5b00-aeb1-2380996c06e6 |  | note | Responsibility - Nominated Authority
label | 991154f0-018b-5415-9274-cd96571b979e |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Reinforcement Welding Specifications & Qualifications
label | 8bc9a2d9-9d1f-5671-883b-2864748d40a4 |  | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
label | ebee1b98-a2b2-566b-9369-3adc4d003f85 |  | note | Acceptance Criteria - Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
text | 6b8ec349-504d-5461-bcf5-02b3d44cd551 |  | textbox | Enter: Teambinder Approval number
label | 733ab2c4-db40-5dcb-b282-4b781d4de24a |  | note | Method - Document Review
label | fb18b20d-53d4-5b60-b52b-62e1c0102f32 |  | note | Frequency - Where applicable, once, 14 days prior to welding
label | e7aff11d-54cf-5aca-b57d-f436276f239b |  | note | Category - HP
label | e4d650e4-39e1-558f-be34-931bad456c88 |  | note | Responsibility - Nominated Authority
label | 34e85cf0-9271-5388-ab2c-9c4abfc43633 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - IFC Drawings
label | 02f3487e-7a44-5424-8e38-d74e3e8313b5 |  | note | Reference - MRPA Quality Management Plan
label | 0a629ace-e87f-5fc8-b3d2-68c52e938bfe |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 941e827c-cd78-5245-898e-cae5ab99b132 |  | note | Method - Document Review
label | 3d501d55-b55f-58b0-9492-7fa6b0efb21a |  | note | Frequency - Prior to starting Works and at regular intervals
label | 758d6763-d52a-5e4b-89dc-04d464c1afde |  | note | Category - HP*
label | aa7e50b0-57e7-5a63-b4b6-e9cf8b2c6868 |  | note | Responsibility - All
label | 9ab37582-6ea2-5aa9-98aa-e0f9e9795cb8 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 4.2 - Survey Set-out
label | d75d8d83-18ce-5693-9344-6be325f6961f |  | note | Reference - IFC Drawings 606.08 (a - c)
label | e7d3c85a-7672-5923-b247-c8494da69ad7 |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | bb08dd98-a3a4-5e63-aa7c-83643a1ef33a |  | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | 5f3528af-4814-5c2a-8638-4f11ce160e45 |  | note | Method - Measure, Visual
label | 2f44c78e-02bc-5775-8d92-f3063a517a34 |  | note | Frequency - Each pile
label | 42d40f5c-42e7-528e-becc-51f0ec451ac3 |  | note | Category - IP
label | 93b0be93-870f-5a4e-8544-21fc926f0349 |  | note | Responsibility - Surveyor, SE
label | df6e2c84-d97f-548f-9ac0-bc37b4afafa7 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 4.3 - Protection of Adjacent Piles
label | abd54425-9406-5a42-a953-3924b8e438a5 |  | note | Reference - 606.04
label | 1d19da5b-1b73-534c-a18f-210420cb3043 |  | note | Acceptance Criteria - Pile construction shall not:
label | d2490933-b71e-597b-8fcb-490e03f172ca |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | fbde29f1-74de-558f-8cd6-17df3d05d12d |  | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
label | abbd86ef-025a-5629-afcc-a9cfd422f10e |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 8d4a5a21-76e4-58ba-810a-b6756e323ccd |  | note | Method - Measure, Visual
label | 244d8aa1-c040-58c9-a9ef-b5551f49ea73 |  | note | Frequency - Each pile
label | 4ef0a8d5-b531-51be-adbd-7b8b468841fb |  | note | Category - HP*
label | cb3cf172-ac68-5f41-b241-c5015604748f |  | note | Responsibility - SPE/PE
label | 3a04e6ef-9101-5320-ac20-e85f58def130 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 5. Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Boring Operations
label | 9d323a10-3a5a-53c9-ba03-f41014c974d0 |  | note | Reference - IFC Drawings 606.03 (a)
label | e8093f8f-5c19-5a4f-947c-b195c43f4ad0 |  | note | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | a432f664-3f0f-562c-9f59-56d4e2ca9c40 |  | note | Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | 2f181057-df10-5ded-a93f-7e28aceffdba |  | note | • Excavation clean and de-watered (where applicable) for inspection.
label | c0422aa1-6ce3-5879-8175-945b728980be |  | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in
label | 84c0a7de-a014-5375-9ddd-1662a6b61a0a |  | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
label | 190aab8b-5eaa-5f47-8dac-5f49e25fcc7b |  | note | Method - Measure, Visual
label | e5236c84-fc04-5bdc-8736-45e8b32a3b7e |  | note | Frequency - Each pile
label | 8d5b9a0c-36e7-5776-baa9-1a087f8cee4d |  | note | Category - IP
label | dae80ee6-e578-540b-a41d-2edc80a8c25b |  | note | Responsibility - Surveyor, SE/PE/SPE
label | e34454f5-4f8e-5df0-9be9-11ebac9e0f2b |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.2 - Formwork Extension
label | 875a628e-5a1e-53a1-9942-3a04759c6257 |  | note | Reference - IFC Drawings
label | ac323ac1-7687-57e1-bc5e-fee02fbc206c |  | note | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | e5376c2e-9526-554e-943b-fb55b5df2369 |  | note | Method - Measure, Visual
label | dcc693e7-8e22-5609-950d-5249981a1ad4 |  | note | Frequency - Where applicable, each pile
label | 19695304-e827-59fd-a075-7d1d9681af1a |  | note | Category - IP
label | 33b240ce-1d50-5d3d-9fe6-2545a9e25fba |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 72c26afa-720b-5fc8-a3ba-81ae7bcd8eca |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.3 - Inspection of Pile Excavation
label | 348c85ce-7360-527b-9027-7bb67662fe33 |  | note | Reference - 606.05
label | 714bd385-a796-5af4-bed8-4682ad0f6ebe |  | note | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 0abfcaf2-8de2-5986-a637-5e6b7066e70d |  | note | Attach: Geotechnical Field Sheet or Report
label | 7fc4ff6d-2403-56a0-a692-f1a436298d64 |  | note | Method - Measure, Visual
label | b763f9af-c7ef-5e6b-80db-4be7c25a3192 |  | note | Frequency - Each pile
label | 3037953b-d049-58f3-b9e2-bf72be317719 |  | note | Category - HP
label | 70ae129b-1a9e-5516-b3e1-3c9801f18a4f |  | note | Responsibility - Geotechnical Engineer
label | 6442a920-9395-588d-8d07-03a56b9624d6 |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Reinforcement - Placement
label | f88b1a63-7d7a-52cc-a50a-a2ed50b6fd60 |  | note | Reference - IFC Drawings
label | 1819c9e6-8dca-5276-89de-490a0736cf13 |  | note | • 611.06
label | 7544be1a-279d-5785-9b51-3d858c951f52 |  | note | • 611.09
label | d8aa8e11-57f9-5748-938d-37d2e9503e0d |  | note | • 611.10
label | 88303a6d-db42-55b6-9d64-e05478c9333e |  | note | • 611.11
label | 6f3d244f-daf9-5af4-a06f-3e4ed6e0a105 |  | note | • 611.12
label | 3ee40575-40a0-55e9-b0a0-82211e0fab27 |  | note | • 606.06 (a)
label | d1eda92b-8019-5905-a66c-e43e1a5be4e9 |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | b5b9f8ff-3bef-5641-a8cd-7fb9801b0a24 |  | note | • Projecting reinforcement is the correct length and location.
label | 616d71b3-2a58-522d-852f-4abba2bc4422 |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | 1a0395f2-4e3b-52fb-85ba-4a6152994467 |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | 16966cc7-9cd2-5706-af1b-da789b709c37 |  | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | a882721d-021b-5416-aa80-5087a64ba74c |  | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | a607965b-8cf4-50d1-8606-1d668e6f1031 |  | note | Method - Measure, Visual
label | cb5731fc-954a-5d35-b139-167fa92f05c0 |  | note | Frequency - Each pile
label | f89f649c-f448-5874-b463-a9669978e2e6 |  | note | Category - IP
label | cc31fdb1-4e56-5a55-a323-b39b3e461b08 |  | note | Responsibility - Foreman, SE/PE/SPE
label | cc8dbe71-4ae9-54a3-b24d-d5c71f4cb1d1 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.5 - Reinforcement - Electrical Continuity and HD Bolts - Electrical Continuity
label | d7aea5b4-1acc-533d-bf5d-141e29bad945 |  | note | Reference - IFC Drawings 610.29 (d) 610.43
label | fb81158d-d34a-5e7e-b9d1-403910d2f7be |  | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
label | 1fe75c70-b5fc-55a1-95a7-911eef639bc3 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 7a3c8c13-3203-587e-ad37-23e2b6f8cf45 |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | 8b2e60c2-552d-5a5f-bdab-5455458e126b |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | b7c72e5d-de73-5988-a73d-3f023663b28d |  | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | fa59a9ba-c09f-503c-8aaf-0ece013df7c7 |  | note | • Overhead wiring structures shall be fully earthed, by bonding the hold-down bolts to the pile reinforcement
label | 9f75330e-6cd9-560e-860e-c3f3c224fc0b |  | note | • A minimum of 2 No. hold down bolts shall be electrically continuous with the pile reinforcement. This is achieved by tack welding 70mm of stranded copper cable between the hold-down bolts and reinforcement
label | 7145aeaf-06e8-54c0-9495-cee4309264ce |  | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 36a95d80-8873-5d7b-8ba2-41a6bf6ec52d |  | note | Method - Measure, Visual
label | 47836e7a-91c6-518a-9124-e442c2a566ee |  | note | Frequency - Where applicable, each pile
label | 88b7ce34-9dc5-5e75-aae8-a8cddd6316dc |  | note | Category - IP
label | 8f6db2a9-310a-5c8f-955c-496429e55481 |  | note | Responsibility - SE/PE/SPE
label | 91fdca11-0f2e-5eb5-9317-215b61877a7b |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.6 - Cast-in Items
label | f2f36ab1-eca6-5435-bad9-15d15492f738 |  | note | Reference - IFC Drawings
label | 9a9fc0e0-57d7-5c13-af40-4216bdde1d4a |  | note | • 610.46 (a), Table 610.462
label | 1c4cf6c4-6536-5a00-9219-79879354cedb |  | note | • 610.47 (a), Table 610.472
label | c7611c31-f9af-5fd1-ad3e-569f026d9b62 |  | note | • AS3810.1 Table 3.3.6.2
label | e6e1f715-a33f-545a-9853-03dd459aa402 |  | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 91b91468-db96-5700-bf96-d73678aff904 |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | df51edab-53df-5f50-8fab-da8c7b427099 |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 67ecea6e-cb66-5639-8b11-4b23b0620991 |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking
label | e847a825-7a49-562a-95e4-572b0ede217c |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 998c7056-79de-526b-a966-0f1ef0bff36a |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | bf21ee75-d55e-5b47-839f-aab01f20dacd |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 17d7717e-e3e2-5af1-b7c6-e2888406613c |  | note | iii. Ducts and conduit location = ±12mm
label | 2d3191c4-1ad5-5d52-97fc-510d1a26b010 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | d3170435-fdc0-5d81-a759-308469170f8c |  | note | Method - Measure, Visual
label | f49e993d-e73e-5ef5-ac89-a0ff4319633c |  | note | Frequency - Where applicable, each pile
label | e1b537f7-d1a8-5f91-99b1-938f35cedb25 |  | note | Category - IP
label | b4223b7b-5928-5722-960a-cd0a4d372e63 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 6abd5362-2740-549c-8303-c31854820961 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.7 - Pre-pour Inspection
label | 137d834d-a665-5ab4-8470-9ed4ac30cd78 |  | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | 3cbdd7eb-c3ee-5fb5-981e-569cc1f184d0 |  | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority. All foreign material has been completely removed from the excavation.
label | 2ca92fd8-40a9-5a19-829e-641b47c47d86 |  | note | Attach: Pre-pour inspection checklist
label | 816b67fd-31e8-504b-b5a8-032c45453d4f |  | note | Method - Measure, Visual
label | faf2c412-8fef-5fbc-ab6c-162774ddc711 |  | note | Frequency - Each pile
label | 61341418-e4f5-524a-a69c-a34ca557e9ef |  | note | Category - HP
label | 8debcfe5-76bd-5dae-abba-9dd3a797887f |  | note | Responsibility - Nominated Authority
label | 175bde89-2df4-57c9-9f26-4696e12df01a |  | note | Verifying Documents - ConQA Hold Point Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 - Weather Conditions & Evaporation Limits
label | b67a3327-8d53-5a02-bebf-88184b02a99b |  | note | Reference - Hot and/or Cold Weather Concreting Procedure
label | 67536b1c-effb-5a8d-8c5b-7833569225e3 |  | note | 610.17, 610.17 (a) & (e), Table 610.171
label | c02b52dd-8c4e-5a45-8284-5844b15401f5 |  | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | aca97baf-8ddb-507e-b708-662356f93c8c |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C
label | e0ea8c11-bf39-5378-b477-b2123212d6a4 |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | ea6a937c-d5ab-596c-b0d8-e028356913ca |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 1c7c438f-9d8a-5267-9de1-6390ee5119b2 |  | note | • Record: Required information on the Concrete Pour Record.
label | 512ea921-7582-5312-af91-cae3b8d666db |  | note | Method - Measure, Visual
label | 6989e803-a179-54fd-b747-9326d69f5ce7 |  | note | Frequency - Each pile
label | 1fc0add7-3b95-5fa4-8bb2-f461c666a648 |  | note | Category - IP
label | 2f362302-5f70-55dc-8501-a576aa74a1c3 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 0fac5482-23eb-543a-bc59-6939953044bd |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.9 - Concrete Testing - Sampling Frequency
label | ab3ed66b-7893-5d53-99c7-13ccc1da5895 |  | note | Reference - Site Sampling & Testing Procedure 610.16 (b), Table 610.161
label | 86de89b9-623c-5610-8d25-3117da8db987 |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 14afaead-2658-574b-8615-ac1d50f5a6f1 |  | note | • 0m³ to 10m³ = 1 sample
label | c2752f8a-2bf1-5f79-9367-19445320eb6d |  | note | • 10m³ to 25m³ = 2 samples
label | 79424a81-1823-5ae9-9ef0-c74b3f3c458d |  | note | • 25m³ to 50m³ = 3 samples
label | 701077a5-9472-58a9-b7ca-7bbdff7d8933 |  | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 6d86ec8e-233c-5107-b10a-c0af4a6ce163 |  | note | • For each additional 50m³ and additional sample shall be taken.
label | f93d6fb7-d291-50b3-ab4c-e408862e0f3e |  | note | • Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete.
label | 3dcc49af-bfd9-5801-992c-3318e8654f28 |  | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ec7643b5-13ae-5c13-b5dd-b3709844a09d |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | a910de4c-9586-5bc7-926d-bcc27e2d388b |  | note | • Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 6813406c-29f4-5b72-80fb-a54cebca6303 |  | note | • Record: Required information on the Concrete Pour Record.
label | e6e965a6-8013-59f1-bdc5-f9b5d90ed064 |  | note | Method - Test
label | 9f14260a-5e32-50e8-8885-11475cb78d66 |  | note | Frequency - Each pile
label | 7fc91ca3-d95b-57a3-aea7-aa80ec882734 |  | note | Category - IP
label | 24182c06-55c9-53b6-ac77-0a9e04f79024 |  | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | b7f12ee4-6d53-56ca-9eac-88875f061d9a |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
label | c0820e52-8f07-5bb4-8efb-da4f81042e8d |  | note | Reference - 610.13 (b)
label | 4d5914eb-698f-5ee8-9728-a49776abf191 |  | note | Acceptance Criteria - Spread range = 550mm to 750mm
label | 3c5634cb-f14b-5104-90fe-c02b51877d0d |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 344eb366-30a7-51f6-9742-c955676ac6b7 |  | note | • Passability = ≤10mm (aggregate height differential)
label | 1e9c33c2-fa5f-5873-82dc-151cbbc1b410 |  | note | • Record: Required information on the Concrete Pour Record.
label | fe7242f6-15c8-516a-b416-dce52bb00621 |  | note | Method - Test
label | d69d7829-ea92-5468-aee4-3cca324cb0f5 |  | note | Frequency - Each sample of Self-compacting Concrete
label | 237d73de-38b8-5794-bac2-8aa5ff6f4b36 |  | note | Category - IP
label | 8685bc1c-1fbe-5068-98d6-8a3553f0385e |  | note | Responsibility - Concrete Tester
label | 75fac9f1-ecc5-5aa1-8a05-f405a14f6215 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.11 - Concrete Testing - Slump Test
label | 01d8e568-829f-5ffc-9cdb-51af66cbf73a |  | note | Reference - 610.16 (c), Table 610.162
label | 776771bf-cc00-5e6f-900f-3543181b2474 |  | note | Acceptance Criteria - Consistency of concrete to be determined by a slump test in accordance with AS 1012.3.1
label | fa95401f-2425-5489-9358-6152a2a1c83e |  | note | • Slump to be within limits as per Table 610.162
label | 33f48bef-67fc-5110-8861-e6faa7e837d7 |  | note | Method - Test
label | efdb63ca-be0a-5f52-b469-df0b8c173498 |  | note | Frequency - Each sample
label | 7cb8d994-f047-57f9-b743-d49db740425c |  | note | Category - IP
label | aa18e3a9-dac1-5566-8d4d-d4b6cdc4961c |  | note | Responsibility - Concrete Tester
label | 00ebd30f-c79c-5f8c-ada5-41a65c0dede4 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.12 - Concrete Testing - Compressive Strength Cylinders
label | d3bee8f9-b06a-5f82-9b96-74be1853ceb5 |  | note | Reference - Site Sampling & Testing Procedure 610.16
label | ed25b051-1609-5758-8b44-4374b7bb68a7 |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | a4b98818-ec65-54f4-b44c-6e5c73eceb2e |  | note | • Record: Required information on the Concrete Pour Record.
label | f011b391-536f-5567-8cde-9c00d26ff0e8 |  | note | Method - Test
label | 7c0b35a2-1298-5541-8658-3fe5884cb524 |  | note | Frequency - Each sample
label | 423ec98e-9dbf-5c75-9b66-145d736f42eb |  | note | Category - IP
label | c66928a2-f69b-560c-a6a9-486577c8318f |  | note | Responsibility - Concrete Tester
label | c8fc1277-1bed-5e15-970a-38fff0a65b06 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.13 - Placement & Compaction (Dry or Wet Excavation Conditions)
label | bcbaeb3e-e5b2-5a89-abbc-70d1f1d03572 |  | note | Reference - Piling Quality Procedure 610.18 (a) & (b) 610.18 (d) (i) 606.06 (a & b)
label | 0e9e4dcc-bc7e-5764-aa4e-49fd90c63f30 |  | note | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm. All concrete batches are traceable.
label | 4af505f3-82ad-5a40-b360-b84b4488de6f |  | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m. The initial discharge is pumped to waste until a consistent workable mix is discharged. the ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | 45fe1315-e631-58e1-bf91-ade20de5448a |  | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | b3b87ce8-0417-5c63-8c50-d1b9136964b5 |  | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | 231b56f2-3f89-545f-84ba-27d045c43bd3 |  | note | • Record: Required information on the Concrete Pour Record.
label | 3a44e041-e683-548e-9c9a-acaf4af683fd |  | note | • Attach: Concrete Pour Record
label | aad7249d-696b-521b-82c6-9a6060495344 |  | note | • Attach: Concrete Dockets
label | c37b7bce-ac5b-5e6d-99c0-10c50a710028 |  | note | Method - Visual
label | 30d1915d-1d91-55fd-a2dd-29000774d4e5 |  | note | Frequency - Each load
label | 75fb5568-49d2-5054-b2eb-b8bd47b25f20 |  | note | Category - SP
label | e136336a-2bde-5bd2-80c4-f769656a5580 |  | note | Responsibility - Foreman SE/PE/SPE
label | e937cfe1-ee26-5711-a848-3de79d707a25 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 5.14 - Surface Finishes
label | c3d71bdc-9f3a-5110-b496-7af8f1554b32 |  | note | Reference - IFC Drawings 610.31 610.20
label | 8f0a57b5-d3e2-55a4-94d2-2a9cd606b7bd |  | note | Acceptance Criteria - Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 9f269fdd-7eaa-59b6-868a-5950241ccd3f |  | note | Method - Visual
label | 44833f4f-fab0-5487-8ce8-88f38b822494 |  | note | Frequency - Each pile
label | b5706f54-8f38-5178-b8ee-271decddd291 |  | note | Category - IP
label | 050f1f8e-8c26-5c7f-b4bd-c0b20deb3b71 |  | note | Responsibility - Foreman SE/PE/SPE
label | 20169090-0151-52db-ad2a-9dd92e3cd2f8 |  | note | Verifying Documents - This ITP
checkpoint-group |  |  | section | 6. Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Compressive Strength Test Results
label | fff6907e-65f4-5467-90d2-000792791833 |  | note | Reference - IFC Drawings Table 610.05.051 610.16 (g)
label | 3b63ece6-4fd0-515d-b5d8-31611fe40551 |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 9111bc53-0485-55d8-8a1e-5c7c1bfd19f6 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | ea454378-a0b2-57d8-b59f-a6bf5764b7d2 |  | note | Attach: Compressive Strength Test Results
label | a0faf426-f004-503f-90d6-e864ca69fad7 |  | note | Method - Document Review
label | 819d2039-1659-5c7f-9be5-8165651d8e25 |  | note | Frequency - Each cylinder
label | ac23d88d-5eaa-537b-a87f-c588464dc3d8 |  | note | Category - IP
label | 172a32dc-6840-5766-a4a4-160f9b5fca7a |  | note | Responsibility - SE/PE/SPE
label | 081151e7-be56-5a12-9318-7dd10c4ccb94 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.2 - Pile Integrity Testing
label | 07334617-8c27-547b-9e4c-bb8f0f8280fa |  | note | Reference - 606.07 (a, d & e) AS2159 Clause 8.8
label | 03da2f59-2869-57d1-92f6-f757d1adaf86 |  | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | 65e0dc03-50bc-5578-ad66-ed589936c74d |  | note | Cross-sectional area = ≥95%
label | d8cf11df-b173-5180-bd41-e4cf9f0744d4 |  | note | If any test fails, all piles shall be tested.
label | 7369a072-e54b-5cd0-8a1a-7ffa777f8f42 |  | note | Attach: Pile Integrity Test Report
label | 2e7342eb-53f1-52e3-8886-3183ed1e38ec |  | note | Method - Document Review
label | dea1839d-1e4e-5160-98be-e277138df491 |  | note | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | ba7f953e-c3d5-5e6b-a4cb-14622ec8748c |  | note | Category - IP
label | f5e00654-e023-5591-917d-b5384cd032d9 |  | note | Responsibility - Testing Consultant SE/PE/SPE
label | f89b5c1d-4689-594a-b259-177bb4ced69d |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.3 - As-built Survey
label | bb940145-3d41-5699-ba97-cc48ecaa917b |  | note | Reference - IFC Drawings 606.08 (a - c) AS2159 Clause 7.2.2
label | 1c5b3fa2-64ca-5735-9230-c6e74c2b0b35 |  | note | Acceptance Criteria - The following tolerances apply to piles:
label | 51832e71-c061-57d4-816f-ce24c0bccd5e |  | note | i. Pile head plan location = ±75mm
label | 1b55898b-28f8-599f-a994-15d284860969 |  | note | ii. Variance from vertical or rake = 1:100
label | 4eec18ec-da58-599f-ab18-fd08d9c51e68 |  | note | iii. Irregularities in straightness = 1:100
label | 96914fad-f377-5bea-8598-1f69579b16d6 |  | note | iv. RL = ±25mm
label | 23f6dcd2-b3a6-5c84-85b8-d73d94dceead |  | note | Attach: Survey As-builts / Survey Report
label | 42ba2410-7130-5096-b6b5-30e4c376e862 |  | note | Method - Document Review
label | eaa52dc3-1c01-5f10-8a75-e13c8ae0961a |  | note | Frequency - Each pile
label | 5b23bf33-058e-5fdd-b8c9-79159dd44c96 |  | note | Category - IP
label | a5b41953-8ca7-500b-9bcd-0d9d35ca946b |  | note | Responsibility - Surveyor SE/PE/SPE
label | 858c0a12-778b-54ae-b7ba-109382579f71 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | 6cb72887-727e-55f4-89db-ddeddc523b32 |  | note | Reference - MRPA Quality Management Plan
label | afda1f76-7681-5667-bd1c-30baf67e19ef |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | f42c1f86-158e-50cf-bd91-c94117e750c1 |  | note | Method - Document Review
label | 33529240-cd58-5aab-a8dd-402445ca3537 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 018ceca3-b319-5537-870e-13c45754ab86 |  | note | Category - HP*
label | c5683397-2598-5130-8668-2ba6e420a9a0 |  | note | Responsibility - SE/PE/SPE
label | b6b096a4-7642-506e-9524-485e9d8a0a97 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | ce008633-ee3a-5091-b887-644bdc24eac6 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 890a42a3-707e-5439-a264-feba315b06ed |  | textbox | Name:
text | f3ca944c-8e2e-5d1e-8a1d-d2f84bfbe1c9 |  | textbox | Position:
text | 78f38e3a-ad91-5c2c-8ced-09c089ae69a5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-028-CIV-Brunt-Tactile Indicators (Supply and Install) |  |  |  |  | Yes | ITP-028-CIV-Brunt-Tactile Indicators (Supply and Install) | f3b842f6-7be3-46d2-af4f-93c74f0ea49e
checkpoint-group |  |  | section | 1. Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1. Referenced Documentation
label | 8e75e9ca-efe9-5bb5-8f8d-802257850201 |  | note | Document Title: ITP-CIV-Brunt-Tactile Indicator (Supply and Install)
label | 54427697-c1bc-58c6-ac84-cc4b4bd8dc75 |  | note | ITP Description: Brunt-Tactile Indicator (Supply and Install)
label | 25beff45-fd7c-504b-b9d2-5b68817b91b4 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | e9165758-7893-5402-bede-d10f343a3d07 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 01dc2020-46c7-5280-9dd7-4364fa703a74 |  | note | Revision Number: 0
label | 12bc21bb-7fec-5d0b-ab1b-e70edae47f90 |  | note | Revision Date: 28/02/2023
label | b6d168fe-17ee-5e12-9146-cb47de98611d |  | note | ITP created by: Jason Lee
label | 277e75e1-7250-50df-ae5c-b771df7eef66 |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 3e905e4c-c773-5792-ba87-f3bdb388e5df |  | note | Reference - AS1428.4.1
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 14580d31-dc6a-5206-b020-51da7449352b |  | note | Reference - VicRoads Section 160.A9
checkpoint-status |  |  | checkpoint | 1.3 - Non Dependent
label | 17ae885f-25d3-5c78-aff7-7bce3f68902b |  | note | Reference - IFC Drawings
checkpoint-group |  |  | section | 2. Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance
label | 422e4587-b563-5f79-945b-31c2b214af81 |  | note | Reference - AS1428.4.1 Section 2.2 & 2.3.1
label | bee8700c-08c1-5eaa-a1a7-6254966ab456 |  | note | Acceptance Criteria - Tactile Indicators must conform with the requirements of AS1428.1.1 Section 2.2 & 2.3.1
label | 952e1e67-3be0-5c45-bf59-829280f7250c |  | note | ○ Attach: TeamBinder Material Approval Ref No
label | 077ee115-69ca-5c84-9bdc-427b95f7214b |  | note | Method - Document Review
label | 7a266cc6-4d6f-596a-b271-99f683de9d9a |  | note | Frequency - Prior to works start
label | 5c2109f9-51ed-5dfa-a870-531b6cb82dc5 |  | note | Category - HP
label | 8aed34b8-fe8c-53f3-8622-5ae77a6a17b0 |  | note | Responsibility - Nominated Authority
label | 2c6f99ad-a50a-59e2-83d3-98e50eddab26 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Preliminaries - Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Documentation Conformance
label | 84ce62df-b73f-51b9-b822-8f5160177037 |  | note | Reference - DoT Handover Process
label | b809b874-c2c4-5014-928b-5cc6001fec45 |  | note | Acceptance Criteria - Tactile to be yellow in colour, VicRoads approved as per design note RDN 06-05 and DDA Compliant
label | 8ad9db83-4cb6-54c0-8132-fd02ca1b9589 |  | note | Method - Visual & Document Review
label | 25e053d0-5322-5a22-90b2-83ca6e82f892 |  | note | Frequency - Prior to works start
label | 42543203-f0e4-54ad-93f3-531cb98a0b1e |  | note | Category - HP*
label | 92589faa-d232-5f8d-bbc8-668b33c6b4b2 |  | note | Responsibility - SE/PE
label | 8389de24-ece6-581b-b653-a9b23e58a387 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 4. Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | a956e336-312b-5045-b682-53c84330268d |  | note | Reference - IFC Drawings
label | faa830ae-ee8d-5925-b980-74d7b62b4030 |  | note | Acceptance Criteria - The required positions of the tactiles are clearly set out by a surveyor as per IFC Drawings.
label | 206faacb-2b4b-5e70-a867-2c22a7482a63 |  | note | Method - Measure, Visual
label | 218d02c6-f235-5918-990e-0d677624a9d2 |  | note | Frequency - Per Lot
label | 42197c27-a548-5de7-bd46-a7cf8669e420 |  | note | Category - IP
label | b6fa9b8b-1568-5947-b3cd-b956cc46005d |  | note | Responsibility - Surveyor, SE/PE/Site Supervisor
label | 48b670ca-bb08-5ae1-a268-89f39180b58b |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 5. Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Installation
label | 254a156e-4abd-553d-87fc-60fbcebab0f0 |  | note | Reference - AS1428.4.1 Section 2.3.3
label | f5a81d6d-f514-5a94-ae96-7f71cc0bba32 |  | note | Acceptance Criteria - Notify Nominated Authority prior to installation.
label | 98b48cb3-ce32-51b4-8d61-5f7d45964f4a |  | note | ○ Warning indicators shall be installed as follows:
label | 79c9b47f-231a-5d59-adb0-dba5c06bbafb |  | note | (a) For the full width of the path of travel
label | 0321adbe-6056-51b2-80ac-7ac29cae5277 |  | note | (b) Perpendicular to the direction of travel when approaching the hazard.
label | 1750f37c-d785-5b78-a2af-f88af9ee20f2 |  | note | (c) Set back 300 +/-10 mm from the edge of the hazard except at railway platforms and wharves.
label | 665804cb-a091-53ef-9b35-2a2630753a6a |  | note | (d) Where integrated warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below, over a minimum depth of 600 mm to 800 mm from the direction of approach.
label | 4f47a977-6ea8-5321-87db-1b43c6e04f40 |  | note | (e) Where discrete warning TGSIs are used over a depth of 300 mm to 400 mm, the arrangement shall be as shown in Figure 2.1 below with a minimum of 6 discrete truncated cones in the direction of travel.
label | b909090d-f514-5606-ba57-aa5a3f1005dd |  | note | (f) Where discrete warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below with a minimum of 12 discrete truncated cones in the direction of travel.
label | de774656-4288-5bfc-89c2-c8739d815bdb |  | note | ○ Where required on a path of travel, warning indicators shall be located at both the top and bottom of stairways, ramps, escalators and moving walks
label | 9e4fd6af-0504-57fc-afba-7fac1c011641 |  | note | Method - Visual/Site Inspection & Document Review
label | 2d67d4f8-1d97-5f7d-a5ef-596355a3084a |  | note | Frequency - Per Lot
label | 51fc4391-1e19-54b0-bc73-769873a5d2cf |  | note | Category - HP
label | 1cddd39e-cba8-56e5-ae37-1c696638696f |  | note | Responsibility - Nominated Authority
label | 91e7cec2-6acf-5834-a3e2-d55921ebb301 |  | note | Verifying Documents - Conqa HP Release
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Laboratory and On-site measurement of luminance contrast
label | ce5e4a5f-e365-5e98-9e81-2f35b79b0659 |  | note | Reference - AS1428.4.1 Appendix E
label | 0ec367ae-35fb-5e76-a56b-baa1a247600e |  | note | Acceptance Criteria - Submit Test report to AS1428.4.1 E5.4: The following shall be reported:
label | f961abfb-d90a-5b7c-a595-c4c65da89ca3 |  | note | (a) Full description of the surfaces tested with product details where known.
label | e503b15e-cdf3-51e2-90f0-5211233a89b2 |  | note | (b) The instrument being a luminance meter with a 1° measurement area corrected to approximate the CIE 1931 Standard Observer.
label | a3aae981-8a2a-5e9c-af5e-fa94f9f3a214 |  | note | (c) The location of the sample, if on-site.
label | 56fb0b7c-56fc-5ee3-ad29-f671b3d71e1b |  | note | (d) The location of the sample of the measurements on the TGSI.
label | cb6117c1-6c73-5a53-8c50-d12d15c89b61 |  | note | (e) A description of the light source(s) illuminating the sample, including type, [e.g. fluorescent tube, incandescent, high pressure sodium discharge, metal halide, and colour (in general terms)].
label | 5cf4ec8d-ad3a-5224-82b2-3dca8b991923 |  | note | (f) The mean luminous reflectance of the adjacent surrounds to the tactile indicator under the conditions set out in Paragraph E5.3
label | 1bd7cc91-1f5f-5a97-a25b-d206d0a0be1d |  | note | (g) The mean luminous reflectance of the tactile indicator under the conditions set out in Paragraph E5.3
label | da8d0eb2-bd23-53ef-bb09-025910403cbb |  | note | (h) The luminance contrast with the surrounds on both sides of the tactile indicator.
label | a074fe00-e422-51c1-9a5c-2d96fd473e6f |  | note | (i) A reference to this test method, i.e., AS/NZS 1428.4, Paragraph E5, Appendix E.
label | 556c14a7-d7d6-5ce9-9b62-92b67063133c |  | note | ○ Attach: Laboratory Test report
label | 3a639eaa-5be8-5eb8-8915-bc0a5b20c485 |  | note | Method - Visual/Site Inspection & Document Review
label | 19122103-fe3e-57b1-b301-b5aa83167887 |  | note | Frequency - Per Lot
label | db8463b5-bcec-5fc5-8db1-459e28f4418e |  | note | Category - IP
label | 33ea5f3c-70c1-5042-9bd7-ef55c3a49c62 |  | note | Responsibility - SE/PE
label | b9b32ae1-779b-5818-9ab7-ad0fb215ef16 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 5.3 - Distance between tactiles and sleeve
label | 90ebdf45-ce6a-5489-8169-8891b7b31d4e |  | note | Reference - DoT Handover Process
label | 2760a26f-8d34-5f6e-b575-b726141c9912 |  | note | Acceptance Criteria - Distance between tactile and sleeve to be a minimum of 300mm as per note 1 of the Handover Process
label | 9563b40a-243d-549f-b430-285807d06138 |  | note | Method - Visual Inspection, Measure
label | 71180c9b-3be8-5794-b0f0-e310c15e28bf |  | note | Frequency - Per Lot
label | c355c0ac-0ac1-5af8-9f49-c2ca732c801c |  | note | Category - HP*
label | dd870336-3def-57ba-918c-60e599385bf3 |  | note | Responsibility - SE/PE
label | 2f5f8b3b-b833-5763-ab03-76fcd2ec351d |  | note | Verifying Documents - This ITP Signed-off
checkpoint-group |  |  | section | 6. Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | a35c44f4-e897-5bc8-95fd-cc746b8afd30 |  | note | Reference - IFC Drawings VR 160.A9
label | f84482eb-4780-5d50-b159-786478071bac |  | note | Acceptance Criteria - As-constructed’ information shall be progressively documented during the work under the Contract and shall be provided to the Superintendent in a neat and clean format Attach: Survey As-built / Survey Report
label | ad833244-84bb-570c-b20e-6e0cc318bbf4 |  | note | ○ Attach: Survey Conformance Data/Report
label | 46a9343c-6b88-5f74-90f0-022711c637aa |  | note | Method - Document Review
label | 98b1afdb-a5b2-5d68-92e8-4b55195a294b |  | note | Frequency - Per Lot
label | 48c0cf0d-7d66-56ee-9222-9e0bce3fae79 |  | note | Category - IP
label | 4d34d05f-f664-5186-8f4c-4fd28e4831fb |  | note | Responsibility - Nominated Authority
label | 38ebcac8-443e-5006-9ed4-24cbc885b2b1 |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | 127e9ecd-2f88-5ef5-b610-755bccbeb13a |  | note | Reference - MRPA Quality Management Plan
label | 829e9b3a-80a8-53fb-bad5-9e0446be97b4 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 123f22a3-eab2-52fb-9a31-296a1e5f83a9 |  | note | Method - Document Review
label | 45d0357f-a6cb-596c-b466-7454d16bd990 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 1a8c7f04-e476-51c9-b5a3-9bdbaea5de2a |  | note | Category - HP*
label | 91b0c3e1-4394-5569-a1a1-0041bf8e0bf0 |  | note | Responsibility - SE/PE/SPE
label | 6535e693-5604-5003-b500-f9e2750a689c |  | note | Verifying Documents - This ITP Signed-off
checkpoint-status |  |  | checkpoint | Final Inspection
label | 54c2951f-c042-52f0-a3a4-8ae6cafa98e3 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 13f5a694-8eb3-5a6e-a92c-caf0fb02f51c |  | textbox | Name:
text | a7b5cff4-7576-50df-acfd-f7aa6cab62f6 |  | textbox | Position:
text | 10097da9-3731-5196-9a6c-22b2302d5ce9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | itp |  |  |  | Yes | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | ff9eef7c-b76e-4ebb-adde-76ac9eb4fd12
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | ca058ea5-8c87-5e65-8a7a-c55d60fc3bb1 |  | note | Document Title: CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
label | ca51afac-b065-5024-b5d2-4ed023f8bf68 |  | note | ITP Description: Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
label | 6c8d57fd-4a64-5ddc-9007-a99936afaaa7 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 571fbc40-7f9f-5ba9-8fd5-102081e4d637 |  | note | Revision Number: 0
label | 7b12ef80-3036-5b54-a129-47ead4e7e414 |  | note | Revision Date: 20/06/2023
label | f91dc7a5-1494-5490-9d1f-7f3a6b4a6779 |  | note | ITP created by: Kamel Alshobaki
label | 844db0de-8120-54be-b60e-7a2a273b9915 |  | note | ITP approved for use by: Jon De Castro
checkpoint-status |  |  | checkpoint | 1 - Materials - Fabrication
label | 2afe560e-8a8e-5d75-b1bd-e80897526766 |  | note | Reference / ITP Reference - IFC Drawings
label | f03010f3-ae40-55e9-a154-a9b9722893a0 |  | note | • Section 620
label | 6f0132bf-69b0-500f-b8d9-f9d1acb54445 |  | note | • Section 701
label | f39995d6-46b1-57ab-ade8-b7697051c4c7 |  | note | • Section 705
label | 2dc3073f-d70c-51c0-a62c-8eb4600387d5 |  | note | Acceptance Criteria - (1) Precast items manufactured in accordnace with IFC Drawings
text | 79ee452b-5933-5e26-82a0-9a2b25162578 |  | textbox | Drawing Ref No.
label | db09458a-8dfb-51cd-8a89-5985011d413b |  | note | Method - Visual Inspection
label | 7d4ec4ab-52da-5c46-8416-6cc7b90cc60c |  | note | Frequency - Each Lot
label | 80566e82-963b-559d-997a-c381681e6f6d |  | note | Category - IP
label | 25bafebb-935c-55d4-81d9-c500c534d519 |  | note | Responsibility - SE
label | 5ee6b328-4e1a-5f23-95ac-17b8b6c1d220 |  | note | Verifying Documents - Material Delivery Docket
checkpoint-status |  |  | checkpoint | 2 - Materials - Delivery
label | 0d4b9058-4228-5584-94c0-52b51596a64f |  | note | Reference / ITP Reference - IFC Drawings
label | 16f22079-b753-5259-afee-cd57e168ca34 |  | note | • Section 620
label | 2bae689f-3a62-5b0b-ac05-2e8db04e5583 |  | note | • Section 701
label | d7bf7983-01bc-524a-ba29-f45637c19686 |  | note | • Section 705
label | aa362452-0cdf-51c4-8501-e5a04236261a |  | note | Acceptance Criteria - (1) Purchase Order and Material Description and Qtys matches
label | be31409f-4b88-586f-ab6a-ad76d7636717 |  | note | (2) Ensure precast concrete elements are as per IFC Drawings with no damages upon delivery
label | 38ed00d5-8df2-583a-a915-c2ce93be9c43 |  | note | (3) Lifting and Manufacture compliance certification provided
text | 96f410f0-4951-56bf-8391-fe27223b48bf |  | textbox | Purchase Order No.
label | c76177b2-7387-5a86-932d-86d0dd87291d |  | note | Method - Visual Inspection
label | 9379ef11-fd13-5c56-9d9f-f4e19e5ea75a |  | note | Frequency - Each Lot
label | bf130132-8e63-569c-ac4b-f71c1138b79f |  | note | Category - IP
label | a4af80b5-a8b6-5bc4-98fb-2a50be6a273c |  | note | Responsibility - SE
label | e6138e48-c7f3-5862-a0a3-0fbf9cd671c7 |  | note | Verifying Documents - Material Delivery Docket
label | 65bb8a6e-0f56-586d-a729-a2e8893d766b |  | note | • Purchase Order
checkpoint-status |  |  | checkpoint | 3 - Materials - Manufacture's Certificate of Compliance
label | 687028d4-ab51-5347-906a-14413c6907f4 |  | note | Reference / ITP Reference - IFC Drawings
label | 14bc78e2-a496-57db-b460-160f378eb575 |  | note | • Section 620
label | fdd00bad-aff9-5b84-afb0-fc78ff71c65b |  | note | • Section 701
label | 74c1408d-1170-51d6-92ea-b8e22270b176 |  | note | • Section 705
label | 22040989-7877-53b7-8f7e-ea3ea19c7330 |  | note | Acceptance Criteria - (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting.
label | 21da3e72-7c46-562b-93bf-576934b075fd |  | note | Method - Visual Inspection
label | 77022cc2-4959-5ca4-b5c5-3a93e76870af |  | note | Frequency - Each Lot
label | b6e0646d-2aa1-5d9e-8b92-206a8190fc1d |  | note | Category - IP
label | 17961cf4-4f99-510f-a14f-1fc26c379fd9 |  | note | Responsibility - SE
label | 91f9fc94-cafc-5e30-9719-f566af67b5cc |  | note | Verifying Documents - Material Delivery Docket
label | c5cc54cb-851b-56ed-b30c-4f1e2d4548f4 |  | note | • Compliance Certificate
checkpoint-status |  |  | checkpoint | 4 - Materials - Delivery to site & Storage
label | 5d6f12a3-fb0f-5a96-ad9d-fc99ab90fb02 |  | note | Reference / ITP Reference - IFC Drawings
label | c442ddd8-83ee-55c1-96af-100e862c20bc |  | note | • Section 620
label | 9b152493-ed1d-55fe-8a9f-4ca1889f7e50 |  | note | • Section 701
label | c1041134-f97b-5980-9d8c-652c20de5260 |  | note | • Section 705
label | 5570f4b0-29e1-5e29-8d91-c5839627f8ef |  | note | Acceptance Criteria - (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element.
label | 6c79a671-baa9-5e41-833f-d3d8b84628ba |  | note | (2) Precast elements are unloaded and stored properly on site as per manufacturer's recommendations.
label | cf0d0994-1fd9-5a30-94d7-a0201069e0f8 |  | note | Method - Visual Inspection
label | 3b7d96c8-4b44-50a8-b6cb-e3f471b4a248 |  | note | Frequency - Each Lot
label | cb9e7dbc-a933-5d10-8720-65bfbbcc0f3d |  | note | Category - IP
label | df384184-3a30-5ca4-84f5-b39c10b8efda |  | note | Responsibility - SE
label | 4a5b82c0-1d15-5e8b-8080-19c75835b580 |  | note | Verifying Documents - Material Delivery Docket
checkpoint-status |  |  | checkpoint | 5 - Materials - Others
label | aa74b915-0cdd-5d64-bafa-ebd15db9b9a3 |  | note | Reference / ITP Reference - IFC Drawings
label | d18f61a4-cd48-53ed-9080-df2e8f09b8a1 |  | note | • Section 620
label | 09472dca-f89a-5543-83d1-0b136eb49a9d |  | note | • Section 701
label | e38c0d09-0a83-5f23-bb2c-7568685e7697 |  | note | • Section 705
text | 4f1bd8ce-b26b-5fd7-8bad-6b02c75891b9 |  | textbox | Acceptance Criteria - Enter: Additional Comments
label | c3c3584f-2f97-50cb-89ec-895922371683 |  | note | Method - Visual Inspection
label | 63c9bb3a-5b90-56e0-9979-a703fed467dd |  | note | Frequency - Each Lot
label | 65d3f9fa-bbae-51f1-a7c2-79b738df3d5d |  | note | Category - IP
label | ce2fbc30-275d-55ac-92c0-81fdf0b90672 |  | note | Responsibility - SE
label | a7496a4a-3b20-5b7d-8910-b2af1d34e82e |  | note | Verifying Documents - Material Delivery Docket