## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Gravel Pathway |  |  |  |  | Yes | Gravel Pathway | 07e78652-ebe1-4044-a357-8414263abfe7
checkpoint-group |  |  | section | Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 65e30115-d4e7-5c42-b836-79390c49a002 |  | textbox | Drawing and Revision Number
checkpoint-status |  |  | checkpoint | Survey Set out – Check Position
checkpoint-group |  |  | section | Road Subgrade Inspection
checkpoint-status |  |  | checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | f73571d1-2771-5986-b781-d6db1c409355 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subgrade
text | e394014d-0be3-5069-a94f-f6187eaffa79 |  | textbox | Thickness (mm)
label | 111d2b51-eabf-5aed-a67f-a868d6d2b9f4 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 766ddb18-3db7-56ba-bc4c-ec8f5ce1a027 |  | button | Compaction Method | Standard,Modified
text | f05798ed-5189-51af-92a1-bc172bc5b13e |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 6761f57a-480f-5a42-96fb-18bc23cd72ed |  | button | Compaction Method | Standard,Modified
text | 7223495b-6010-553c-a01e-3955b008476e |  | textbox | Minimum Dry Density Ratio (%)
label | 6cadbef7-07a9-5054-b157-9c66d1bcdf36 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 1
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | 7bdd79b2-e818-5ca3-80b8-c90d1559bfea |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | c2b1891e-c800-5447-80c8-f0ca88b589dc |  | textbox | Thickness (mm)
label | 32fedf33-83cf-5129-9ab8-315366abe84e |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | b1497cee-5c28-5da3-b216-f089a807c67f |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | e0d0039e-7808-5f85-ab0f-a4f4adb0f330 |  | button | Compaction Method | Standard,Modified
text | eb3639ec-1f47-5a61-aea6-6c89257642e6 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | baae88f8-0caf-5a11-88fa-a0b43575d5da |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | b3f360f0-c94f-5824-b204-33f0e587a5df |  | button | Compaction Method | Standard,Modified
text | 48c7d053-69bd-529f-a205-f2b06325383e |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 7f9e5511-35dc-54cb-90a6-efe4d0684844 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 2
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | 7f54bf13-8441-5252-8276-2bcbe1b88b46 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | f685cc49-0615-5f75-946e-10ef7e093842 |  | textbox | Thickness (mm)
label | b1b492c7-c656-58e1-b369-51034c26cf44 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 6edc27da-3b3e-5d2b-833a-b063e0dbb182 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | de070f59-8d14-5ab9-b78e-5ed1ef547726 |  | button | Compaction Method | Standard,Modified
text | 97d73ef0-af5c-544c-8167-7af31bacf728 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 40533c5e-6774-56ea-baf8-7d0c2b2589f6 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 7aaec5cf-9ae6-504c-92c2-5a07ef7ff665 |  | button | Compaction Method | Standard,Modified
text | 1653c07a-9aaf-5ec0-84b6-059098264108 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 8dbbd5f9-b3f5-598b-a937-0b0150383de0 |  | note | Attach photos of Material Compact Report
checklist-sectioned |  |  | checklist | Trench Excavation & Backfill ITP |  |  |  |  | Yes | Trench Excavation & Backfill ITP | 0ad877b8-1f8d-4d51-ac42-7fa8bf72b51d
checkpoint-group |  |  | section | Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 5ba95bf8-2a6c-5fb7-8d33-4475bdaa0b61 |  | textbox | Drawing and Revision Number
checkpoint-status |  |  | checkpoint | Survey Set out – Check Position
checkpoint-group |  |  | section | Excavation Activity Inspection
checkpoint-status |  |  | checkpoint | Removal of Unsuitable Spoil (Soft spot & nominal 300 from existing surface
checkpoint-status |  |  | checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | 6e19ad3b-27f8-5beb-9eb9-de8880c0ef58 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Depth of Trench
text | 3aab5914-a7ee-5dda-9b1d-ef4f270b82bf |  | textbox | (m)
checkpoint-status |  |  | checkpoint | Trench Protection Method
button | 3b46fe86-9288-55f1-9372-c035b7e996c1 |  | button | Protection Method | Sloping,Benching,Shoring
label | 76915132-ed58-5ae1-938b-5ffb49c7f109 |  | note | Attach photos of Protection Method
checkpoint-status |  |  | checkpoint | Subgrade preparation of area is ok to Backfill
label | b34c844f-d0e3-5021-82ea-8a0a6fc74077 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Commencement of Backfill
button | e84139ce-b022-5c24-b36f-f29d87217564 |  | button | Delta Group Representative Signed | Yes,No
button | 123591a0-b412-509b-bdb7-429e312c4c03 |  | button | Besix Watpac Representative Signed | Yes,No
checkpoint-group |  |  | section | Place Backfill Inspection
checkpoint-status |  |  | checkpoint | Top of Filling level
text | 58eda90e-8da3-556a-b42f-18ede51100e6 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Fill
text | 9a939967-d602-5689-8b32-84e3659141cb |  | textbox | Thickness (mm)
label | 581c7a94-1067-56da-b143-c370db648413 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Mud Map (Indicate date and location)
label | 1de4507a-9dbb-53eb-b655-7b9ac4fba276 |  | note | Attach the Mud map
checkpoint-status |  |  | checkpoint | Material Requirement
button | 8b026aa7-a42d-5ade-a3c9-3127a0b18f3a |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | e9183bed-b82b-5af0-a4e1-0a45ce6dd092 |  | button | Compaction Method | Standard,Modified
text | 0d05e86e-cc11-55a3-8016-1c748ff689b1 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 9741a3c7-b287-5102-b6c7-6870ca1e4ba2 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 6b904f3b-cbd4-5b49-a591-5fc2bc7d2afb |  | button | Compaction Method | Standard,Modified
text | 10b91cf4-b65c-5b55-b59c-ad6a5344ed34 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | eff28cdf-4217-5c0d-8eef-4f60a8a8d101 |  | note | Attach photos of Material Compact Report
checklist-sectioned |  |  | checklist | Rigid pavement - Light vehicle ITP |  |  |  |  | Yes | Rigid pavement - Light vehicle ITP | 413a7ea3-3c67-4a1c-bb54-6bb6b78e2765
checkpoint-group |  |  | section | Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | ec01f0c4-bc55-5574-8a52-45759fcdfb7e |  | textbox | Drawing and Revision Number
checkpoint-status |  |  | checkpoint | Survey Set out – Check Position
checkpoint-group |  |  | section | Road Subgrade Inspection
checkpoint-status |  |  | checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | ba638e9b-3c57-51f1-8621-1d226f5a7950 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subgrade
text | 6987a3f7-540d-51de-a304-04464cd1ca6d |  | textbox | Thickness (mm)
label | 3b2aa310-bb5d-597f-9eb7-f09346713c23 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 47b63b37-247d-5d43-933d-6228bfac7c97 |  | button | Compaction Method | Standard,Modified
text | 830490e6-c8ae-59f9-b6bc-a2e3f2efa3b1 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 4d6ac095-53ef-55d0-acfa-acc0731de08b |  | button | Compaction Method | Standard,Modified
text | 6558698b-f780-53e1-8bbd-3abaaed0da36 |  | textbox | Minimum Dry Density Ratio (%)
label | a952dcf6-28e0-5e79-9d9e-47397a4c0263 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Capping Layer Inspection
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | cfdeb959-1a34-5067-a5f8-dcf4bac37d41 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | b2b753bd-aaa3-5c7b-aa2b-088080891459 |  | textbox | Thickness (mm)
label | 0039c657-cf9a-5a8e-941f-274cd661ddcf |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 9322f4ef-3bb5-526a-a1a5-de05ce4f6af6 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 08306781-043a-5e42-9b03-97a8f91510ac |  | button | Compaction Method | Standard,Modified
text | 5fc5748f-a897-5ca0-9545-cb400be4474d |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 754f8530-1b6b-52c8-908c-e53572e71e31 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | de3779ea-4666-53cc-985d-5f662bcb02c9 |  | button | Compaction Method | Standard,Modified
text | ca7f2826-059a-5cb0-baf4-fe0f9b5c1c36 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 5212926f-384a-558f-92df-8493b8a02b23 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 1
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | 4e09e3c5-a47b-51e5-8500-e1a36b47dcac |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | 4dcb2e17-1127-55cf-aa63-86721154068c |  | textbox | Thickness (mm)
label | 0ee4eeec-1ce9-5b1c-830f-df7d970514f0 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 40d0f934-9751-5492-99c4-499ee97d6115 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 5065f2e7-7481-59c4-8334-bb981ac9ba68 |  | button | Compaction Method | Standard,Modified
text | 1949f4c9-370b-5730-bc24-dc3e92d98078 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 52eb7a2c-4058-523a-896b-d25911136425 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | e3ec9733-1ea6-5493-ae41-9a50c8ee2253 |  | button | Compaction Method | Standard,Modified
text | f9596bc9-8a3e-5369-9ee4-862002715a23 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | ce4283b3-2dba-5fd6-a588-b82b567a471f |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Concrete Pre Pour Inspection
checkpoint-status |  |  | checkpoint | Vapor Barrier Placed, Lapped and not pierced
checkpoint-status |  |  | checkpoint | Reinforcement Requirement
text | e16ba5ce-ca62-5db7-8c8a-9be10f029c76 |  | textbox | Cover (mm)
button | c6d36f38-3cb3-54e8-baf1-3ee6703a8cfb |  | button | Steel Mesh Type | SL82,SL72,Other
label | 4b82e535-01a1-5ef9-a1b5-13f3cdacaa17 |  | note | Attach photos of Reinforcement
checkpoint-status |  |  | checkpoint | Commencement of Pour
button | 890772ba-b736-5411-9b76-b272854689a9 |  | button | Delta Group Representative Signed | Yes,No
button | a742e260-becf-5178-ac60-6262c73b085a |  | button | Besix Watpac Representative Signed | Yes,No
checkpoint-group |  |  | section | Road Concrete Placement
checkpoint-status |  |  | checkpoint | Thickness of Concrete
text | b0341672-b19c-5e17-930e-38940603741c |  | textbox | Thickness (mm)
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket
text | 075d9905-453a-5cb9-a5b2-6ebcf6071b82 |  | textbox | Docket Number:
label | 2aa9cd5a-7436-5cb9-ac99-48976344daac |  | note | Attach photos of Concrete Dockets
checkpoint-status |  |  | checkpoint | Pile Concrete Details
button | aa59e87a-94f1-5799-afb2-be26aed79926 |  | button | Concrete Strength (MPA) | 32,40,other
text | e088803c-846e-51d8-80d3-4a1147599e73 |  | textbox | Cover (mm)
checkpoint-status |  |  | checkpoint | Mud Map (Indicate date and location)
label | 7528890e-da36-57ba-bbea-c371d4baba58 |  | note | Attach the Mud map
checkpoint-group |  |  | section | Pile Post Pour- Sign off
checkpoint-status |  |  | checkpoint | Post Pour requirement
text | c72f39f7-1c63-5ee9-a7fc-e21c2f24d3b3 |  | textbox | Concrete Test Certificate number
text | 45b8ccfb-acec-52b7-b652-1440f893c315 |  | textbox | 28 /56-day Concrete Compressive Strength (MPA)
label | 5f5bfad9-7ac5-5f7e-93b8-f0c89a270aca |  | note | Attach photos of Concrete Crack Test
checkpoint-status |  |  | checkpoint | Post Pour Signed off
button | 1e5ea6be-5d62-57b3-8411-da43ed9332b5 |  | button | Browns Piling Representative Signed | Yes,No
button | 0d5c40ab-7749-5239-9145-f4c6e8ffec4e |  | button | Delta Group Representative Signed | Yes,No
button | 75f83da5-4fd3-53e6-8ce6-4c9585f35f4c |  | button | Besix Watpac Representative Signed | Yes,No
checklist-sectioned |  |  | checklist | Rigid Pavement - Concrete footpath ITP |  |  |  |  | Yes | Rigid Pavement - Concrete footpath ITP | 5c967d29-649b-45da-9254-44816fcb5267
checkpoint-group |  |  | section | Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 3119a67d-8557-53ec-a42d-9d6c66f879bc |  | textbox | Drawing and Revision Number
checkpoint-status |  |  | checkpoint | Survey Set out – Check Position
checkpoint-group |  |  | section | Road Subgrade Inspection
checkpoint-status |  |  | checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | 7b8d409b-0e42-5088-969d-c46a28bd9049 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subgrade
text | 93fa4931-e745-5e28-b7b5-ad320a70adf0 |  | textbox | Thickness (mm)
label | d83f2984-fcf6-529a-a190-c4db8418507c |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | b6ec1e45-4b26-5a33-b705-06944f0a1b76 |  | button | Compaction Method | Standard,Modified
text | 70025cd8-324c-5662-a719-d605acb1fe34 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | ffca2d92-6a45-5358-b4e0-1427c5a20025 |  | button | Compaction Method | Standard,Modified
text | 74252a52-894d-5802-bb6f-e7f226912201 |  | textbox | Minimum Dry Density Ratio (%)
label | d3867456-08de-5873-a88c-fe4679bc3db7 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 1
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | 06609a63-123f-5c6b-acba-369bbcb98bba |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | c4f582e2-9583-541e-a758-8c3e975495fa |  | textbox | Thickness (mm)
label | 9d00ac05-82bc-585c-864f-afaa15a78350 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 7b881a8f-f600-5576-aa78-8b53d5904a28 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 00388ad0-1880-500c-98b5-c142cd0faad6 |  | button | Compaction Method | Standard,Modified
text | 96b4fa66-ff9f-5430-af46-8a80fac554e1 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 00c9feda-ca66-5777-a7bd-7b23f930bd38 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 2da240a6-f42a-52e2-8d7a-0e083abda793 |  | button | Compaction Method | Standard,Modified
text | ce276d09-d6c4-5d88-a11a-538a3febf2ee |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 689f9c2f-3c53-56c4-bb8f-916726315960 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Concrete Pre Pour Inspection
checkpoint-status |  |  | checkpoint | Vapor Barrier Placed, Lapped and not pierced
checkpoint-status |  |  | checkpoint | Reinforcement Requirement
text | 44a2809e-f990-5b99-8057-4173a07a009c |  | textbox | Cover (mm)
button | eead4025-4b48-5329-a012-95270a6e0cc4 |  | button | Steel Mesh Type | SL82,SL72,Other
label | 61afbaaa-e453-5209-8717-abf385357ae8 |  | note | Attach photos of Reinforcement
checkpoint-status |  |  | checkpoint | Commencement of Pour
button | 8f4d08b3-ffea-5a6d-9c0c-3ff40f9df514 |  | button | Delta Group Representative Signed | Yes,No
button | e208b38f-eff3-52df-a5fb-bb0ccd045551 |  | button | Besix Watpac Representative Signed | Yes,No
checkpoint-group |  |  | section | Road Concrete Placement
checkpoint-status |  |  | checkpoint | Thickness of Concrete
text | c5c638cf-d9f6-5bd4-a037-356d2286645d |  | textbox | Thickness (mm)
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket
text | 6ac2f9df-e071-5b9d-bc82-07dae609182d |  | textbox | Docket Number:
label | 0160a68b-0655-5d90-87a5-f7896f43b47f |  | note | Attach photos of Concrete Dockets
checkpoint-status |  |  | checkpoint | Pile Concrete Details
button | bdf2dcca-dd0a-508b-adc4-a6a843875ebf |  | button | Concrete Strength (MPA) | 32,40,other
text | 1707b736-f4f5-5e8d-8d6d-994f06ad6f1b |  | textbox | Cover (mm)
checkpoint-status |  |  | checkpoint | Mud Map (Indicate date and location)
label | a836240b-0589-53e7-9da6-25168cc1b461 |  | note | Attach the Mud map
checkpoint-group |  |  | section | Pile Post Pour- Sign off
checkpoint-status |  |  | checkpoint | Post Pour requirement
text | 10543948-5c90-5937-8f72-25b397a39cf7 |  | textbox | Concrete Test Certificate number
text | b5dec3c1-092d-51eb-ba77-da1acc6f3a49 |  | textbox | 28 /56-day Concrete Compressive Strength (MPA)
label | df6009ff-22c9-5d86-bcc1-849b49726172 |  | note | Attach photos of Concrete Crack Test
checkpoint-status |  |  | checkpoint | Post Pour Signed off
button | 2f179599-1ece-5031-8c1b-d927af36933f |  | button | Browns Piling Representative Signed | Yes,No
button | ebdd22f1-58d9-5cfd-83fa-5f00d14044d2 |  | button | Delta Group Representative Signed | Yes,No
button | 55f04f74-938f-5215-9dd9-e475a4c813d4 |  | button | Besix Watpac Representative Signed | Yes,No
checklist-sectioned |  |  | checklist | Bulk Earthwork Infill ITP |  |  |  |  | Yes | Bulk Earthwork Infill ITP | 75839955-394a-4d5b-92e0-a36670c8537c
checkpoint-group |  |  | section | Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 069f1ed0-d4af-5772-89e7-61237e937824 |  | textbox | Drawing and Revision Number
checkpoint-status |  |  | checkpoint | Survey Set out – Check Position
checkpoint-group |  |  | section | Excavation Activity Inspection
checkpoint-status |  |  | checkpoint | Removal of Unsuitable Spoil (Soft spot & nominal 300 from existing surface
checkpoint-status |  |  | checkpoint | Stockpile to maximum 2m height
checkpoint-status |  |  | checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | 30b4c7b4-3a6b-526c-a449-91a99259d317 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Subgrade preparation of area is ok to receive fill
label | ade40e00-a2f3-5791-bbc0-5a3729ddd6c3 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Commencement of Fill
button | e8582cbb-73fa-5197-922a-3c142af80b02 |  | button | Delta Group Representative Signed | Yes,No
button | 00fa8caa-91d3-5374-9732-2d9808fe2d5c |  | button | Besix Watpac Representative Signed | Yes,No
checkpoint-group |  |  | section | Place infill Inspection
checkpoint-status |  |  | checkpoint | Top of Filling level
text | ab10ec0e-c223-5cb0-aedf-8dde8237a319 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Fill
text | 616a461c-aef3-54bc-b4ff-a39549ec49ee |  | textbox | Thickness (mm)
label | 2b7efeb0-f0b0-5271-a541-70040b262e80 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Mud Map (Indicate date and location)
label | f56e6e24-8f59-5342-ab3f-2ce0992c5fbe |  | note | Attach the Mud map
checkpoint-status |  |  | checkpoint | Material Requirement
button | cc03d22c-b83e-5afe-adc7-326a3a17dbdf |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 17fc476f-6533-5c85-b605-70d5570da569 |  | button | Compaction Method | Standard,Modified
text | 22b8c1d2-0881-5813-8323-1918e372e381 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | a1714590-8dac-516e-a4f5-5c2ddfa7ca25 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | fafda753-2aed-594f-8528-d5586dd20eb0 |  | button | Compaction Method | Standard,Modified
text | 5ee9c763-63d7-56a7-919e-70102dd30896 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | fb86ee1a-f657-5673-a66a-2f2f48d50a13 |  | note | Attach photos of Material Compact Report
checklist-sectioned |  |  | checklist | RP1- Rigid Pavement ITP |  |  |  |  | Yes | RP1- Rigid Pavement ITP | 7aa093b7-c986-44b0-9b09-e072ba785410
checkpoint-group |  |  | section | Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | c7992481-bc1f-55bb-b98a-da0721ef0d96 |  | textbox | Drawing and Revision Number
checkpoint-status |  |  | checkpoint | Survey Set out – Check Position
checkpoint-group |  |  | section | Road Subgrade Inspection
checkpoint-status |  |  | checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | 02e25ded-a950-5c71-9f4c-52328284a6b4 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subgrade
text | b95610e9-7bbf-58b9-8953-f01c602103f1 |  | textbox | Thickness (mm)
label | 2e18bc69-444b-5498-9727-600ed3eeaa50 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | a0df6386-f0f2-5103-b282-b1b22f5d7f20 |  | button | Compaction Method | Standard,Modified
text | 11606147-4d8d-5fe5-b1ce-da76973d991e |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 0e783727-e762-57f0-afe9-4b0cfcf8df0d |  | button | Compaction Method | Standard,Modified
text | 9f355525-6770-5bfb-8703-11361e50f514 |  | textbox | Minimum Dry Density Ratio (%)
label | 0f80126a-dd40-5ccb-91dc-b3ee7e08c3d8 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Capping Layer Inspection
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | 9c7358f8-2a97-5d8c-9c95-7e05bac8b180 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | fb489245-96cc-5692-b730-c2c5362b9eeb |  | textbox | Thickness (mm)
label | bee541d2-e488-5cbc-84b0-29c92c84ea5b |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 930a543a-c4cd-5ece-96e9-7441806ca91b |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 6ba9d2fa-7d94-588f-b9c8-c7654c3a1107 |  | button | Compaction Method | Standard,Modified
text | 8246ca42-cbe9-5259-ab4d-9fd37139e8b1 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 59811541-c9b1-54c7-b71d-4b5fceaa059f |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | f97fe231-f5c3-5b1f-8d36-bd68c413cf91 |  | button | Compaction Method | Standard,Modified
text | 06436ce8-e137-59b1-9ceb-cfbd2fc1f197 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | cee60a7b-f7da-51dc-aadf-40139e9572cb |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 1
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | a9acf53b-d9b2-55a6-932d-75d382765949 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | 1f1e9354-993b-5d35-a6eb-fa83d35ab17b |  | textbox | Thickness (mm)
label | ceb42a62-c90d-58a4-85ef-0279e8925de1 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | caa29252-48d8-5513-8751-e7b14eb811af |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | a97a4c73-0203-52a2-8945-c7a917e90705 |  | button | Compaction Method | Standard,Modified
text | 2c5fe381-4bab-5976-a410-24184895893f |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | d9fab6d6-828e-5482-bacf-969163d0495c |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 965ca8e1-e42c-57d5-92cb-2a9bd71294cf |  | button | Compaction Method | Standard,Modified
text | 173667e9-b8da-5187-abfa-74b6efa29cd9 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 4b3566dd-a3ac-5819-a4d5-8a97f720de92 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Concrete Pre Pour Inspection
checkpoint-status |  |  | checkpoint | Vapor Barrier Placed, Lapped and not pierced
checkpoint-status |  |  | checkpoint | Reinforcement Requirement
text | 56937e8c-7919-5b8f-aa47-ecc58c7f0162 |  | textbox | Cover (mm)
button | 212e60b5-c6ca-510c-adcc-bb9d69be5e73 |  | button | Steel Mesh Type | SL82,SL72,Other
label | f7090882-088c-5215-ae1b-8178ae8089aa |  | note | Attach photos of Reinforcement
checkpoint-status |  |  | checkpoint | Commencement of Pour
button | d12c8d80-eaef-5ff7-892c-0fcfa0142711 |  | button | Delta Group Representative Signed | Yes,No
button | 9029949b-bf76-5c71-be43-07c797c2dbc9 |  | button | Besix Watpac Representative Signed | Yes,No
checkpoint-group |  |  | section | Road Concrete Placement
checkpoint-status |  |  | checkpoint | Thickness of Concrete
text | d5fe5f4e-0c9e-50af-8940-16cada82a74f |  | textbox | Thickness (mm)
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket
text | 90a8b9f4-1c8c-5355-854b-ba7bab38041e |  | textbox | Docket Number:
label | db1e2fa3-b4d3-56f2-b8ad-88e90325faa9 |  | note | Attach photos of Concrete Dockets
checkpoint-status |  |  | checkpoint | Pile Concrete Details
button | d9c79509-189d-5973-bef7-b7bd8dc11e2a |  | button | Concrete Strength (MPA) | 32,40,other
text | 8361444e-1f39-5bf9-9a0b-727e0afb3ff6 |  | textbox | Cover (mm)
checkpoint-status |  |  | checkpoint | Mud Map (Indicate date and location)
label | 37c2c2a5-d5c5-5928-a676-e038630cdee8 |  | note | Attach the Mud map
checkpoint-group |  |  | section | Pile Post Pour- Sign off
checkpoint-status |  |  | checkpoint | Post Pour requirement
text | 159262c0-cd8a-5f36-a46e-d50bfb09a5ec |  | textbox | Concrete Test Certificate number
text | 74c74061-33dd-5d73-b531-37ac93783bcc |  | textbox | 28 /56-day Concrete Compressive Strength (MPA)
label | 41155933-1d93-5e38-b377-3a9797e5cf15 |  | note | Attach photos of Concrete Crack Test
checkpoint-status |  |  | checkpoint | Post Pour Signed off
button | dc907548-4373-5ae7-821a-f7822353309e |  | button | Browns Piling Representative Signed | Yes,No
button | 4f3bb84b-761b-52b8-94fb-ad1cf539410a |  | button | Delta Group Representative Signed | Yes,No
button | 11ed162e-7d0d-5df9-84ee-023549325928 |  | button | Besix Watpac Representative Signed | Yes,No
checklist-sectioned |  |  | checklist | Foundation Pile ITP |  |  |  |  | Yes | Foundation Pile ITP | 7ce77b8a-6f15-434a-bc54-b9621c68c14f
checkpoint-group |  |  | section | Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | ba82802a-cee8-5a3b-ab67-dc8e51bdfca6 |  | textbox | Drawing and Revision Number
checkpoint-status |  |  | checkpoint | Survey Set out – Check Position
checkpoint-group |  |  | section | Foundation Pile Information
checkpoint-status |  |  | checkpoint | Pile Diameter
text | ebf94b87-281b-543a-9dd3-0cf3c7fee13d |  | textbox | Diameter (mm)
checkpoint-status |  |  | checkpoint | Approval of Socket
text | 03ca6a6c-9bf7-5544-b7da-ae6a97a1e434 |  | textbox | Designed Pile Socket Length (mm)
text | 7e945081-7e76-5d47-b931-ae871e8fe9ad |  | textbox | Actual Pile Socket Length (mm)
checkpoint-status |  |  | checkpoint | Pile Details
text | e8774483-06ee-554b-882b-e04258a1132f |  | textbox | Top of Steel RL (m)
text | ac6e39c1-c141-5e80-a495-ae281f404dc3 |  | textbox | Length of Pile (m)
text | 688018ef-270b-519c-ba4b-50bae19721c9 |  | textbox | Top of Concrete RL (m)
checkpoint-status |  |  | checkpoint | Check of excessive water in hole
checkpoint-group |  |  | section | Pile Reinforcement & Pre Pour
checkpoint-status |  |  | checkpoint | Reinforcement information
text | d893fbda-47d8-558f-8692-945dc944f187 |  | textbox | Main Bars (e.g 6N24)
text | f5b85dec-faf3-5be1-8598-89bfd30bb2df |  | textbox | Ligs (e.g N12-300)
text | 55f689ee-c79d-5328-8732-23537bf5c14e |  | textbox | Cage Length
label | 2ed4c47c-5707-5501-b7aa-2e4bfc959530 |  | note | Attach photos of pile reinforcement
checkpoint-status |  |  | checkpoint | Sign off Required
button | a3edd71e-8352-5f6b-b8d8-ff0977fac9f5 |  | button | Engineer/Building Surveyor Sign off | Yes,No
checkpoint-status |  |  | checkpoint | Commencement of Pour – Ok to pour
button | 4aacc94b-5b4c-5cb5-b8a1-caf9ed94c21b |  | button | Delta Group Representative Signed | Yes,No
button | 0a018b81-51c7-5c51-bd5a-98f3547d8d0a |  | button | Besix Watpac Representative Signed | Yes,No
checkpoint-group |  |  | section | Pile Concrete Placement
checkpoint-status |  |  | checkpoint | Date of Pour
text | 992d0cee-2b8a-50ca-b21f-e88703f8de21 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket
text | e30f81e1-ca93-5618-a0e7-b665d120cd80 |  | textbox | Docket Number:
label | 11b708df-724c-5ef3-a077-524f46f0bb4b |  | note | Attach photos of Concrete Dockets
checkpoint-status |  |  | checkpoint | Pile Concrete Details
text | 815f4774-c0e5-5960-a10b-e413e8bea8ad |  | textbox | Concrete Strength (MPA)
text | 16d2f9c8-7485-5cce-ae40-d3a908223275 |  | textbox | Cover (mm)
checkpoint-status |  |  | checkpoint | Mud Map (Indicate date and location)
label | f7fcf78b-301f-5b6a-9648-963dff7f2647 |  | note | Attach the Mud map
checkpoint-group |  |  | section | Pile Post Pour- Sign off
checkpoint-status |  |  | checkpoint | Post Pour requirement
text | 496c5164-1c31-564e-a862-0ecc2a8afa8a |  | textbox | Concrete Test Certificate number
text | 8901fc98-cc40-51ba-b03c-d0c33e189409 |  | textbox | 28 /56-day Concrete Compressive Strength (MPA)
label | 4a09cf8b-0335-588b-a17c-7b3edefd0d15 |  | note | Attach photos of Concrete Crack Test
checkpoint-status |  |  | checkpoint | Post Pour Signed off
button | eb507f1e-d9c8-57b9-9e6f-67d4495ad5f9 |  | button | Browns Piling Representative Signed | Yes,No
button | d8a3ff34-9f69-548e-8735-4bea74f90cc8 |  | button | Delta Group Representative Signed | Yes,No
button | 877c5b38-0fb6-57ac-b41f-cb6d8d386c8b |  | button | Besix Watpac Representative Signed | Yes,No
checklist-sectioned |  |  | checklist | Switchyard Pavement |  |  |  |  | Yes | Switchyard Pavement | b13b8b2d-8204-431d-8923-811591b2644a
checkpoint-group |  |  | section | Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 5f5c2cc2-e393-5dbc-b714-d9487ec08b86 |  | textbox | Drawing and Revision Number
checkpoint-status |  |  | checkpoint | Survey Set out – Check Position
checkpoint-group |  |  | section | Road Subgrade Inspection
checkpoint-status |  |  | checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | 66370cad-7b3c-5fe8-b842-fb81ef9aa6fe |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subgrade
text | 250dd9b3-1980-539b-90f9-de77a5edb3cb |  | textbox | Thickness (mm)
label | f990fa67-2b1a-5eaa-9d99-e97672b988d4 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | d000e578-3342-533b-a513-d99b1cf8bde6 |  | button | Compaction Method | Standard,Modified
text | cb698e1c-3ae3-5e8e-b494-570ebe98ba27 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 041a3ce8-3bbe-5142-b027-e3eb7b59167c |  | button | Compaction Method | Standard,Modified
text | e44b0f57-0b02-5a86-98a4-08347f9d7ddd |  | textbox | Minimum Dry Density Ratio (%)
label | d59e023d-e7d0-54f3-9bee-a22f0b8f9588 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 1
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | e0905f9d-4ef2-5761-b57e-d5053bd637fa |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | ccf02d18-71d3-5ed9-a562-fa27e8b401fc |  | textbox | Thickness (mm)
label | 6af75143-0588-5906-8f4e-7314c254ff71 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 24cca1a4-5740-5177-8ad3-7c151f7b4a22 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | c4e5b2f6-c426-541b-8110-f7827ac1d794 |  | button | Compaction Method | Standard,Modified
text | 046ebb43-c9b1-5bb4-8c12-14a0475a87d2 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | fd06ea56-7e14-510a-9b4b-7a56ad0d0894 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 081db48c-0330-53bf-8f38-e81847f696cd |  | button | Compaction Method | Standard,Modified
text | 998c5389-6b8f-511a-b1d9-1c908987f383 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 246dfbb3-fef8-5c5a-8ee9-e211bd3d1193 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 2
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | 5882e55c-ad3c-5160-84bc-c28e507b4085 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | e384cfce-efdc-546b-bbeb-e82407cb3623 |  | textbox | Thickness (mm)
label | 4208c3f0-8c81-5868-9bcb-813ea317cddc |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | e5ca96cc-7df2-5d5d-983c-26f7ae675897 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 91163f53-a068-58da-8b25-745019242506 |  | button | Compaction Method | Standard,Modified
text | 6ab17ca9-3ec9-57f4-ba56-23c681629a92 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 6afc9038-6e37-59dd-baab-abfe3c703bde |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 1e374aa4-5d77-5025-9ce4-c6c22b464f06 |  | button | Compaction Method | Standard,Modified
text | e25e8222-ebd0-5891-b8d9-dc6dfa9e09a0 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 73a29b74-d944-5177-8c1b-e212d6fb9d9c |  | note | Attach photos of Material Compact Report
checklist-sectioned |  |  | checklist | Unsealed Hardstands |  |  |  |  | Yes | Unsealed Hardstands | bdc76195-6cde-4dfe-ab63-59a82655bf5e
checkpoint-group |  |  | section | Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 99fd02f6-8590-5da0-b19d-be011a9585a7 |  | textbox | Drawing and Revision Number
checkpoint-status |  |  | checkpoint | Survey Set out – Check Position
checkpoint-group |  |  | section | Road Subgrade Inspection
checkpoint-status |  |  | checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | ae19392d-5323-5684-853e-c97738ad7274 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subgrade
text | 631f544c-bdad-536e-927d-db318a8a474d |  | textbox | Thickness (mm)
label | 95ecee2f-9419-5c13-acf9-8abd8cd57114 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 3949c6fe-8d93-59b6-9fdb-0f45a78f8380 |  | button | Compaction Method | Standard,Modified
text | 9e9f30d4-2e74-5ec2-9edc-1865620312f6 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 84ee8540-00d7-5425-8037-6759849f564f |  | button | Compaction Method | Standard,Modified
text | 49e78e95-8937-5b29-8a0e-b6df3178058e |  | textbox | Minimum Dry Density Ratio (%)
label | e15d05d4-4dfe-5258-a42e-e234e4665abc |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Capping Layer Inspection
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | 95c29cdd-0770-5df2-9b4e-c58b4fe4f178 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | bf9ec2da-9897-5e8d-b35d-5a9191f0ae82 |  | textbox | Thickness (mm)
label | b3794518-7905-5425-ad6e-50f969d2e508 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 5736d016-5124-570a-882d-516aef407039 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 6320ee65-6b6e-5cf4-a000-00fcbe47f045 |  | button | Compaction Method | Standard,Modified
text | d53206f1-8a75-5ca0-a08d-27d832507823 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 83cc5eee-d6ba-5f13-8a43-18db03df4efd |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | df8be0f9-6696-5c75-a37c-691f7e4195e1 |  | button | Compaction Method | Standard,Modified
text | 5229817d-b442-50f3-86f5-2fea9328b36e |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 6775468d-0005-51f5-9b35-30b6c1b6bc5e |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 1
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | f8e6f0fa-1625-57df-9153-1a769ddee526 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | 826f8120-1609-5f60-8794-2f15975b1e41 |  | textbox | Thickness (mm)
label | 4cea7c6e-0678-5b61-a92b-74d30b955eb3 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 9194df00-b06d-547d-9068-351a067e4482 |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | f0a5b57c-97c6-5f47-82d5-b450f153eaa6 |  | button | Compaction Method | Standard,Modified
text | 475fc81c-9666-5084-8ad1-679ab91996c0 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | ec276a48-6f89-5997-8816-4a26ca1bf8cd |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | aebadff9-c3b2-5bde-9fa6-ae7ab503df37 |  | button | Compaction Method | Standard,Modified
text | 752f3da4-e591-5dc7-8982-d225db86611d |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 554a2a62-0163-50e3-b91a-3670751366e3 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 2
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | cebc01ff-864d-530b-9b8c-f1a8e9d777a2 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | 9a11f660-3d4c-5ef2-b3a5-6725c047b9ec |  | textbox | Thickness (mm)
label | f5dfe585-2d3a-5535-8b49-341a95d5e4cf |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 2fa36a47-4409-5f2b-9ca8-bcf9e9a8b73b |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 13d8a751-9492-5489-91e1-3a8186d94681 |  | button | Compaction Method | Standard,Modified
text | 6197f56d-ce7d-5dd1-ae98-3801be102739 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 83097b17-e7d1-5a22-b2d6-3d305eb69ccb |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | e6592380-dcc8-5211-a67a-d5a5496c5e97 |  | button | Compaction Method | Standard,Modified
text | 458471be-ba1f-5dfe-8292-d1bd4b6334f7 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 2534aef3-b9d4-5dab-add3-45b1e7101510 |  | note | Attach photos of Material Compact Report
checklist-sectioned |  |  | checklist | Switchyard Unsealed access pavement |  |  |  |  | Yes | Switchyard Unsealed access pavement | dd39f24b-d8bd-4134-9ce3-46c76b101ef8
checkpoint-group |  |  | section | Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 6f66f978-c291-5084-a2eb-5dc904ec7d5b |  | textbox | Drawing and Revision Number
checkpoint-status |  |  | checkpoint | Survey Set out – Check Position
checkpoint-group |  |  | section | Road Subgrade Inspection
checkpoint-status |  |  | checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | 75760e0a-4cde-5d70-ab87-6893ae057b9d |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subgrade
text | 58e190dd-c88d-5b92-88df-8016b3e909bb |  | textbox | Thickness (mm)
label | e1a09d68-beb2-518e-8e97-dcce551eb468 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 3e3c46b4-cb23-5cec-8509-1605aaef14eb |  | button | Compaction Method | Standard,Modified
text | e48632ef-cfc1-59d6-bf30-2f8c3be7cde6 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 243c753d-2501-5848-9de5-2591d5b9da5c |  | button | Compaction Method | Standard,Modified
text | e623af9a-c321-55a3-9956-230a70b467c4 |  | textbox | Minimum Dry Density Ratio (%)
label | 6cf1ce5b-2c05-50c2-bd8b-5f0405389890 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 1
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | 848eec7b-9df3-5feb-a6cb-94cd46fa2ccb |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | d1c9938f-a453-5764-8615-12df151847f3 |  | textbox | Thickness (mm)
label | 313a0c2b-83a0-587c-af45-b95e9f0e1e5a |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 897fe872-9f99-5d99-a647-a7245d9aee3a |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | ed73c23d-8a92-5c60-b3d9-6c3e71192e1a |  | button | Compaction Method | Standard,Modified
text | 06516d95-9296-5fde-9374-f216eddfe730 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | ca234936-474e-5a44-9a9a-d105d2fe6d8c |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 1e094110-376d-5dc1-97f5-0b1c6599b9d3 |  | button | Compaction Method | Standard,Modified
text | b9e4a3f2-6cdc-5fac-ab32-a3129c9e32ef |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 70c3bdc6-3d14-5be0-9d83-5057260f0365 |  | note | Attach photos of Material Compact Report
checkpoint-group |  |  | section | Road Subbase Inspection Layer 2
checkpoint-status |  |  | checkpoint | Top of Subbase Layer
text | e5bd67ac-ae80-5708-8b23-8de68c540316 |  | textbox | RL (m)
checkpoint-status |  |  | checkpoint | Thickness of Subbase
text | b246c58f-0ae3-5cd6-9063-891a55ef9386 |  | textbox | Thickness (mm)
label | 68206cf9-9da3-55ec-98ce-bc58729e4089 |  | note | Attach photos of Subgrade
checkpoint-status |  |  | checkpoint | Material Requirement
button | 47a5b5a5-bddb-56b7-aa21-0d80412d572c |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 471cd697-369d-58e7-ad1c-e138efdf4996 |  | button | Compaction Method | Standard,Modified
text | cb895893-1073-5667-9452-66179ad09125 |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Material Compact Test Report
button | 35a828e2-7c2c-5d5c-be1f-ebcc6060011e |  | button | Subbase Material | Class 1,Class 2,Class 3,Class 4,Class A,Other
button | 494298bf-6db7-5a3e-aad4-527d66769639 |  | button | Compaction Method | Standard,Modified
text | c7ad75e5-066f-59c7-ac3e-660377f4126f |  | textbox | Minimum Dry Density Ratio (%)
checkpoint-status |  |  | checkpoint | Compact Material Test
label | 00b4d0f5-8935-5e14-9ff8-e77ff5a54acc |  | note | Attach photos of Material Compact Report
checklist-flat |  |  | checklist | Piling Records ITC / R |  |  |  |  | Yes | Piling Records ITC / R | e5edee59-4987-4827-82c0-eccc9e26f9ec
checkpoint-status |  |  | checkpoint | Pile Drilling Sequence
text | 4e92b948-dff2-55dc-b05c-f8954453f719 |  | textbox | Platform Level (RL m)
text | f56913ba-411c-5f67-a9f3-2295ba5c4d3f |  | textbox | Diameter (mm)
text | 6bf2624d-d404-55a9-a8f9-1f016c934365 |  | textbox | Concrete Grade (MPa)
text | b0b57d2b-cbfe-52a0-bb2a-b926c1f9312f |  | textbox | Drill Depth (m)
|  |  | textbox | Founding Depth Material
text | 28dcaa09-51b9-5059-98bd-f11a3f9e1f61 |  | textbox | Socket Length (m)
text | 25cb52c2-0eaa-5bfe-8b11-9de58f884e6a |  | textbox | Top of Concrete (RL m)
text | 23310a63-5ec1-5a1b-a2d9-79f9a2b56122 |  | textbox | Concrete Volume (m3)
checkpoint-status |  |  | checkpoint | Reinforcement - Cage
text | 5f4addef-eb67-51ea-b5ca-ab5931659fe1 |  | textbox | Top of Cage (RL m)
text | 3fc88b3f-9f39-5bec-92cf-ab3f680a89f0 |  | textbox | Bars xNyy
text | 70c0c812-3023-5b62-a42b-850858f58164 |  | textbox | Spiral Size (mm)
text | 3e19de90-95d7-537b-92bc-caacced18d67 |  | textbox | Spiral Pitch (mm)
text | 5791495e-3777-5a67-9c77-f2281df9e42d |  | textbox | Length (m)
checkpoint-status |  |  | checkpoint | Reinforcement
select | b2e36b17-0822-5015-ae23-f663c35c6cb4 |  | dropdown | Coupling Bars Included? | Yes,No
text | 702c420c-b810-5ef6-9339-f49260b3a9eb |  | textbox | Bars xNyy
text | 562f1e49-59e8-5622-84f8-d826edaa96d4 |  | textbox | Length (m)
checkpoint-status |  |  | checkpoint | Final
text | bc661725-6786-5f6c-b20b-20d2e42463dd |  | textbox | Verticality (mm / m)
text | e4826715-c811-554a-903e-215c3354277b |  | textbox | Offsets (mm / direction)
button | 0a847469-378c-55f5-acdf-c8fec6d87946 |  | button | Concrete Test | Yes,No
text | 37a547be-d450-5ba0-aae3-c02dd270ac9a |  | textbox | Concrete Test Result
checkpoint-status |  |  | checkpoint | Keller Superviser Sign Off / Handover
checkpoint-status |  |  | checkpoint | Delta Group Sign Off