## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | NEL-CNT-SDC-2990-PQA-ITP-0029 Rev 3 - Unbound Flexible Pavements | itp |  |  |  |  | NEL-CNT-SDC-2990-PQA-ITP-0029 Rev 3 - Unbound Flexible Pavements
section | 1.0 Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
checkpoint | 1.1 - Construction Package Approval
label | Resp. Person - PE
label | Specification Reference - PSDR Part F6 2 (a) to (h)
label | Acceptance Criteria - Construction Documentation shall be submitted and approved prior to commencing work at site.
label | Test Method - R
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - IFU Construction Package
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Design status
label | Resp. Person - PE
label | Specification Reference - PSDR Part F5, 2(b) & (c)(i)
label | Acceptance Criteria - Design to be IFC prior to works commencing
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - IFC Drawings
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - All Equipment calibrated
label | Resp. Person - SE
label | Specification Reference - CQMP Plan Section 11.1
label | Acceptance Criteria - Equipment calibration certificates filed in InEight
label | • Ensure all equipment associated with the relevant works is calibrated
label | Test Method - R
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Calibration Certificates
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Survey Set Out
label | Resp. Person - SE
label | Specification Reference - PSDR Part F4 Section 6, IFC Drawings
label | Acceptance Criteria - Clearly mark limit of works; Chainage, offsets, cut/fill level etc. (if required)
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Survey Record
textbox | • InEight Reference: #
label | • Lot Map
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Crushed Rock Mix Registration
label | Resp. Person - PE
label | Specification Reference - VR812.04 RC500.02 IFC Drawings
label | Acceptance Criteria - All crushed rock proposed for use on VicRoads funded works shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
label | • Mixes registered by VicRoads as ‘General’ may be used in the construction of roadworks.
label | • Mixes registered as ‘Conditional’ may be used provided the conditions are complied with. Mixes registered as ‘Experimental’ shall only be used with written approval from Design (CRFI from CPS).
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - CRFI
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Materials Conformance
label | Resp. Person - PE
label | Specification Reference - VR 304.03, VR801, VR812 VR 811, VR 818, IFC Drawings
label | Acceptance Criteria - Material supplied complies with the Class of material required on the IFC drawing.
label | • Prior to the commencement of work, the Subcontractor shall nominate the material source from which the crushed rock and aggregate will be obtained.
label | • Material sources used in the production of crushed rock shall comply with the relevant requirements of Section 801 Source Requirements for the Production of Crushed Rock and Aggregates.
label | • Sand, Gravel and soft or ripped rock material shall meet the relevant requirements of Tables
label | • 811.041 and 811.042 and shall be free from vegetable matter and lumps or balls of clay or other deleterious matter. Verify conformance via CRFI to Design.
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - CRFI
textbox | • InEight Reference: #
label | • Grading Figures Material Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Water Source
label | Resp. Person - PE
label | Specification Reference - VR304.03
label | Acceptance Criteria - Any water added to the pavement material must meet the following criteria:
label | • Clean and substantially free from oils, salts, acids, alkalis and vegetable substances. Maximum of 1000 mg/L of suspended solids.
label | • Where dissolved salts are known or likely to be present, electrical conductivity less or equal 3500 µS/cm.
label | • Potable water is exempt from these requirements.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Test Results
bool | • Quantity of Water Added (L):
textbox
checkpoint | 1.8 - Sub-Subcontractor(s) quality documents + Inspection Test Plan (if required)
label | Resp. Person - PE
label | Specification Reference - CQMP Section 8.2.2.4
label | Acceptance Criteria - Ensure Sub-subcontractor(s) have submitted signed ITP’s and checklists along with all relevant supporting documents.
label | • Ensure ITP Review Checklist is complete (only applicable to Sub-Subcontractors ITP).
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Approved Subcontractor’s Quality Documentation
section | 2.0 Operations (Include Work Execution – Installation / Manufacturing Process step-by-step)
checkpoint | 2.1 - Subgrade Preparation
label | Resp. Person - SE
label | Specification Reference - VR204, VR210, VR304.04
label | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
label | • The subgrade has been prepared for placement and Earthworks Excavation ITP signed off.
label | • Confirm that subgrade compaction testing, level conformance and proof roll have passed.
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • Subgrade Lot Number:
textbox
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Verify Conformance of Previous Layer
label | Resp. Person - SE
label | Specification Reference - VR304.06, VR304.10, Table 304.101, IFC Drawings
label | Acceptance Criteria - Previous layer completed. Documentation available and complying.
label | 1 Testing rolling -
label | 2 Compaction testing
label | • Refer VicRoads 204 for subgrade,
label | • Table 304.101 (below) for previous controlled product layer
label | 3. Level survey conformance, As-built Records for all lots immediately below this new layer.
label | Test Method - R
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | Subgrade Lot Number:
textbox
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Placement of Material
label | Resp. Person - SE
label | Specification Reference - VR 304.06 & VR304.08 & IFC Drawings
label | Acceptance Criteria - Material has been spread and compacted such that the material is properly mixed both transversely and longitudinally to produce a homogeneous material for each lot.
label | During compaction shall have a moisture content of not less than 85% of optimum.
label | ○ Surface finish to be:
label | • Smooth and uniform.
label | • Free of segregated areas.
label | ○ Base layer shall not exceed 150mm.
label | ○ Sub-base layer shall not exceed 200mm
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - This ITP
checkpoint | 2.4 - Material of Nominal Size Greater than 40mm (if required)
label | Resp. Person - SE
label | Specification Reference - VR304.08 (c)
label | Acceptance Criteria - The first lot shall be placed as a trial section. Following acceptance of the trial section, the Subcontractor shall then confirm the moisture control and compaction procedure and submit the procedure to the Nominated Authority for review and record.
label | Test Method - V
label | Test Frequency - X1
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - HP Release
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Jointing
label | Resp. Person - SE
label | Specification Reference - VR304.07
label | Acceptance Criteria - Joints have been minimised.
label | • Transverse - Offset by >2m to any underlying pavement layers.
label | • Longitudinal - Offset by >150mm to any underlying pavement layers.
label | • longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - This ITP
label | • Lot Map showing construction joints
checkpoint | 2.6 - Testing – Stability (Proof Roll)
label | Resp. Person - SE
label | Specification Reference - VR304.08 VR173
label | Acceptance Criteria - During testing, material has a moisture content of >85% OMC.
label | • The Subcontractor shall provide for the Nominated Authority to be present during all test rolling.
label | • Testing frequency shall be in accordance with Appendix A of this ITP.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - HP Release
textbox | InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Post Compaction
label | Resp. Person - SE
label | Specification Reference - VR173, VR304.08, Table VR304.081 VR304.10, Table 304.101, Table 304.103 VR304.11, Table 304.111 IFC Drawings
label | Acceptance Criteria - During testing, material has a moisture content of >85% OMC
label | • Any segregated areas have been rectified.
label | • Tests performed using Modified compactive effort to Scale A. Six tests per lot.
label | ○ Requirements:
label | • Subbase Layers – CBR not less than 98%
label | ○ Base Layer - Characteristic Density Ratio not less than 100% directly beneath bituminous surface or 99% for other layers.
label | • The test samples to be used for post-compaction grading and PI tests shall be a combined sample made up from six randomly selected increments extracted from the lot of pavement construction being assessed.
label | ○ Post compaction PI for: Class 1 Crushed Rock shall be between 2 and 6
label | • Class 2 Crushed Rock shall be between 0 and 6
label | • Class 3 Crushed Rock shall be between 0 and 10
label | • Post compaction grading based on sieve analysis. See Table 304.101 for grading requirements.
label | Test Method - V
label | Test Frequency - X1
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
textbox | • NATA Compaction Report Number
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Protection of Compacted Layer
label | Resp. Person - SE
label | Specification Reference - VR304.09
label | Acceptance Criteria - Surface of each compacted layer has been kept moist, in good order/condition & free from contamination until the subsequent pavement work is to commence.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - This ITP
checkpoint | 2.9 - Reuse of trimmed material (if required)
label | Resp. Person - SE
label | Specification Reference - VR304.06
label | Acceptance Criteria - Any material that has been compacted and then trimmed from the compacted surface to conform to the correct level or thickness as shown on the drawings shall not be re-used in the pavement construction without the approval of the Nominated Authority.
label | Test Method - V
label | Test Frequency - X1
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - WP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - WP Release
textbox | • InEight Reference: #
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Post Operations (Include Inspection and Testing)
checkpoint | 3.1 - Survey Conformance
label | Resp. Person - SE
label | Specification Reference - VR304.06 Design Management Plan NEL-CNT- SDC-2990-PDM- MPL-0001 Section 5.4
label | Acceptance Criteria - Each pavement course has been finished to smooth and uniform surfaces, free of segregated areas, and conforming to the limits for level, line, grade, thickness and cross section shown on the drawings or as specified.
label | • Width and Alignment:
label | • Is not less than the specified offset width or >50mm outside when measured at right angle from the design line
label | ○ Shape:
label | • Surface does not vary by >8mm from a 3m straight edge, or 10mm from a 6m straight edge, placed in any direction. Water cannot pond on the surface of any pavement layer.
label | • The surface level of the pavement courses has been measured in accordance with the requirements of Scale A (80pts per lol less than 4000m2)
label | ○ Surface Level – Scale A: Lower Subbase
label | • Range (mm) +6 to -10 Max. S (mm) 10
label | ○ Upper Subbase
label | • Range (mm) +4 to -8, Max. S (mm) 8
label | ○ Base
label | • Range (mm) +5 to -5, Max. S (mm) 8
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - As-Built Survey Report
textbox | • InEight Reference: #
checkpoint | 3.2 - Redline Drawings
label | Resp. Person - PE
label | Specification Reference - Design Management Plan NEL-CNT- SDC-2990-PDM- MPL-0001 Section 5.4
label | Acceptance Criteria - Redline Drawings submitted to Project for creation of As- Built Drawings.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Red-Line Marked Up IFC Drawing(s)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Verification and Lot Records complete
label | Resp. Person - PE
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - Progressive monitoring and signoff of Checklists occurs, and test records are collected.
label | • Ensure completed work checklists, inspection and test results and Subcontractor conformance records are progressively and permanently saved and stored as soon as possible after they are received.
label | • Completed construction lot records are transferred to the project Quality Team for final record verification prior to being closed
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - This ITP Lot Record
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Quality
checkpoint | 4.1 - Identification and control of non- conforming products or services (if applicable)
label | Resp. Person - QSR
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - Review and confirm closure of NCR’s and associated RFI’s prior to closing of construction lot.
label | Test Method - R
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Records/Documents - NCR closed with related documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Check all quality records for lot closure
label | Resp. Person - QSR
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - All applicable quality records are complete.
label | Test Method - R
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Records/Documents - Compiled documents (all data reports and records)
holdpoint | AUTHORITY HOLDPOINT