## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | NEL-CNT-SDC-2990-PQA-ITP-0040 Rev 1 - Cement Treated Crushed Rock | itp |  |  |  |  | NEL-CNT-SDC-2990-PQA-ITP-0040 Rev 1 - Cement Treated Crushed Rock
section | 1.0 Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
checkpoint | 1.1 - IFC Drawings issued
label | Resp. Person - PE
label | Specification Reference - IFC Drawing Number: PSDR Part 6 Section 2(h)
label | Acceptance Criteria - IFC Drawings, approved plans, technical specification issued for construction
label | • Construction of any Construction Package must not commence until at least 5 Business days after the later of when:
label | i). the Construction Documentation has been submitted to the State, the IREA and any Returned Asset Owner (if applicable) in accordance with section 2(f) and
label | ii). Any requirements of the IREA under section 2(g) have been complied with.
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - IFC Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - All Equipment calibrated (NATA Approved)
label | Resp. Person - PE
label | Specification Reference - Quality Management Plan
label | Acceptance Criteria - Equipment calibration NATA certificates filed in InEight Document.
label | • Prior performing inspections, measuring and testing tasks, ensure equipment is calibrated, if damaged or out of calibration, the user will immediately tag it “out of service” and arrange for repairs / calibration.
label | Test Method - I
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - InEight Document References:
textbox
checkpoint | 1.3 - Survey Set Out
label | Resp. Person - PE
label | Specification Reference - Quality Management Plan, IFC Drawings
label | Acceptance Criteria - Confirmation and visually inspect survey set out as per the IFC Drawing
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - InEight Document References:
textbox
label | • Lot Map
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Material Registration
label | Resp. Person - PE
label | Specification Reference - VR (2019) Section 306.04, VR (2016) Section 815.04, VR Code of Practice RC500.02 VR 801, 815 VR 812.04
label | Acceptance Criteria - The cement treated crushed rock must be a current, registered mix in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
label | • The supplied registered mix shall not be changed unless the Nominated Authority has been advised of the change and given written approval.
label | • Mixes registered as “Conditional” shall not be used unless the Superintendent has been advised of any mix registration conditions and approved the mix for use.
label | Test Method - I
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - HP
label | Records/Documents - VicRoads Letter of Registration
label | • Material Test Reports / NATA approve
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Use of alternative binder
label | Resp. Person - PE
label | Specification Reference - VR 306.09
label | Acceptance Criteria - If the Contractor proposes to use an alternative cementitious binder to those included in Table 306.091, laboratory test results shall be produced to the Nominated Authority showing that the binder satisfies the required working time determined in accordance with the VicRoads Test Method.
label | • In addition, the cementitious treated material using the alternative binder shall meet specified strength requirements of 500MPa.
label | Test Method - R
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - InEight Document References:
textbox
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Verify Layer Compaction and Surface Level
label | Resp. Person - SE
label | Specification Reference - VR 304 Table 304.061, VR 304.062 IFC Drawings
label | Acceptance Criteria - Previous layer completed. Documentation available and complying.
label | 1. Testing rolling
label | 2. Compaction testing
label | 3. Level conformance - See tables below
textbox | Lot no.
textbox | Lot no.
textbox | Lot no.
label | Test Method - V
label | Test Frequency - PW + PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Signed ITP
section | 2.0 Operations (Include Work Execution – Installation / Manufacturing Process step-by-step)
checkpoint | 2.1 - Material Placement
label | Resp. Person - SE
label | Specification Reference - VR306.05, 306.09 Table, 306.091 VR 306.11 IFC Drawings, VR 306.03(a)
label | Acceptance Criteria - Place, trimmed to level and fully compacted within max. allowable working time refer to table VR 306.091.
label | • Ensure that width of the pavement course has been constructed as per requirement 306.03(a) where the width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset.
label | • Moisture content within +0.5% and -1.0% from the Optimum Moisture Content from the Modified optimum moisture content.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Material Delivery Dockets
label | • Quarry Batch Records
checkpoint | 2.2 - Transverse and Longitudinal Jointing
label | Resp. Person - SE
label | Specification Reference - VR 306.08 IFC Drawings
label | Acceptance Criteria - The layout of the joints shall conform to the following requirements:
label | a). material shall be spread in such a manner as to minimise the number of joints
label | b). in any layer, transverse joints in adjoining paver runs shall be offset by not less than 2m
label | c). transverse joints shall be offset from one layer to the next by not less than 2m.
label | d). longitudinal joints shall be offset from one layer to the next by not less than 150mm.
label | e). longitudinal joints shall be located within 300mm of the planned position of traffic lane lines or within 300mm of the centre of a traffic lane.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Signed ITP
checkpoint | 2.3 - Proof Rolling (If required)
label | Resp. Person - SE
label | Specification Reference - VR 306.091, VR 306.10, VR 173.03
label | Acceptance Criteria - If test rolling is chosen to be carried out, then it must be done within the maximum allowable working time for the type of CTCR and time of year as specified in Table 306.091
label | • Ensure test roll area is prepared for test roll and is in accordance with test roll procedure prior application.
label | • Ensure no visible deflection or springing.
label | • The extent of test rolling and a requirement to provide not less than 24 hours’ notice of the location and commencement time for the test rolling to the Superintendent / Nominated Authority.
label | Test Method - I
label | Test Frequency - X1- refer to procedure
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - Test Roll Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Post compaction density testing
label | Resp. Person - SE
label | Specification Reference - VR 815.141, VR 306.09, VR 173.04 Design Package
label | Acceptance Criteria - Maximum lot size <5000m2 - Test frequency compliance to specification table VicRoads 815.141 Scale A:
label | • Characteristic value of density ratio ≥ 96% modified
label | • Standard lot 6 tests per lot.
label | • Lot size > 500m2, 6 tests per lot Lot size < 500m2, 3 tests per lot. At 2% greater than a (6-lot Std) 96.0% (6-Lot Std) 98.0% (3-Lot Std)
label | • Minimum compacted thickness on a single layer shall not be less than 100mm and the maximum compacted thickness shall not be more than 200mm.
label | Test Method - I
label | Test Frequency - Scale A: 6 tests / lot
label | • Scale B: 3 tests / lot
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - NATA Test Report
checkpoint | 2.5 - Curing and protection of compacted layers (Pavement Design Modulus of 500MPa or not specified)
label | Resp. Person - SE
label | Specification Reference - VR 306.11(a)
label | Acceptance Criteria - 1 Surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage.
label | 2 Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Nominated Authority.
label | 3 Subbase shall be kept in good order and condition and free from contamination.
label | 4 Water can only be added for the purposes of curing to the cementitious treated material.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Signed ITP
checkpoint | 2.6 - Curing and protection of compacted layers (Pavement Design Modulus of 3500MPa or not specified) – If Applicable-
label | Resp. Person - SE
label | Specification Reference - VR 306.11(c)
label | Acceptance Criteria - (HP) Requests by the Contractor to vary the rates of application shall be submitted in writing to the Superintendent for review.
label | (HP) The Contractor’s Environmental Management plan shall include procedures to minimise all risks of damage to the environment associated with priming and primer sealing.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - Signed ITP (If Applicable)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Survey Conformity with Drawings
label | Resp. Person - SE
label | Specification Reference - VR 306.03 (a)(b)(c) Table VR 306.031, Table VR 306.032
label | Acceptance Criteria - Surface level of the pavement courses shall be measured in accordance with Table 306.031 & 306.032
label | • Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot as specified in Table 306.031
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - InEight Survey Report References:
textbox
section | 3.0 Post Operations (Include Inspection and Testing)
checkpoint | 3.1 - Red-Line
label | Resp. Person - PE
label | Specification Reference - VR 703.15 IFC Drawings
label | Acceptance Criteria - Ensure Redline survey is compared within the required tolerance to Design specification.
label | • Ensure all locations and work area highlighted as per Construction Lot in Work Lot Map.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Red-Line Mark- Up Drawings
checkpoint | 3.2 - Final Inspection Site Walk
label | Resp. Person - PE
label | Specification Reference - CQMP
label | Acceptance Criteria - Ensure at the end of each work conducted that Quality Control conduct an Inspection walk with Engineer to identify potential defects.
label | Test Method - I
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
bool | • Surveillance Report
bool | • Punch List Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - RFI’s, DRFI’s & DCN’s
label | Resp. Person - PE
label | Specification Reference - CQMP DMP
label | Acceptance Criteria - Ensure all Design Change(s) are noted within the scope of the Construction Lot.
label | • Link all relevant RFI’s included only to the specific Construction Lot.
label | • Ensure RFI’s are closed out prior to Construction Lot close out.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • RFI’s
textbox | • InEight Reference Form #
section | 4.0 Quality
checkpoint | 4.1 - Identification and control of non- conforming products or services (if applicable)
label | Resp. Person - QSR
label | Specification Reference - CQMP
label | Acceptance Criteria - Review and confirm closure of NCR’s and associated RFI’s prior to closing of construction lot
label | Test Method - R
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - NCR closed with related documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Check all quality records for lot closure
label | Resp. Person - QSR
label | Specification Reference - CQMP
label | Acceptance Criteria - All applicable quality records are complete
label | Test Method - R
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Compiled documents (all data reports and records)
holdpoint | AUTHORITY HOLDPOINT