## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | NEL-CNT-SDC-2990-PQA-ITP-0057 Rev 0 - Guard Fence Installation | itp |  |  |  |  | NEL-CNT-SDC-2990-PQA-ITP-0057 Rev 0 - Guard Fence Installation
section | 1.0 Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
checkpoint | 1.1 - IFC Drawings Issued
label | Resp. Person - PE
label | Specification Reference - CQMP
label | Acceptance Criteria - IFC Drawings, approved plans, technical specification issued for construction
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - IFC Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Crushed Rock Mix Approved
label | Resp. Person - PE
label | Specification Reference - VR 812.04
label | Acceptance Criteria - Crushed Rock Mix is registered with VicRoads certificate
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - Mix Registered on InEight
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Concrete Mix Approved
label | Resp. Person - PE
label | Specification Reference - VicRoads 703.05, VicRoads 708.05
label | Acceptance Criteria - Concrete shall comply with AS1379 and as specified in VicRoads 703 for either:
label | – Portland cement-based concrete, N20 strength grade or
label | – Geopolymer concrete, 20MPa strength
label | • Use of chemical admixtures to comply with requirements of Section 703
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Mix design:
textbox
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Guard Fence Components
label | Resp. Person - PE
label | Specification Reference - VicRoads 708.05 VR708.04 VR Road Design Note 06-04
label | Acceptance Criteria - Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
label | • Steel w-beams, posts and all plastic components of proprietary end treatments unobtrusively and permanent in text not more than 20mm high, the following information:
label | – name of manufacturer
label | – batch number or date
label | – strength grade and base metal thickness
label | – Test certificate demonstrating compliance of materials and components with the specification for the proprietary Guard Fence system and VicRoads 708
label | – Signed statement and certificates of compliance have been accepted by the Nominated Authority (14 days prior to installation)
label | • W-beams to AS1594 Grade HA350 Posts to AS1594 Grade HA250 Steel components hot dip galvanised
label | • Non-Standard Post Lengths (if used) are to have details of the measures proposed and evidence of the effectiveness of the barrier system maintenance submitted for consideration by the NA
label | Test Method - R
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
bool | • Test certificates
bool | • Manufacturer’s compliance certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Material Supply inspection
label | Resp. Person - SE
label | Specification Reference - VicRoads 708.06
label | Acceptance Criteria - Materials are free from distortion and damage
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Completed incoming inspection checklist
section | 2.0 Operations (Include Work Execution – Installation / Manufacturing Process step-by-step)
checkpoint | 2.1 - Survey of guard fence alignment
label | Resp. Person - SE
label | Specification Reference - VicRoads 708.08 IFC Drawings
label | Acceptance Criteria - Confirm and visually inspect survey set out as per the IFC drawing offsets
label | • Prior to installation, the contractor shall confirm with the Nominated Authority the required location and length of all guard fence
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - Survey Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation of maintenance strip
label | Resp. Person - SE
label | Specification Reference - VicRoads 703.20
label | Acceptance Criteria - Excavation extents comply with IFC drawings. Extends minimum 300mm clear of the rear of the post and 300mm clear from the face of w-beam, 75mm deep
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Photos
checkpoint | 2.3 - Lay crushed rock
label | Resp. Person - SE
label | Specification Reference - VicRoads 703.21, VicRoads 812
label | Acceptance Criteria - Bedding material is a compacted size 20mm 3 crushed rock (Section 812) or Class 3 crushed concrete (section 820)
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Photos, Delivery Dockets
checkpoint | 2.4 - Install posts
label | Resp. Person - SE
label | Specification Reference - VicRoads 708.7, VicRoads 708.8, VicRoads 708.9
label | Acceptance Criteria - Post holes in rock shall have a 75mm minimum clearance from back of post to face of hole Post holes in rock to be backfilled with granular material. Other post holes to be backfilled with selected earth, free of rock.
label | • Backfilling compacted in 100mm layers.
label | • Variation from true plan position of posts ±20 mm Variation of posts from Vertical (measured at top of the post) ±15mm
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Photos
checkpoint | 2.5 - Install W- beams
label | Resp. Person - SE
label | Specification Reference - VicRoads 708.8, VicRoads 708.11
label | Acceptance Criteria - W-beam sections to be lapped so exposed ends face away from near-side approaching traffic. Variation of line of w-beams from specified vertical profile ±10 mm
label | • Variation of w-beams from specified horizontal alignment ±20 mm
label | • Orientation of block and/or post to w-beam +0 mm, - 15 mm
label | • Top of bolt head relative to w-beam -0 mm, +5 mm All bolts to be fully tightened
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Install end- treatments
label | Resp. Person - SE
label | Specification Reference - VicRoads 708.8,
label | Acceptance Criteria - Ropes are not twisted
label | • Nuts at the end of each rope is tightened to a minimum torque of 50Nm or as per manufacturers requirements
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
checkpoint | 2.7 - Concrete maintenance strip
label | Resp. Person - SE
label | Specification Reference - VicRoads 708.12
label | Acceptance Criteria - Edges of the infill area are boarded up prior to placing concrete or expansion joint is sawcut to 75% concrete depth.
label | • Where concrete strip is adjacent to kerb or pavement, a cork expansion joints is produced.
label | • Full depth expansion joints provided perpendicular to the line of steel beam guard fence, 200mm each side of every post
label | • Concrete is as per approved mix design
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Delivery Dockets, Maintenance Strip Location Record
section | 3.0 Post Operations (Include Inspection and Testing)
checkpoint | 3.1 - Concrete Strength Results
label | Resp. Person - SE
label | Specification Reference - VicRoads 703.11
label | Acceptance Criteria - Testing cylinders to be taken per 50m3, 28-day Compressive Strength = 20MPa
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Concrete Strength Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Compliance Audit
label | Resp. Person - SE
label | Specification Reference - VicRoads 708.10
label | Acceptance Criteria - Safety Barrier compliance Audit undertaken for entire project Guard Fence Installation and Certificate of Compliance signed by the Contractor and Licensed supplier provided.
label | Test Method - V
label | Test Frequency - X1
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - Compliance Audit Certificate of Compliance
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Quality
checkpoint | 4.1 - Identification and control of non-conforming products or services (if applicable)
label | Resp. Person - QSR
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - Review and confirm closure of NCR’s and associated RFI’s prior to closing of construction lot
label | Test Method - R
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Records/Documents - NCR closed with related documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Check all quality records for lot closure
label | Resp. Person - QSR
label | Specification Reference - CQMP Section 8.3
label | Acceptance Criteria - All applicable quality records are complete
label | Test Method - R
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Records/Documents - Compiled documents (all data reports and records)
holdpoint | AUTHORITY HOLDPOINT