## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | NEL-CNT-SDC-2990-PQA-ITP-0074 Rev 0 - General Concrete (Footpath, Driveway, Median / Island Pavement) | itp |  |  |  |  | NEL-CNT-SDC-2990-PQA-ITP-0074 Rev 0 - General Concrete (Footpath, Driveway, Median / Island Pavement)
section | 1.0 Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
checkpoint | 1.1 - IFC Drawings issued
label | Resp. Person - PE
label | Specification Reference - IFC Drawings
label | Acceptance Criteria - IFC Drawings, approved plans, technical specification must be issued for construction
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
textbox | • InEight Reference Document #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - All Equipment Calibrated
label | Resp. Person - PE
label | Specification Reference - QMP
label | Acceptance Criteria - Equipment calibration NATA certificates filed in InEight Document.
label | • Prior performing inspections, measuring and testing tasks, ensure equipment is calibrated, if damaged or out of calibration, the user will immediately tag it “out of service” and arrange for repairs / calibration.
label | Test Method - IP
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
textbox | • InEight Reference Document #
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Premixed Concrete
label | Resp. Person - PE
label | Specification Reference - VR 703.05 IFC Drawing
label | Acceptance Criteria - Concrete / Footpath Pavement Material to be in accordance with design requirements
label | Test Method - R
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Concrete Mix Design
checkpoint | 1.4 - Survey Set-out
label | Resp. Person - PE
label | Specification Reference - VR 703.17 IFC Drawings
label | Acceptance Criteria - Clearly mark limit of works; Chainage, offsets, cut/fill level etc. (if required).
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
textbox | • InEight Document References:
label | • Lot Map
checkpoint | 1.5 - Construction Procedure Submission
label | Resp. Person - PE
label | Specification Reference - QMP
label | Acceptance Criteria - Construction Procedure submitted and in place and all required permits from the Safety and Environmental team are obtained.
label | Test Method - R
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Signed ITP
section | 2.0 Operations (Include Work Execution – Installation / Manufacturing Process step-by-step)
checkpoint | 2.1 - Setting Out
label | Resp. Person - SE
label | Specification Reference - VR 703.17, PSDR (section 9 a))
label | Acceptance Criteria - The Nominated Authority will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the IFC drawings.
label | Test Method - V
label | Test Frequency - PW
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
textbox | • InEight Survey Report References:
label | • Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation and Foundation
label | Resp. Person - SE
label | Specification Reference - VR 703.20
label | Acceptance Criteria - The Contractor shall box out to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving. Excavation not to extend more than 150mm from the adjacent face of existing pavement.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Signed ITP
checkpoint | 2.3 - Bedding materials and compaction
label | Resp. Person - SE
label | Specification Reference - VR 812.12 VR 703.21 IFC Drawings AS 3798
label | Acceptance Criteria - Bedding material shall be compacted 20mm Class 3 or Class 4 Crushed Rock to 98% standards compaction unless shown otherwise on the drawings
label | • Material properties, testing and testing frequency shall be in accordance with section 812.12
label | Test Method - IP
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WR
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - NATA Test Reports
checkpoint | 2.4 - Bedding depths (compacted)
label | Resp. Person - SE
label | Specification Reference - VR 703.21 (a) (c) IFC Drawings
label | Acceptance Criteria - (a) Edgings: Where not constructed over pavement layers, bedding not less than 100 mm compacted.
label | (c) Footpaths and other Surfacing:
label | • Bedding not less than 100 mm compacted.
label | • Bedding trimmed to appropriate levels, moistened as necessary, and firmly compacted.
label | Test Method - IP
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Material Delivery Docket
checkpoint | 2.5 - Ambient weather for concreting
label | Resp. Person - SE
label | Specification Reference - VR 703.09, VR 610.17 (a)(b)(c) (d), VR 610.13
label | Acceptance Criteria - Restrictions and treatments to be applied for concreting in hot, cold and wet weather.
label | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10˚C or greater than 32˚C.
label | • Ambient temperature not to be less than 5˚C and no more than 35˚C.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Signed ITP
label | • QC Checklist
checkpoint | 2.6 - Steel reinforcing grade and placement
label | Resp. Person - SE
label | Specification Reference - VR 703.13, VR 611 PSDR Part B Section 17.4
label | Acceptance Criteria - 1/ Steel reinforcement shall comply with the relevant requirements of AS/NZS 4671
label | 2/ Galvanising where specified shall be in accordance with the requirements of AS/NZS 4680
label | 3/ Minimum cover shall be 50 mm unless shown on the drawings
label | 4/ Concrete or plastic chairs to be used. Wire chairs (with or without plastic tips), bricks, pieces
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Reinforcement Steel Delivery Dockets
label | • Product Conformity Certificate
label | • QC Checklist
checkpoint | 2.7 - Formwork
label | Resp. Person - SE
label | Specification Reference - VR 703.12 AS 3610.1 2018 (TableC2)
label | Acceptance Criteria - Construction and stripping of formwork shall comply with the relevant requirements of AS3610. Joints in formworks shall be constructed such that loss of mortar is prevented.
label | ○ Stripping of Formwork after casting shall not be less than:
label | • 2 days (Between 12˚C & 20˚C).
label | • 1 day (> 20 ˚C).
label | • 3 days (Between 5˚C & 12˚C).
label | ○ Minimum time shall also not be less than:
label | a). 2 days for vertical formwork on external surfaces and,
label | b). 1 day for vertical forms on permanently hidden surfaces.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Signed ITP
label | • QC Checklist
checkpoint | 2.8 - Concrete Placing, Compacting
label | Resp. Person - SE
label | Specification Reference - IFC Drawings AS 1379 VR 703.01 VR 703.08 VR 610.121 VR 703.11
label | Acceptance Criteria - Concrete strength to comply with detail on IFC drawings and AS1379
label | • Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedment and into corners of formwork or excavations to produce a dense concrete free from voids.
label | • Workable concrete mixes are exempt from vibration requirement.
label | • Minimum testing requirements for aggregates to comply to VR Table 610.121 and VR 703.11
label | Test Method - IP
label | Test Frequency - X1
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - NATA Test Result
label | • Delivery Docket
label | • QC Checklist
checkpoint | 2.9 - Surface Finish
label | Resp. Person - SE
label | Specification Reference - VR 703.25 (a) (b) IFC Drawings
label | Acceptance Criteria - Footpaths, and other surfacings: Finish with a wooden float to produce a lightly textured non-skid surface. Compact with internal vibration and worked until mortar comes to the top.
label | • Edgings: All edgings shall be rendered and have a steel trowel finish. Rendering applied within 30 minutes of placing or extruding concrete. Thickness not exceeding 3 mm. Mortar shall be 2 parts fine aggregate, 1 part cement & sufficient water to produce suitable consistency
label | • Surface finish to comply to VR 703.25. All discoloured concrete shall be cleaned or replaced.
label | Test Method - IP
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Signed ITP
label | • QC Checklist
checkpoint | 2.10 - Jointing between concrete elements
label | Resp. Person - SE
label | Specification Reference - VR 703.26
label | Acceptance Criteria - Transverse joints shall be constructed at right angles to the back of edgings and the edge of footpaths and shared use paths. Joints in footpaths and shared use paths shall align with joints in adjacent edgings.
label | a). Edgings
label | (i) Transverse joints & expansion joints
label | (ii) Expansion joints & control joints
label | b). Footpaths, other Surfacing and Shared Use Paths
label | (i) Expansion Joints
label | (ii) Control Joints
label | (c) Details on de-bonding methods
label | • Sawcut or tooled joints shall be provided at maximum 2m centres to all footpaths or pedestrian paving. A 19mm expansion joint shall be provided where rigid pavements abut fixed structures or at max 15m centres to footpaths.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Signed ITP
label | • QC Checklist
checkpoint | 2.11 - Curing of concrete
label | Resp. Person - SE
label | Specification Reference - VR 703.10 (a), (b)
label | Acceptance Criteria - Exposed concrete surfaces shall commence curing treatment immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days
label | (a) General
label | (b) Geopolymer concrete
label | Test Method - IP
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Signed ITP
label | • QC Checklist
checkpoint | 2.12 - Marking of Conduit Positions
label | Resp. Person - SE
label | Specification Reference - VR 703.28
label | Acceptance Criteria - Existing conduits passing under edgings shall be marked by a chase in the edge immediately above the conduit together with a suitable identification mark.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Photos
checkpoint | 2.13 - Tolerances on line, level, and shape
label | Resp. Person - SE
label | Specification Reference - VR 703.15
label | Acceptance Criteria - All surfaces shall be finished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as specified, within the following limits:
label | (a) Paving within 5mm
label | (b) Departure of finished work from line & level shall not exceed 10mm at any point
label | (c) Section dimensions overall width shall not exceed >15mm
label | (d) Median surfacing cross fall between 1% and 3% towards the edges
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Tick Off to confirm compliance as per the required acceptance criteria:
bool | (a) Paving
bool | (b) Finished work
bool | (c) Dimension
bool | (d) Median Surface
label | • QC Checklist
checkpoint | 2.14 - Concrete repairs
label | Resp. Person - SE
label | Specification Reference - VR 703.08 VR 703.30 Crack Repair Procedure
label | Acceptance Criteria - Any concrete repairs shall be carried out using a method and materials accepted by the Superintendent.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents - Crack Repair Procedure
label | • QC Checklist
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Post Operations (Include Inspection and Testing)
checkpoint | 3.1 - Red-Line
label | Resp. Person - PE
label | Specification Reference - VR 703.15 IFC Drawings
label | Acceptance Criteria - Ensure As-Built survey is compared within the required tolerance to Design specification.
label | • Ensure all locations and work area highlighted as per Construction Lot in Work Lot Map.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Red-Line Mark-Up Drawings
checkpoint | 3.2 - Final Inspection Site Walk
label | Resp. Person - PE
label | Specification Reference - QMP
label | Acceptance Criteria - Ensure at the end of each work conducted that Quality Control conduct an Inspection walk with Engineer to identify potential defects.
label | Test Method - IP
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
bool | • Surveillance Report
bool | • Punch List Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - RFI’s, DRFI’s & DCN’s
label | Resp. Person - PE
label | Specification Reference - QMP DMP
label | Acceptance Criteria - Ensure all Design Change(s) are noted within the scope of the Construction Lot.
label | • Link all relevant RFI’s included only to the specific Construction Lot.
label | • Ensure RFI’s are closed out prior to Construction Lot close out.
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents -
bool | • RFI’s InEight Reference Form #
checkpoint | 3.4 - NCR Close out
label | Resp. Person - PE
label | Specification Reference - QMP
label | Acceptance Criteria - All NCR’s presented for closure
label | Test Method - V
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | Inspection/Verification (Name, signature & date): IREA - WP
label | Records/Documents -
bool | • NCR InEight Reference Form #
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Quality
checkpoint | 4.1 - Identification and control of non-conforming products or services (if applicable)
label | Resp. Person - QSR
label | Specification Reference - CQMP
label | Acceptance Criteria - Review and confirm closure of NCR’s and associated RFI’s prior to closing of construction lot
label | Test Method - R
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - NCR closed with related documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Check all quality records for lot closure
label | Resp. Person - QSR
label | Specification Reference - CQMP
label | Acceptance Criteria - All applicable quality records are complete
label | Test Method - R
label | Test Frequency - PL
label | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | Inspection/Verification (Name, signature & date): IREA - NR
label | Records/Documents - Compiled documents (all data reports and records)
holdpoint | AUTHORITY HOLDPOINT