## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
a89d80df-d40a-59b8-b3c4-4089f5c635db | checklist | SYS - ITP - Pavement & Surfacing - AP40 Material - Rev 1 | itp | ITP - Pavement & Surfacing - AP40 Material - Rev 1
624c9523-567e-5961-bcbb-c2696781b917 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
b0529998-93c5-5453-a2e5-2c44366e9f2c | checkpoint | 2.01.01 - Basecourse CBR
dbbd429c-71bb-5812-85da-dcc9a18eedc9 | note | Acceptance / Conformance Criteria - (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand Vibrating Hammer Compaction Test at Optimum Water Content and;
a371278e-8f76-5b57-b0e1-d6b44c03d6d2 | note | (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
b40b0852-21dd-5607-a013-f8e6812c5725 | note | Standard / Specification - TNZ M/4: 2006
8ead24d5-9c8f-5d9f-b807-27ff02162e82 | note | Verifying Document - IANZ Lab Reports
030068ab-38a5-5036-82f6-7ac7a7c1bd1e | note | Frequency - 10,000m3
659025bf-5cfa-55f8-856f-5b915f8d83d3 | note | Activity - HP
a35891e0-edbc-595c-9be3-8427f6ef9c14 | note | By - ENG
29ed9ccb-712c-50ab-9d42-c0fd44745cb4 | signoff | AUTHORITY HOLDPOINT
b837b78b-b0a4-557a-8a87-e178b07b8903 | checkpoint | 2.01.02 - Running Course Material Approval
9fb00a71-854c-50c7-beeb-d555fad763b0 | note | Acceptance / Conformance Criteria - The running course shall have a crushing resistance of not less than 130 kN when tested in accordance with NZS 4407: 1991, Crushing Resistance Test, Test 3.10. It shall be free from all non-mineral matter.
d7dcc15a-3087-5bd3-8abd-001433a8da70 | note | • The grading of the running course shall conform with Figure 3 of TNZ B/2:2005, 10.2, when tested in the same manner as required for the parent basecourse. (IF USED)
9938c1d4-af1e-54ec-ab05-56cbfcbe7dab | note | Standard / Specification - TNZ B/02: 2005 - 10.2
97c4a02d-759c-5772-a5d0-568ae3601e2a | note | Verifying Document - IANZ Lab Reports
667eba4a-5457-54fb-b177-accc707507cc | note | Frequency - 1 test every stockpile
02b79946-e421-55fa-8f12-ece77e587346 | note | Activity - HP
2f400810-37b2-5c86-8734-bfb55b54c3d5 | note | By - ENG
694bbc49-b523-5ff7-a549-6e3e5d78408f | signoff | AUTHORITY HOLDPOINT
548ad985-2ecf-52ce-8844-2be0a9fd6e9f | checkpoint | 2.01.03 - Basecourse MDD and OMC
92929d68-63f0-57fb-ac65-531cb6e97659 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test on heavy compaction, vibrating hammer.
7ae1ef54-9208-5e9a-9fa2-285c104c3707 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
80a36b75-0644-57d6-b71a-01cbf8adf488 | note | Verifying Document - IANZ Lab Reports
1c6e177a-3638-54ba-b5da-acd2905a56f3 | note | Frequency - 1 test per material type
23d37c95-78a9-507c-934c-2f3070031b71 | note | Activity - H
45af7d7f-9458-53aa-8eec-57f4e7c57ee8 | note | By - PE
75ece572-d277-549f-97f5-9d2eea646d14 | checkpoint | 2.01.04 - Crushing Resistance
e71f59ac-edd0-5e70-beca-82c70dca5b37 | note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
b86b747b-e06f-56e2-b657-241efaf003a0 | note | Standard / Specification - NZS 4407: 1991 Test 3.10.
c489a8b1-a8ea-5f82-80ba-4ff4eded1c9a | note | Verifying Document - IANZ Lab Reports
d0adc64e-bcd5-5457-86b4-ec52e3ab0aa1 | note | Frequency - 2 tests per source 4 weeks before use in the works
90bd30ec-e53e-5268-94dc-d9959a20dc19 | note | Activity - HP
a78cabee-87cf-590d-9de2-bf174b81ae9d | note | By - ENG
a003c3fc-8627-5101-be25-bc6c38bfe92a | signoff | AUTHORITY HOLDPOINT
4b4fe5d4-91f3-5027-a33b-636e1248f7a0 | checkpoint | 2.01.05 - Weathering Resistance
3a8afc40-bfb2-549a-9089-5e6cbffcfc0d | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
18e72bbf-5f3e-5c0a-b3e4-b741b323ed91 | note | Standard / Specification - NZS 4407: 1991 Test 3.11
2cfd3280-099b-589e-b0ad-7f3ef4136fe4 | note | Verifying Document - IANZ Lab Reports
f2948c97-c966-5ad9-a79d-7bcb312db057 | note | Frequency - 2 tests per source 4 weeks before use in the works
3d3935ec-fb55-5601-bae8-b23d5ec8039c | note | Activity - HP
512ba664-826d-5b63-aede-02a1b8d62ee4 | note | By - ENG
0755029e-495b-5e5b-9bc5-ce9ec5b00d8a | signoff | AUTHORITY HOLDPOINT
1be2a772-ef73-5a20-9f7b-ff55584b77db | checkpoint | 2.01.06 - Particle Size Distribution
e166ae74-624b-5e5b-8d9a-3a8218aff852 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
de055241-e1a2-5d0b-af5e-54efa88d6216 | note | Standard / Specification - TNZ M/4: 2006
3bcda7c7-cfe0-5d4e-9e67-ea1bf377c756 | note | Verifying Document - IANZ Lab Reports
c0544496-3ce2-5232-addd-e6938e540abe | note | Frequency - 0 to 400m³ - 2 tests
95f11bf1-a8e0-5084-9d61-adb3d2756506 | note | • 400 to 1,500m³ - 3 tests
a9ad710d-e165-5ea8-9e4a-195b132d5d53 | note | • 1,500 to 4,000m³ - 4 tests
dc69b47a-7de9-58a0-8dc6-5dfc49859c1a | note | • >4,000m³ - 1 test for each additional 1,000m³
9a56c638-031b-545e-9eb5-c0d4183f3245 | note | Activity - HP
282114fb-13aa-5084-ab72-3c09c1f08c61 | note | By - ENG
78a21ef1-b7d3-5597-95ee-fba52abdc91d | signoff | AUTHORITY HOLDPOINT
2c48e4c6-f0da-570a-b0f9-774b3da00b3c | checkpoint | 2.01.07 - Sand Equivalent
dc243aeb-782c-5f73-b035-5d90192571f4 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
b0c97723-290e-5e45-b606-54c180dd52e6 | note | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
c9462b1e-4a16-5f8f-a838-4b695ad099c3 | note | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
de976264-2028-5f1e-8b40-58405ee4b2d9 | note | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
b5a313f0-8f07-5136-8235-a6fc300ace71 | note | Verifying Document - IANZ Lab Reports
b094c546-d0d7-50d0-91ac-5751b343c6f2 | note | Frequency - 0 to 400m³ - 2 tests
63050626-6c95-5026-82a3-995cfa0ad37c | note | • 400 to 1,500m³ - 3 tests
11d0194c-7dd2-5a24-ba3b-3914d16c2c9c | note | • 1,500 to 4,000m³ - 4 tests
5075cb26-5316-5c35-b943-3c3389df5642 | note | • >4,000m³ - 1 test for each additional 1,000m³
eb21c904-de19-506e-a6d7-a5f4bfdd9438 | note | Activity - HP
17607f79-1af7-545b-97b2-a7dccc8a076a | note | By - ENG
b7f2b347-0e8d-5e6f-b844-c75eb8ea8162 | signoff | AUTHORITY HOLDPOINT
454d072b-71d1-59c6-b531-512bf3793c41 | checkpoint | 2.01.08 - Liquid Limit
8450682a-d54d-54ca-a371-5bb0648b9165 | note | Acceptance / Conformance Criteria - The Liquid Limit shall be ≤ 25 when tested in accordance with NZS 4402 Test 2.2.
8e0dcf5b-a8df-5f00-b697-e5b4bce57cf6 | note | Standard / Specification - PS - 7.2.3
b8033767-e17d-51ab-bb92-a013d34318a7 | note | Verifying Document - IANZ Lab Reports
bab4c537-af20-54f8-af38-8deb39ed41a2 | note | Frequency - 0 to 400m³ - 2 tests
278f4a50-e7d8-5134-80fb-5ad235f4576a | note | • 400 to 1,500m³ - 3 tests
3423ebfa-0c74-5182-b8a1-5bd4e9ada4e3 | note | • 1,500 to 4,000m³ - 4 tests
9fa9f428-e6a4-5101-a662-97844c9a622b | note | • >4,000m³ - 1 test for each additional 1,000m³
e0e7bccd-4b87-5d6c-9289-5819baf1887c | note | Activity - HP
4870641c-355e-51da-897b-78e73a111d11 | note | By - ENG
e812b52f-9fe9-518a-8788-a0160c62bc55 | signoff | AUTHORITY HOLDPOINT
16ce7ace-e77c-5302-99e6-731cd605e2a3 | checkpoint | 2.01.09 - Plasticity Index
aa160684-d90c-5c2f-8670-9c7345013797 | note | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
6fd83484-45a3-58f8-9dfb-7c1c0a96d94b | note | Standard / Specification - PS - 7.2.3
96340ffb-3e65-5eac-96b6-68c84daeac5e | note | Verifying Document - IANZ Lab Reports
baf33aa0-13cb-5856-9ee2-6358746e87ea | note | Frequency - 0 to 400m³ - 2 tests
c7ebfe0c-56a3-53c5-927d-4715673a2ac2 | note | • 400 to 1,500m³ - 3 tests
2e63751b-2609-5a3d-a6ec-0035cf8985f6 | note | • 1,500 to 4,000m³ - 4 tests
c3006d0d-325f-559f-a85a-fbdb8b8bf5d4 | note | • >4,000m³ - 1 test for each additional 1,000m³
d3e0e39c-c80d-5977-892a-84f380b69882 | note | Activity - HP
ad281e7d-78b9-5e34-a2bc-d46572f79532 | note | By - ENG
8068389f-81b5-5e5c-add9-417418b5ff36 | signoff | AUTHORITY HOLDPOINT
52a5e716-c19f-5ad8-8370-8bbc35daeeb5 | checkpoint | 2.01.10 - Clay Index
9d5e3f97-39f7-5393-8985-e46df7d9353c | note | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
9e6d2939-557c-5f76-9ccd-0aaf26976c71 | note | Standard / Specification - PS - 7.2.3
e2d3939b-60a7-5161-99e9-c40aa73acc53 | note | Verifying Document - IANZ Lab Reports
a9885a41-188f-5625-9424-581588ef206f | note | Frequency - 0 to 400m³ - 2 tests
c2a0b25b-48f3-5d30-9933-3bc05f48181c | note | • 400 to 1,500m³ - 3 tests
a5393c6e-4bf8-5dc9-b8a0-9fe9bf6779f0 | note | • 1,500 to 4,000m³ - 4 tests
952ea3f9-ef8c-55ac-9a0c-f75ebc319466 | note | • >4,000m³ - 1 test for each additional 1,000m³
0b7ea872-5971-5448-acee-b363c516d9bc | note | Activity - HP
090588ed-6242-57a0-b608-4e8b82de9a5a | note | By - ENG
37c9d3b1-676e-5e35-87a1-efb852bd8594 | signoff | AUTHORITY HOLDPOINT
3243bdbe-628e-5c36-8ebd-fd3becd9b18b | checkpoint | 2.01.11 - Accelerated Weathering Testing
c54a8880-c803-53c9-905e-907270e1e49d | note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
4f2614cf-5d0f-5220-b839-2250b118dac0 | note | • The levels of smectite clay minerals are not classified as “abundant”
0a07615c-bdc7-587d-93e7-0fa6ef846f00 | note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
509cb0c4-b4c6-5133-83a7-abddb21b59b5 | note | Verifying Document - IANZ Lab Reports
8546fa8e-8880-5859-9034-8b5f93cc0f54 | note | Frequency - 2 tests per source 4 weeks before use in the works.
88f457ae-d9e2-5dda-96de-604c02b89acd | note | Activity - HP
1b214982-fb22-5d0e-ad43-16521eead8bc | note | By - ENG
6ab4e183-98ed-530e-bb16-371ac278c73f | signoff | AUTHORITY HOLDPOINT
d0430dca-b283-5720-b469-62a57fdf94d1 | checkpoint | 2.01.12 - Repeat Load Triaxial Test
b4a7ebbb-018c-5af9-9c36-b41eb6e36384 | note | Acceptance / Conformance Criteria - In accordance with NZTA T15
a908229c-118d-555b-8caa-30536f9ea3d8 | note | Standard / Specification - NZTA T15
2a799e2e-2862-583b-9ee6-f85293c43566 | note | Verifying Document - IANZ Lab Reports
f7bac258-a191-5284-b56a-383259c8f3bc | note | Frequency - 2 tests per source 4 weeks before use in the works.
b45a69e9-5f6f-5327-84db-99e2e8e8e8ac | note | Activity - HP
d88b2f97-bb88-5415-8669-2314cddde2d5 | note | By - ENG
740b30b9-cfca-5337-a89e-aca4c87f0759 | signoff | AUTHORITY HOLDPOINT
fced821f-9140-5acb-adeb-311c37d3b39f | checkpoint | 2.01.13 - Broken Face Content
5c67f160-a2f0-52f8-bd42-ca23ee461ed7 | note | Acceptance / Conformance Criteria - The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407: 1991, Test 3.14 Broken Face Test.
ea889ddb-0e1d-5c83-bc77-c98178a4b221 | note | Standard / Specification - TNZ M/4: 2006, 4.2.2
9c527da4-f334-5def-9908-16581146a1d7 | note | Verifying Document - IANZ Lab Reports
12ebf109-2be6-5908-ab45-7c266f20332a | note | Frequency - 1 Test per Source
11e72989-7bc6-5b31-9135-f0d7b62160fe | note | Activity - HP
888d745c-7ad7-5f0a-9f6e-38e8a8b6c5ca | note | By - ENG
a3df93d1-6c56-587a-86a1-2946c4363d06 | signoff | AUTHORITY HOLDPOINT
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
| textbox | Contractor's Rep Name:
| textbox | Engineer's Rep. Name:
| date | Date:
| signoff | Add Signature
03635e0c-99d6-5d68-b693-2154f48da3fd | checklist | SYS - ITP - Pavement & Surfacing - AP65 Material - Rev E | itp | ITP - Pavement & Surfacing - AP65 Material - Rev E
d9ad54c1-a038-5152-8598-fb6c422dc437 | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials
60a57887-488e-553a-9235-dee549dad0fa | checkpoint | 5.01.01 - Sampling and testing
f168b349-b948-59e0-834f-0b2ba45e5df5 | note | Acceptance / Conformance Criteria - For all aggregates, test information confirming compliance shall be supplied to the Engineer not less than five working days prior to delivery of the material to site.
94791044-7035-5d70-836b-5bd471f60add | note | Standard / Specification - PS - 7.2.4
72003631-2a30-59ed-9ccd-8bb41b9e6939 | note | Verifying Document - IANZ Lab Reports
a294e292-acfa-5d4d-8bb2-ac429ec82d86 | note | Frequency - five working days prior to delivery of the material to site.
f3890077-fa2d-5c9d-ac37-159c3531b5d4 | note | Activity - HP
a55f805a-3e05-57ce-9887-0771a0f2e46b | note | By - ENG
def14926-a024-5a92-85d5-c6280e455630 | signoff | AUTHORITY HOLDPOINT
44bbb52e-eb08-5fb4-9a98-c4769a88e409 | checkpoint | 5.01.02 - Sampling and testing
1a02b294-b8c7-54a8-88ad-4b2eadf677b4 | note | Acceptance / Conformance Criteria - Water to be used in stabilisation - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening, strength or durability of the bound aggregate layer.
de15fba3-2af3-5447-92e4-0ff93b28081b | note | • Water from sources other than public supply may have its suitability established to the satisfaction of the Engineer by repeating the final approved laboratory based mix design tests with the water now being considered for use.
c8b38c01-7756-58f6-b0f0-b99d29d920dc | note | • The results of these subsequent mix verification tests shall be greater than 90% of the final results from the previously verified mix design. In addition, work shall be stopped if any discolouration or residue is observed when adding or sprinkling water into or onto the material.”
bfa862fa-eabc-5114-9532-f6da19c44f1a | note | • Verifying documents to be dockets from fill up station, or proof of using public water supply. Or Lab reports for alternative supply.
bb7cea44-7b13-513c-8a99-abf001a2a74e | note | Standard / Specification - NZTA B/6 item 5
eadf6b0e-0f1f-54ef-b126-27840805effb | note | Verifying Document - Lab reports
2e2bf3d8-49b0-592e-bc51-775d11041343 | note | Frequency - Prior to Works start, per source
2b4890f2-3351-5dd2-ae9a-5f9515c05422 | note | Activity - HP
80f049ce-3bc5-58f0-8bd7-7c9c9d3deeeb | note | By - ENG
9e0439f0-b29c-5ad6-b128-ee827b0bc0be | signoff | AUTHORITY HOLDPOINT
899bfcc4-56fb-51f7-a6a0-b3bf3866f97d | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate
dcf4666f-ed3b-5158-a808-679d32a007f3 | checkpoint | 5.02.01 - Sub-base MDD and OMC
c9ddb8f7-8811-5c24-a98e-4a7b7bde9d00 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
da0f5c1e-3efd-569f-b2ef-0d62230cc56f | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
503a87ad-53dc-5338-b7d6-41d39018bdad | note | Verifying Document - IANZ Lab Reports
4b686472-ead5-5dca-9e19-e1a7af89afd6 | note | Frequency - 1 test per material type
cb4be3d2-1fc8-5f91-99ab-ff9da052c5f2 | note | Activity - H
abad576a-df96-543f-9ab1-765a1ff468b2 | note | By - PE
08dc85f6-1e83-5eb9-95c8-9381d1b2b315 | checkpoint | 5.02.02 - Cement for sub-base stabilisation
f2cfb2e7-40b5-5204-868e-224c0ffe7c5f | note | Acceptance / Conformance Criteria - Cement for stabilisation shall meet the requirements of NZTA B6.
7b7caba1-a9c4-5c5d-a3af-5fea17a64691 | note | Standard / Specification - PS - 7.3.2, PS - 7.2.6
1ac5d31f-9758-50ae-9f72-48d864679110 | note | Verifying Document - Datasheets
9af7f4d5-44b2-586a-b84d-14083db10bdc | note | Frequency - Prior to Use
703a7061-48ec-50a2-bf67-28fd4c8b61f9 | note | Activity - H
3ecbad6b-6769-52d3-8371-9bae9e3e68bc | note | By - PE
78ae2b7a-c28e-5b57-a046-1fdb2eff521d | checkpoint | 5.02.05 - Crushing Resistance
aaf3fcc6-69cf-5107-bdd2-324afb462409 | note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
32d89166-cc92-5257-8a02-b42deb788bcf | note | Standard / Specification - NZS 4407: 1991 Test 3.10.
fc6cde74-b4bb-53b0-8942-0552487547d2 | note | Verifying Document - IANZ Lab Reports
835b815b-b849-51c9-8abc-91b75b5897e4 | note | Frequency - 2 tests per source 4 weeks before use in the works
10b65111-54b2-5545-b5b5-be46c4838f88 | note | Activity - HP
c72f6072-5eca-5743-b96b-117fc11d2cf9 | note | By - ENG
fefe6c68-50e3-5203-b081-fc14cfcc29be | signoff | AUTHORITY HOLDPOINT
9022871e-5b68-5285-8105-45564ce8225d | checkpoint | 5.02.06 - Weathering Resistance
b85e3249-9895-5172-a001-1466f4265669 | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
1ee3589b-5081-5efc-bdad-6aba26d6e9a5 | note | Standard / Specification - NZS 4407: 1991 Test 3.11
a3776b5d-7d91-53eb-bb08-1af17fb325a2 | note | Verifying Document - IANZ Lab Reports
3b65390a-1386-58dd-8d6a-5e763cde91a7 | note | Frequency - 2 tests per source 4 weeks before use in the works
88a73c18-536b-5f46-bb46-d7b80e90b423 | note | Activity - HP
83e5610e-6576-5395-a4fa-7274e96a60c7 | note | By - ENG
8d6baafb-7a8d-5d80-9269-13464595db51 | signoff | AUTHORITY HOLDPOINT
85ee47d1-ad42-5e77-9b51-b0b7d10ea380 | checkpoint | 5.02.07 - Particle size distribution
4892293b-c97e-5f7b-8af6-863f1c449d64 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1.
b82eadfd-0943-56e1-8a03-094e7c34f50c | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
3551a47b-12a0-5a1a-8ea5-7b63cff98b4c | note | Verifying Document - IANZ Lab Reports
8251bbf9-5e57-58ad-aee4-43bbe9f37c78 | note | Frequency - 0 to 400m³ - 2 tests
a4146f77-cb32-5f0c-9c04-6338cd5be9c9 | note | • 400 to 1,500m³ - 3 tests
21f6550a-d45f-508e-b98b-d3e37a65df52 | note | • 1,500 to 4,000m³ - 4 tests
331f9d0f-783e-5e9f-b806-2a9a12477903 | note | • >4,000m³ - 1 test for each additional 1,000m³
2f965ecd-3d80-5c1e-b02f-bacb5b4dbeb4 | note | Activity - HP
75b5399a-dc99-5dfa-963c-e1fb07b29c37 | note | By - ENG
129b8835-7d77-5545-af8f-f202ea555b78 | signoff | AUTHORITY HOLDPOINT
c0dcf9e2-6abe-544f-b671-04d7121ee831 | checkpoint | 5.02.08 - Sand Equivalent
04e2ce5c-fc23-51ac-b996-8b395cb81ee1 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 25 when the aggregate is tested
c79417a1-d3da-5554-8196-a20418d2f028 | note | Standard / Specification - NZS 4407: 1991 Test 3.6 (Wet Method)
be91c280-43e7-5a2f-b532-dea6df56a8d0 | note | Verifying Document - IANZ Lab Reports
7ce457fc-836f-5cc6-a269-ba8371d1833a | note | Frequency - 0 to 400m³ - 2 tests
84a096bf-3ee3-5f72-a1d9-f550bc29364f | note | • 400 to 1,500m³ - 3 tests
038c979c-acff-5c79-bdf8-95a17d456d70 | note | • 1,500 to 4,000m³ - 4 tests
25a6b6d3-0568-511b-98c0-be8b869b3e71 | note | • >4,000m³ - 1 test for each additional 1,000m³
80588976-67d6-54ca-9d40-618b6fdcc383 | note | Activity - HP
04ab84ac-2b34-54a7-83a8-ae3a2671554f | note | By - ENG
1cfc74a4-63e3-58ba-a4fb-88a40554c1c8 | signoff | AUTHORITY HOLDPOINT
ae882592-6535-5217-89b2-b66f7d161cf7 | checkpoint | 5.02.09 - Liquid Limit
57abe783-f1ed-53d3-84cc-34e27300e213 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested - The LL may also be inferred (where appropriate) from the Cone Penetrometer Limit (CPL).
f3e06d3b-2107-5ca4-ab1d-8e980c44d108 | note | Standard / Specification - NZS 4402 Test 2.2, NZS4407:2015 Test 3.2.
b91bd336-8e5c-532c-ad9d-fea08ac6590e | note | Verifying Document - IANZ Lab Reports
46a082e0-947d-55f6-9700-208f12e701e9 | note | Frequency - 0 to 400m³ - 2 tests
b0e66bd0-e4af-5d26-8d47-bf34fe7b8ca6 | note | • 400 to 1,500m³ - 3 tests
7b9507c3-415a-57b6-ad99-2fa7d63f6ca9 | note | • 1,500 to 4,000m³ - 4 tests
6508a44f-453c-5a9b-9892-a3c9a4715ac5 | note | • >4,000m³ - 1 test for each additional 1,000m³
af0c1297-5477-5cdc-8dd4-ebec258aa331 | note | Activity - HP
ad6cdfd4-a91c-5346-8f1d-c169cd1087b2 | note | By - ENG
523797f1-355d-5b2b-98ca-c9f9f751c1cd | signoff | AUTHORITY HOLDPOINT
a21cc376-5cf7-5d74-91c9-7c1733c3fd7d | checkpoint | 5.02.10 - Plasticity Index
2de608fd-6034-5977-8b48-ace7c120a2de | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
c076cd42-6e8e-5b46-a0df-e078704d7870 | note | Standard / Specification - NZS 4407 Test 3.4
f288a3ff-d1e2-5f20-920c-7fa4a3abc914 | note | Verifying Document - IANZ Lab Reports
f0c423cb-1eba-5011-80ac-05005e695439 | note | Frequency - 0 to 400m³ - 2 tests
35184592-ddea-5789-9628-76295e981225 | note | • 400 to 1,500m³ - 3 tests
5948452b-0aae-5278-993c-de000a64b387 | note | • 1,500 to 4,000m³ - 4 tests
937a1689-6e30-514e-b5a1-1790273f2d37 | note | • >4,000m³ - 1 test for each additional 1,000m³
1854c9f6-3b9b-5c63-82e5-a9666a9dd2a2 | note | Activity - HP
fc35ac17-93f1-5400-aa20-a74b5557447b | note | By - ENG
5196aee7-d9f1-55aa-b012-a6ce06f7ee5c | signoff | AUTHORITY HOLDPOINT
cb3bf6ca-20c8-5a7c-847e-d41f73e602ed | checkpoint | 5.02.11 - Clay Index
7dcc80a1-3999-5c00-bfc3-bf293b8a8647 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
cf25e97d-2159-5462-a6ce-4196b9d4293a | note | Standard / Specification - NZS 4407 Test 3.5
3b2b548d-399e-519d-9d69-9a2927c0b6b1 | note | Verifying Document - IANZ Lab Reports
5303e7de-4445-5c0f-9266-790d456b0644 | note | Frequency - 0 to 400m³ - 2 tests
de272e7d-a2c4-580c-9190-796fa51c3638 | note | • 400 to 1,500m³ - 3 tests
ca2a2111-0158-5182-be1b-445174fedcb3 | note | • 1,500 to 4,000m³ - 4 tests
70cecf18-9657-5d43-bafb-b89341c01cc6 | note | • >4,000m³ - 1 test for each additional 1,000m³
b7dbf86f-bc15-5ca8-aa3a-7e41cd34899b | note | Activity - HP
b985f042-7de4-52a8-b779-c1e47281412f | note | By - ENG
94cd9054-2ac2-5d95-86eb-2a71edade0c7 | signoff | AUTHORITY HOLDPOINT
00a049c7-fa08-5eaa-a1c1-4286cf25b2b3 | checkpoint | 5.02.12 - Proportion of Broken Rock
8f8865c0-7ffc-5b16-807d-503d621cbc5a | note | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves not less than 50% by weight shall have two or more broken faces
cf749d9a-5bf1-50bf-a203-7e3c464d3673 | note | Standard / Specification - PS - 7.2.2
aa34d7ad-4e05-5677-b27c-5f6f1411f00b | note | Verifying Document - IANZ Lab Reports
69f6c763-0a03-51d9-bfa5-534ccacaf6ef | note | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
d91ec8a3-6ce2-52e2-80f0-1b03438f13ee | note | Activity - HP
87e701c1-161f-5285-9b2e-cd20ebb3e36d | note | By - ENG
4fac71dd-be3d-5be6-a8e7-ade3236dd1f1 | signoff | AUTHORITY HOLDPOINT
b87390da-e8b4-5066-b43c-5d098cda23ee | checkpoint | 5.02.13 - Organic Matter
da3f72b4-b1e3-5657-808e-2bc54fe47d04 | note | Acceptance / Conformance Criteria - It shall be free of organic matter
24f9b6df-5b16-5895-9f6b-b49960501d8d | note | Standard / Specification - PS - 7.2.2
94fee484-a5b3-5490-bb40-6bf4b0938f69 | note | Verifying Document - Photos
99cdf68f-0152-5f34-b1a5-3760076113bb | note | Frequency - Continuous
7ddb2bae-c964-5cf3-8183-009d7060c3bb | note | Activity - I
1cfad76f-afa0-56a5-94e6-cd4c58e6b657 | note | By - SE/PE
cafccf67-d4a4-52ce-86ca-59031142aa61 | checkpoint | 5.02.14 - Accelerated Weathering Testing
201f6146-1817-5edb-a22c-c29f7f45f2a0 | note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
f17dd1db-7f20-5312-b139-97755128b80c | note | • The levels of smectite clay minerals are not classified as “abundant”
749b65f8-ccd4-520b-90d3-1e9fdbd250c1 | note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
6586c6f9-d9c7-524c-beaf-40df78cc4131 | note | Verifying Document - Lab Reports
914cde35-1363-5dfb-920a-556fed6e74b9 | note | Frequency - 2 tests per source 4 weeks before use in the works.
658e3f08-7984-52e5-8b16-f6fa47795fdf | note | Activity - HP
225138d5-1d17-52dd-9634-c4b08fb236a4 | note | By - ENG
4fc46efe-5434-5360-aeea-81ccc050ba8c | signoff | AUTHORITY HOLDPOINT
52a5baa6-7252-5829-85ae-9f01011c7607 | checkpoint | 5.02.15 - Repeat Load Triaxial Test
46b9f88e-99c9-5a60-a968-15cc96292ceb | note | Acceptance / Conformance Criteria - In accordance with NZTA T15
8f09f694-78a6-5532-93a0-59f7ad96ba2a | note | Standard / Specification - NZTA T15
4afa3e59-c79c-5e6c-b5c5-86d8c9c5c9b0 | note | Verifying Document - IANZ Lab Reports
2be0fa1c-b437-5b11-a13e-69e22b6f8b08 | note | Frequency - 2 tests per source 4 weeks before use in the works.
ce80a921-3335-5a15-a8f6-c9b7326838fd | note | Activity - HP
5f9d6dc1-3b64-5181-89c5-19a73f488add | note | By - ENG
44646cc1-0805-5206-8ff2-ad2805cd38d2 | signoff | AUTHORITY HOLDPOINT
0b3c41da-9864-553d-886c-e0e0f1bdd386 | checkpoint | 5.02.16 - Unconfined Compressive Strength (UCS)
decd180e-26e7-56c8-a3c1-c00f8720c9e0 | note | Acceptance / Conformance Criteria - Unconfined Compressive Strength (UCS) testing of source aggregate for modified layers to test sensitivity to additives.
c865ae35-c13e-5881-99c9-18bc78a225a6 | note | Standard / Specification - PS - Table No. 7.2
f64e7a3a-7098-52be-8784-a85fae85996e | note | Verifying Document - IANZ Lab Reports
177e1bb7-f470-50c1-bb79-20e420d6426e | note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
f69b2107-9d61-5d1d-afc0-990e1ee682b7 | note | Activity - HP
572e474c-67c5-55ad-aa87-750d7a624c7e | note | By - ENG
03cf8542-b3b1-5080-a4b3-84858ca10066 | signoff | AUTHORITY HOLDPOINT
74060e22-bf57-5ae1-9306-20409b4430fa | checkpoint | 5.02.17 - Indirect Tensile Strength (ITS)
9a4fb5ed-bd27-535b-a022-bebf285b6004 | note | Acceptance / Conformance Criteria - In accordance with draft NZTA T/19 at the rate specified in Table A7.4 using 4.0%, 4.5% and 5.0% cement (with 7 days curing) and results forwarded to the Engineer not less than 7 Working Days prior to construction for confirmation or adjustment of the additive contents.
00eb80fa-3200-5417-b532-c46d18a37a6a | note | Standard / Specification - NZTA T/19 - Table A7.4
c1e6242b-b982-5e22-a725-33ef54319773 | note | Verifying Document - IANZ Lab Reports
d2116d61-7adf-57d3-8106-1c51336749a8 | note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
a2dcec01-55c7-552c-b0b0-ddc1a435ae63 | note | Activity - HP
ca9469bb-b5fa-592e-b002-a0f30567b1c6 | note | By - ENG
69dfb56e-21ee-5ddd-a6dc-cf1b2b495b33 | signoff | AUTHORITY HOLDPOINT
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
| textbox | Contractor's Rep Name:
| textbox | Engineer's Rep. Name:
| date | Date:
| signoff | Add Signature