## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Prefix
ce89e2c3-92c3-4532-b5c5-8bea55f7b656 | checklist | Commissioning Document |  | Commissioning Document
b152ee0e-78f6-4d21-b800-3748af9cb859 | checkpoint | Please attached commissioning document and pictures
2a9628d4-038f-5ea7-b387-0074ac866db3 | checklist | ITC-001 DUCT ROUGH IN |  | ITC-001 DUCT ROUGH IN
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
ab71e213-f13e-5103-8d87-5f3e61a64b6b | checkpoint | Installed to Entire standard (ENT-STD-3.1) and to latest drawings
6ecf71b4-7c6b-5dd2-bac5-c1af4af1361e | checkpoint | Cleats installed
bcd797b1-534a-5337-baa5-fe969652e445 | checkpoint | Insulated as required
482ee3db-6f04-5363-98cd-6ee38c5efd5a | checkpoint | No visible damage
d2eb3452-7078-50f4-96e3-b54548749662 | checkpoint | Flex Supported to Entire standard (ENT-STD-1.1)
88be402d-1dca-535a-bd99-a07ab43d3221 | checkpoint | Seismic restraints installed as per Seismic design
bfdf87bd-ebe0-5c3b-9db1-6bd249c357f5 | checkpoint | Fan Coil Units installed as per the latest drawing
6c551f67-8816-51d6-bd5c-e919ba49e4b6 | checklist | ITC-002 PIPE ROUGH IN |  | ITC-002 PIPE ROUGH IN
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
93a545e7-7502-5b0b-abe3-b8c7cbbedb7d | checkpoint | Pipes installed to Entire standards and latest drawings
ec0ea9ab-2cda-5276-830f-1440f9463de1 | checkpoint | Hydrostatically tested as per (ITC-010 & ITC-011)
b60ae240-d6b9-5efe-965b-7776041f68b8 | checkpoint | Pipes insulated as required
88be402d-1dca-535a-bd99-a07ab43d3221 | checkpoint | Seismic restraints installed as per Seismic design
30064092-46b7-5000-9ea0-c34a67b786ee | checkpoint | Drains installed to standard & on correct grade
aa0a2940-2cbd-5140-b7a0-c960562d7dd8 | checkpoint | Refrigeration pressure test as per (ITC-013)
1abbab8e-4156-505d-93ea-e75858a881f2 | checklist | ITC-003 Floor Fit Off |  | ITC-003 Floor Fit Off
52f837fa-499b-580f-b260-d2391770aaa4 | section | Grilles
a5db1d62-4e31-573f-80a5-65e6754a8061 | checkpoint | Installed to latest drawing
c3616b25-490e-5de4-a053-924be04470b1 | checkpoint | Balancing dampers open
482ee3db-6f04-5363-98cd-6ee38c5efd5a | checkpoint | No visible damage
6e23c08a-9180-5c70-8ab6-c8e267a66798 | section | Filters
cd19ea75-cb3d-4a76-a56e-ae9e72f134bd | checkpoint | Installed to latest drawing
c31b2cba-b937-5613-8bfa-f7818b88cd0a | checkpoint | Accessible
56377b54-fde7-5406-837c-3890686afe74 | section | Equipment
3d3ab952-0804-5813-987f-f1f38d2b8dd5 | checkpoint | Access panels in correct location
b9b4166f-f76e-5c2b-ac76-7cf5ceca3ed4 | checkpoint | Equipment clearly labelled
b2a0f432-8835-5bfa-9492-c7e58c49e2e9 | checklist | ITC-004 Penetration Treatment (sign off by relevant sub contractor) |  | ITC-004 Penetration Treatment (sign off by relevant sub contractor)
9cac26a2-4c4f-516e-a752-7613e04a3b30 | section | Penetrations
ff9e7d34-42c4-51f8-b23d-385909560d4f | checkpoint | Acoustic penetrations correctly sealed
9481689d-18b3-5213-a396-16c7e79ad882 | checkpoint | Fire Penetrations correctly sealed
3f9eca7d-068a-58c2-93ff-3e88e60cff2e | checkpoint | Photos and documentation captured by contractor
dc3db1bd-2d96-555b-b25c-facbaaecd07a | checkpoint | Penetrations labeled as required
243a68e5-3acb-54f4-b104-af708e3d24ef | checklist | ITC-005 Equipment Installation ADMIN ROOF Plant Room |  | ITC-005 Equipment Installation ADMIN ROOF Plant Room
79926eb8-0713-549e-a7ff-63174b2831f0 | section | Fans
e043fca1-1f36-5453-83f9-b60661a3cac9 | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
2342da2f-67d4-52a4-9ef6-49f9bca13f78 | checkpoint | Vibration isolations installed
395bd320-3a36-5f01-bd01-09adc7188acc | checkpoint | Seismic restraints Installed as per Seismic design
7a23791a-a1b0-56d2-ad21-35cae509487f | checkpoint | Labelled
7e8d519d-4dbb-5d69-814c-a1718257632d | section | Evaporative Cooling Units
1f0bae44-15aa-4509-9e0d-f5e6e3abd116 | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
cf5354f5-1c7f-446e-99ad-312dcdc13985 | checkpoint | Vibration isolations installed
bf2c2dcc-f61c-4880-acf8-1f12b7a66483 | checkpoint | Seismic restraints Installed as per Seismic design
ae9b26b3-400d-59b2-97a1-fca7a1834e07 | checkpoint | Unit clearly labelled
0c690b81-cef6-5dc3-bd78-1a348b80d67f | section | DX Split Systems Condensing Units
a598bcae-539a-4605-b258-61da161bdfe2 | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
4870d417-2683-4821-b4aa-076f2c990c63 | checkpoint | Vibration isolations installed
b9807ee7-8f6e-4ff1-a4fc-3b5e3eeaa211 | checkpoint | Seismic restraints Installed as per Seismic design
0f4f78f2-1691-551d-b649-f875f2598a98 | checkpoint | Units clearly labelled
868e96ec-e9bd-59df-8e72-b7257d0a497d | section | HEAT PUMPS
67cb47cd-ec5b-4b2b-863c-727b15fa05a6 | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
eac5a202-bbc9-4991-9c6f-f79259310d86 | checkpoint | Vibration isolations installed
50f44f08-5d93-4eda-97a8-5628baef025e | checkpoint | Seismic restraints Installed as per Seismic design
3de1c248-8c56-49a1-995e-246abf207137 | checkpoint | Units clearly labelled
813d5a05-1aff-57c5-adef-b5cfa1e4918a | section | Pumps
4b704374-f03a-420d-b60f-cbd9f180f2fd | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
bd32f67e-55fe-4442-a604-0f1b962aa8f0 | checkpoint | Vibration isolations installed
af3ce586-2c8b-4573-a202-af8293f55db7 | checkpoint | Seismic restraints Installed as per Seismic design
89b474b5-be43-4ae0-99aa-0e5acd17585d | checkpoint | Units clearly labelled
7c3b96a3-5273-570f-96eb-b1cd0e2c5abc | section | Buffer Tanks
1070407c-0199-47e2-b5a7-884a53c820c6 | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
11428864-844a-482a-ab48-eecebbe750e9 | checkpoint | Seismic restraints Installed as per Seismic design
396095bb-92cf-402c-8cf8-6ffcd55d82b3 | checkpoint | Units clearly labelled
ee323bc0-43fd-5b30-9cc3-9da945200e38 | section | Expansion and Auto Fill Systems
a5db1d62-4e31-573f-80a5-65e6754a8061 | checkpoint | Installed to latest drawing
e2dcd1ef-b335-4559-ae80-c30051921bec | checkpoint | Units clearly labelled
dd24b02d-d486-5925-93fe-d7162842d8d4 | checklist | ITC-006 Subcontractor Rough In (sign off by relevant contractor) |  | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
47afd8f1-6916-5d03-907a-880a0069095e | section | Mechanical Electrical
99fc0cee-1e7b-5800-9c9b-d8488baa055b | checkpoint | Mech elec wires installed as per design
0fe90881-67ec-5c8f-bf84-9d465c313705 | checkpoint | MSSB Installed as per design
7dd7bfb0-83a5-5653-a896-9f31c9e192e3 | checkpoint | Wall and or Ceiling rough in complete (If required) ready for closing up by ceiling/wall contractor
ef7c6c03-fa93-5ff7-91e1-e0400db2770b | section | Controls
b54bed7b-44b0-529e-b4ec-4c8b6fd01a48 | checkpoint | Control wire installed as per design
64ec7bdc-8ba7-5dcd-81b6-30304d00cfed | checkpoint | Control Panel Installed as per design
36ac3f01-dc17-4f79-a289-1d1e735de5ef | checkpoint | Wall and or Ceiling rough in complete (If required) ready for closing up by ceiling/wall contractor
f77bb787-f950-5c14-b900-c9120f7ccd2c | checkpoint | Devices fit off as required
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
3bf5b146-f8c5-57e3-bac8-4a6679019679 | checkpoint | Pipe Insulation installed as required
e7dd1e1d-0fa6-5517-a5ac-d4903c5e47fd | checkpoint | Pipe Cladding Installed as required
d6627dbe-9adc-5dd1-a66a-c13a14577e2b | checklist | ITC-07 Fire/smoke damper checklist |  | ITC-07 Fire/smoke damper checklist
afe21e6a-840b-57ed-905a-c7b85a77b9f9 | section | Fire/smoke dampers
214535fd-4942-5ac4-a7fb-0c622d1681c0 | checkpoint | Access panel in duct / ceiling for damper access, installed
d4a88b74-4954-5695-988d-e3531f50734b | checkpoint | Fire/Smoke dampers labelled
3554a29a-ba76-5358-83f8-a448cd486da1 | checkpoint | Installed to manufacturers requirements
0558873a-4b60-52d2-93f7-216c5a11b3ef | checklist | ITP-NWPA-XXXX TMF - Mechanical Services RevA | itp | ITP-NWPA-XXXX TMF - Mechanical Services RevA
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
0b4ad232-5674-51d3-9408-aef0b58a609d | checkpoint-no-value | Details:
4c852cfd-8613-5d22-aa6a-a50203947b74 | textbox | AMS Number:
f981dd06-4a84-5c65-9431-81f582b0b6f3 | textbox | AMS Title:
0586c035-a39d-5596-961a-ff3cae1a52e1 | textbox | Work Lot Number:
475b96f1-1305-5305-a218-53f85609d66e | textbox | Work Lot Description:
a8cce907-3242-5deb-b91f-01861801a714 | textbox | Design Package:
d275e70b-6b09-5730-b86d-03f1d481fa25 | textbox | Associated Design Packages:
2eb53350-d62b-5410-891d-525d71209857 | checkpoint | Author (Mandatory)
fa222e26-3885-5917-9639-841a446352a1 | textbox | Name:
9f5fedf4-d780-5f2e-9cec-9d0a455ce0c7 | note | Position: Site Engineer
68a5285a-e6cf-5d61-a0ab-6072fe9df51f | date | Date:
0f535cda-671a-5970-b1da-b499293c7746 | signoff | Signature
2eab499f-b075-5f2a-a829-b18958735454 | checkpoint | Reviewer & Approver (Mandatory)
0a1d229e-e4e5-5d13-b32a-025c4c588c03 | textbox | Name:
8583ada8-9156-5f75-8aae-a87cdb636832 | note | Position: Project Engineer
a0f2ca73-f42e-5c3b-a15b-36076157d38e | date | Date:
52d6d8da-eb6c-5858-92bf-3fe5cbf6f792 | signoff | Signature
9f8470fb-b854-53e4-92ec-507a0cd66726 | checkpoint | Additional Reviewer (If Applicable)
51921e87-8a3d-5b13-b87a-dac533473298 | textbox | Name:
7fe9ef3b-d580-5259-bd2f-72c842392ee3 | textbox | Position:
7594243d-0483-5c44-a495-f6ea1a13c75a | date | Date:
46a1859a-da76-5ece-ba17-9a8a972733e4 | signoff | Signature
1d2e93d8-5cdb-5481-9f39-40fdac1f17e4 | checkpoint | Authorisation (Mandatory)
07dae21d-32f1-5895-bd4d-ee910c458bd3 | textbox | Name:
43c40360-390a-54e6-9106-5212fce3ead0 | textbox | Position:
900d0eee-04e2-50f1-8506-4abebe89c66c | date | Date:
3471e40e-e8ad-55c3-a426-8b9741eeca53 | signoff | Signature
8e4e1f84-dbf1-5bd8-a098-4b0fa6efb20c | section | 1.0 PRELIMINARIES - Prior To Commencement of Work – Master Worklot Records (if applicable)
d687912d-4b55-52da-a5fd-d1e79bc8f5bb | checkpoint | 1.1 - Preliminary activities completed
75a084b9-10db-5d24-a2dd-a8d011a06128 | note | Specification Reference - JH-MPR-SQE-006 Managing SQE Risks
cfcf7e7d-98c0-51c1-b247-dd0903a6cb83 | note | Acceptance Criteria - All ‘pre-construction’ authorisations and checks completed and recorded in Pre-Commencement Checklist in PPW as part of the AMS establishment
24180840-954c-5fa8-b74d-89e0abe4fcf6 | note | Test / Inspection Method & Frequency - Prior to works commencing
a20df9f3-5ba4-5f43-93e9-dc126790e6e4 | note | Inspection: Project Team - PE (H)
ad0e236b-47dc-5d7a-afa7-1f35eb082ba3 | note | Records & Comments -
b412297c-9690-5765-90be-fb212663f366 | tickbox | Pre-Commencement Checklist completed in PPW
f0892b3e-42f4-5c8f-b59e-020a8d3cb39c | textbox | PPW Record No.: |  |  | AMS/NWPA/00
03f635f8-8a21-5667-b603-9112dcefab9c | signoff | HOLD POINT
ec8e0bc3-5e65-5153-9ebc-8939c58d4732 | checkpoint | 1.2 - Work Lot Map
cc75854a-1f48-5aa6-ac69-1781feb20aea | note | Specification Reference - NWP-000-NWA-PRO-XQA-0003 - Work Lot Management Procedure
c7ecaa29-b01a-550e-bd79-86cc9d030336 | note | Acceptance Criteria - Work Lot Map attached to Work Lot
f7031380-55f7-5bb3-8d09-ed72b086fa1e | note | Test / Inspection Method & Frequency - Per work lot
5d45b373-d7c0-5ecb-8554-4c1c8c00c776 | note | Inspection: Project Team - SE (H)
ec248a1a-f10c-5867-a693-b94b3766b52d | note | Records & Comments -
d3a681fe-8f60-574a-9616-a2f152785fb1 | tickbox | Work Lot Map
f939736d-922c-5669-bb83-bea09ccc389e | signoff | HOLD POINT
51f7942e-6fb5-5a24-a26b-4fbd5e774b43 | section | 2.0 MATERIAL COMPLIANCE - Prior To Commencement of Work – Master Worklot Records (if applicable)
8fab87e3-1a52-5886-a560-71a320f0a17d | checkpoint | 2.1 - Calibration Certificates
034da917-fc99-5da7-80c7-a88f44931e0d | note | Specification Reference - JH-MPR-QUA-010
7dce1d12-1313-5ede-b594-7047c8e0def7 | note | ○ Process Control
da71c5bc-3515-5520-b735-ff0432de50e9 | note | Acceptance Criteria - Confirm that external equipment calibration and testing facilities are registered in PPW.
5b0745cd-2001-551b-bdd5-238cfb3e4a2a | note | ○ External equipment calibration meets contract requirements for each item of test equipment.
34c3c020-7434-5118-a45b-94c7e10b438c | note | Test / Inspection Method & Frequency - Visual check with certificates, ITP, checklist or inspection report
18530b5e-7f8d-5e57-b37b-9b074f9a1d05 | note | Inspection: Project Team - SE (H), QA (R)
af7dfded-c08b-53e5-b26c-c2666a3b9147 | note | Records & Comments -
60cb672c-4e59-534d-a924-1ba1b2d3ff3b | tickbox | Record of visual inspection
6d985f89-2f1b-5b6f-b981-c688d9f34961 | tickbox | Calibration Certificates
506bde12-e8fe-5b26-9b96-9f78771c3669 | signoff | HOLD POINT
fd1564dd-9a4e-5094-b9d6-5f967bafdb22 | checkpoint | 2.2 - Shop Drawing Approval
65d5f4ed-d0a8-52f8-a341-44424183e688 | note | Specification Reference - IFC Drawings
d0c9c8ca-2086-5679-b0a4-7687911bca3f | note | Acceptance Criteria - Mechanical shop drawings have been reviewed and approved by NWPA
d70fff1a-0081-5e16-b3df-35385370f2d5 | note | Test / Inspection Method & Frequency - Prior to works commencing
dd3dae0b-b59c-59a5-94e9-c3b229f5adcd | note | Inspection: Project Team - PE (H)
62ec07a6-5503-56ea-bfbc-7873a20bb401 | note | Records & Comments -
9de8d407-a497-54d0-9248-aee17df85886 | tickbox | Approved Shop drawings
a89c9c3f-23c1-54f3-93b1-84bab3a430c4 | signoff | HOLD POINT
bbbfa262-a3d5-5783-8a11-19b309f178b8 | section | All preliminary records have been reviewed and approved. ITP signed at sections 1 to 3 and uploaded to Master lot with all preliminary records. Works may proceed onsite.
2440a0d3-40b9-55c4-b156-65daab7b5cc8 | checkpoint | Site Engineer
f536dd0c-6649-5bf1-8289-2dc35779f820 | textbox | Site Engineer Name:
b8d45384-85d2-5120-9052-b8a2989083c8 | date | Date:
04302fe0-fb24-5e01-b65f-2dfaab43a8aa | signoff | Site Engineer Signature:
bee57047-e48c-584f-8aba-40c39bcb06fe | checkpoint | Project Engineer
464f354c-e2e2-550a-97f5-64d3e1716922 | textbox | Project Engineer Name:
772cad66-4afd-5911-9ca6-47a6fba99f08 | date | Date:
c88030ed-182c-5f4f-a847-d3f39a45fb1d | signoff | Project Engineer Signature:
85ef2b11-85e2-5166-ad6e-bc1167361346 | section | 4.0 CONSTRUCTION ACTIVITIES - Prior To Commencement and During Works – Sub-lot Records (if applicable)
018c3478-d126-5ba9-a5cc-9ae85291b274 | checkpoint | 4.1 - Inspection of incoming materials:
1d249125-1409-576b-8584-01c08afbb43a | note | ○ All mechanical Units – ERV, AC, DX, IEC, fans etc.
5a254a56-2e42-5f63-8e39-ae8169793a7d | note | ○ Grilles
01f1693c-c428-5446-8027-590c114b96a7 | note | ○ Pipework
f146844f-98d1-5fcb-b0bf-f7fb092817e0 | note | ○ Ductwork
16e18766-45fe-555e-9e3f-354f9f3d70ed | note | Specification Reference - NWP-000-NWA-PLN-XPM-0022
f4c56c0e-eb67-500c-a986-001db3169b83 | note | ○ JH-MPR-PMA-007 - Material Control
fb98855f-ba58-53ef-9944-e2d935d22d0c | note | ○ Project Requirement Specification
6281f31d-a81c-54f4-bb64-ea77cb353f2a | note | Acceptance Criteria - Materials conform to IFC drawings and Specifications
8679f665-2433-5654-b511-154fcfd31fa1 | note | ○ Qty conform to purchase order requirements
47fc3a7a-b2f2-55ce-b5de-4742c8315cda | note | ○ Free of defects, transportation damage and/or imperfections
dc7275b5-8577-5f63-a3f0-fde4b1995702 | note | Test / Inspection Method & Frequency - Visual check with written notes in Delivery docket, ITP, checklist or inspection report.
e038648a-95b6-56c1-84c3-9f39b9c39e08 | note | ○ Upon Delivery
26b5d9bb-01ca-51a7-8f06-d74da18d00e1 | note | Inspection: Subcontractor - SF (H)
ac891dc2-fe44-5959-aa98-a30ab5ebd50d | note | Inspection: Project Team - SE (H)
c48e73f8-348f-5dce-842f-1f6c3dc4812c | note | Records & Comments -
9b3b852d-7f6b-5685-9b14-4a4976c74243 | tickbox | Ductwork Installation Checklists
a6225a54-ff7d-5978-88f3-11361d67bd20 | tickbox | Ductwork Insulation Checklists
7239b3c2-fba2-558d-8128-69f01d0cc7d6 | tickbox | Grille Installation Checklists
721ce710-6df0-508e-95ab-92786461a262 | tickbox | Mech Electrical Installation Checklists
5f1670ab-1ada-5c83-8915-779279808a2b | tickbox | Controls Installation Checklists
3d633afe-3b44-5512-8301-ad9dadaf9868 | tickbox | FCU Installation Checklists
c2ed03a9-b88a-5e9c-888c-7b511770976a | signoff | HOLD POINT
3eaaf249-24a6-5fca-8a0c-00bca306577f | checkpoint | 4.2 - Mechanical Equipment Installation
6777406a-1213-5a3f-af38-0845dd301b64 | note | Specification Reference - IFC Drawings
59a8b675-39cc-58ff-b3f6-5c7c8842957c | note | ○ AS 1668
3a7f266c-fa5d-5cd6-b5b0-c1ec3f396d21 | note | ○ AS 3000
34f63ede-bc70-5b9e-9bb6-acfe57cf230e | note | ○ Manufacturer Requirements
6e13de4d-1336-54ba-8fcd-25c4b4a7bc22 | note | Acceptance Criteria - All pipe work and duct work has been installed as per design specifications and relevant standards
763b14d4-3ad8-56ed-bf91-c2a3c846ccc3 | note | Test / Inspection Method & Frequency - As per each equipment
f49ba609-ff0d-5cf0-aa7a-6eb52a802ff3 | note | Inspection: Subcontractor - SF (W)
312c2dd6-46d2-52f1-b53c-c673db7c2513 | note | Inspection: Project Team - SE (S)
ff1f35ee-838f-59f1-a998-0669cf5a1ff3 | note | Records & Comments -
257f031b-7f9c-56c8-a89f-753eb88e1011 | tickbox | Ductwork Installation Checklists
20206a69-9078-56d7-85df-1b845b5dee44 | tickbox | Ductwork Insulation Checklists
059d79b2-fa82-5aca-b425-942cc78bdf57 | tickbox | Grille Installation Checklists
ea403bc2-3423-5f90-9919-db44780798c9 | tickbox | Mech Electrical Installation Checklists
685bac57-7249-56f2-bcb3-e51bb88f1651 | tickbox | Controls Installation Checklists
0e5c120a-83f9-5746-a14e-47fe35524e05 | tickbox | FCU Installation Checklists
fd1759c5-eaf9-52c8-ad98-b8d6b0316473 | section | 5.0 TESTING AND COMMISSIONING REQUIREMENTS – Post Construction Works – Sub-lot Records (if applicable)
d32682b9-e4b6-5598-bc88-4b5a0bfb59f8 | checkpoint | 5.1 - Refrigeration Pressure Testing
61ccd275-b44f-5de1-8f52-a7fb0e41a9ed | note | Specification Reference - IFC Drawings
0b4f485c-23ef-5865-97d8-2028ebe1adbb | note | ○ AS 1668
8eea4028-b6d1-5ac1-a1dc-7329550f5c0e | note | ○ AS 3000
c54a6237-8ace-5f68-9b40-a49b9fea8d25 | note | ○ Manufacturer Requirements
1f58de3d-25e8-586b-bc6d-0be0fc5ed3a0 | note | Acceptance Criteria - Pressure testing should be in accordance with the design specifications and relevant standards
6a2f3c4f-6927-56dc-94a2-7199fa90349a | note | Test / Inspection Method & Frequency - As per each air conduiting unit
c40a790b-6431-5979-8c92-16569ffbe36b | note | Inspection: Subcontractor - SF (R)
85dbf77e-5c6e-5bd5-8ad9-5f0d2f7c12d7 | note | Inspection: Project Team - SE (R)
e7bfe373-cfc1-5e39-ba97-4273536cc032 | note | Records & Comments -
703c3590-3386-5d4a-80ab-c3c4d24ceb71 | tickbox | HHW Pipework Install Checklist
bb5379a2-d847-5eef-a5fb-008dcec77e51 | tickbox | Refrigeration Pipework Install Checklist
ba83748a-e6f2-5456-86eb-e9c23fb822ef | checkpoint | 5.2 - System Commissioning
dff150ed-c4cf-552a-a315-a258b558f814 | note | Specification Reference - IFC Drawings
1f2fec5c-c25d-5661-8d1f-8db2fe7c4f40 | note | ○ AS 1668
835260c2-cffe-5f6d-b12c-6b20bc2d59c5 | note | ○ AS 3000
bf588031-ae71-5360-b78c-aef80e43b2ee | note | ○ Manufacturer Requirements
e98e580d-6361-58c6-a3ac-9a1ea91778a1 | note | Acceptance Criteria - Mechanical systems are tested to perform in accordance with the design specifications and relevant standards
6839260c-8c47-548e-a508-9c7943ebb6e9 | note | Test / Inspection Method & Frequency - As per each equipment
11ddac9b-ea0e-57c0-af74-9c354603e671 | note | Inspection: Subcontractor - SF (R)
b0f26a9f-54a4-5184-a845-dcbc22f9b74e | note | Inspection: Project Team - SE (R)
8bf79ca4-9e1b-52c8-8182-0d57ce12ce55 | note | Records & Comments -
0dd94588-2953-5b67-af54-e517f9826cd1 | tickbox | Mechanical Commissioning Checklists
bbdf9c34-d964-5667-a053-0580ece2d24a | section | 6.0 COMPLETION REQUIREMENTS – Post Construction Works – Sub-lot Records (if applicable)
3abd02ac-c3f0-5840-8916-44b55a105c80 | checkpoint | 6.1 - Works Completion Inspection (with Subcontractor)
973e42c4-c5b3-5189-ad8b-cb91cb015098 | note | Specification Reference - NWP-000-NWA-PRO-XDC-0002 – Outstanding Works, Works Completion and Defect Management Procedure
95d26586-d626-57ed-a18e-1ea153147e1a | note | Acceptance Criteria - Works completed in accordance with IFC Dwg and Specifications
592f648b-a742-57a3-944d-e03e57992754 | note | ○ Inspection completed & recorded prior to releasing activity
ca922363-0a69-544b-a8e9-04da61724d74 | note | Test / Inspection Method & Frequency - Visual Inspection with Subcontractor at the end of work activity prior to signing off ITP
0f7650a3-605d-56cf-9269-0ad4123a4890 | note | Inspection: Project Team - PE (H)
816c37c0-1a74-5ad7-a92e-0e077a29e528 | note | Inspection: Project Team Sign Date - Refer to CHK241
014d0fdd-87a1-5cd9-8036-bafd6edcabe2 | note | Records & Comments -
ed0b0c14-7d39-5c65-aa71-8a355c07c2f3 | tickbox | NWPA Completion Checklist – CHK/NWPA/00241
a9316efb-f2de-56ff-b1bc-40adf467305d | signoff | HOLD POINT
b6c4fad3-3a1a-5305-adde-1b25507dbebe | checkpoint | 6.2 - Close out NCR(s)
010e2b0c-b7bc-5c5b-91a6-2008498a9b2f | note | Specification Reference - NWP-000-NWA-PLN-XPM-0022 Quality Management Plan
957afd99-b151-53ba-b7cb-5ab83584483b | note | Acceptance Criteria - All out of tolerances notified via NCR reporting system
25466b45-6a95-5ecf-a100-523b784bb8d0 | note | ○ All NCR’s applicable to the works to be raised in a timely manner and, if applicable, designer confirmation to be obtained.
bfa36e11-68a8-5e7c-bfe5-f420615a08fd | note | Test / Inspection Method & Frequency - Prior to closing and signing ITP
ff51b489-fa96-5eda-b25e-fb90ce04b0e7 | note | Inspection: Project Team - PE (H), QM (H)
d40b4ac5-5d6b-5f37-b20f-2e2eba53f1b1 | note | Inspection: Project Team Sign Date - Refer to CHK241
5fb68270-a144-57a0-b351-0694e1afdba5 | note | Records & Comments -
38981a5e-2ea9-5f7d-a7d8-8e0036735a8b | tickbox | NWPA Completion Checklist – CHK/NWPA/00241
7c79cb9f-2425-5b51-a399-8e3233b9c432 | signoff | HOLD POINT
0bd1d591-4b59-584e-90f8-506c71f14e97 | checkpoint | 6.3 - Relevant DCN(s) and RFI(s):
3c9c90f3-dddd-5516-b823-929677d2adb2 | note | Specification Reference - NWP-000-NWA-PLN-XPM-0006 Design and Engineering Management Plan
21cef955-7049-5389-96b1-4ea432f26a45 | note | Acceptance Criteria - Design/Construction Queries or clarifications relating to this ITP are addressed and closed.
8d0f2168-b102-525a-a9eb-7c4941047195 | note | ○ All ‘parts’ of RFI are included
c7931691-ef99-554f-8c63-72ac4bc4686d | note | ○ All ‘supporting evidence’ is included
5661c008-68c0-546e-8040-bb9f543b06bb | note | Test / Inspection Method & Frequency - DCNs and RFIs closed and linked to NCRs where applicable
e94c6d6e-7fec-5ca8-909e-acfc5f74fcb5 | note | Inspection: Project Team - PE (H)
878efb26-5b48-5a87-a594-44037b28cc8c | note | Inspection: Project Team Sign Date - Refer to CHK241
c1ef3927-b3dc-5cf6-9bb9-820c1f297012 | note | Records & Comments -
a937ca98-ddd6-576a-b72d-8d19b3925014 | tickbox | NWPA Completion Checklist – CHK/NWPA/00241
110a78d1-0a42-55ec-a524-0971303b8a8b | signoff | HOLD POINT
9538db04-7a74-5812-afba-48ea9db0b4ec | checkpoint | 6.4 - Redline Marked-up Drawings
f48b8bc7-cb6e-5cf3-85b4-1e71dc68b13f | note | Specification Reference - NWP-000-NWA-GUD-XDM-0002 Red Line Guidelines
dae96eb8-07dc-552c-921f-3c519ab7ab83 | note | Acceptance Criteria - Redline drawing to be produced & maintained by engineers to include all changes made during construction
a6cfda7c-cf59-5800-bdca-2aba7157776f | note | ○ Redline to use latest IFC version of the design drawings and be marked- up in red pen, to identify any variations
2fba03dc-690c-5239-92e7-7c42e2e34e5c | note | ○ RFI, DCR, ECW and Client Wavers to be referenced in redlines (as required)
3457386a-f558-54cb-91d3-40ed44419a25 | note | Test / Inspection Method & Frequency - Completion of Works
ee2e23f7-f49d-54cc-95c5-97c5cf6bb6ca | note | Inspection: Project Team - PE (H)
a0fa88e9-60d4-54e6-a4f7-b1b9d188ba50 | note | Inspection: Project Team Sign Date - Refer to CHK241
af709619-0c6e-5866-b780-5ee2398d5eb1 | note | Records & Comments -
a8f07a8e-56bc-57d4-bc47-85f9456c35a7 | tickbox | NWPA Completion Checklist – CHK/NWPA/00241
18043c6f-e846-525e-89f8-c29e2f412f90 | signoff | HOLD POINT