## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
0b09ab51-85d1-4203-82e9-cf08d6284952 | checklist | Checkers Checklist - Abutment Base -Type A-10M |  | Checkers Checklist - Abutment Base -Type A-10M
1d48422a-f00e-49d1-ad64-3f2de2ea57cf | section | Details
72be8ff8-8bc2-4f14-9944-159eee7bfa29 | checkpoint | Site Safety / Workers Safety
ce0dfc2a-0be7-4d86-8da0-3b8db6ba1ba6 | checkpoint | Availability of updated shop drawing
cc359e67-f9aa-433e-8f7b-87e88d812056 | checkpoint | Double Check the Ferrule placement -Type AA
c035a66a-6199-40f5-bf91-5290630372fa | checkpoint | Overall Measurements of construction Element
385064c5-e0bd-4646-8dcd-e9e662ef7d21 | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm)
2e2b4fad-7a02-47a4-9dd4-0df9288b1e77 | checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm)
94aa816d-6172-49f5-8e3a-7006904e5eb8 | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
b9b07ba1-8418-421d-ac3b-e90c3b1919b3 | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
8583a249-b073-40bf-8b15-6b52d4717588 | checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mm Dia ,300mm
18798649-d4d8-4faf-a137-23d29961d837 | checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
52014107-1573-44a4-b2f9-388f3d661907 | checkpoint | Concrete cover check minimum 30mm
c9a35076-6066-4cf2-bc17-4fb09a552095 | checkpoint | Panel length check, alignment check -4400x800mm
8dd97a21-147b-4742-81ac-db51641a865e | checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
58601fa8-4eea-4879-b537-bedfe27a6a4a | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
8964a227-9f1d-4e69-a48e-90c9150ca50c | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
baa6c75a-e92d-4c56-9f4b-0599e6b66349 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
f954da10-afc2-4e4a-a6c4-1f6c52fc652b | checkpoint | Curing Procedure arranged
e8927543-90c8-4115-9afb-3275c12beb8c | checkpoint | Photo Taken
a81ccdaf-5e72-4bee-9cfd-e84787cea5eb | checklist | Checkers Checklist - Abutment Base -Type B-12M |  | Checkers Checklist - Abutment Base -Type B-12M
50989090-d9c5-4d3d-9808-2f3599ce41f5 | section | Details
68b9bf0a-7804-41f0-b9ce-cef60e30b9b8 | checkpoint | Site Safety / Workers Safety
0924f381-819e-42cb-9989-387407cd7eb5 | checkpoint | Availability of updated shop drawing
aec1ad5f-3a1a-4c93-b100-bc62849cdfea | checkpoint | Double Check the Ferrule placement -Type BB
3123d1e3-cf29-43a8-ba92-031470b39154 | checkpoint | Overall Measurements of construction Element
d9f0d62a-5152-436b-a435-dc51b0ecb211 | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm)
77ff81a8-a050-47d8-b5f1-240862a0da86 | checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm)
1266fa65-2fed-44f0-872f-4f61b9a374e1 | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
a040b52b-daa5-4d20-8619-4f8758f13ca5 | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
015b96c6-0188-4669-b9f4-c5c99d61379d | checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mm Dia ,300mm
08ba1e4e-f858-4434-952f-e48480a9dfbe | checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
c0c5952f-153f-4f4f-b9cc-8f3d900d390c | checkpoint | Concrete cover check minimum 30mm
d97a24c0-400a-499e-9827-0fd1d52897ac | checkpoint | Panel length check, alignment check -4400x800mm
2a3c7929-71df-4195-ab1a-bbdf2714cc7c | checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
be322d7d-59ef-4bf7-91a2-2ab202207fe8 | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
5a1aff82-da4a-48ab-91a5-91df9cda56d6 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
49f4af01-61ac-40be-a69f-635e660efd37 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
ae41a13f-0982-4868-8cc4-7f84c89001ee | checkpoint | Curing Procedure arranged
358b5757-ea25-44e8-8dd3-572113848753 | checkpoint | Photo Taken
6cff8dac-b27e-43dd-bb04-36a891643af7 | checklist | Checkers Checklist - Type A - Bridge Plank |  | Checkers Checklist - Type A - Bridge Plank
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a034dfe1-af60-495b-8c90-781dc03422e7 | checkpoint | Site Safety / Workers Safety
08bcbc54-b7cc-4ee1-ad4e-d384fbfd05c7 | checkpoint | Availability of updated shop drawing
fa52582e-aab1-4329-9e9e-d2fd940a4d25 | checkpoint | Double Check the Ferrule placement -Type A (600+1450)
27eb39f9-67a8-55bc-9435-5964b7bd6daf | dropdown |  | 600F1450F, 550F1450F
ae386f8c-d2d4-4976-9d1f-3c1b47169b19 | checkpoint | Overall Measurements of construction Element
162d3ad1-e9bd-4513-8d6f-161e07d240a9 | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm)
0d3e97b7-a9f5-4c4a-8ea5-822512b44acb | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
dce12243-2651-472e-ac13-1d1163789568 | checkpoint | Concrete cover check minimum 30mm
97aececc-473b-4ed1-914a-bc02549ae12f | checkpoint | Panel Thickness check,alignment check (150mm)
c0cdda09-a7d4-5a92-b132-dd3dd0c06961 | dropdown |  | 150mm, 200mm
e631744e-2fa2-4cac-ad92-40ecb87f681d | checkpoint | Panel length check, alignment check (4500mm)
afc9e5de-608a-5c05-84e0-3138292f07b9 | dropdown |  | 5000mm, 4500mm
935413b7-7ffa-41ff-b3c0-759aaa764e3f | checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
73450327-7c2b-4124-b008-fd527de9f172 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
1ef5a150-8f85-4223-bec8-b882651985f1 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
dc0debb7-7932-4a26-8407-0ed1575cfce7 | checkpoint | Curing Procedure arranged
781f77d5-bd7d-4371-8fe6-d3396ce3bc2a | checkpoint | Photo Taken
62ed2554-fd41-4a54-9e48-d4201abbc718 | checklist | Checkers Checklist - Type A-10M- Bridge Plank |  | Checkers Checklist - Type A-10M- Bridge Plank
3a0c07ff-8d1d-40ae-b16f-15e747c021bb | section | Details
b3010b79-5a2c-483e-a129-5c8daabd83fc | checkpoint | Site Safety / Workers Safety
c4017eca-1753-44ca-b386-c6ae9d5704b7 | checkpoint | Availability of updated shop drawing
a86e3398-dc20-471a-9f86-0d5f9cfdb7ef | checkpoint | Double Check the Ferrule placment -Type AA
d34c06a1-f3e0-424f-860d-b3ecb96ced68 | checkpoint | Overall Measurements of construction Eliment
69af539b-d5c2-417b-848d-7d720662aeb7 | checkpoint | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
c925f167-ea16-4a69-be41-d7fafdaa5821 | checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
518da600-5402-4b41-8876-25bc566d3184 | checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
b68f9ae9-e30b-489f-b7db-145b35cee55b | checkpoint | Concrete cover check minimum 30mm
7581bd3f-e949-4b4a-941a-73d6a46729e8 | checkpoint | Panel Thickness check,allignment check -150mm
15f7eb17-8ad7-4554-a40d-98f2a46c2a25 | checkpoint | Panel length check, allignment check -4500mm
501c78f1-fdf2-43a8-b44a-938388deeabb | checkpoint | Diaganal length check, allignment check
3240d6a4-ac98-46da-bda1-c91a8368633b | checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
e173881a-78d9-4e5c-ad51-5470ed5a9211 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
a4d25805-2274-42d4-b7f8-00a0b306ef1b | checkpoint | Reinforcement (Reo) placed, cleaned, tightned
590a826b-d1cf-4350-abbe-68478b320d25 | checkpoint | Curing Procedure arranged
36751828-874d-4a09-bb7f-d105ff62fd39 | checkpoint | Photo Taken
38025a45-20b0-4b14-856b-bc29b189da54 | checklist | Checkers Checklist - Type AB - Bridge Plank |  | Checkers Checklist - Type AB - Bridge Plank
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a034dfe1-af60-495b-8c90-781dc03422e7 | checkpoint | Site Safety / Workers Safety
08bcbc54-b7cc-4ee1-ad4e-d384fbfd05c7 | checkpoint | Availability of updated shop drawing
fa52582e-aab1-4329-9e9e-d2fd940a4d25 | checkpoint | Double Check the Ferrule placement -Type AB
ae386f8c-d2d4-4976-9d1f-3c1b47169b19 | checkpoint | Overall Measurements of construction Element
162d3ad1-e9bd-4513-8d6f-161e07d240a9 | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm)
0d3e97b7-a9f5-4c4a-8ea5-822512b44acb | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
dce12243-2651-472e-ac13-1d1163789568 | checkpoint | Concrete cover check minimum 30mm
97aececc-473b-4ed1-914a-bc02549ae12f | checkpoint | Panel Thickness check,alignment check (150mm)
c0cdda09-a7d4-5a92-b132-dd3dd0c06961 | dropdown |  | 150mm, 200mm
e631744e-2fa2-4cac-ad92-40ecb87f681d | checkpoint | Panel length check, alignment check (4500mm)
afc9e5de-608a-5c05-84e0-3138292f07b9 | dropdown |  | 5000mm, 4500mm
935413b7-7ffa-41ff-b3c0-759aaa764e3f | checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
73450327-7c2b-4124-b008-fd527de9f172 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
1ef5a150-8f85-4223-bec8-b882651985f1 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
dc0debb7-7932-4a26-8407-0ed1575cfce7 | checkpoint | Curing Procedure arranged
781f77d5-bd7d-4371-8fe6-d3396ce3bc2a | checkpoint | Photo Taken
030af2a0-b63d-4211-af19-e2d7bd88dcfa | checklist | Checkers Checklist - Type B- Bridge Plank |  | Checkers Checklist - Type B- Bridge Plank
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c8cdb1f8-b0fe-4eea-8d32-e8b9ad053142 | checkpoint | Site Safety / Workers Safety
56323356-4589-4c89-b6b3-b45f8f3d4f64 | checkpoint | Availability of updated shop drawing
70a4415a-48f5-41d2-8b11-24afa5b1a1f0 | checkpoint | Double Check the Ferrule placement -Type A (600+1450)
3ad162dd-c6a5-54c4-8e41-aa5fe96873b4 | dropdown |  | 600F1450F, 550F1450F
90290a8a-4562-4bc4-8083-083ce9f84fb9 | checkpoint | Overall Measurements of construction Element
95c8ded7-74ac-458f-a033-908b75de827c | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm)
7fe9ecba-00bd-481c-a1d4-d2e875670b1d | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
9df92e1a-1578-422b-acc6-247498038637 | checkpoint | Concrete cover check minimum 30mm
e9df32cc-5bf8-4147-95de-bdb9e26414f2 | checkpoint | Panel Thickness check,alignment check (150mm)
7429bc2f-000c-5dfc-bba0-6e184bcd8b29 | dropdown |  | 150mm, 200mm
05af30c5-f49e-494a-8404-56d73b0e5a87 | checkpoint | Panel length check, alignment check (4500mm)
2bd3d9ad-e48d-5789-8686-4915c3bda1f5 | dropdown |  | 5000mm, 4500mm
97930e67-bf5a-4b95-85e8-d26ec9d3510c | checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
031cda75-2260-4053-912b-499c05b567f7 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
5da31b0f-115b-4057-b02b-9ed70c649e0e | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
8a83c279-a538-465a-b049-56f14b70c659 | checkpoint | Curing Procedure arranged
6cf0de48-026d-4a28-a1cb-84bec7981942 | checkpoint | Photo Taken
79bcb567-625c-4b6a-839e-09761c8dd400 | checklist | Checkers Checklist - Type B-12M- Bridge Plank |  | Checkers Checklist - Type B-12M- Bridge Plank
2ff99198-86ab-4349-9f21-3fa5f198c4e7 | section | Details
03c0c689-99d7-46b6-860c-4da607b72dcf | checkpoint | Site Safety / Workers Safety
4c2c5dba-381d-4670-95bf-8f724095e16a | checkpoint | Availability of updated shop drawing
751ebfaa-5bbe-4586-8948-7f08aae185e1 | checkpoint | Double Check the Ferrule placment -Type BB
2199029f-2761-46d5-a971-d32fb929bf50 | checkpoint | Overall Measurements of construction Eliment
150a6228-f7e5-4a9a-9517-fd5dc00c49e2 | checkpoint | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
85fcab77-4c21-4994-a7cd-1168ef882d14 | checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
1ecac7fb-f780-4bea-ae92-df54fbb7f516 | checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
9b2b0803-8d0c-4767-8ade-164532c4d44f | checkpoint | Concrete cover check minimum 30mm
e5ca6636-33eb-47a4-9f03-8da2fc7053a9 | checkpoint | Panel Thickness check,allignment check -150mm
c17f632a-99dc-4714-b0fe-0bfdbc71f9db | checkpoint | Panel length check, allignment check -4500mm
1d95dbc2-ea63-4685-965d-7137f89da706 | checkpoint | Diaganal length check, allignment check
3ae5ab34-c7ce-443c-a7cd-e1c959d4b1a7 | checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
00f97c3d-d590-4bef-a5dd-16e87ed3ee1d | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
8f7dd12b-0f53-45ee-8724-b1f43c349fb4 | checkpoint | Reinforcement (Reo) placed, cleaned, tightned
20107f5d-571f-49e6-abf1-35bc65a4245d | checkpoint | Curing Procedure arranged
06b437bc-a235-4c83-804b-c3207d8ee271 | checkpoint | Photo Taken
5a303a2b-445c-4966-b7fe-2bf03ab87fa2 | checklist | Checkers Checklist - Upper Wall -Type B-12M |  | Checkers Checklist - Upper Wall -Type B-12M
4ec04a30-c97c-4f48-9ec6-ef8f0439ddee | section | Details
a6a0f929-89b3-4174-991f-09047dbf9ac1 | checkpoint | Site Safety / Workers Safety
1b4e03ba-e8f5-41a8-a40b-c0b98943176f | checkpoint | Availability of updated shop drawing
86cda54a-3bb5-4a10-b542-dfad32678239 | checkpoint | Double Check the Ferrule placement -Type BB Wall Height -
1b0c8044-80ad-52ea-a5af-cadd76061791 | dropdown | Height: | Other,694mm,582mm
215fcf8f-7b6a-402a-800a-c4e7728508df | checkpoint | Overall Measurements of construction Element
2a521174-fd95-4cf4-81f6-e7548b9572af | checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation
4c7d1c4d-dbfb-463d-a276-3c872c256d3d | checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
f807ffa8-0863-46f7-916b-4ee75e050c48 | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
3c053c96-cf13-4ec3-9668-4a09c77ee5f5 | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
f81c4afe-fce2-4cf0-a4b1-07ee96ec0d30 | checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
425523e0-4a1f-4d66-a108-526c6d67311e | checkpoint | Concrete cover check minimum 30mm
e851f8dd-4524-4deb-8807-b8857f2dd63d | checkpoint | Panel Thickness check,allignment check -150mm
f7a17b83-a1e3-47bb-abb2-9325c905a4b5 | checkpoint | Panel length check, alignment check -5000x800mm
20dc1fe7-8a4a-4954-b438-a69b6b145fb2 | checkpoint | Diagonal length check, alignment check (5034 mm or close to this)
748f3fb8-bef8-4767-8398-4b7c085a30cd | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
fbbe7df3-4cc8-4870-af09-dee71982d079 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
88757878-0250-4a6a-944d-8927f1d60db5 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
8ce39b87-d871-4ebb-a35a-b08005550f7d | checkpoint | Curing Procedure arranged
8ced0f5f-b262-465a-ba65-ad61f91c82e2 | checkpoint | Photo Taken
e3fadd57-0884-4b94-90c5-6065e7520f66 | checklist | Checkers Checklist - Upper Wall Type A-10M |  | Checkers Checklist - Upper Wall Type A-10M
ee73d7ce-00ad-4413-8822-96fc23397aa9 | section | Details
43ba27db-96d1-4137-ab9c-0b3d42d08ba3 | checkpoint | Site Safety / Workers Safety
3f8af4d6-800a-4039-8f8b-af223d94b3b8 | checkpoint | Availability of updated shop drawing
c998d50e-03f7-48c1-9e28-a48ab9af391b | checkpoint | Double Check the Ferrule placement -Type AA Wall Height -
9f7dcafc-8b3c-505b-ba23-5adb52a4d133 | dropdown | Height: | Other,694mm,582mm
ed4459fc-57a4-48ec-b985-4211558d0b85 | checkpoint | Overall Measurements of construction Element
c33a9f3a-1939-4cd3-9aed-898777308185 | checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation
ab39da5a-fac7-4edf-865a-cd6b3f824251 | checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
bb9047e2-22d4-4471-9715-ee19ef4d5317 | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
a7092df6-8248-466c-9945-a749c1da9973 | checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
42c17b9e-fc47-4e39-974b-c92679a334a5 | checkpoint | Double check ferrules are firmly positioned & Fixed with Reo
1ab0b326-7a60-4d50-9a25-15e7726dd7a5 | checkpoint | Concrete cover check minimum 30mm
e01913c7-853d-451a-bf43-4d587b5aee89 | checkpoint | Panel Thickness check,allignment check -150mm
92fabb35-6654-4979-88d4-6b5307b6bb79 | checkpoint | Panel length check, alignment check -5000x800mm
e35c77a1-5a64-41c1-81cb-55c29b865c93 | checkpoint | Diagonal length check, alignment check (5034 mm or close to this)
fe8ead20-a8da-4ff1-9eaf-b8d325335805 | checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
d3366045-a69c-4375-94e8-033f6c036c77 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
b4a8fd82-9c9d-42e4-b980-fca0c7fb5854 | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
c0963916-17fc-48ea-8ec0-5eff27d4a28f | checkpoint | Curing Procedure arranged
346b6ac5-e400-455d-9fc6-bf71eb77568f | checkpoint | Photo Taken
580849e4-8a17-4918-924f-f404b48150ad | checklist | Installers Checklist - Abutment Base - Type A-10M |  | Installers Checklist - Abutment Base - Type A-10M
81142c01-ef1b-4b83-929d-489cada9068c | section | Job Approval Documents/Construction Documents
0e0add34-dcea-4f40-8c84-5514f3bdfcad | checkpoint | Availability of updated shop drawing
7017e9f2-5bfd-41b6-975d-fb23a00f6537 | checkpoint | Complete Material "Bucket List"
fef5a6c9-ee2b-486f-aaf8-e52234d6e614 | checkpoint | ID Plate
c9784b33-dd79-55e6-a696-60ef7fd44ae5 | textbox | ID:
28f2e162-d66a-4ca6-b59f-96b0d4781454 | section | Pre-Pour Check Approvals
b10b4824-a79b-48bc-ac5c-40819958f818 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
7ac2d7d2-4762-4307-bdf2-60b01873adf9 | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
064ac840-010b-41fe-9181-e13f6f7d987e | checkpoint | Temporary Fix ID Plate to Formwork
974a9a6d-1880-4169-9e18-b457943c7f73 | checkpoint | Double Check the Ferrule placement -Type AA
df4623ec-b998-4410-a83e-ca36c569ea02 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
7e502d82-6b6d-4256-b2bc-979b8f6d7c60 | checkpoint | Embeded Items - Fixed Firm & aligned -Check
c28dee5f-1a73-591c-9b78-f2c3ab52f66e | tickbox | Ferrules - Position,Size,Orientation -M24 (96mm)
6cb8f8c8-22b7-552d-8805-ade8a1f037aa | tickbox | Ferrules for Dowels - Position, Size -M24 (96mm)
4fad315e-3052-5628-991a-7ecd059cd96d | tickbox | Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
bc68cbc1-6b06-4b4a-93ab-03921653db39 | checkpoint | Concrete cover Check - minimum 30mm
56a94f64-2236-4ea5-835d-c446f2a1413a | section | Quality Assurance
dfaa1df4-0e3c-4094-ba6a-f533b5c03f9b | checkpoint | QA - Final Check of ALL measurements
c0875111-520a-4d2d-826d-ba4db8da62f9 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
d14be8cd-91ba-4e92-9cd5-9aef737b9284 | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
4facf71d-e6a3-4aa7-8ab3-978beee5c5bf | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
07e718be-724f-544c-a560-545cd57e60da | date | Pour Date
6619d3fc-66af-4ff6-b6fc-2330556cbbf9 | checkpoint | CONCRETE TEST Procedure
225c4067-acc3-4c47-b9f9-e47db5a213af | checkpoint | APPROVAL FROM ENGINEER
9fa34b67-636d-48bd-b7e8-247e1adb8a5c | section | Other Arrangements
9c5b398b-d4cf-4bfe-8b4e-8f529ddac6a0 | checkpoint | Concrete surface Finish Requirement arranged
ccd37081-2af4-503f-bd36-90eaa067dbb3 | dropdown | Finish: | Fine finish,Broom finish
81ddd3ce-afa3-4eb5-957a-bbe4b0375e2a | checkpoint | Curing Procedure arranged
3319e3c7-929d-4730-b81b-11e7b63db4b4 | checklist | Installers Checklist - Abutment Base - Type B-12M |  | Installers Checklist - Abutment Base - Type B-12M
2882aecc-aa50-4d48-9f25-5f5f48960f09 | section | Job Approval Documents/Construction Documents
2c2e1224-af9a-4e41-bf72-17e8f3538084 | checkpoint | Availability of updated shop drawing
b17a9a0f-60c2-41d0-9e30-935788d4ecef | checkpoint | Complete Material "Bucket List"
ac5235a4-acc7-4ec7-96d6-fce05d971d42 | checkpoint | ID Plate
9c8a9cf8-51b6-5b0d-a935-a7f682d89840 | textbox | ID:
fa4a9b23-558e-41c0-897e-c948c0cf87c5 | section | Pre-Pour Check Approvals
1444732f-8b75-4da7-a0c1-778ae4b5fda8 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
5a5af62e-22a8-4819-a666-a472ef2ec2df | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
0b92756d-3515-4483-bb94-497edb0650dc | checkpoint | Temporary Fix ID Plate to Formwork
b0944ab5-e633-44df-a6bd-aecff897624b | checkpoint | Double Check the Ferrule placement -Type BB
f5fe47bf-8d9d-46ce-8249-c613abe0db99 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
b015fcdd-db5e-44c6-a71e-ec3285f98e52 | checkpoint | Embeded Items - Fixed Firm & aligned -Check
c19bd586-affc-5db0-a054-b1d573cd6e4c | tickbox | Ferrules - Position,Size,Orientation -M24 (96mm)
c183dbf5-b7c1-52cd-9f87-cb188ec5c204 | tickbox | Ferrules for Dowels - Position, Size -M24 (96mm)
36500329-16d5-58cc-8d66-22df0375f7a1 | tickbox | Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
d66b7695-a1c9-41c3-93bb-5816d6269a52 | checkpoint | Concrete cover Check - minimum 30mm
6646d840-9e39-4d88-8396-3561cdb7164b | section | Quality Assurance
8a301b00-0dde-406c-a33a-22c61d837561 | checkpoint | QA - Final Check of ALL measurements
aca1279d-2ade-4d6b-ba62-b5499643c86e | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
b4280eba-4c96-48ce-8718-ce6b7fcc1a13 | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
c8c8516a-afad-481e-93c1-31fcaff97d2e | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
e5c0cf74-f797-520e-9130-0b8d149286bf | date | Pour Date
63420ed3-4142-4267-82b2-d53f216302e2 | checkpoint | CONCRETE TEST Procedure
222c8a5f-5c18-45c7-b644-498c65e6cb2b | checkpoint | APPROVAL FROM ENGINEER
1d6c4164-646c-4064-8bb0-bce25931b84e | section | Other Arrangements
e39334de-270b-4b7e-9fd1-73f552bad884 | checkpoint | Concrete surface Finish Requirement arranged
188fd23a-914c-5c3b-a178-03656606ee37 | dropdown | Finish: | Fine finish,Broom finish
c91b0308-5367-4177-afad-43fa568d78f9 | checkpoint | Curing Procedure arranged
fce73cb5-a6e1-4095-a6ed-ff6b43d814b3 | checklist | Installers Checklist - Type A - Bridge Plank |  | Installers Checklist - Type A - Bridge Plank
1bb6e8f2-4b8e-482e-8f64-51cecc540565 | section | Job Approval Documents/Construction Documents
188925bd-b050-4ce2-93cb-fa46fdd22905 | checkpoint | Complete Material "Bucket List"
7a5d3fa3-4fe3-4f21-99d9-175f5998774d | checkpoint | Eye Anchor - 2.5T
cde6dbaf-036a-5ff7-b1ba-39f93b69b639 | textbox
352e3cc8-bc12-4a5f-a73f-9798911de1f0 | checkpoint | Ferrules - M20 x 96mm
cf37eee7-90a3-5bde-93f7-0b1a9bed8590 | textbox
14bf7870-8cad-47a0-a930-c3439f88cea4 | checkpoint | ID Plate
789968c6-aaa5-5423-99bc-6a389b87ceb7 | textbox
12535983-b292-4f15-9cc1-277a43df46f8 | section | Pre-Pour Check Approvals
9923e0df-8f4c-473d-b3a8-2b472321790d | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
f04629c4-eec9-4b7c-a9eb-da2a69f9d2bc | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
cb2a1cd8-7b5e-4a9e-8b92-050a3d6a8cd0 | checkpoint | Temporary Fix ID Plate to Formwork
79690ace-0293-4fd7-8bdf-26cf6045fa78 | checkpoint | Double Check the Ferrule placement -Type A
ea8a050e-88e4-49df-bc9f-cc6b3b5ec271 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
115d88f1-8302-44e6-b033-a5703015a098 | checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
e09c43a1-c5ea-4fcb-909f-31cf2b28febe | checkpoint | Concrete cover Check - minimum 30mm
71f9e967-4ccb-4424-87a7-608a0203fcd4 | section | Quality Assurance
30ab27bb-8301-4a3c-acc8-e245db460bb9 | checkpoint | QA - Final Check of ALL measurements
63796298-2841-4f7e-8917-697c35c10575 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
6607c965-574e-48c5-982f-22161151a303 | checkpoint | QA - Concrete mix design ,variations%, adjustments%,mix time
36ca3359-1273-4e32-b7fd-c23715e2cbfe | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
d91e17d5-f907-5565-9339-d160eb73cea4 | date | Pour Date
ab16a28f-3b02-4b6f-a998-dfb41e9af4cc | checkpoint | CONCRETE TEST Procedure
80e348cb-e853-4bd6-8b21-4f8e5598f2b5 | checkpoint | APPROVAL FROM ENGINEER
758a0d0c-5b50-4b3e-8aa1-98f8b3a8a6b6 | section | Other Arrangements
19d67d71-73ec-4d60-a956-e15533ac953e | checkpoint | Concrete surface Finish Requirement arranged
4c32305f-b223-58cf-8491-6adae17977ca | dropdown |  | Fine finish, Broom finish
a938a6c2-d5c2-49e5-996e-7282f744c8be | checkpoint | Curing Procedure arranged
65b6e7c5-af2a-4f5c-b778-cede16dccbdb | checklist | Installers Checklist - Type A-10M- Bridge Plank |  | Installers Checklist - Type A-10M- Bridge Plank
6ce4bfb9-3f55-49bb-9bc3-39db26538940 | section | Job Aproval Documents/Constrction Documents
1fe053a2-9e7a-458a-b770-885c24c4e17b | checkpoint | Availability of updated shop drawing
d20998eb-571a-4c4d-a39a-ab3aaf48e28d | checkpoint | Complete Material "Bucket List"
1a83418e-34a5-437d-a659-0c7eddb99018 | checkpoint | Eye Anchor - 2.5T - 04
81a304e5-653a-4c42-82f6-253e26a16041 | checkpoint | Ferrules - M20 x 96mm - 10
8e19b065-a38b-47b2-8cc3-0a75c3403d00 | checkpoint | ID Plate
8b78137d-283b-5609-afa5-7133172d2fa7 | textbox | ID:
6174da10-8adc-46bb-8e72-47d623dea68b | section | Pre-Pour Check Approvals
fa1887f5-ce4d-430b-ab50-ed4c62be596c | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
ad558d4e-9a47-4c69-972a-c411ecc1ee9b | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
e56bd42f-dcc2-4f9e-a485-b68dbddf40fd | checkpoint | Temporary Fix ID Plate to Formwork
31e2dc3c-21e1-475c-88a1-6476c9886c69 | checkpoint | Double Check the Ferrule placment -Type AA
b6f0949d-f7ef-49a8-b7d9-b4a7d530bceb | checkpoint | Reinforcment Check - Reo as-per Shop Drawing
563119b4-2c5b-4a58-b338-f8b7b01cce5b | checkpoint | Lifters, Ferrules Fixed Firm & alligned -Check
692569ac-323f-51b7-bd0b-83b7dcf10b30 | tickbox | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
f1b9548e-d554-51b7-b907-5216cd687488 | tickbox | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
fc3fb45f-b3b7-4d4e-be59-8ed1824ae159 | checkpoint | Concrete cover Check - minimum 30mm
91c196ad-8bf1-4d58-a3a4-0bfc269f5a28 | section | Quality Assuarance
db090760-d74f-443c-9098-224ebaa403c3 | checkpoint | QA - Final Check of ALL measurerments
906a7a43-d9c0-422d-b4ac-a35298b35ffb | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
a85d1790-e687-4932-b539-09785e2edff0 | checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time
06598038-0f20-48ee-a96e-a077e3c0263b | checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK
c5117944-61fe-5432-ba4d-10acb0024692 | date | Pour Date
98d7fec4-30e2-4e38-ac2c-4c1c595a18df | checkpoint | CONCRETE TEST Procedure
5eb20a0f-8957-4c3e-8ca3-ec7a77b1c266 | checkpoint | APPROVAL FROM ENGINEER
6d942dab-71f8-4814-ab10-5b8888312398 | section | Other Arangments
ba134a72-b76b-4263-815b-d73800f80be6 | checkpoint | Concrete surface Finish Requirment arranged
446724d1-0f6c-522e-a699-b59014523d0b | dropdown | Finish: | Fine finish,Broom finish
266ddb91-3dd8-44fd-8b3c-a4979ca20376 | checkpoint | Curing Procedure arranged
d750abaf-4827-4bfe-832e-94aad8f7cef0 | checklist | Installers Checklist - Type AB - Bridge Plank |  | Installers Checklist - Type AB - Bridge Plank
1bb6e8f2-4b8e-482e-8f64-51cecc540565 | section | Job Approval Documents/Construction Documents
188925bd-b050-4ce2-93cb-fa46fdd22905 | checkpoint | Complete Material "Bucket List"
7a5d3fa3-4fe3-4f21-99d9-175f5998774d | checkpoint | Eye Anchor - 2.5T
cde6dbaf-036a-5ff7-b1ba-39f93b69b639 | textbox
352e3cc8-bc12-4a5f-a73f-9798911de1f0 | checkpoint | Ferrules - M20 x 96mm
cf37eee7-90a3-5bde-93f7-0b1a9bed8590 | textbox
14bf7870-8cad-47a0-a930-c3439f88cea4 | checkpoint | ID Plate
789968c6-aaa5-5423-99bc-6a389b87ceb7 | textbox
12535983-b292-4f15-9cc1-277a43df46f8 | section | Pre-Pour Check Approvals
9923e0df-8f4c-473d-b3a8-2b472321790d | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
f04629c4-eec9-4b7c-a9eb-da2a69f9d2bc | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
cb2a1cd8-7b5e-4a9e-8b92-050a3d6a8cd0 | checkpoint | Temporary Fix ID Plate to Formwork
79690ace-0293-4fd7-8bdf-26cf6045fa78 | checkpoint | Double Check the Ferrule placement -Type AB
ea8a050e-88e4-49df-bc9f-cc6b3b5ec271 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
115d88f1-8302-44e6-b033-a5703015a098 | checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
e09c43a1-c5ea-4fcb-909f-31cf2b28febe | checkpoint | Concrete cover Check - minimum 30mm
71f9e967-4ccb-4424-87a7-608a0203fcd4 | section | Quality Assurance
30ab27bb-8301-4a3c-acc8-e245db460bb9 | checkpoint | QA - Final Check of ALL measurements
63796298-2841-4f7e-8917-697c35c10575 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
6607c965-574e-48c5-982f-22161151a303 | checkpoint | QA - Concrete mix design ,variations%, adjustments%,mix time
36ca3359-1273-4e32-b7fd-c23715e2cbfe | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
d91e17d5-f907-5565-9339-d160eb73cea4 | date | Pour Date
ab16a28f-3b02-4b6f-a998-dfb41e9af4cc | checkpoint | CONCRETE TEST Procedure
80e348cb-e853-4bd6-8b21-4f8e5598f2b5 | checkpoint | APPROVAL FROM ENGINEER
758a0d0c-5b50-4b3e-8aa1-98f8b3a8a6b6 | section | Other Arrangements
19d67d71-73ec-4d60-a956-e15533ac953e | checkpoint | Concrete surface Finish Requirement arranged
4c32305f-b223-58cf-8491-6adae17977ca | dropdown |  | Fine finish, Broom finish
a938a6c2-d5c2-49e5-996e-7282f744c8be | checkpoint | Curing Procedure arranged
a91bba0c-a74b-4435-86d1-05a1573b83e3 | checklist | Installers Checklist - Type B-12M- Bridge Plank |  | Installers Checklist - Type B-12M- Bridge Plank
5f49ebac-5848-493b-a279-1642db64e55c | section | Job Aproval Documents/Constrction Documents
6443b084-cdb1-4880-8c5d-d0ed2a30b991 | checkpoint | Availability of updated shop drawing
c70f3a3f-fb85-403b-8e16-b8a6c18cf428 | checkpoint | Complete Material "Bucket List"
fb47da60-7c89-4cdd-968b-2f5f12809d08 | checkpoint | Eye Anchor - 2.5T - 04
c77bb529-8ae2-42ef-ae25-b9e6a62b3850 | checkpoint | Ferrules - M20 x 96mm - 10
7f756be7-4de1-4893-af4c-4d1c349ab47d | checkpoint | ID Plate
86fa0b5e-91fc-5e2b-9e5b-228dd48e7885 | textbox | ID:
3ed6f582-7e70-4605-9085-39ffcce4da12 | section | Pre-Pour Check Approvals
8d9013a1-fb7c-402c-b103-d1c12a634f74 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
ca27b85f-154b-4124-b1d9-6fefb3b05fc3 | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
81e82184-eeb1-4039-87c7-e3c6387b2227 | checkpoint | Temporary Fix ID Plate to Formwork
a1722f4c-470c-4da3-9ed2-cfd21c8f0dd1 | checkpoint | Double Check the Ferrule placment -Type BB
6f3124cb-16fe-4827-9537-7dc5861a1e5d | checkpoint | Reinforcment Check - Reo as-per Shop Drawing
d6867ad3-5bf6-4094-aa77-11b5dc404405 | checkpoint | Lifters, Ferrules Fixed Firm & alligned -Check
0bc59ec8-8c1a-5a61-8684-529c8dafb778 | tickbox | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
2ff40459-4d9c-5f02-aa82-a2b56e5f8d1c | tickbox | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
3c3e0ce6-bea3-408c-a983-30bb6dbf0178 | checkpoint | Concrete cover Check - minimum 30mm
8cfde5af-a75f-491e-847e-b8821de2bd93 | section | Quality Assuarance
55229937-6fe2-411c-9259-b72aafa605fe | checkpoint | QA - Final Check of ALL measurerments
01ddce77-5425-46d2-973d-aeaad7e71004 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
df15372a-4874-4510-80ee-ba61421afc55 | checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time
535eab05-e974-4fcd-a6ca-17a07721105f | checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK
fed0712a-9f70-5155-9894-55d131f17844 | date | Pour Date
30015758-90fd-4c1b-b2f3-1c7d66a72d6a | checkpoint | CONCRETE TEST Procedure
76a23c77-49d6-4d86-a868-85cbf64adc9c | checkpoint | APPROVAL FROM ENGINEER
6eb1c83d-8c85-40e4-b2d9-e1911940e98d | section | Other Arrangements
a49651c6-18fe-4922-bbd4-7da31170baa1 | checkpoint | Concrete surface Finish Requirment arranged
4ea5be24-ad50-58ea-ada3-621438731f47 | dropdown | Finish | Fine finish,Broom finish
e241c896-d216-484e-a3a8-404d5ef4d665 | checkpoint | Curing Procedure arranged
f997320c-c1ff-422d-bf1b-8ef19089bfcf | checklist | Installers Checklist - Upper Wall l -Type B-12M |  | Installers Checklist - Upper Wall l -Type B-12M
21a99765-fb68-4da9-a8a9-e8a59922149d | section | Job Approval Documents/Construction Documents
fe109fef-dea9-4b11-8227-93be351bf625 | checkpoint | Availability of updated shop drawing
ecb73e8b-e24c-41f6-a14b-80ffc299e401 | checkpoint | Complete Material "Bucket List"
7dff1800-8bce-4eb6-8ac9-46959639b339 | checkpoint | Eye Anchor - 2.5T(170mm) - 04
e3cd89c7-e1be-4e51-83cc-4ef9085a228c | checkpoint | ID Plate
77b81c4e-a768-56c0-982f-0356ac3e30a7 | textbox | ID:
2860aca3-d446-42aa-9bd0-e72271d121bc | section | Pre-Pour Check Approvals
c43f9869-494c-4bc8-aa70-babc8578c45c | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
ce49e84d-2261-4b52-b5ce-8ee5b1fba3b6 | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
09a5a541-f4bb-498e-b63b-26c96e087f4e | checkpoint | Temporary Fix ID Plate to Formwork
6afb17c7-548e-49a5-9e86-4951ec57d424 | checkpoint | Double Check the Ferrule placement -Type BB Wall Height -
643b8bed-c6ff-50c0-b84d-06727ffd9f0d | dropdown | Height: | Other,694mm,582mm
6ac6f59b-653c-4d91-ac99-3c468b9cf508 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
9f740494-5009-4073-88d4-75dbab7cb3a7 | checkpoint | Embedded Item - Lifters, Ferrules Fixed Firm & aligned -Check
d8f5d5a4-be36-5ffe-93e3-96963f2b2d89 | tickbox | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
634a94ea-1ee8-56bc-82d5-95e64e39646f | tickbox | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
94ea21fb-a543-53b2-8276-614f44ef66a3 | tickbox | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
42353487-7e7f-5fbd-b67f-dfd1c9b33e4a | tickbox | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
499dd5cd-0ebd-47ef-b9cc-42e8e8407b0d | checkpoint | Concrete cover Check - minimum 30mm
1925e843-51e0-4cb6-b282-c8044a197eba | section | Quality Assurance
73fa4eea-f5a6-4d08-90de-e1cd2123e384 | checkpoint | QA - Final Check of ALL measurements
aec2db3c-ebfd-4bd4-93e5-78c171e10962 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
808ccda1-d899-4358-b0fe-ae6d90e633f5 | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
8487afa7-695c-4ad6-bccf-352e42e81c05 | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
55e80b58-3631-5ccd-b407-fdb5dab959b2 | date | Pour Date
4229615c-fa63-4a86-a895-8c5d4daa6d42 | checkpoint | CONCRETE TEST Procedure
e9b21b8f-78e7-45fc-a7c1-5201f8b228eb | checkpoint | APPROVAL FROM ENGINEER
80153028-c420-45b7-b4da-4cdae4e964dd | section | Other Arrangements
13f299a3-4921-473d-9208-d1af4db24db6 | checkpoint | Concrete surface Finish Requirement arranged
a2a32852-e55c-56d9-94c2-06b6dc7449ad | dropdown | Finish: | Fine finish,Broom finish
3adc7656-04d8-49ac-a5a7-9b4a27ddca8b | checkpoint | Curing Procedure arranged
1bb287a2-538a-498c-bdde-27cf976cb2ed | checklist | Installers Checklist - Upper Wall Type A-10M |  | Installers Checklist - Upper Wall Type A-10M
000d7802-c914-43bf-bf27-6f4997fe8a44 | section | Job Approval Documents/Construction Documents
d8725a97-d5ae-4838-aba5-e186ae78b24c | checkpoint | Availability of updated shop drawing
157fd3a0-965b-4fa0-a004-08ea0e96a335 | checkpoint | Complete Material "Bucket List"
372f2bca-e6c3-4f5a-9118-62738d94d323 | checkpoint | Eye Anchor - 2.5T(170mm) - 04
9fa333d2-507a-498d-9002-0a3ad2ee9f8c | checkpoint | ID Plate
e7bf5d6f-0727-587c-b850-f4886493644d | textbox | ID:
dba8e708-b86e-42ae-927e-117512460739 | section | Pre-Pour Check Approvals
71ea3bcd-afe4-4ea8-9648-474d6a7844c2 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
477fcfe3-13d9-446e-8d71-cb1b3f7f8fb1 | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
cf852dac-e067-4eee-a780-76e55a414747 | checkpoint | Temporary Fix ID Plate to Formwork
453e114c-0886-4883-8df4-4ff0d0a3e5d5 | checkpoint | Double Check the Ferrule placement -Type AA Wall Height -
be947760-1cc6-5e0c-ac2e-69b5871d0ea7 | dropdown | Height: | Other,694mm,582mm
7973aa42-fad6-4bac-b379-887fc8a7b093 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
5e378970-6d1c-48f5-abc6-5525ba53fc83 | checkpoint | Embedded Item - Lifters, Ferrules Fixed Firm & aligned -Check
1bf3a5f9-5f8b-5c02-8d97-0a0d59819c94 | tickbox | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
4515a240-fee0-5df8-a99d-c099b8b08047 | tickbox | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
68d97c3d-b467-5ab9-a309-a9f4a3ee9d61 | tickbox | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
726884ba-d7ea-5841-a072-1d9c6273634b | tickbox | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
da19d82a-7d7f-4b94-8064-0added07c814 | checkpoint | Concrete cover Check - minimum 30mm
e5a5efb3-001a-4944-86cc-2ccfd40b48e4 | section | Quality Assurance
2f9bf28f-4576-4bfe-9781-1fb051ae9843 | checkpoint | QA - Final Check of ALL measurements
6f058ecf-4b67-4108-8db4-f279ca2fbc15 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
9b1d4826-264d-4287-a3ca-59d72a61dfca | checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
fcce25ec-3779-4896-ab79-9af497883b1b | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
54793fcc-cf9b-5dbd-a994-6f4e8855ef5a | date | Pour Date
25b7da75-bc34-4d09-b0f2-9070dd62676f | checkpoint | CONCRETE TEST Procedure
ca804889-972a-4ade-804e-5843149b98d7 | checkpoint | APPROVAL FROM ENGINEER
d759eaa6-18bc-4b20-972e-9c0bffcf6de2 | section | Other Arrangements
1a4ea9d9-99eb-44e5-a5d6-f2a77881bf0c | checkpoint | Concrete surface Finish Requirement arranged
e50dca02-4369-574b-ab55-9edfab341494 | dropdown | Finish: | Fine finish,Broom finish
40ce5c48-bbc2-4dcb-bf02-16928209367c | checkpoint | Curing Procedure arranged
340c5276-b9cf-40f8-aad5-2e0c1283e435 | checklist | Installers Checklist t - Type B- Bridge Plank |  | Installers Checklist t - Type B- Bridge Plank
685d9d6b-af31-41b6-881b-3d99bdf88a8f | section | Job Approval Documents/Construction Documents
ee21d8ce-6864-4532-8eec-c9bf591f79e3 | checkpoint | Complete Material "Bucket List"
c9734f8b-7d5f-4f9d-8748-07de06dd60e6 | checkpoint | Eye Anchor - 2.5T
2d998933-5923-568c-8d9c-b53d781d635c | textbox
321d7e86-6cca-46e2-b324-02c7d19beca9 | checkpoint | Ferrules - M20 x 96mm
630dcf7c-6e48-5486-925d-754430ccc666 | textbox
87e96194-9e98-45cc-b6df-cfcaa9371d72 | checkpoint | ID Plate
88422b15-8907-5571-8eb7-11459e570ada | textbox
54342a85-2ec6-491e-a1a4-ff5c9e7cf1d2 | section | Pre-Pour Check Approvals
e28d22d7-6a21-430e-a6c0-1d8d256f6798 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
daeda3b0-0f4a-4a3e-ab17-e6eebd85154e | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
439bedec-73af-4adc-916a-ddf82aafd52a | checkpoint | Temporary Fix ID Plate to Formwork
f34898ec-a60a-4a5b-80a2-15ce55f8f2ae | checkpoint | Double Check the Ferrule placement -Type B
e9eeb7d4-6429-4dbb-8574-03b8a3f70d3c | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
6df3bfc6-d461-4cbd-8641-e318632d79f4 | checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
e768953f-0b35-4f27-a935-ea95569f68cf | checkpoint | Concrete cover Check - minimum 30mm
65080fb3-6da0-4759-87b0-62f29842d032 | section | Quality Assurance
8fdeda10-6f09-41b9-87e8-5265cab07a3f | checkpoint | QA - Final Check of ALL measurements
0a72b684-c75f-4fb0-93b1-fc73e97abecd | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
47d17b57-a2f3-4c9d-b421-26d892c15790 | checkpoint | QA - Concrete mix design ,variations%, adjustments%,mix time
16aaa4ff-99a3-452d-9552-c842113c7524 | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
15c44e43-4ae0-53c4-9d13-f7a204a386f8 | date | Pour Date
68178722-f662-45d4-af43-1374c89ce3a2 | checkpoint | CONCRETE TEST Procedure
ae416424-7294-471f-a3d6-174fa4be2365 | checkpoint | APPROVAL FROM ENGINEER
f3b02677-61bc-4009-bdc7-129743c05da0 | section | Other Arrangements
461dbdfa-918c-404e-88d1-ee4c5cd87c86 | checkpoint | Concrete surface Finish Requirement arranged
c60f2a9a-50cd-5593-8d97-cee74de95466 | dropdown |  | Fine finish, Broom finish
e36dc6de-1757-4b9c-a0ec-8987232df053 | checkpoint | Curing Procedure arranged
d011e28d-2c17-4443-a270-04997073db5a | checklist | Precast Components ITP |  | Precast Components ITP
783771d0-c2b2-488d-a4a3-d58224f6bd61 | section | Documentations
f43bd42b-7590-4257-9475-e23ec8daf31e | checkpoint-no-value | Special Instructions
a544f2d8-2b00-4464-91af-2e7271df1a1e | checkpoint-no-value | Approved Shop Drawings
8977bede-1b3b-5ff1-81a0-9bf0fd4515d7 | tickbox | 4.2m Wide Deck Panels (DP)
f82ae150-ff2c-5831-8c5f-f3b207b369f1 | tickbox | Abutment Base (UB)
4bc8326d-1bf0-51a3-a2bc-97fd6413c9ed | tickbox | Upper Wall (UW)
56d12bdc-585f-470c-9c37-fa342597b96f | checkpoint-no-value | Other
af310717-4588-48ed-94e5-759636a20819 | section | Job Approval Documents/Construction Documents
e9b1236c-8bf0-4e4e-8084-212b68f6af3d | checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction"
775dfaba-fce5-47ec-8e64-91f8a3385917 | checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
d3ac69d7-b1f5-4a48-8c0e-6cdc00880c0f | section | Pre-Pour Check Approvals
10026e6a-9486-4e85-a7aa-623584d64b2b | checkpoint-no-value | Formwork
a121587b-542a-4e69-a608-659cbd6abf83 | checkpoint-no-value | Reinforcement(Reo)
6d5d664d-2f64-487f-9073-d0988f9162db | checkpoint-no-value | Embedded Items and their placement
acaa1a9a-9306-44b4-ba2b-563e972a6d58 | checkpoint-no-value | Lift Procedure
9a7d48d5-e4f3-47f5-aaea-9436c8487359 | checkpoint-no-value | Concreting (mix design
cbf3fee1-9f75-4f58-be91-df9b0e8308f4 | section | Test on Concrete (requests and approvals)
3d3a0a14-399b-48b6-8356-f96b52d27e78 | checkpoint-no-value | Request From Client
ab638037-015f-47c4-ae68-32c9df956f45 | checkpoint-no-value | Test schedule and Test Results
45773aa6-9401-4de2-a63b-65c52f008706 | section | Transport 01
8c6a12fd-7c3b-448a-a39e-ea76a6a3b325 | checkpoint | Any Lifting, Loading, Transport Instructions from Client
857d9164-c7f1-4cdc-b79c-3d78925c73e8 | checkpoint | Transport Vehicle Approvals
71333b7e-4352-4001-a7ec-743befc091e9 | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
c4cf4610-13ac-4b75-965c-75f68e517090 | section | Transport 02
d516e64f-5ab3-4789-8b6f-8c097e4b29ce | checkpoint | Any Lifting, Loading, Transport Instructions from Client
e3b7d249-f602-437c-87a8-f48d5d784d69 | checkpoint | Transport Vehicle Approvals
df731671-74fc-4b27-853d-f1d5ae45313a | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
565f5ffb-f7ed-4cb4-a036-1d37785213ee | section | Transport 03
b00704f6-3fda-4e5d-aec6-167b92e30cf3 | checkpoint | Any Lifting, Loading, Transport Instructions from Client
19ef6f37-1975-4f47-ba0e-85ce7ffb7973 | checkpoint | Transport Vehicle Approvals
36f6d361-a773-4770-9f0e-7a9f99f5cf0e | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
9f1d7086-34ea-4d1e-8775-f0969e28525d | section | Transport 04
178989f3-964a-45db-9abe-0b0539974bb6 | checkpoint | Any Lifting, Loading, Transport Instructions from Client
713216a9-6054-4ed5-b932-06335b81e564 | checkpoint | Transport Vehicle Approvals
a9ef35dd-c64a-4bf0-a1ee-8a1817870ddb | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
eef707af-a70b-4329-a7e9-6887895be909 | section | Other Documentations
44183e0f-e30d-4424-bb5f-f49243b64ef7 | checkpoint | Special Instructions
b3e59fd8-e2ac-4bce-a617-f8a438b02a3d | checkpoint | Other
41b94023-7968-4577-a63b-65edf2c583ad | section | Installation
9ad24bcb-fcd4-4f34-bd49-02ff3cd603d3 | checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
a815c034-c479-4558-bb25-a49bbc6d825b | checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
838600a8-8a02-5edd-8601-2aee4e05d810 | tickbox | Set out
61f8bbde-d5dd-5aab-88b2-de94b6175635 | tickbox | Core Holes
b027ba4d-4749-5ac5-896e-e808e168f8fb | tickbox | Install dowels
27257ffb-9de3-475b-acd2-df5781eba4ad | checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings.
b17260e2-5384-475e-89e9-eafaa0ec79f9 | checkpoint | Grouting and sealing
23f55de8-7c98-4088-9e72-91ee3ea9fec6 | checkpoint | Remove back propping when instructed by consulting Engineers.
6c20fbfb-f247-4679-9d2b-3f4627d1489d | section | Final Inspection
72306cc2-ef32-42ea-adde-b56dc5d19fd0 | checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
dc64269d-25f9-4337-962a-c24033387d4d | checklist | Upload document/drawing |  | Upload document/drawing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d86fb2b9-179a-4d22-bfd1-db6fbce3df10 | checkpoint | Upload document/drawing