## ChecklistsITCs
Delete rows that aren't applicable to the project, then create the project breakdown and send to CONQA
type | name | values | prefix | postfix
checklist | Site Establishment and Safety Checklist | Pass, Fail
checkpoint | Delivery and goods lift location
checkpoint | Delivery requirements i.e. booking process
checkpoint | On site storage / office location
checkpoint | Site specific restrictions i.e. noise / starting times
checklist | Ductwork Checklist | Pass, Fail
checkpoint | Rectangular duct installed as per latest drawing | Yes, No
checkpoint | Duct flanges firmly bolted and sealed where required | Yes, No
checkpoint | Cleats installed as required | Yes, No
checkpoint | Correct hanger spacing / supports installed | Yes, No
checkpoint | DW insulated where required and damage free | Yes, No
checkpoint | Ductwork restrained for wind/seismic where required | Yes, No, N/A
checkpoint | Any required ductwork leakage testing | Pass, Fail
checkpoint | Spiral installed as per latest drawing | Yes, No
checkpoint | Spiral joins sealed correctly | Yes, No
checkpoint | Correct hanger spacing / supports installed for spiral | Yes, No
checkpoint | Spiral insulated where required and damage free | Yes, No, N/A
checkpoint | Additional taping/sealing to medium/high pressure spiral | Yes, No, N/A
checkpoint | Pops & flex installed as per latest drawing | Yes, No
checkpoint | Correct hanger spacing / supports installed for flex | Yes, No
checkpoint | Free from support off other services | Yes, No
checkpoint | Flexible duct connections completed correctly | Yes, No
checkpoint | Blade dampers installed as documented and left in the open position | Yes, No
checkpoint | BD pop access panel coordinated and marked | Yes, No, N/A
checkpoint | Cushion boxes installed as per latest drawing | Yes, No
checkpoint | Balancing dampers installed as documented and left in the open position | Yes, No, N/A
checkpoint | Location of register coordinted with other services and marked on plan or floor | Yes, No
checkpoint | Volume Control Dampers installed as per latest drawing | Yes, No
checkpoint | Motorised dampers installed as per latest drawing / actuator fit off | Yes, No, N/A
checkpoint | Smoke dampers installed as per latest drawing / actuator fit off | Yes, No, N/A
checkpoint | Fire dampers installed as per latest drawing / access panel in DW where required | Yes, No, N/A
checkpoint | Damper access panels coordinated and marked | Yes, No
checkpoint | Photos of ductwork correctly sealed through smoke wall & smoke damper | Yes, No, N/A
checklist | Indoor Equipment | Pass, Fail
checkpoint | Indoor Unit (IDU) correctly supported as per project engineering requirements | Yes, No
checkpoint | Correct IDU installed as per latest drawing | Yes, No
checkpoint | Flexible connections installed and sealed | Yes, No
checkpoint | Access to filter bank / filters installed | Yes, No
checkpoint | Access to all relevant controls and isolators | Yes, No
checkpoint | IDU access panel coordinated and marked | Yes, No
checkpoint | Ventilation fan correctly supported as per project engineering requirements | Yes, No
checkpoint | Correct fan installed as per latest drawing | Yes, No
checkpoint | Fan connections secured and sealed | Yes, No
checkpoint | Access to fan and isolator | Yes, No
checkpoint | Ventilation fan access panel coordinated and marked | Yes, No
checkpoint | Correct VAV installed as per latest drawing | Yes, No, N/A
checkpoint | Access to VAV and controls | Yes, No, N/A
checkpoint | VAV access panel coordinated and marked | Yes, No, N/A
checklist | Grille Fit-Off Checklist | Pass, Fail, N/A
checkpoint | Grilles installed in correct location as per latest duct layout / RCP | Yes, No
checkpoint | Correct grille type installed | Yes, No
checkpoint | Grille installed flush and square | Yes, No
checkpoint | Are all grilles installed correctly? Air leaks, vibration or failure | Yes, No
checkpoint | Grille color as per schedule | Yes, No
checkpoint | Grille left clean of fingerprints and caps installed where required | Yes, No
checkpoint | Grille fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below) | Yes, No
checklist | All Subbie Rough-in Progression Checklist | Complete, Incomplete
checkpoint | All work in zone completed and appear compliant | Yes, No
label | Pass once all work complete
checklist | All Subbie Fit off & Testing Progression Checklist | Complete, Incomplete
checkpoint | All work in zone completed and appear compliant | Yes, No
label | Pass once all work complete
checklist | As Builts Checklist | Complete, Incomplete
button | Update As-Built's of any known changes | Yes, No
checklist | Pipework Checklist | Pass, Fail, N/A
checkpoint | Pipework installed as per latest drawings | Yes, No
checkpoint | Pipework installed level and free of damage | Yes, No
checkpoint | All joins welded / crimped as per manufacturer's instructions | Yes, No
checkpoint | Air bleeds installed in pipework where required | Yes, No
checkpoint | Riser or area branch valve access panel coordinated and marked | Yes, No, N/A
checkpoint | Correct hanger spacing / supports installed for pipe runs | Yes, No
checkpoint | No other services suspended from pipework | Yes, No
checkpoint | Correct coil valves installed as per schedule | Yes, No
checkpoint | Test points, drains and bleeders installed where required | Yes, No
checkpoint | Coil valves accessible and not blocking any service points | Yes, No
checkpoint | Coil valveset access panel coordinated and marked | Yes, No
checkpoint | Correct coil valves installed as per schedule | Yes, No
checkpoint | Test points, drains and bleeders installed where required | Yes, No
checkpoint | Coil valves accessible and not blocking any service points | Yes, No
checkpoint | Coil valveset access panel coordinated and marked | Yes, No
checkpoint | HHW Pressure Test – ITR attached | Pass, Fail, N/A
checkpoint | HHW Flushed - plan, photos of flow readings and water quality attached | Pass, Fail, N/A
checkpoint | Drain trapped where required | Yes, No
checkpoint | Correct hanger spacing / fall | Yes, No
checkpoint | Drain tested | Pass, Fail
checkpoint | Drain pump installed level and tested | Yes, No
checkpoint | Drain terminates at a tundish | Yes, No
checkpoint | Drains, pump and tundish access for maintenance. | Yes, No
checklist | Pipework Testing | Pass, Fail, N/A
checkpoint | Pipe tested and recorded as per Pipe Testing ITP
checkpoint | Initial pipe pressure test (attach photo)
checkpoint | 24hr pipe pressure test (attach photo)
checkpoint | Piping cleaned and flushed
checklist | Fan Checklist | Pass, Fail, N/A
checkpoint | Fan installed as per latest drawing
checkpoint | Inspect the fan. Record and report for any issues
checkpoint | Fan is labelled clearly
checkpoint | Confirm ductwork connections to the fans are correct and include flexible connections
checkpoint | Confirm test points, sensors and gauges have been provided and installed as documented
checkpoint | Confirm correct electrical connections to the fan
checkpoint | Adequate maintenance clearance maintained
checkpoint | Unit complete with acoustic wrapping as per documented
checkpoint | Confirm seismic bracing to requirements
checkpoint | Installed as per manufacturer's requirements. Refer to specific equipment schedule for detail.
Checklist | Drains | Pass, Fail, N/A
checkpoint | Drain trapped where required
checkpoint | Drain pump installed on a gradient/ level
checkpoint | Drain terminates at a tundish
checkpoint | Drain pipe insulated where required
checkpoint | Drains, pump and tundish access for maintenance
checkpoint | Drain pipe is labelled clearly
checklist | PAC Unit Checklist | Pass, Fail, N/A
checkpoint | PAC installed as per latest drawing
checkpoint | Inspect the unit casing is not damaged. Record and report for any issues
checkpoint | Unit is labelled clearly
checkpoint | Unit correctly supported as per documented
checkpoint | Confirm safety tray and/ or condensate drain provided to the units and is piped to adjacent waste point
checkpoint | Confirm installation of any dampers on the units
checkpoint | Confirm correct CDW pipe work installed as per latest drawing (e.g. Valves, binder points, air vents)
checkpoint | Confirm electrical connection to unit
checkpoint | Flexible connections installed
checkpoint | Air filters installed
checkpoint | Confirm seismic bracing to requirements
checkpoint | Unit complete with acoustic wrapping as per documented
checkpoint | Adequate maintenance clearance maintained
checklist | VAV Checklist | Pass, Fail, N/A
checkpoint | Unit installed as per latest drawing
checkpoint | Inspect the unit casing is not damaged. Record and report for any issues
checkpoint | Unit is labelled clearly
checkpoint | Unit correctly supported as per documented
checkpoint | Confirm test points, sensors and pressure points have been provided and installed as documented
checkpoint | Confirm electrical connection to unit
checkpoint | Confirm ductwork connections to the unit are correct
checkpoint | Unit complete with acoustic wrapping as per documented
checkpoint | Adequate maintenance clearance maintained
checkpoint | Installed as per manufacturer's requirements. Refer to specific equipment schedule for detail
checklist | Plantroom / Outdoor Equipment | Pass, Fail
checkpoint | Access to filter bank / filters installed | Yes, No, N/A
checkpoint | Access to all relevant controls, isolators and maintenance items | Yes, No, N/A
checkpoint | Floor or Platform Mounted Thermal Plant correctly supported as per project engineering requirements | Yes, No, N/A
checkpoint | Maintenance and ventilation clearance maintained as per manufacturer's specs | Yes, No, N/A
checkpoint | All manufacturer specific requirements have been provided in addition to project requirements | Yes, No, N/A
checkpoint | Drain terminates at a tundish | Yes, No
checkpoint | Drains, pump and tundish access for maintenance. | Yes, No

## TO BUILD - LEVEL 2
Project Breakdown |  | Checklists
PROJECT NAME: 380 St Kilda Rd Level 2, 5, and 11
OHS |  | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
PIPEWORK:
Pipework Checklist
Pipework Testing
PAC UNITS:
| PAC-2-1 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-2-2 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-2-3 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-2-4 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-2-5 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
VAVs:
| VAV-L2-E-19 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-18 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-3 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-4 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-6 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-7 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-15 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-8 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-9 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-11 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-12 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-16 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-17 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-1 | VAV Checklist
Ductwork Checklist
| VAV-L2-E-2 | VAV Checklist
Ductwork Checklist
FANS:
| GEF-L2-E-1 | Fan Checklist
| OAF-L2-E-1 | Fan Checklist
| OAF-L2-E-2 | Fan Checklist
| OAF-L2-E-3 | Fan Checklist
| OAF-L2-E-4 | Fan Checklist
| GEF-L2-E-5 | Fan Checklist
SITE QA |  | All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Indoor Equipment

## TO BUILD - LEVEL 5
Project Breakdown |  | Checklists
PROJECT NAME: 380 St Kilda Rd Level 2, 5, and 11
OHS |  | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
PIPEWORK:
Pipework Checklist
Pipework Testing
PAC UNITS:
| PAC-5E-A1 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-5E-B1 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-5E-B2 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-5E-C1 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-5W-D1 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-5W-E1 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-5W-E2 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
| PAC-5W-F1 | PAC Coil Unit Checklist
Drains
Ductwork Checklist
Grille Fit-Off Checklist
FANS:
| GEF-5-A | Fan Checklist
| GEF-5-B | Fan Checklist
| GEF-5-C | Fan Checklist
| GEF-5-D | Fan Checklist
| GEF-5-E | Fan Checklist
| GEF-5-F | Fan Checklist
| OAF-5E-A1 | Fan Checklist
| OAF-5E-B1 | Fan Checklist
| OAF-5E-B2 | Fan Checklist
| OAF-5E-C1 | Fan Checklist
| OAF-5E-D1 | Fan Checklist
| OAF-5E-E1 | Fan Checklist
| OAF-5E-E2 | Fan Checklist
| OAF-5E-F1 | Fan Checklist
VAVs:
| VAV-L5-E-1 | VAV Checklist
Ductwork Checklist
| VAV-L5-E-1A | VAV Checklist
Ductwork Checklist
| VAV-L5-E-1B | VAV Checklist
Ductwork Checklist
| VAV-L5-E-2 | VAV Checklist
Ductwork Checklist
| VAV-L5-E-2A | VAV Checklist
Ductwork Checklist
| VAV-L5-E-2B | VAV Checklist
Ductwork Checklist
| VAV-L5-E-3 | VAV Checklist
Ductwork Checklist
| VAV-L5-E-3A | VAV Checklist
Ductwork Checklist
| VAV-L5-E-3B | VAV Checklist
Ductwork Checklist
| VAV-L5-E-4A | VAV Checklist
Ductwork Checklist
| VAV-L5-E-4B | VAV Checklist
Ductwork Checklist
| VAV-L5-E-4C | VAV Checklist
Ductwork Checklist
| VAV-L5-E-5 | VAV Checklist
Ductwork Checklist
| VAV-L5-E-7 | VAV Checklist
Ductwork Checklist
| VAV-L5-E-6 | VAV Checklist
Ductwork Checklist
| VAV-L5-E-6A | VAV Checklist
Ductwork Checklist
| VAV-L5-W-1 | VAV Checklist
Ductwork Checklist
| VAV-L5-W-2 | VAV Checklist
Ductwork Checklist
| VAV-L5-W-2A | VAV Checklist
Ductwork Checklist
| VAV-L5-W-3 | VAV Checklist
Ductwork Checklist
| VAV-L5-W-4 | VAV Checklist
Ductwork Checklist
| VAV-L5-W-5A | VAV Checklist
Ductwork Checklist
| VAV-L5-W-5B | VAV Checklist
Ductwork Checklist
| VAV-L5-W-6 | VAV Checklist
Ductwork Checklist
| VAV-L5-W-7 | VAV Checklist
Ductwork Checklist
| VAV-L5-W-8 | VAV Checklist
Ductwork Checklist
| VAV-L5-W-8A | VAV Checklist
Ductwork Checklist
| VAV-L5-W-9 | VAV Checklist
Ductwork Checklist
SITE QA |  | All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Indoor Equipment

## TO BUILD - LEVEL 11
Project Breakdown | Checklists
PROJECT NAME: 380 St Kilda Rd Level 2, 5, and 11
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA | All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Indoor Equipment