## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-260-CIV-FER-Piling Pad (Supply and Install)
ITP Description: |  | Piling Pad (Supply and Install)
Discipline (e.g. CIV/STR/RAIL: |  | 260-CIV-FER
Revision Number: |  | 0
Revision Date: |  | 2025-05-07
ITP created by: |  | Josiah Butter
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Ferris Road use only
Inspection & Test Plan - Piling Pad (Supply and Install) WAP_FER_260
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-05-07
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Standard Section 204 (Dec 2015) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Standard Section 173 (Oct 2008) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | Temporary Works Design - Crane Piling Pad Design | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Class 3 Crushed Rock | IFC Drawings VicRoads: Section 204 Section 173 | Material shall meet the requirements as per Temporary work design requirements Enter: TeamBinder Material approval No. | Document Review | Each Lot | HP | SE/Site Supervisor | NATA Test –Material Test Report PSD,LL,PI,PL,MMD & OMC This ITP
2.2 | CTCR | IFC Drawings VicRoads: Section 204 Section 173 | Material shall meet the requirements as per Temporary work design requirements Enter: TeamBinder Material approval No. | Document Review | Each Lot | HP | SE/Site Supervisor | NATA Test –Material Test Report PSD,LL,PI,PL,MMD & OMC This ITP
2.3 | Recycled Concrete | IFC Drawings VicRoads: Section 204 Section 173 | Material shall meet the requirements as per Temporary work design requirements Enter: TeamBinder Material approval No. | Document Review | Each Lot | HP | SE/Site Supervisor | NATA Test –Material Test Report PSD,LL,PI,PL,MMD & OMC This ITP
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | Temporary Works Design Drawings VicRoads: Section 204 Section 173 | Survey to set out extent of piling pad requirements. Survey pegs in place and clearly marks out the limits of works. | Visual and Measure | Each element | IP | Surveyor SE/PE | This ITP
3.2 | Check location of underground and above ground utilities | DBYD Combined Services Plan | Ensure that: - Dial Before You Dig - Services isolated - Permits obtained from internal and external authorities | Visual and Measure | Each Lot | IP | SE/PE | This ITP
4 | Construction / Installation Activities
4.1 | Ground Conditions | IFC Drawings | All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each Pad | IP | SE/Site Supervisor | This ITP
4.2 | Preparation of piling platform foundation (proof Roll) | Temporary Works Design Drawings VicRoads: Cl 204.12 | Areas upon which fills are to be constructed, all layers of fill, shall be test rolled in accordance with Section 173. Any unstable areas detected by test rolling shall be rectified. Nominated Authority to be present during all test rolling. Temporary work Design Drawing and equipment design requirements. No waving indication. | Visual | Each Pad | HP | SE/Site Supervisor Nominated Authority | This ITP
4.3 | Fill, Compaction and testing | Temporary Works Design Drawings VicRoads: Cl 204.10 Cl 204.13 | Bearing Test to support piling rig (as indicated in temporary works design). Testing and acceptance of compaction and moisture content as per VicRoads Cl 204.13 Attach: compaction test results | Test | Each Pad | HP | SE/PE | NATA Bearing Test Report Compaction Test Results
4.4 | Service Protection | Asset Protection Design | Install asset protection as required in Asset Protection Design | Test | Powercor | HP | SE/PE | This ITP
4.5 | Verify survey conformance | Temporary Works Design Drawings VicRoads: Cl 204.03 | Construction Tolerances finished ground level ± 40mm or equipment requirements Attach: Survey report | Visual | Each Pad | IP | SE/Site Supervisor | This ITP Survey report
5 | Post-construction / Post-Installations Activities
5.1 | Geotechnical Report | IFC Drawings Temporary Works Design Drawings VicRoads: Section 204 Section 173 | Geotechnical report to be conducted to ensure piling pad suitable for requirements Attach: Geotechnical report | Test | Each Pad | HP | SE/PE | Geotechnical report
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /