## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-260-CIV-FER-Piling Pad (Supply and Install) | itp |  |  |  |  | ITP-260-CIV-FER-Piling Pad (Supply and Install) Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-260-CIV-FER-Piling Pad (Supply and Install)
label | ITP Description: Piling Pad (Supply and Install)
label | Discipline (e.g. CIV/STR/RAIL): 260-CIV-FER
label | Revision Number: 0
label | Revision Date: 7/05/2025
label | ITP created by: Josiah Butter
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Standard Section 204 (Dec 2015)
label | 1.2 - Non Dependent
label | Reference - VicRoads Standard Section 173 (Oct 2008)
label | 1.3 - Non Dependent
label | Reference - Temporary Works Design - Crane Piling Pad Design
label | 1.4 - Non Dependent
label | Reference - IFC Drawings
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Class 3 Crushed Rock
label | Reference - IFC Drawings
label | ○ VicRoads: Section 204, Section 173
label | Acceptance Criteria - Material shall meet the requirements as per Temporary work design requirements
textbox | Enter: TeamBinder Material approval No.
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - NATA Test –Material Test Report PSD,LL,PI,PL,MMD & OMC, This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - CTCR
label | Reference - IFC Drawings
label | ○ VicRoads: Section 204, Section 173
label | Acceptance Criteria - Material shall meet the requirements as per Temporary work design requirements
textbox | Enter: TeamBinder Material approval No.
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - NATA Test –Material Test Report PSD,LL,PI,PL,MMD & OMC, This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Recycled Concrete
label | Reference - IFC Drawings
label | ○ VicRoads: Section 204, Section 173
label | Acceptance Criteria - Material shall meet the requirements as per Temporary work design requirements
textbox | Enter: TeamBinder Material approval No.
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - NATA Test –Material Test Report PSD,LL,PI,PL,MMD & OMC, This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Survey Set-out
label | Reference - Temporary Works Design Drawings
label | ○ VicRoads: Section 204, Section 173
label | Acceptance Criteria - Survey to set out extent of piling pad requirements.
label | ○ Survey pegs in place and clearly marks out the limits of works.
label | Method - Visual and Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Check location of underground and above ground utilities
label | Reference - DBYD Combined Services Plan
label | Acceptance Criteria - Ensure that:
label | — Dial Before You Dig
label | — Services isolated
label | — Permits obtained from internal and external authorities
label | Method - Visual and Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Construction / Installation Activities
checkpoint | 4.1 - Ground Conditions
label | Reference - IFC Drawings
label | Acceptance Criteria - All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | Method - Visual
label | Frequency - Each Pad
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Preparation of piling platform foundation (proof Roll)
label | Reference - Temporary Works Design Drawings
label | ○ VicRoads: Cl 204.12
label | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, shall be test rolled in accordance with Section 173. Any unstable areas detected by test rolling shall be rectified. Nominated Authority to be present during all test rolling.
label | ○ Temporary work Design Drawing and equipment design requirements. No waving indication.
label | Method - Visual
label | Frequency - Each Pad
label | Category - HP
label | Responsibility - SE/Site Supervisor, Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Fill, Compaction and testing
label | Reference - Temporary Works Design Drawings
label | ○ VicRoads: Cl 204.10, Cl 204.13
label | Acceptance Criteria - Bearing Test to support piling rig (as indicated in temporary works design).
label | ○ Testing and acceptance of compaction and moisture content as per VicRoads Cl 204.13
label | ○ Attach: compaction test results
label | Method - Test
label | Frequency - Each Pad
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - NATA Bearing Test Report, Compaction Test Results
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Service Protection
label | Reference - Asset Protection Design
label | Acceptance Criteria - Install asset protection as required in Asset Protection Design
label | Method - Test
label | Frequency - Powercor
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Verify survey conformance
label | Reference - Temporary Works Design Drawings
label | ○ VicRoads: Cl 204.03
label | Acceptance Criteria - Construction Tolerances finished ground level ± 40mm or equipment requirements
label | ○ Attach: Survey report
label | Method - Visual
label | Frequency - Each Pad
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP, Survey report
date | Date Completed:
section | 5. Post-construction / Post-Installations Activities
checkpoint | 5.1 - Geotechnical Report
label | Reference - IFC Drawings, Temporary Works Design Drawings
label | ○ VicRoads: Section 204, Section 173
label | Acceptance Criteria - Geotechnical report to be conducted to ensure piling pad suitable for requirements
label | ○ Attach: Geotechnical report
label | Method - Test
label | Frequency - Each Pad
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - Geotechnical report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP