## Table 1
Abbreviations
Third Party |  | TP |  |  | RSA Contractors | RSA |  |  | Nominated Project Personnel |  | NPP | Principle Contractor |  |  | PC
Surveyor |  | SUR |  |  | RPEQ | RPEQ |  |  | Supervisor |  | SUP | Inspect |  |  | INS
Test |  | TST |  |  | Project Engineer | PE |  |  | Witness Point |  | WP | Hold Point |  |  | HP
Visual |  | VIS |  |  | Check | CHK |  |  | Written |  | WRI | Monitor |  |  | M
Milestone |  | MST |  |  | Review | R
Inspection and Test Plan Details | [11 empty] | Contractor |  |  | Client
Item | Inspection Activity |  | Work By | Standard / Spec |  | Criteria |  |  |  | Frequency | Record | Resp | Type | Signoff | Resp | Type | Signoff
1 | Survey Set Out |  | Contractor | Technical Specification |  | The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works |  |  |  | Prior to commencement | ITP Verification Checklist/Site Survey | RSA | WP |  | Senex | WP
2 | Site Services |  | Contractor | Technical Specification |  | Contractor shall take reasonable steps to locate all existing service on the site. Where existing services are identified they shall be clearly marked for the duration of the works. |  |  |  | Prior to commencement | Site general layout drawing | RSA | HP |  | Senex | Hold Point
3 | Lot Identification |  | Contractor | Technical Specification |  | Location of works identified in accordance with the Project Technical Specifications. |  |  |  | 1/Lot | Attached Drawing | RSA | CHK |  | Senex | Check
4 | Clearing |  | Contractor | Technical Specification |  | Clearing shall be performed within the limits of the works indicated on the drawings. Trees, shrubs, logs, debris, perishable material, organic matter, fallen trees, overhanging branches and surface obstructions shall be removed from the stripping area. |  |  |  | 1/Lot | ITP Verification Checklist | RSA | HP |  | Senex | Hold Point
5 | Grubbing |  | Contractor | Technical Specification |  | Roots from trees and large shrubs shall be excavated to the extent to be agreed with the Superintendent. |  |  |  | 1/Lot | ITP Verification Checklist/Lot Map | RSA | CHK |  | Senex | Check
6 | Stockpile of Materials |  | Contractor | Technical Specification |  | Cleared and grubbed materials shall be stockpiled or disposed of as directed by the superintendent |  |  |  | 1/Lot | ITP Verification Checklist/Lot Map | RSA | CHK |  | Senex | Check
Built in accordance with this document: | [7 empty] | Signed Position |  |  |  | Date
Test results received. Lot conforms to Specification: | [7 empty] | Signed Position |  |  |  | Date
Document Status
Revision Status |  | Responsible Person |  |  | Signed |  | Dated |  | Revision
Draft By: |  | Madhu Achana
Reviewed By:
Submitted By:
Approved By: