## Master List Templates
Id | Type | Name | Values | Prompting Name
6824d8e7-41a9-4dca-bef7-b072ac9b82c0 | checklist | RSA.WP28.FIC - ACCESS TRACK - Rev2.0 | itp | RSA.WP28.FIC - ACCESS TRACK
69387c76-6a81-4cd5-b6a1-5fb8b21f99b2 | section | FIELD INSPECTION CHECKLIST ACCESS TRACK
022fd95d-5237-41be-947f-5d65485e7d37 | checkpoint | CH and FDM clearance
ecd64d70-71b0-4c45-b19d-ef348573705d | signoff | HOLD POINT
fa656ecc-8a11-4fd3-8b48-e85d2de166a8 | checkpoint | Identify extent of work area, clearance boundaries and any required surveying works
9cd406a0-7916-4cf2-84aa-1cd3ef7f23f8 | checkpoint | Measure access road dimensions as per IFC
39d8127c-4df2-42da-8a43-20634c7914c7 | checkpoint | Clear & Grub
62d483f9-9717-459b-8507-3c390f3b7ae2 | checkpoint | Form track profile
9d0dbe2b-ba18-4b5d-9190-d8dc61793978 | checkpoint | Construct erosion and sediment controls
db5541c9-66d7-4b26-be35-507e91222438 | checkpoint | Construct water way barriers crossings
8ef879d7-2257-4f9d-8429-40efeb51cab3 | checkpoint | Gravel cap access track (if applicable)
e5960946-98c8-450c-9374-3a9adb1efd53 | checkpoint | RSA QA Inspection
29102593-1758-4123-b5b7-25627eede0c1 | signoff | HOLD POINT
81ac979c-6389-4763-b9a5-182d12096eed | checklist | RSA.WP28.FIC - FENCING & GRIDS - Rev2.0 | itp | RSA.WP28.FIC - FENCING & GRIDS
fe3b6b3a-395c-4e1f-8cd6-8457c3d37cfd | section | FIELD INSPECTION CHECKLIST FENCING & GRIDS
c5e2fbfd-517c-47a7-8dd3-585197f53867 | checkpoint | CH & FDM Clearance
1d86cd3c-1c45-4588-b040-928cd6bc756d | signoff | HOLD POINT
91f45ff0-2a78-47a0-b18c-cc897ff200b9 | checkpoint | Identify Work Area, boundaries of Fencing
e43dae43-2af4-4f3f-a2ab-44e7d07ffb44 | checkpoint | Inspect fencing materials
83ff1169-bd15-4472-afda-be13ec4fa6fc | checkpoint | Installation of fencing
c399b626-d3e9-432e-bcb7-a2cef7acefed | checkpoint | Concrete for base of fencing
9050c22d-0cdb-4f8d-9d98-38e9efb6d067 | checkpoint | Fence posts caps
ec952728-95a9-4d3d-a797-3adfa2b5b196 | checkpoint | Welding
b242b80f-c61d-43c0-8377-a8fa2db5acbb | checkpoint | Welds Galvanized Painting
15c7992f-55d2-4ca0-84bb-369113072faa | checkpoint | Gate Chain and Carabiner clips
b187d229-1ef3-4c62-b0a7-f8af9f2b6f85 | checkpoint | Box Out Grid Footings and Prep Site
41b71f21-327e-4afc-98df-9bb78afd6bcc | checkpoint | Inspect grid materials
9a7e08f6-af83-4ec6-bee7-06a88c9d9d64 | checkpoint | Compaction for Grid base
1d1e0818-68eb-45c6-a7b3-bac784e6d73b | checkpoint | Concrete Abutment / Install Base Slab (if required)
0465663b-a0b6-4e62-8519-809113177a84 | checkpoint | Position and Install Grid
25579f57-9e69-48df-ba45-9be41f42cdda | checkpoint | Install and Compact Gravel Ramps
95318c65-425c-4f30-a7bf-e01cabbed195 | checkpoint | Attach Fence to Box Assembly
99485ed6-e7ff-4695-afb1-f454172a9332 | checkpoint | RSA QA inspection
6f4cfae8-0531-44f8-814c-049e6334ab2a | signoff | HOLD POINT
a2f28301-ad52-4600-adf7-85ceaf790734 | checklist | RSA.WP28.FIC - LEASE PADS - Rev2.0 | itp | RSA.WP28.FIC - LEASE PADS
f51fedc0-fa6b-44cd-8b0c-d780ffaae9f9 | section | FIELD INSPECTION CHECKLIST LEASE PADS
cb8b0a99-5fd0-425a-873d-86dc491fb502 | checkpoint | CH and FDM clearance
1e094529-19b3-411a-991b-ac1018ed126a | signoff | HOLD POINT
f6a6b65f-46f3-4688-ab37-57a92dfdcbaf | checkpoint | Identify work area, boundaries and survey requirement
8f18f6f6-44ad-42d2-92a1-800791b3005d | checkpoint | Clear & Grub Topsoil and stack timber
072d34b6-613b-42ce-ab8e-f599f3531cfc | checkpoint | Lease Entry Construction
ed51c11b-1006-4c98-afed-520a9534beee | checkpoint | Lease construction
a2365bd3-d844-4786-83a5-b0ac4ce0e38a | checkpoint | Compaction of layers in 300mm layers
bac5b8eb-e813-4801-b37f-1ea055a7e56a | checkpoint | Proof roll
4417cd67-86a5-4a89-864a-b89288a0154a | checkpoint | Verification of cross falls/laser set ups
d46dac32-34bb-4c41-8565-14db0cbb69cb | checkpoint | Final Trim
3b5097b0-2749-47cb-b951-529fd87b3445 | signoff | HOLD POINT
11e7a05b-3b5e-4256-b29f-fe3bdebdc116 | checkpoint | DCP Testing
09866dc9-38ea-445d-b786-c575f4420528 | signoff | WITNESS POINT
a14f9901-271b-47fa-9a7a-69026aa125c9 | checkpoint | Gravel Cap (as required)
b26012a9-9c09-4e9e-9c05-edecfd3751de | checkpoint | Install ESC
5ad1a4c9-4620-4f50-8b61-85c29a8338ca | checkpoint | Cellar Installation
7bd2a227-6be0-425a-9790-f512d0f7cc09 | checkpoint | Conductor Installation – Record plumb
366fb9b2-36ce-410c-b910-bf5811ebfcd2 | checkpoint | Conductor cemented in place
54f716c1-ada9-41ef-88aa-52dfd809f0ca | checkpoint | 4 x cattle panels to be installed
2e30158d-48d1-403f-8c98-fe7eb452d3db | checkpoint | Well signage and Pipeline entry mark completed
be858ad0-ac49-4b59-b219-f5d25fe7793e | checkpoint | As Built Completed
df28eb7c-e3c4-48ba-87b1-76f9672bb41e | checkpoint | RSA supervisor inspection
8bedfbdd-7ac2-42bd-9c27-ec20351f38ec | signoff | HOLD POINT
cf576cdc-3ae5-41af-bd9b-2d78c5d476d2 | checklist | RSA.WP28.FIC - PRELIMINARY - Rev2.0 | itp | RSA.WP28.FIC - PRELIMINARY
113ae58b-3e03-4a2d-941d-8b9bceb8d1a9 | section | FIELD INSPECTION CHECKLIST LEASE PADS
93e363bd-3c35-4235-9930-675bbefbd32d | checkpoint | Access documentation of relevant ATW, LARs/PTA, Cultural Heritage, Clearance Request
e9bc2d2f-7b2e-432f-aaa8-91b07b26a2cf | signoff | HOLD POINT
25c23025-b9a2-4229-9c53-72be2794cffb | checkpoint | Mobilisation of Machinery & Fit for Purpose inspection
141eb26d-6031-4789-9d7f-2588c2ddf3d1 | signoff | HOLD POINT
0fd53f78-656e-40d9-aed1-433c179fa64f | checkpoint | Gravel Compliance
db9e68e9-2210-4718-b706-26a3fef98fa7 | checklist | RSA.WP28.ITP | itp | RSA.WP28.ITP
3b25b908-a6c8-48de-bf4b-65181a189d03 | section | 1 - Preliminary
850f0d2d-e837-45e1-957a-2c0c2bea1604 | checkpoint | 1.1 - Access Documentation
71c2652f-7ab6-5b8e-afd5-0999f1ee4481 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Relevant ATW
97ae41d2-6732-56ca-9fb9-64ea2941a8d4 | note | ○ LARS / PTA
6a0359e9-cc47-5927-a9b2-ed9b4a787f82 | note | ○ Cultural Heritage Clearance Request (Works Notice)
d604ac57-73cc-5b5f-afb5-440d174be5f0 | note | Frequency - Prior to Start
a800cf7d-c606-50ae-bacc-65efa86b9387 | note | Test Method - Review
7ff3cadf-d9f2-57b3-9200-a0a6909f0805 | note | Acceptance Criteria - All documents in place and correct.
0150894b-d52f-5631-843d-2ee874db1a54 | note | Verifying Documents - LARS / PTA
75400374-4aef-59a7-9fd6-d101805f10b0 | note | ○ Landholder Notification
588b7862-2838-583b-a2aa-f3eb6a7f436c | note | ○ Weed Washdown Cert.
122e8c07-037c-5d44-9453-3f33288412e8 | note | ○ Species and Fauna Management
3d6d9a8f-a1d6-5ee0-aae3-5ed7ff8a237e | note | ○ Cultural Heritage Induction Attendance Register
a1557186-6986-583d-a255-dee2bc65ba71 | note | ○ Cultural Heritage Clearance Report / Form
d8dd3f3b-5552-5f65-bc70-2b66681032fd | note | Responsibility: RSA - H
9a85cf4c-a1e4-584a-8f63-bf382649b517 | note | Responsibility: Senex - H
6714bc34-c61a-4e96-88cc-4323e4cde7a5 | signoff | HOLD POINT
19b16ff4-7eef-4840-a386-028e5d20bc96 | checkpoint | 1.2 - Mobilise Machinery & Fit For Purpose (FFP) Inspection
381c782b-00ca-5ca8-9c5c-4382d4c9d6bf | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs), and Construction Management Plan (CMP)
065bd560-768b-5cb9-841d-a84d4043fa81 | note | Frequency - Prior to Start
18f47546-90e5-54e6-af8e-d3c69fcdfa8a | note | Test Method - Review
eae80768-863c-5915-beb3-671f35b3d196 | note | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant.
211967ee-ba0d-541b-9ee4-03158a196dd9 | note | Verifying Documents - Weed Declaration Certificate.
e12e18f0-78ca-51f0-89c9-a93ce4c77fff | note | ○ Appenate FFP Form
8c4945ca-d2cf-5cf6-8a42-87bae3f60b96 | note | Responsibility: RSA - H
4dd3db65-480c-5365-9730-f2b736ccec03 | note | Responsibility: Senex - W
a6fba66c-3e3c-4f01-9799-288ac753c774 | signoff | HOLD POINT
8229142c-0706-4362-9241-0bd14005ecc6 | checkpoint | 1.3 - Gravel Compliance
385afd1d-df84-575e-af4f-af410405c9fc | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 6
c76360b0-71ba-5e28-8c3b-538f04689c68 | note | Frequency - Each Quarry
e2bc2527-6b8a-5ab2-810b-f252894cae43 | note | Test Method - Lab Testing
ed741200-ce4a-5f2b-9775-8b07097075b0 | note | Acceptance Criteria - Grading C
2e089bff-de73-5253-91c0-d9b81a026d66 | note | Verifying Documents - NATA Test Report
bb87964a-eb52-58e6-b550-0871125d05a3 | note | Responsibility: RSA - R
9af022e6-a69e-5ac8-8524-c5679a55f3f0 | note | Responsibility: Senex - W
9a667e0f-dc3b-424b-83b1-8497bcd09dbb | section | 2 - Access Tracks
5ad1f17d-9eaf-4846-9df3-14990b351427 | checkpoint | 2.1 - CH and FDM Clearance
30c443b9-3322-5a7e-900a-4889c351ba5d | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW
5185c499-a3f4-56ab-88a9-0996883b0a09 | note | Frequency - Each Track
977f8040-eef7-559a-b57e-0d60266ea000 | note | Test Method - Visual Inspection
eca97658-4b03-5a7e-83a4-401c7a4480b7 | note | Acceptance Criteria - CH FDM clearance certificate
8a7f3a78-a3cc-5c58-b3c4-3704cd178fab | note | Verifying Documents - Access Track FIC
f222fc20-48a8-5b3b-a6e5-c61d894c7d5b | note | Responsibility: RSA - H
668dea2f-8766-5ee4-918a-233d29d3aaa7 | note | Responsibility: Senex - W
5c819ef6-e291-4fdc-9b52-73eaefe2549c | signoff | HOLD POINT
cc36f2c8-609d-4d86-a973-5ff58ecb89ff | checkpoint | 2.2 - Identify work area, boundaries and survey requirement
b2b10686-2ba6-5db7-ad6d-394f71aadb6b | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC and GIS
c083b610-b6e0-5b84-bf40-2263c8970a13 | note | Frequency - Each Track
78693886-f437-52bc-8968-27d34e5fc4d7 | note | Test Method - Set out by Licensed Surveyer
4db46a11-42cd-596d-b8f1-ffc0fc107498 | note | Acceptance Criteria - In accordance with IFC Drawing
024671a2-f03f-58d9-a4db-8f717c951189 | note | Verifying Documents - Access Track FIC
ed2e8a97-a632-5986-b559-ba8fe49f7573 | note | Responsibility: RSA - M
4e383561-d48a-5183-8c0c-17d00ecf3cb2 | note | Responsibility: Senex - W
26c61e15-1310-42fd-abf3-2ba4e610c09b | checkpoint | 2.3 - Confirm dimensions
1ea9ed77-1863-5765-8dd7-6b3e6be4a471 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
49eee572-842c-551a-986c-ad3fffce1b08 | note | Frequency - Each Track
b54ed677-af33-50d0-8024-fb46f4c7e004 | note | Test Method - Visual Inspection
966370cf-92e4-5235-9b75-a17c3b4ec5ba | note | Acceptance Criteria - Standard road is 6m wide and maximum disturbed area is 10m
5035bc4e-bdc0-5f65-a2c3-a9fab55d6228 | note | Verifying Documents - Access Track FIC
baae03a8-4935-5253-9461-20cde25f0f01 | note | Responsibility: RSA - M
57349cf7-4d4b-5e68-9c23-a82f3d6697db | note | Responsibility: Senex - W
90b9b923-28e2-411b-8fbd-ac3e3f1e7b1e | checkpoint | 2.4 - Clear & grade
caf420a0-69c6-5324-8458-f65d0f8219de | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 3.2
f6d8847e-8f67-5e34-b8fd-1d719c6efb25 | note | Frequency - Each Track
bf7ea54b-e639-512d-8b69-55c423a20398 | note | Test Method - Visual Inspection
24462674-f55a-552c-8985-e3b91d348bf7 | note | Acceptance Criteria - Cleared vegetation stockpiled at regular intervals.
26f401f0-c7e7-5da9-9423-7abce781de96 | note | Verifying Documents - Access Track FIC
85c1b368-4261-5cc9-b69d-8dd821d0e61d | note | Responsibility: RSA - M
f2f12b5e-7e0d-5db8-b78b-490dfad69578 | note | Responsibility: Senex - W
109c90b4-05ad-4cfc-bd56-dc91a202a1af | checkpoint | 2.5 - Form track profile
728a64a0-8f55-519f-9d37-f17fdaebb317 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
fed6f6b3-6c36-5a38-ab4d-46ee2aeb0bb8 | note | Frequency - Each Track
43ba0971-364a-5b5b-9b57-4825c1d81dbb | note | Test Method - Visual Inspection
8c6c732e-fede-5b3a-be5b-ec99a903ec06 | note | Acceptance Criteria - Roads flat grade and rills blended into shoulders
28c83248-fbf4-5b8c-b278-6dc84377af11 | note | Verifying Documents - Access Track FIC
a388cc4d-b8e4-5ef9-8450-18aee29c80cf | note | Responsibility: RSA - M
4337e830-738f-5dc3-9f83-d04bdc219034 | note | Responsibility: Senex - W
f031dd33-5663-47ed-afcc-55fd059bbd2d | checkpoint | 2.6 - Construct erosion and sediment controls
0dd456fb-3c6c-5287-ac1b-ca744ac731df | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - ESC IFC, SOW Section 4.3.2, Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
8e3811c4-8482-5e08-b462-5c7b34e0a5b5 | note | Frequency - Each Track
506797d4-4801-5460-a966-faf9ad5bf996 | note | Test Method - Visual Inspection
1fab1059-e279-566f-a48f-14f130825665 | note | Acceptance Criteria - Ensure site specific erosion and sediment control plan implemented.
900e59a1-d8f0-57ab-b0b4-da2650ea2f7b | note | Verifying Documents - Access Track FIC
671bf565-37e2-565a-b7f9-cd527a3d693c | note | Responsibility: RSA - M
e6936ca9-4a86-59b9-9e1b-9eb4803ed453 | note | Responsibility: Senex - W
7ec7b574-936e-49ba-8a58-e481af6b95b6 | checkpoint | 2.7 - Install water way barriers
d1c9eec5-c240-5684-a6b4-879211276f9c | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC GAR, Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2.12, SOW section 4.3.2, OPS-ATLS-CS-DWG-021 WP28 HILLANDALE CROSSING CID
63ef24ba-b3f7-510a-b8bf-3d25067b1792 | note | Frequency - Each Crossing
53389d7b-e0de-5817-baa0-4a9ab4b81d04 | note | Test Method - Visual Inspection
ed8dcfae-eafa-55c2-a0ef-60be074978a7 | note | Acceptance Criteria - Crossings shall be battered to permit heavy vehicle access, bases may be boxed out and backfilled with compacted gravel as detailed in specific construction design and approved by Senex.
618aae41-cbe8-5efa-a85a-d577c26e4ed4 | note | Verifying Documents - Access Track FIC
c610e7bd-5c50-57ff-abf0-74b41219ad01 | note | Responsibility: RSA - M
756efaef-53e1-542e-a5e9-c84b2023e895 | note | Responsibility: Senex - W
1b0fd264-9545-4a1d-9538-2e044f5a67b2 | checkpoint | 2.8 - Gravel cap access track
2df38e39-db83-5331-8aad-f23f88a79cc0 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
b561f9a5-5945-579c-95fd-88e1c5735ac4 | note | Frequency - Each Track
872e3559-2163-56e5-aaca-1be5af609a7e | note | Test Method - Visual Inspection
678a8fda-6b43-5e93-ae67-1dff9362a4f7 | note | Acceptance Criteria - Compacted to 80 mm and from approved source.
0fa64714-022b-5898-9516-e78df935af66 | note | Verifying Documents - Access Track FIC
d9f8f40c-12d4-5ae1-a668-32e26cfb6d41 | note | Responsibility: RSA - M
11a4b761-e759-5681-9373-8653cdabd984 | note | Responsibility: Senex - W
a3291f52-3917-4123-8864-3e08c9e1a4dc | checkpoint | 2.9 - RSA QA inspection
42cb65bf-b111-5a54-9e12-d023367d0056 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
a5fb43a7-60e2-59a2-80fd-7de67421d4d0 | note | Frequency - Each Track
f0e6481a-cf1b-569d-9463-a83cd1da767b | note | Test Method - Visual Inspection
9121480d-2407-559a-8bf1-b9c9f13ddd01 | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
32c2b27f-7e05-59f6-bcc3-17253cec4dee | note | Verifying Documents - Access Track FIC
22ce588f-7126-50c2-a198-7dfb5d8d4ada | note | Responsibility: RSA - H
346b5b1d-0537-5430-a530-106858ac772d | note | Responsibility: Senex - N/A
b2cc6697-593d-4085-9e7e-1956e09bf93d | signoff | HOLD POINT
f479ab23-723e-4f5e-819a-15ef56e38d9e | checkpoint | 2.10 - Final inspection of access tracks
4219a84c-6515-54e9-807a-b7eaf042211b | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
aa1e469f-600a-50f3-a12e-d67ea71254c7 | note | Frequency - Each Track
7bacc9ff-be70-5434-9243-1d327a5c1360 | note | Test Method - Visual Inspection
27ce9cd6-7a35-5aff-adfc-4fa7f95b1d6d | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve access road is fit for purpose prior to machinery being demobilised.
662a3ebc-87f1-5885-a949-fe8da499983d | note | Verifying Documents - Access Track FIC
6a7fb81d-d50b-5272-9319-b6206065559f | note | Responsibility: RSA - N/A
9cd8c4d0-ca51-5faf-bf9a-d14173d90998 | note | Responsibility: Senex - H
48512afa-dd59-43da-bd3d-2b72143fd68a | signoff | HOLD POINT
0f3e0f6b-895d-48d6-9211-041617e0cb24 | section | 3 - In Field, Property Fencing and Grid (Fencing)
e8c463d7-16d0-4cfe-9b5d-d3cb95c17342 | checkpoint | 3.1 - CH and FDM Clearance
b3350eda-f686-5468-a4a1-713693de11b0 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW
c0bb5a0e-7d70-5cda-9916-06613295acae | note | Frequency - Each Track
f6544ef5-54b7-516f-890c-287f2fa78f10 | note | Test Method - Visual Inspection
7302d98a-0475-5cf1-8f45-33a3c1d472c2 | note | Acceptance Criteria - CH FDM clearance certificate
7b295463-902f-58ff-aa54-62f33ee43a54 | note | Verifying Documents - Grid &Fence Installation FIC
c933dd94-e48e-5a16-bdc3-884d88c8ce88 | note | Responsibility: RSA - H
5356ada4-12a9-5ed5-9b38-31db2d3eb42d | note | Responsibility: Senex - W
5379c057-6b81-4b92-98e6-932a2fdcf5ce | signoff | HOLD POINT
d8be985d-6a61-482f-8749-32de0b38c197 | checkpoint | 3.2 - Identify work area, boundaries and survey requirement
608a920b-dbcc-5a9f-aec5-9e5b74d76cf6 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC
6ad1779d-3c05-5f6a-a769-86779b78ab9b | note | Frequency - Each Fence ID
2f8e1065-5a3c-52e7-a462-4ebf6296c848 | note | Test Method - Set out by Licensed Surveyer
212cfc38-1b6c-5a1b-90ea-516b669d3ac5 | note | Acceptance Criteria - GIS Survey Data
2e717952-00e3-5730-809c-eeb2969f4b99 | note | Verifying Documents - Grid &Fence Installation FIC
f8af2027-28e9-5771-ba70-a656f6bbba32 | note | Responsibility: RSA - M
b1f3e031-1ff5-50bf-8f91-43a199b919a4 | note | Responsibility: Senex - W
a430d830-2694-4561-a443-432307b18cf1 | checkpoint | 3.3 - Inspect fencing materials
0d1f95b0-3c9a-509f-b2ac-7aae366d3535 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
cbd6b87a-fc56-586f-9f25-8f40f6d04bf2 | note | Frequency - Each Delivery
8273aff2-da89-527d-8d8a-f7522e6ac965 | note | Test Method - Visual Inspection
a54b5c27-1368-5919-bd45-765e85758105 | note | Acceptance Criteria - AS 1725.1, AS 3679.1, All steel items shall be hot dip galvanised in accordance with AS 4680.
f542227f-669f-556e-8372-dccaf64726ed | note | Verifying Documents - Grid &Fence Installation FIC
525c590e-ff2f-5c9f-b256-480ab7f92a93 | note | Responsibility: RSA - M
acd34ec9-49c4-504f-84d8-b0c1fdeb081e | note | Responsibility: Senex - W
8380e6bd-fb45-4fbc-b2b3-4d4e369cdc0a | checkpoint | 3.4 - Installation of Fencing
4d62397a-75e6-5f16-83e3-181d67fe7885 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
89edaa9d-cbaa-50d1-87fe-5b029df7b71b | note | Frequency - Each Fence ID
dca4e1b8-d405-5ad4-86ae-eca6fcec1b00 | note | Test Method - Visual Inspection
c7f53dea-d620-5a2b-8238-05e3fa82b56a | note | Acceptance Criteria - Holes shall be a minimum of 250mm in diameter and 900mm deep, protude heights for strainer & coners posts shall be 1300mm, for stay blocks 300mm, for star pickets 1250mm, nominal depth for star pickets 550mm, Spacing between any 2 posts shall not be less than 3m or greater than 5m.
dafd4551-10c7-5c3f-84d8-336703228a00 | note | Verifying Documents - Grid &Fence Installation FIC
8a2e7f96-c614-5183-b79c-99c2aa35b3da | note | Responsibility: RSA - M
9648a8db-8592-5c2c-84e1-97a69382b1d8 | note | Responsibility: Senex - W
963f0b50-0baa-42f6-b03e-1bf1c286448c | checkpoint | 3.5 - Concrete for base of fencing
10cfca6d-dfed-5e29-903b-4ed8f4010bff | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
04d82ca1-4b81-5bbf-833d-0927bd75dfd0 | note | Frequency - Each Fence ID
91618a94-ed10-59b3-8c5b-72ad460c2a39 | note | Test Method - Visual Inspection
b99f0869-563a-58f1-ba73-1fd96a159770 | note | Acceptance Criteria - Posts and stay blocks shall have concrete around the base to a minimum height of 50mm above ground level, concrete 25MPa
735b22c8-bc95-59c1-9516-077e27f8a338 | note | Verifying Documents - Grid &Fence Installation FIC
73dea84a-3e92-516e-8751-9a5ec6beacda | note | Responsibility: RSA - M
10c629d1-d24c-5e60-b6c5-7da1e01f5704 | note | Responsibility: Senex - W
d70184e5-4bcb-4d33-ab5a-3ff96904623a | checkpoint | 3.6 - Welding
9be878fd-2804-5455-bf34-fc8f6451112d | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 3.3
ef53dce5-48e8-5c97-a66c-98a19d6585aa | note | Frequency - Each Fence ID
150a70b3-5089-591c-ad99-1e6a41898635 | note | Test Method - Visual Inspection
330e74d0-1626-5ccf-a9f2-9df5f0debaab | note | Acceptance Criteria - Stays shall be fully welded to posts and stay blocks, Gate hinges shall be fully welded to gates and posts, Welded joints to be coated with a zinc rich coating.
98af8858-4b36-5f6c-bf5d-fc3c0209838c | note | Verifying Documents - Grid &Fence Installation FIC
2ab04a1f-10eb-5e79-baa0-1d08aeb6907c | note | Responsibility: RSA - M
d9b3ec14-cc1e-571f-bbca-2db8e80a0e05 | note | Responsibility: Senex - W
517ea42b-c552-479d-a864-b973c5beeb80 | section | 3 - In Field, Property Fencing and Grid (Grid)
6ffd652f-ec23-482a-9621-b93a79e5c7ee | checkpoint | 3.7 - Box out Grid Footings and Prep Site
69739b47-8f7a-52d7-a7f1-d2c6fe0d27ae | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC
31e6f89e-29e3-5d8f-9679-f9b8da3d98eb | note | Frequency - Each Grid
f91af252-f90a-546d-ae84-e8d1dedd54d2 | note | Test Method - Visual Inspection
762b68fe-3e8e-5d5e-b182-27ebeb9a5b51 | note | Acceptance Criteria - No more than 150mm
a3770ce1-bdf1-57db-854f-e1e912ddeb1d | note | Verifying Documents - Grid &Fence Installation FIC
55ea5b38-224d-54f2-9a7a-9ada9152aa00 | note | Responsibility: RSA - M
86d8f843-cfa2-5951-b412-459e2284c061 | note | Responsibility: Senex - W
4d19bd7e-1778-476c-8928-366c0adffc9c | checkpoint | 3.8 - Inspect Grid materials
1136fbc4-ad2b-58e4-81cb-93a5997c6036 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4
77d534fc-f522-5b0c-a01c-81a94dcf6d01 | note | Frequency - Each Delivery
c1655859-6553-5c39-88cd-00dcc16a6fb8 | note | Test Method - Visual Inspection
b1b83eb6-9889-5363-b399-884c65693ee7 | note | Acceptance Criteria - AS 1725.1, AS 3679.1, All steel items shall be hot dip galvanised in accordance with AS 4680.
b8e29335-a94a-5557-b03a-07cde5445b3e | note | Verifying Documents - Grid &Fence Installation FIC
ef6531c9-0eac-51fe-b687-087a01560cbd | note | Responsibility: RSA - M
3ce1e7f0-bde1-57c5-9aed-6acfadf92fd5 | note | Responsibility: Senex - W
9ab73d4a-1686-4e0e-9144-1f16919356b3 | checkpoint | 3.9 - Compaction for Grid Base
cbdc2e8e-2e8f-511e-928f-d64fa84c8daa | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.3
fef92fba-8359-5c3b-8dd0-c56fa7fea1d9 | note | Frequency - Each Grid
0bdb1ec1-6946-5f2b-8648-0809c5a826a1 | note | Test Method - Visual Inspection
e29d1bcc-55ba-5325-a6a3-37fb4c2009ba | note | Acceptance Criteria - Compact sub-grade adequately to provide a firm foundation.
ac157748-51eb-55dc-b9ba-5ae8bdee76a8 | note | Verifying Documents - Grid &Fence Installation FIC
24c4f43b-f9e2-5e3f-ae19-1548cb6882c2 | note | Responsibility: RSA - M
06b603eb-1a8e-53e6-93b2-8e740f55484a | note | Responsibility: Senex - W
c28c7cc2-ce11-45b5-a498-aa6db0cb2232 | checkpoint | 3.10 - Concrete Abutment/Install Base Slab (if required)
8d452b36-9cc6-56d4-84a0-e64590ecc5ae | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4
97acee21-3ff3-5ba2-b202-1fae84464aa8 | note | Frequency - Each Grid
fc83bcd8-de52-5656-9049-073b1b9bd5c7 | note | Test Method - Visual Inspection
b1f0cf02-4606-5d33-806a-1f01c18d1ae2 | note | Acceptance Criteria - Posts and stay blocks shall have concrete around the base to a minimum height of 50mm above ground level, concrete 25MPa
71bdab26-18b8-564a-893f-24d198a89416 | note | Verifying Documents - Grid &Fence Installation FIC
611d7720-ef3a-5797-8867-9019695d59eb | note | Responsibility: RSA - M
40884875-d3e8-5a41-88a7-3c25a4907dd3 | note | Responsibility: Senex - W
50cfe786-5b27-498b-9987-b43aa9958eff | checkpoint | 3.11 - Position and Install Grid
c4c7e191-c922-5dcc-b58b-d6c84d5750d9 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4.4
806a3660-3d95-50a4-86af-1ad0e9dd50f0 | note | Frequency - Each Grid
08d99d0b-1ed3-51ff-bb4c-b0991ba3b07a | note | Test Method - Visual Inspection
46efd4cf-213d-5da5-b4a9-0c928b6b58e0 | note | Acceptance Criteria - Loaction and position in accordance with drawings as applicable
e7430aea-0550-5348-92bb-301c2020a1ad | note | Verifying Documents - Grid &Fence Installation FIC
05eec265-03e7-5fe0-8d10-5e48d2bd49b9 | note | Responsibility: RSA - M
48b4d40e-315c-57e5-8880-c556f60b53f1 | note | Responsibility: Senex - W
6bc06196-dc0e-4d26-b080-d46cc4cbf043 | checkpoint | 3.12 - Install and Compact Gravel Ramps
3c82bfcc-a7c4-5d11-b283-b7312311c0f2 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Std Drawings
657e387c-47c6-5d10-9ab6-f40acf741924 | note | Frequency - Each Grid
42ca19ab-9701-5ff3-a331-62068849c432 | note | Test Method - Visual Inspection
72e26060-3aa3-57fa-8daa-2011175dd7a4 | note | Acceptance Criteria - Ramps adequateley compacted
08e3792b-2d7b-525a-8963-b6ada3760e88 | note | Verifying Documents - Grid &Fence Installation FIC
bd609ba3-975e-59be-9a6a-7a9ab8a30177 | note | Responsibility: RSA - M
15262867-b4b8-505a-a3db-a61cba5f7108 | note | Responsibility: Senex - W
cfacbe90-9f4d-4251-8ff0-702292535954 | checkpoint | 3.13 - Attach Fence and Gates to Box Assembly
9d5d0ce4-3849-569a-bfe5-5c7e1bffaae8 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Std Drawings
b1810841-ab52-5060-80cc-367aa9e22f7b | note | Frequency - Each Grid
329cc764-6094-529c-95dc-ac594dc7b3a9 | note | Test Method - Visual Inspection
49f6aa77-c623-5c02-8906-96b4643e16df | note | Acceptance Criteria - In accordance with drawings
d9597ee6-cf60-558a-ace9-44e5b7aa3895 | note | Verifying Documents - Grid &Fence Installation FIC
e264d52c-f2bd-50c8-be6f-e4317f5e2f40 | note | Responsibility: RSA - M
e7eb0e9d-5a92-5ecb-858c-78ddc1f99720 | note | Responsibility: Senex - W
6338b478-60e3-4d55-9bd2-e1ca0fa199a8 | checkpoint | 3.14 - RSA QA inspection
56315118-5a29-5e84-9bd2-88ef1f7c930d | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
9eee845a-5b64-5c36-8f4d-d3f5a3fa2d30 | note | Frequency - Each Grid
28d75ef2-bf0a-51f2-97d2-caec73f52535 | note | Test Method - Visual Inspection
709f73e5-5ed6-5bfa-8f9c-0754c64a268f | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
eae51c37-ff80-5163-8230-41d1557a0c2b | note | Verifying Documents - Grid &Fence Installation FIC
b596122e-8d39-5884-9a03-f1a684141ed7 | note | Responsibility: RSA - H
ee404a61-27a2-5ef5-8b4e-521351410070 | note | Responsibility: Senex - N/A
73b830a9-79f6-4513-960f-e638094163fb | signoff | HOLD POINT
a16c5e69-7d9e-43bd-b97c-01bbbe101c85 | checkpoint | 3.15 - Client Signoff
6a7cf3e6-3ed5-5c55-8705-dc44201f45e8 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
13d3f1b0-c976-5230-b04a-ed0f42cc97aa | note | Frequency - Each Grid
f21911c7-8756-5f97-bb7a-bb894e684879 | note | Test Method - Visual Inspection
5f43cbe5-5342-5944-b9b2-e4319ba05cc1 | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
a33a9079-484e-5a64-bd18-766210d3da69 | note | Verifying Documents - Grid &Fence Installation FIC
ac71f739-5a26-5541-a671-d593c1b00c23 | note | Responsibility: RSA - N/A
3e74f123-d7fc-5b78-a196-3be2f982dd2b | note | Responsibility: Senex - H
8aaf4bb8-1163-4b9b-bae2-183bded972b4 | signoff | HOLD POINT
0f33aece-7d30-4cd1-b16f-902899fdc216 | section | 4 - Lease Pads
2cf0878c-587e-4c05-9aa7-e9fe2ddd793a | checkpoint | 4.1 - CH and FDM Clearance
db815886-7611-5a9e-9f7d-c7d2f7d8226a | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SOW
e62688ed-6080-51ef-a110-dd2e4e6cee33 | note | Frequency - Each Track
8968094a-5b2b-5d53-9707-a0fb69a47642 | note | Test Method - Visual Inspection
68c83728-07db-500c-b85c-df12a7f9c2df | note | Acceptance Criteria - CH FDM clearance certificate
36ab60ed-2cda-5be0-9775-608fd615993e | note | Verifying Documents - Lease Pad FIC
68084d1f-f5c2-5a69-a5d0-86eca9d4951e | note | Responsibility: RSA - H
4dd84816-3d87-58d6-abd9-78ac7b3076d4 | note | Responsibility: Senex - W
2d0b9b9a-03d0-4a46-8836-134917c43c4d | signoff | HOLD POINT
a5fc9710-c238-4078-a126-414013183bc6 | checkpoint | 4.2 - Identify work area, boundaries and survey requirement
5bb4e77a-0ccf-5853-82b9-8ad5fe881e65 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specification/SOW/IFC
79659bc0-7d3e-5dde-aebe-4797de251208 | note | Frequency - Each Pad
9b53adb4-106e-5021-be93-1c9f39ce9b6f | note | Test Method - Set out by Licensed Surveyer
eec36b56-1f52-53e1-ae76-1f75e30dd8ae | note | Acceptance Criteria - GIS Survey data
1a8cdeef-f917-5aa0-ae59-a7e95464a432 | note | Verifying Documents - Lease Pad FIC
d744ccc7-a605-5cb7-aace-f3fc6f7cf257 | note | Responsibility: RSA - M
54a3e599-8b48-5ca2-b25e-28a62e204150 | note | Responsibility: Senex - W
2d3521f1-2464-42f4-9d6a-0b5468ea6233 | checkpoint | 4.3 - Clear & grade
0e73c60e-f035-5e11-b1d1-e056de9b9033 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 3.2 & 4
2d39d3da-e0bb-5331-872b-e5d99412b667 | note | Frequency - Each Pad
1b2d29e8-1442-58f0-aab6-86e94fce2e55 | note | Test Method - Visual Inspection
7fdbb518-7bb1-53dc-862a-e3d071c47303 | note | Acceptance Criteria - Cleared vegetation and topsoil stockpiled at regular intervals.
7a1cf8e5-582a-58dc-868f-375614d2998a | note | Verifying Documents - Lease Pad FIC
19f2f20a-71c2-5484-b6ac-517e0897e257 | note | Responsibility: RSA - M
43d1e7ed-78d4-5f58-8ac8-fee28d67ae63 | note | Responsibility: Senex - W
78794d06-2e92-4076-bb84-c78b93dff820 | checkpoint | 4.4 - Lease Entry Construction
13a6101f-e6f0-5586-b80e-6380604c4bc0 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5
270d0597-9576-5d00-9974-004cee5d0206 | note | Frequency - Each Pad
dd7b143d-9181-56d7-8866-38d9e1370377 | note | Test Method - Visual Inspection
445cc346-c290-5a98-b24f-637c85eee5b4 | note | Acceptance Criteria - Access points into the lease pad shall be 12.0m wide minimum.
65dc846d-1325-5bd5-8e1a-42b63efbf3c3 | note | Verifying Documents - Lease Pad FIC
2a298de7-606d-5d54-b242-d0d16250dfb8 | note | Responsibility: RSA - M
4c394f6c-7dec-5851-b0c8-ba962811ac88 | note | Responsibility: Senex - W
4beb8d3b-2048-45d8-b1dd-6c76c63f39d4 | checkpoint | 4.5 - Lease construction
0250a1d2-a9dc-5f63-9336-e46aad6e6ebe | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002 Rev 0 Sections 5
a76cc721-82d5-5060-aee6-660f2037b4d9 | note | Frequency - Each Pad
5606388d-fbb5-57b7-9305-9f4d231c4030 | note | Test Method - Laser Level and Visual Inspection
3cd6d9b7-182e-50c2-a7c3-08af46f830bc | note | Acceptance Criteria - Lease pad shall be minimum 78m long and 66m wide. Lease pad surface shall have a crossfall of between 0.65% to 1%
a4a8c94a-66c0-51e6-9e68-457d2a73eb2e | note | Verifying Documents - Lease Pad FIC
9710aede-e4ff-5c39-b4dd-d502e0958dbd | note | Responsibility: RSA - M
be14d55e-b08e-59fa-9818-629ad762bfda | note | Responsibility: Senex - W
6e79e404-4333-4d51-80ac-065e9fdb5bbd | checkpoint | 4.6 - Earthworks compaction of layers in 300m layers
ccff948f-0cc4-5c5b-8357-48018e176044 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 3.3.5
709a08c1-dc7b-5e10-bf93-49fadd86a90d | note | Frequency - Each Pad
5f518703-7c68-5217-8497-189248c39da3 | note | Test Method - Visual Inspection
2d09ad25-8b5e-5b8f-8628-8224267df523 | note | Acceptance Criteria - AS1289.5.2.1, AS1289.5.1.1, AS1289.5.6.1, AS1289.5.1.1
d8be7567-686f-512f-8438-65821a916719 | note | Verifying Documents - Lease Pad FIC
43f7d542-0350-57cb-a3db-452e3b90cd93 | note | Responsibility: RSA - M
359826e5-38f7-5a95-94b6-e8298c2071e3 | note | Responsibility: Senex - W
22ce8de1-ca16-443b-a01a-012554bb9a29 | checkpoint | 4.7 - Proof Roll
78412160-4c13-5817-b5cb-4f26ec32aa85 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 4 & 5
e5c6ea3e-cf4d-5fa1-bce0-faed8ca40066 | note | Frequency - Each Pad
76a8001f-098c-503b-94f8-36a059b55a56 | note | Test Method - Visual Inspection
26a01e45-bada-58bc-8dde-878ec6c0c4fc | note | Acceptance Criteria - Proof roll the pad surface to identify any soft or loose zones which shall be stripped and stockpiles or tined, dried out and re-compacted.
2446a39f-6a4a-5841-9b86-e2bfb58e0e02 | note | Verifying Documents - Lease Pad FIC
7f1d745d-1e8c-515c-a796-62d426022f85 | note | Responsibility: RSA - H
01ea3155-1396-5f8b-a4d4-bde5b18ad086 | note | Responsibility: Senex - H
1d62a51a-4d90-4faf-81d2-4a320b92c70c | signoff | HOLD POINT
10a82c81-83db-4169-8059-bb89b3f40331 | checkpoint | 4.8 - Verification of cross falls/laser set ups
103b5317-f871-5c62-bb49-0a1a0ea7265c | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5
0105fc9a-0069-5ee0-b5a6-657629ac2812 | note | Frequency - Each Pad
d02c70fa-4e2c-5c8d-aba1-2c0e678c6809 | note | Test Method - Laser Level and Visual Inspection
dde8f7b3-4661-5f94-8a30-fbc57cfc1f8d | note | Acceptance Criteria - The lease pad surface shall have a crossfall of 0.4% along pad width and 0.5% along pad length
ff33a8c1-3dd4-573f-9b48-6d3c4ec743e7 | note | Verifying Documents - Lease Pad FIC
5ae50079-cc66-5488-a251-cd9afc4ee765 | note | Responsibility: RSA - M
9b6d4ace-287b-59f7-8fcb-382da35dd467 | note | Responsibility: Senex - W
913b40c2-d173-48e0-a989-7584086b62c5 | checkpoint | 4.9 - Final Trim
610a4d52-8655-5e2c-a8b5-1218bbae7198 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-002: Section 5
773fba31-039c-5325-883d-5a68a99b8335 | note | Frequency - Each Pad
5bd006d5-c2fb-5b10-b393-2736cb9111da | note | Test Method - Visual Inspection
cbfc78fa-f329-539c-9fca-75c82a3fca47 | note | Acceptance Criteria - Surface levels are in accordance wth drawings
9673e223-b5b8-519b-80b6-66a2e7a8de74 | note | Verifying Documents - Lease Pad FIC
ecd871cc-3214-5e16-9870-5462d8ee3d7c | note | Responsibility: RSA - H
62e0a164-ffed-5094-828b-1f7cee663a50 | note | Responsibility: Senex - H
3390e976-cff4-4868-b45d-9ad0c907a22d | signoff | HOLD POINT
a67b6679-58dc-4fce-976b-f73d528856f8 | checkpoint | 4.10 - DCP test on hardstand
49286f28-faad-538d-870b-f3efd7d9a4f6 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-GAR-001 Rev 1A
fe65c750-9b86-5b15-a3df-22c76fba7a26 | note | ○ OPS-QLDS-CI-SPE-002 Rev 0 Sections 3.5 and 6
cc58161e-e865-5137-bbb6-f8021dfb9e79 | note | Frequency - Each Pad
8c0484fb-34af-54c7-b935-39b698a3247f | note | Test Method - DCP Test Record
6a4244b6-614d-546e-b25b-8c784b7278df | note | Acceptance Criteria - Testing undertaken by Senex Representative on the final Layer. Minimum 4 blows per 100 mm.
97f83169-b43c-5eac-bd9d-61f7a9fc33dc | note | Verifying Documents - Lease Pad FIC
a729e989-0a9d-5507-8315-8438aaa7db9a | note | Responsibility: RSA - W
8c651de2-6a00-5f8e-8bbf-f891e1b97113 | note | Responsibility: Senex - H
1d7dc3ff-d0e6-46ad-8d63-4121280bab69 | signoff | HOLD POINT
b9f4b07d-353b-4a3c-b00a-f5e4e4d59e7f | checkpoint | 4.11 - Gravel cap works (where required)
5aecbbcc-0320-5a6d-b887-cb575798eab7 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-GAR-001 Rev 1A
0831df4a-4cd8-5018-b761-83b69b0687d1 | note | Frequency - Each Pad
67f398f5-c2e8-5e4d-8c19-677caf4b9c51 | note | Test Method - Visual Inspection
2f933709-7a59-519a-a93a-2ffe1fc011bb | note | Acceptance Criteria - Required 100-millimetre hardstand thickness
ed60f36c-bdc7-5bb4-add9-431c25291c63 | note | Verifying Documents - Lease Pad FIC
1b23a5c3-f1a2-5d51-91de-daab3c721b09 | note | Responsibility: RSA - M
4c24e5e2-27a5-5a68-8320-eaa7a222f74c | note | Responsibility: Senex - W
7de7fdb1-81a0-4b4b-8211-b59ee2443523 | checkpoint | 4.12 - Install ESC
7a77b136-f1fc-5841-8743-cdba26b87e82 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-EN-PRC-003 Rev 1
8ec1c2b1-0e3f-5db1-a37f-f64b1439ab33 | note | Frequency - Each Pad
40d164e5-9907-5130-bd65-26f946ec7db7 | note | Test Method - Visual Inspection
c2f2f4dc-d195-54a3-80a6-045490067e74 | note | Acceptance Criteria - As per IFC drawings
b29e1df9-0e38-5c0f-9309-0c0c21ddcf34 | note | Verifying Documents - Lease Pad FIC
d1693b7f-3158-58ed-89e8-573ac9b2b1de | note | Responsibility: RSA - M
07eeeec7-8f51-56fc-bc41-4bf60e6c48ac | note | Responsibility: Senex - W
da9e2727-99ec-44fd-9732-9cb3ff1e0e68 | checkpoint | 4.13 - Cellar Installation
801f3803-19f9-590e-b201-9ce6b5c4a481 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001
52e9eaee-62ec-5730-8460-565bf3600e01 | note | ○ SENEX-QLDS-DR-SPE-001
e948df1b-fe62-51c2-b1fb-e98018fc73c5 | note | Frequency - Each Pad
5dd8dc8b-2e6e-50c8-92c4-cc048c8cebd7 | note | Test Method - Visual Inspection
5392092f-7fe3-54c0-9d55-814ce9f0b6fd | note | Acceptance Criteria - Install cellar and conductor as per Senex Specifcations
5383d5c4-5fa1-5cb5-9517-e613d9126bba | note | Verifying Documents - Lease Pad FIC
5a953011-0f55-5e29-9baf-13e8cfde9508 | note | Responsibility: RSA - M
62327299-fbd9-53ea-ab74-db21f1597e64 | note | Responsibility: Senex - W
78d8b988-7fcd-4470-83cd-a4f08c1db105 | checkpoint | 4.14 - Conductor installation
543a0417-e4d1-5de5-88f4-f22bf63a60e4 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001
4a07e841-83d3-5ad0-910f-88854d6aad96 | note | ○ SENEX-QLDS-DR-SPE-001
7b909e33-2d63-53cd-a8e0-7a96667d2d32 | note | Frequency - Each Pad
7b6562d3-7c58-5ee1-8ee0-73368b07e52e | note | Test Method - Visual Inspection
9c22c318-85e3-5a0d-9610-f930dcf1d68a | note | Acceptance Criteria - Install cellar and conductor as per Senex Specifcations
2e7566d8-8c95-5818-a91c-fa5c3e52fe71 | note | Verifying Documents - Lease Pad FIC
dadf14ff-7fa2-54eb-81aa-c3736f2fe1c8 | note | Responsibility: RSA - M
213b9771-6e02-53f6-9108-7a4a97e486d7 | note | Responsibility: Senex - W
426216fe-bd13-41dc-ac36-19fe8d1ef459 | checkpoint | 4.15 - Conductor cemented in place
5a1c598d-0398-5e99-b4bd-0c4e87b2141f | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-GAR-001
a542b032-66c8-54d9-b260-36d62ad7ba81 | note | ○ SENEX-QLDS-DR-SPE-001
74d0dd08-dece-50f3-9878-979b79f5ea32 | note | Frequency - Each Pad
da578f2a-f845-5c13-aa91-564d2b533771 | note | Test Method - Visual Inspection
6215193b-e15a-57e3-8fee-22acb6e7ba9a | note | Acceptance Criteria - Conductor shall be concreted into the conductor bore with Neat Class A concrete with a compressive strength of 25MPa-32MPa.
6da49dd2-c874-5e47-b67b-75f089d9cdd9 | note | Verifying Documents - Lease Pad FIC
a9a8b0b8-fbc8-5a26-b3f2-5dd5396c9176 | note | Responsibility: RSA - M
e8ddd8a7-c546-5848-8b39-ee703a293a17 | note | Responsibility: Senex - W
f3117cd7-e873-4bd0-8f56-c73b40fc7ccf | checkpoint | 4.16 - 4 x cattle panels to be installed
e8343cc9-52ca-59b7-a295-cb5577a85634 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001
195d40fe-b4fd-5799-aadb-c91a68c21a5f | note | Frequency - Each Pad
aca62499-8693-5bb7-89dc-af551e42be37 | note | Test Method - Visual Inspection
94f2ff0d-8d9d-5ab0-ac71-a0999a9f1244 | note | Acceptance Criteria - Installed approriately to barricade cellar.
ee2d84e3-c584-5314-b063-b59e060654ea | note | Verifying Documents - Lease Pad FIC
dfae8373-23e5-5f6e-bc2f-a9770f946f3b | note | Responsibility: RSA - M
f5f48170-8cbe-5a4b-847f-ddf12d8f9a62 | note | Responsibility: Senex - W
ed2ae613-f213-48a2-8d1e-bdaca4983eee | checkpoint | 4.17 - Well signage and pipeline entry mark completed
5e0ba97f-d78c-5e81-a8fe-679464f47b5a | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001
a04efad0-59cd-54a9-8790-1c25ad5e7884 | note | Frequency - Each Pad
5de25e3c-9548-5aa4-b6fb-1639c3e31bbb | note | Test Method - Visual Inspection
d949b94d-11d1-5c4d-9607-9efc905f4d6e | note | Acceptance Criteria - Senex supervisor to install Well signage.
c5bac930-bccd-59a8-a049-d49bd707bc24 | note | Verifying Documents - Lease Pad FIC
91547ff1-7458-5c0c-a7f5-f5f7b79a8854 | note | Responsibility: RSA - N/A
69020045-c239-5d7d-b536-5029091a5e48 | note | Responsibility: Senex - W
de0d7dea-64f1-42e5-8efb-2766c5c4f19f | checkpoint | 4.18 - As Built drawings
78448a3e-b4c5-5ea7-ad03-78464e3299eb | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC Well Pad Cut Fill Lease Pad Layout Drawing,SOW
f54e03cb-a216-5e28-8f8a-7b5d17da36cf | note | Frequency - Each Pad
bea3011a-e100-561c-9704-7b72939217d7 | note | Test Method - As Built Measurement
e22d9a7a-09df-5659-a654-d6ae9ad3c66a | note | Acceptance Criteria - As built Lease Pad Layout Drawing including ESCP
bd0b95ce-102d-5484-9ce0-56715da0005f | note | Verifying Documents - Lease Pad FIC
2edf1584-2b88-5ff7-976e-75b21d77abc8 | note | Responsibility: RSA - N/A
d32ecc59-de32-583e-b058-1948a2d9737f | note | Responsibility: Senex - W
d0aa8a66-adb2-4dd7-9eba-be0da54aeef1 | checkpoint | 4.19 - RSA Supervispr inspection
4ee7d60d-e2c5-59f0-8e3b-05c4ca55c924 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 & OPS-QLDS-CI-SPE-002
00575f72-aa66-5277-8117-554ee62e5478 | note | Frequency - Each Pad
f5f49b26-7082-5a7a-b866-42e9036127f8 | note | Test Method - Visual Inspection
d24190e2-c105-531d-b793-bb998067e882 | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
4f395cd1-bfb3-5d4c-befc-daf2a66a69c0 | note | Verifying Documents - Lease Pad FIC
756f6fdc-b986-53af-8bb1-d3ecea6f6ad4 | note | Responsibility: RSA - H
cdd81c8b-ced8-5dd7-b1c0-d50eb79d9493 | note | Responsibility: Senex - N/A
2b320a1c-8a4b-4c86-bbc6-b9667ad8fd31 | signoff | HOLD POINT
0c74c43e-afea-40e4-8428-5e1f82948ea1 | checkpoint | 4.20 - Client Signoff
88adf751-88f7-5499-a75a-2e36121818e2 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 &OPS-QLDS-CI-SPE-002
faa9f5ef-0a27-50d6-8cc9-215865a2dacc | note | Frequency - Each Pad
1a19e18e-9b90-5df5-a56a-7deac1e079ea | note | Test Method - Visual Inspection
54502229-c3d2-5db9-8c46-4e8887db476f | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
945a166e-e965-5f6b-a45e-79ff36c32594 | note | Verifying Documents - Lease Pad FIC
2505f2c3-85cf-54a4-9d71-58b8af01ee35 | note | Responsibility: RSA - N/A
9e8deef2-a7a5-520b-b5f8-be931d629273 | note | Responsibility: Senex - H
3c4a1e69-50c3-46aa-b2e6-419eb29659ac | signoff | HOLD POINT
2f0e9f06-b599-40c2-a349-b81952e15585 | section | Reference Documents
cd4bac6c-b1fe-408a-9f3c-40a6ca6ee8b2 | checkpoint-no-value | Reference Documents:
3ee55128-e638-55c7-9e0a-edd08bd54646 | note | SENEX-QLDS-EN-PRC-003 rev 1 (Queensland Erosion and Sediment Control Procedure)
f5931ffb-1737-5e76-ba25-8703364e0121 | note | OPS-QLDS-CI-SPE-003 REV 0 (Fencing, Grids and Gateways Civil Specification)
bbfb6c57-357c-50a4-a756-77ed7aac2e62 | note | OPS-QLDS-CI-SPE-002 Rev 0 (Lease Pads, Hardstands, Access Roads Civil Specification)
7df7496a-a078-50fd-8964-3bf189030bfb | note | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
1cc94b81-18d8-5fc7-af30-e21707fbd93e | note | SENEX-QLDS-CI-GDL-001 Rev D (Whoa-Boy Construction Guidelines)
1871146a-0de5-5b5d-bd4f-3e2b4a5af22c | note | SENEX-QLDS-DR-SPE-001 Rev 4 (Conductor and Cellar Installation Specification)
e0800e5c-727d-5637-8ad4-114f4d2cce0d | note | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
587ac5ea-06b4-57ce-8c29-1d7eb5192a15 | note | OPS-QLDS-CI-GAR-001 Rev 1A (Well Lease Layout Standard Drill Rig Civil General Arrangement)
7ec76482-c08a-457a-a805-27986355c9d2 | section | To be completed upon completion of all work activities
cf62cb0b-e4c6-4298-b0e1-4d0e8730e64f | checkpoint | This is to confirm that the above ITP has been completely signed off. All necessary inspections have been completed, the verifying documents have been provided, and the works conform to the contract specification
5f584e7a-a84f-53b7-909c-18ae703aa8c5 | note | Completed By:
8ad45b02-c269-529a-bcc1-de4a886cdb7f | textbox | Contractor Representative - Name:
32a5bead-bd3e-5e5a-825c-2b50efd28c74 | textbox | Contractor Representative - Position:
179cf659-e8c0-5fdc-adf7-3575bd95f808 | textbox | Senex Construction Representative - Name:
2b59d25d-8fe3-5658-9beb-6456c0232a50 | textbox | Senex Construction Representative - Position:
b559f123-c776-59b3-9f83-bccacbc9cc0f | note | Approved By:
282912a7-00bb-5ab8-9f41-44fcb38d7107 | textbox | Client Representative - Name:
5c80d40c-d465-54ca-b9d0-8291c6abb015 | textbox | Client Representative - Position:
db995536-f190-5a12-a959-de32801538fd | date | Date:
96a60e51-6445-4c84-b9e5-dceb1db5722f | signoff | Add Signature