## Enabling Works
ITP - Vulnerability Users Package 13
Site Location |  |  | LINCOLN ROAD
Enabling Works - Footpath, Kerb and channel
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Every site | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Materials
2 | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Every site | Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5 | In process Inspection | FH concrete QA sheet, photos. Concrete Plant Docket | Site Engineer
3 | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Every site | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | In process Inspection | FH concrete QA sheet | Site Engineer
CIVIL WORKS
4 | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
5 | Tactiles | Visual | TDM Technical Standards - FP0010 | Each PX | Warning TGSI tiles should have 100mm concrete slab underneath | Inprocess Inspection, Measurement | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
5.1 |  |  | NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every site | Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. | In process Inspection | Photos | Site Engineer
5.2 |  |  | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every site | Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep. | In process Inspection | Photos | Site Engineer
5.3 |  |  | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every site | TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing | In process Inspection | Photos | Site Engineer
RAMM DATA
6 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | As built records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Sumesh Sharma | Initial | SS |  | Date: | 2023-01-26
Approving Delegate |  | Daniel Tat | Initial | DT |  | Date: | 2023-01-27

## Traffic Islands
ITP - Vulnerability Users Package 13
Site Location |  |  | SANDSPIT ROAD / SOMERVILLE ROAD
Traffic Islands
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Materials
1 | Mountable Kerb | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Everysite | Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint | Inprocess Inspection | FH concrete QA sheet, photos. | Site Engineer
Construction
2 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | As per Construction Drawings | Survey Receipt. | Site Engineer
3 | Concrete Island | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | Kerbs to be haunced with 20MPa Concrete | Inprocess Inspection | Photos | Site Engineer
|  | QA FORM | TDM Technical Standards - IS0001 & IS0003 | Each Site | Basecourse to be 150mm min thickness of GAP65 | Inprocess Inspection | Photos | Site Engineer
4 | Concrete Infil | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 red oxide Cross Fall of 2% or max rise in centre of 180mm | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
Asbuilts
5 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Supervisor and Engineer
6 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Sumesh Sharma | Initial | SS |  | Date: | 2023-02-24
Approving Delegate |  | Daniel Tat | Initial | DT |  | Date: | 2023-02-24

## Stormwater
[7 empty] | Approved |  | Signature
|  |  |  | Contract Name: | Vulnerability Road User Package |  | FH Engineer |  | SS
|  |  |  | Procedure: | Storm water Drainage |  | FH Quality Manager |  | DT
Inspection & Test Plan / Checklist
Job No: 2095247
Detailed Location:
LINCOLN ROAD
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits & Services | H | Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space) | Prior to any construction commencing | Document Review | Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority | Permit attached or permit number noted. | Site Engineer
|  | H | Locate and mark out all existing services | Prior to any construction commencing |  | B4u dig procedure - follow utility protocols | B4u dig plans & GPR report attached | Site Engineer
2 | Pre-Construction Sign Offs | H | Sub-Contract and Supplier Agreements | Prior to commencement. | Document Review | Sub-Contract and Supplier Agreements to be agreed and signed | Subcontract and Supplier Agreements | Site Engineer
3 | Design | H | Design is approved and Drawings are of the latest revision. | Prior to commencement. | Document Review | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Drawing Register. | Site Engineer | Engineers Rep.
4 | Survey Set out | H | Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design | Prior to commencement. | Survey | As per HARRISON GRIERSON ENGINEERING DRAWING: 1040-A2110796 & Set out files | Survey Receipt. | Site Engineer
5 | Pipe and Manhole Material Compliance | H | Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards | Prior to commencement. | Document Review, Visual Inspection | Pipe shall be Check for freshly formed pipes and return if required 1) DN300 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP | Manufacturers Data Sheets, Delivery Dockets | Site Engineer
6 | Locate Existing Services by Hand Digging / Hydro Vac | H | Ensure all services conflicting with the line of trench have been exposed by hand digging. | Prior to commencement. | Potholing / Survey | All conflicts have been located. New services and / or conflicts to be advised to Project Manager. | As-built Drawings. Doc. Review | Site Engineer
7 | Trenching & Excavation | H | Excavation methodology | Daily | Prestart review | The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016) | Prestart RCP | Site Engineer
|  | M | Trench Profile - Width | Daily / as trenching takes place. Different depth methodology | Visual Inspection, Excavation methodology | Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing | Construction Photos | Site Engineer
|  | W | Trench Profile - Depth | Daily / as trenching takes place. | Visual Inspection, Measurement | Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings | FH Drainage Line Record / Construction Photos | Site Engineer
8 | Bedding for Concrete Pipe Laying & Manhole & Cesspit | W | Placing and compaction of Bedding Material. | Inspected continuously during placing and compaction of Bedding Material. | Visual Inspection | Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725 | FH Drainage Line Record / Construction Photos | Site Engineer
9 | Pipe Position Tolerance | M |  | At any point of pipe |  | Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design. | FH Drainage Line Record, Survey Data. | Site Engineer
10 | Trench Backfill - Placing & Compacting | M | Placing and compacting of Trench Backfill Material | Throughout Trench Backfilling operation. | Visual Inspection | Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm | Construction Photos | Site Engineer
11 | As-Built Drawings | W | Red pen marked-up As-Built of every 'Issued for Construction' AT drawings | Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure. | Drawings / Visual Inspection | As Built and GIS Data | Redline As-Built Drawings, scanned as .pdf files. | Site Engineer | Engineers Rep.
Comments:
|  |  | Daniel Tat |  | Signature: |  |  | Date:
QA checked By Quality Manager:
[5 empty] | Signature: |  |  | Date:
Accepted By Engineers Rep:

## Concrete Speedtable
|  |  |  | Process Control Plan |  |  | Approved |  | Signature
|  |  |  | Contract Name: | Vulnerability Users Package 13 |  | FH Engineer |  | SS
|  |  |  | Procedure: | Raised Speed Table |  | FH Manager |  | DT
Inspection & Test Plan / Checklist
Detailed Location |  |  |  | Corresponding Work Instruction: |  | Documentation Required |  | Compliance with Work Instructions and Specifications
LINCOLN ROAD
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer/MSQA Engineer Initials (Grey if not required) | Date(s)
1 | Permits | H | Obtain Permits | As required | Document Review | Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
2 | Pre-construction sign offs | H | Ensure that Sub-Contract and Supplier Agreements are signed | Prior to commencement | Document Review | Signed Subcontractor and Supplier Agreements | Subcontract and Supplier Agreements | Site Engineer
2.1 |  | H | Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS | Prior to commencement | Document Review | TMP is approved by CAR manager for each site and works are only completed within the approved dates.. | TMP on MyWorksites/On Site | Site Engineer
2.2 |  | H | Ensure all Sub-Contractors and Suppliers go through FH induction | On site daily | Induction | Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation | Hazard ID and Pre-starts to safety team | Site Engineer
3 | Design | H | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Prior to commencement | Document Review | IFC drawings have been received by Contractor | Check Drawing Register | Site Engineer | Design Engineer
4 | Installation of Erosion and Sediment Controls | H | Ensure that Erosion & Sediment Control in place | Prior to commencement | Visual Inspection | Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence | Environmental Controls Audit | Environmental Manager/Site Engineer
5 | Survey Setout | H | Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations) | Prior to commencement | Survey + Smart Level | Consistency with Construction Drawing | Site Photos post surveying | Site Engineer
6 | Locate Existing Services by Hand Digging | H | Ensure all services conflicting with the line of trench has been exposed by hand digging | Prior to commencement | Potholing | All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services | Digging and excavation checklist, service planes,As-Built Drawings Doc. Review | Site Engineer
7 | Material Compliance | H | LESA dowels to be used at all construction joints at 600mm clearance | Prior to pouring concrete | Document Review | Photos + Delivery Docket added to QA folder | Delivery Dockets / Photos | Site Engineer
7.1 |  | H | 0.25mm polythene layer placed across all surface area at bottom of raised table | Prior to pouring concrete | Visual Inspection, Document Review | Photos + Delivery Docket added to QA folder | Delivery Dockets / Photos | Site Engineer
7.2 |  | H | 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer. | Prior to pouring concrete | Visual Inspection | CIV >15 | Delivery Dockets | Site Engineer
7.3 |  | H | Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating. | Prior to pouring concrete | Visual Inspection | Photos | Photos
7.4 |  | H | All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder | Prior to pouring concrete | Concrete Delivery Dockets | Delivery Docket added to QA folder | Concrete Delivery Dockets | Site Engineer
8 | Temporary Works (Formwork) | W | Formwork to be set to correct line and level | Prior to pouring concrete | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer | MSQA Engineer
8.1 |  | H | Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry (1:10) and exit ramps (1:40) | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer | MSQA Engineer
8.2 |  | H | Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer | MSQA Engineer
8.3 |  | H | Raised Table ramps to be 1m across for entry and 4m for departure ramp.Toe to be 0.5m to 1m across for both entry and departure with 50mm asphaltic wearing course | Prior to pouring concrete | Measurement | Designer to inspect formation level | Site photos | Site Engineer | MSQA Engineer
8.4 |  | H | Raised Table ramps to be 1:10 gradient for ramps at entry and exit ramps to be 1:40 relative to the road | Prior to pouring concrete | Measurement | Designer to inspect gradient level | Site photos / Concrete Formwork Checklist | Site Engineer | MSQA Engineer
8.5 |  | H | The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured | Prior to concrete pour | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer | MSQA Engineer
9 | Reinforcing | H | All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @600mm centres placed across the construction joint | Prior to pouring concrete | Measurement | Concrete Inspection Record | Site photos/Concrete Formwork Checklist | Site Engineer | MSQA Engineer
10 | Concreting | H | The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required | Prior to concrete pour | Visual inspection | Engineer will be notified via email/SMS at least 24 hours before required for inspection | Email / SMS | Site Engineer
10.1 |  | W | Vibrator to be used throughout concrete pour | When pouring concrete | Visual Inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer
10.2 |  | H | Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top. | At completion of pour | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer | MSQA Engineer
11 | Curing | M | Concrete will be left for 48 hours minimum to cure before traffic is allowed on it. | Post Pour | Monitoring the time allowed for curing | 48 hours minimum have passed | Concrete Formwork Checklist | Site Engineer
12 | Remove formwork | W | Remove formwork after 48 hours | Post Curing | Visual inspection | Concrete Inspection Record | Concrete Formwork Checklist | Site Engineer
13 | Asphalt- Concrete extension slab/ Toe | H | Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC0022 | Prior to pouring concrete | Measurement | Pre pour Inspection Checklist, Concrete Inspection records | Site photos,delivery dockets | Site Engineer
13.1 |  | H | 200mm thick 50MPa Concrete with two layers of 663 mesh | Prior to pouring concrete | Measurement | Pre pour Inspection Checklist, Concrete Inspection records | Site photos,delivery dockets | Site Engineer
13.2 |  | W | Tack Coat between AC and Concrete slab | Post Curing | Visual inspection | Photos + Delivery Docket added to QA folder | Site photos | Site Engineer
13.3 |  | W | 50mm thick DG10 / Mix 7 | Post Curing | Measurement | Photos + Delivery Docket added to QA folder | Site photos,delivery dockets | Site Engineer
14 | Lot Number QA File | W | Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file | At completion of Lot | Document Review | All QA files compiled and sumbitted to client | QA records | Site Engineer
14.1 |  | W | Delivery Dockets to be included in QA file | At completion of Lot | Document Review | Delivery Dockets to be included in QA file | QA records | Site Engineer
15 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer