## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Enabling Works - Footpath, Kerb and Channel | [5 empty] | Sheehan Ave - ITP - Enabling Works - Footpath, Kerb and Channel
section | Site Set Out
checkpoint | 1 - Site Set out
note | VERIFICATION ACTIVITY - Surveyor
note | METHODS OR REFERENCE - Surveyor
note | FREQUENCY - Every site
note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
note | Hold Point - Mandatory HOLD POINT -
note | Records - Onsite records/photos
note | Onsite Responsibility - Site Engineer
holdpoint | HOLD POINT
section | Materials
checkpoint | 2 - Kerb & Channel
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
note | FREQUENCY - Every site
note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
note | Hold Point - In process Inspection
note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
note | Onsite Responsibility - Site Engineer
checkpoint | 3 - Channel Level
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
note | FREQUENCY - Every site
note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
note | Hold Point - In Process Inspection
note | Records - FH concrete QA sheet
note | Onsite Responsibility - Site Engineer
section | CIVIL WORKS
checkpoint | 4 - Concrete Footpaths
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
note | FREQUENCY - 10m Intervals
note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40. Clegg CIV > 12. Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish.
note | Hold Point - Inprocess Inspection
note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 5 - Tactiles
note | VERIFICATION ACTIVITY - Visual
note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
note | FREQUENCY - Each PX
note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
note | Hold Point - Inprocess Inspection, Measurement
note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 5.1 - Tactiles
note | VERIFICATION ACTIVITY - Visual
note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians. AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY.
note | FREQUENCY - Every site
note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
note | Hold Point - In process Inspection
note | Records - Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 5.2 - Tactiles
note | VERIFICATION ACTIVITY - Visual
note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
note | FREQUENCY - Every site
note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
note | Hold Point - In process Inspection
note | Records - Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 5.3 - Tactiles
note | VERIFICATION ACTIVITY - Visual
note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
note | FREQUENCY - Every site
note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
note | Hold Point - In process Inspection
note | Records - Photos
note | Onsite Responsibility - Site Engineer
section | RAMM DATA
checkpoint | 6 - As built information
note | VERIFICATION ACTIVITY - RAMM DATA SHEET
note | FREQUENCY - Every Site
note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
note | Hold Point - In Process Inspection
note | Records - As built records
note | Onsite Responsibility - Supervisor and Engineer
checklist | Traffic Islands | [5 empty] | Sheehan Ave - ITP - Traffic Islands
section | Materials
checkpoint | 1 - Mountable Kerb
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
note | FREQUENCY - Everysite
note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
note | Hold Point - Inprocess Inspection
note | Records - FH concrete QA sheet, photos.
note | Onsite Responsibility - Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
note | VERIFICATION ACTIVITY - Survey
note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
note | FREQUENCY - Prior to commencement.
note | ACCEPTANCE CRITERIA - Survey
note | Hold Point - As per Construction Drawings
note | Records - Survey Receipt.
note | Onsite Responsibility - Site Engineer
checkpoint | 3 - Concrete Island
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002, TDM Technical Standards - IS0001 & IS0003
note | FREQUENCY - Each Site
note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete, Basecourse to be 150mm min thickness of GAP65
note | Hold Point - Inprocess Inspection
note | Records - Photos
note | Onsite Responsibility - Site Engineer
checkpoint | 4 - Concrete Infil
note | VERIFICATION ACTIVITY - QA FORM
note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
note | FREQUENCY - Each Site
note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 red oxide, Cross Fall of 2% or max rise in centre of 180mm
note | Hold Point - Inprocess Inspection
note | Records - FH concrete QA sheet. Concrete delivery, Dockets kept as record
note | Onsite Responsibility - Site Engineer
section | Asbuilts
checkpoint | 5 - As built information
note | VERIFICATION ACTIVITY - Drawings
note | FREQUENCY - Every Site
note | ACCEPTANCE CRITERIA - As built drawings
note | Hold Point - In Process Inspection
note | Records - Asbuilt records
note | Onsite Responsibility - Supervisor and Engineer
checkpoint | 6 - RAMM DATA
note | VERIFICATION ACTIVITY - RAMM DATA SHEET
note | FREQUENCY - Every Site
note | ACCEPTANCE CRITERIA - RAMM SHEET
note | Hold Point - In Process Inspection
note | Records - Asbuilt records
note | Onsite Responsibility - Supervisor and Engineer
checklist-flat | Raised Speed Table | [5 empty] | Sheehan Ave - ITP - Raised Speed Table
checkpoint | 1 - Permits
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Obtain Permits
note | Frequency - As required
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
note | Records - Permit attached or permit number noted
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
note | Frequency - Prior to commencement
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
note | Records - Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
note | Frequency - Prior to commencement
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
note | Records - TMP on MyWorksites/On Site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
note | Frequency - On site daily
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Induction
note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
note | Records - Hazard ID and Pre-starts to safety team
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
note | Frequency - Prior to commencement
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
note | Conformance Criteria - IFC drawings have been received by Contractor
note | Records - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure that Erosion & Sediment Control in place
note | Frequency - Prior to commencement
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
note | Records - Environmental Controls Audit
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
note | Frequency - Prior to commencement
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
note | Conformance Criteria - Consistency with Construction Drawing
note | Records - Site Photos post surveying
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
note | Frequency - Prior to commencement
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Material Compliance
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
note | Conformance Criteria - Photos + Delivery Docket added to QA folder
note | Records - Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.1 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
note | Conformance Criteria - Photos + Delivery Docket added to QA folder
note | Records - Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
note | Conformance Criteria - CIV >15
note | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
note | Conformance Criteria - Photos
note | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.4 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
note | Conformance Criteria - Delivery Docket added to QA folder
note | Records - Concrete Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Temporary Works (Formwork)
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Formwork to be set to correct line and level
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
note | Conformance Criteria - Concrete Inspection Record
note | Records - Concrete Formwork Checklist
checkpoint | 8.1 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15)
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
note | Conformance Criteria - Designer to inspect formation level
note | Records - Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
note | Conformance Criteria - Designer to inspect formation level
note | Records - Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp.Toe to be 0.5m to 1m across for both entry and departure with 50mm asphaltic wearing course
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
note | Conformance Criteria - Designer to inspect formation level
note | Records - Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.4 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Raised Table ramps to be 1:10 gradient for ramps at entry and exit ramps to be 1:10 relative to the road
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
note | Conformance Criteria - Designer to inspect gradient level
note | Records - Site photos / Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.5 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
note | Frequency - Prior to concrete pour
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
note | Conformance Criteria - Concrete Inspection Record
note | Records - Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Reinforcing
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @600mm centres placed across the construction joint
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
note | Conformance Criteria - Concrete Inspection Record
note | Records - Site photos/Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Concreting
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
note | Frequency - Prior to concrete pour
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
note | Records - Email / SMS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1 -
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Vibrator to be used throughout concrete pour
note | Frequency - When pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
note | Conformance Criteria - Concrete Inspection Record
note | Records - Concrete Formwork Checklist
checkpoint | 10.2 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
note | Frequency - At completion of pour
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
note | Conformance Criteria - Concrete Inspection Record
note | Records - Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Curing
note | ACTION (Hold, Monitor, Witness) - M
note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
note | Frequency - Post Pour
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
note | Conformance Criteria - 48 hours minimum have passed
note | Records - Concrete Formwork Checklist
checkpoint | 12 - Remove formwork
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Remove formwork after 48 hours
note | Frequency - Post Curing
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
note | Conformance Criteria - Concrete Inspection Record
note | Records - Concrete Formwork Checklist
checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC0022
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
note | Records - Site photos, delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.1 -
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
note | Frequency - Prior to pouring concrete
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
note | Records - Site photos, delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.2 -
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Tack Coat between AC and Concrete slab
note | Frequency - Post Curing
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
note | Conformance Criteria - Photos + Delivery Docket added to QA folder
note | Records - Site photos
checkpoint | 13.3 -
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - 50mm thick DG10 / Mix 7
note | Frequency - Post Curing
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
note | Conformance Criteria - Photos + Delivery Docket added to QA folder
note | Records - Site photos, delivery dockets
checkpoint | 14 - Lot Number QA File
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
note | Frequency - At completion of Lot
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
note | Conformance Criteria - All QA files compiled and sumbitted to client
note | Records - QA records
checkpoint | 14.1 -
note | ACTION (Hold, Monitor, Witness) - W
note | Detail - Delivery Dockets to be included in QA file
note | Frequency - At completion of Lot
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
note | Conformance Criteria - Delivery Dockets to be included in QA file
note | Records - QA records
checkpoint | 15 - As-builts
note | ACTION (Hold, Monitor, Witness) - H
note | Detail - Red pen mark up drawings to be included in QA file
note | Frequency - At the completion of the Lot of work
note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
note | Records - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT