## Folder Structure
Site QA
Apartment Unit
Zone 1
| Ground Floor | Unit | 001 | Apartment Checklist
|  | Unit | 002 | Apartment Checklist
|  | Unit | 003 | Apartment Checklist
|  | Unit | 004 | Apartment Checklist
|  | Unit | 005 | Apartment Checklist
|  | Unit | 006 | Apartment Checklist
|  | Unit | 007 | Apartment Checklist
|  | Unit | 008 | Apartment Checklist
|  | Unit | 009 | Apartment Checklist
|  | Unit | 010 | Apartment Checklist
|  | Unit | 011 | Apartment Checklist
|  | Unit | 012 | Apartment Checklist
|  | Unit | 013 | Apartment Checklist
|  | Unit | 014 | Apartment Checklist
|  | Unit | 015 | Apartment Checklist
|  | Unit | 016 | Apartment Checklist
|  | Unit | 017 | Apartment Checklist
|  | Unit | 018 | Apartment Checklist
|  | Unit | 019 | Apartment Checklist
|  | Unit | 020 | Apartment Checklist
| Level 1 | Unit | 103 | Apartment Checklist
|  | Unit | 104 | Apartment Checklist
|  | Unit | 106 | Apartment Checklist
|  | Unit | 107 | Apartment Checklist
|  | Unit | 108 | Apartment Checklist
|  | Unit | 109 | Apartment Checklist
|  | Unit | 110 | Apartment Checklist
|  | Unit | 111 | Apartment Checklist
|  | Unit | 113 | Apartment Checklist
|  | Unit | 114 | Apartment Checklist
|  | Unit | 115 | Apartment Checklist
|  | Unit | 116 | Apartment Checklist
|  | Unit | 117 | Apartment Checklist
|  | Unit | 118 | Apartment Checklist
|  | Unit | 121 | Apartment Checklist
|  | Unit | 122 | Apartment Checklist
|  | Unit | 123 | Apartment Checklist
|  | Unit | 125 | Apartment Checklist
|  | Unit | 126 | Apartment Checklist
|  | Unit | 127 | Apartment Checklist
|  | Unit | 128 | Apartment Checklist
|  | Unit | 129 | Apartment Checklist
|  | Unit | 130 | Apartment Checklist
|  | Unit | 131 | Apartment Checklist
|  | Unit | 132 | Apartment Checklist
|  | Unit | 133 | Apartment Checklist
|  | Unit | 135 | Apartment Checklist
Zone 2
| Level 1 | Unit | 137 | Apartment Checklist
|  | Unit | 138 | Apartment Checklist
|  | Unit | 139 | Apartment Checklist
|  | Unit | 140 | Apartment Checklist
|  | Unit | 141 | Apartment Checklist
|  | Unit | 142 | Apartment Checklist
|  | Unit | 143 | Apartment Checklist
|  | Unit | 144 | Apartment Checklist
|  | Unit | 145 | Apartment Checklist
|  | Unit | 146 | Apartment Checklist
|  | Unit | 147 | Apartment Checklist
| Level 2 | Unit | 201 | Apartment Checklist
|  | Unit | 202 | Apartment Checklist
|  | Unit | 203 | Apartment Checklist
|  | Unit | 204 | Apartment Checklist
|  | Unit | 205 | Apartment Checklist
|  | Unit | 206 | Apartment Checklist
|  | Unit | 207 | Apartment Checklist
|  | Unit | 208 | Apartment Checklist
|  | Unit | 209 | Apartment Checklist
|  | Unit | 210 | Apartment Checklist
|  | Unit | 211 | Apartment Checklist
|  | Unit | 212 | Apartment Checklist
|  | Unit | 213 | Apartment Checklist
|  | Unit | 226 | Apartment Checklist
|  | Unit | 227 | Apartment Checklist
|  | Unit | 228 | Apartment Checklist
Zone 3
| Ground Floor | Unit | 021 | Apartment Checklist
|  | Unit | 022 | Apartment Checklist
|  | Unit | 023 | Apartment Checklist
|  | Unit | 024 | Apartment Checklist
|  | Unit | 025 | Apartment Checklist
|  | Unit | 026 | Apartment Checklist
|  | Unit | 027 | Apartment Checklist
|  | Unit | 028 | Apartment Checklist
|  | Unit | 029 | Apartment Checklist
| Level 1 | Unit | 151 | Apartment Checklist
|  | Unit | 152 | Apartment Checklist
|  | Unit | 153 | Apartment Checklist
|  | Unit | 154 | Apartment Checklist
|  | Unit | 155 | Apartment Checklist
|  | Unit | 156 | Apartment Checklist
|  | Unit | 157 | Apartment Checklist
|  | Unit | 158 | Apartment Checklist
|  | Unit | 159 | Apartment Checklist
|  | Unit | 160 | Apartment Checklist
|  | Unit | 161 | Apartment Checklist
|  | Unit | 162 | Apartment Checklist
| Level 2 | Unit | 214 | Apartment Checklist
|  | Unit | 215 | Apartment Checklist
|  | Unit | 216 | Apartment Checklist
|  | Unit | 217 | Apartment Checklist
|  | Unit | 218 | Apartment Checklist
|  | Unit | 219 | Apartment Checklist
|  | Unit | 220 | Apartment Checklist
|  | Unit | 221 | Apartment Checklist
|  | Unit | 222 | Apartment Checklist
|  | Unit | 223 | Apartment Checklist
|  | Unit | 224 | Apartment Checklist
|  | Unit | 225 | Apartment Checklist
Balcony
| Level 1 | Zone 1 Unit 106 |  | Balcony checklist
|  | Zone 1 Unit 111 |  | Balcony checklist
|  | Zone 1 Unit 121 |  | Balcony checklist
|  | Zone 1 Unit 126 |  | Balcony checklist
|  | Zone 1 Unit 128 |  | Balcony checklist
|  | Zone 1 Unit 130 |  | Balcony checklist
|  | Zone 1 Unit 132 |  | Balcony checklist
|  | Zone 1 Grid 5-7, S-T Kitchen |  | Balcony checklist
|  | Zone 1 Grid F-H, 9-12 Multi-use |  | Balcony checklist
|  | Zone 2 Unit 137 |  | Balcony checklist
|  | Zone 2 Unit 138 |  | Balcony checklist
|  | Zone 2 Unit 139 |  | Balcony checklist
|  | Zone 2 Unit 140 |  | Balcony checklist
|  | Zone 2 Unit 142 |  | Balcony checklist
|  | Zone 2 Unit 143 |  | Balcony checklist
|  | Zone 2 Grid 17-18, G-J Lounge 3 |  | Balcony checklist
|  | Zone 3 Unit 148 |  | Balcony checklist
|  | Zone 3 Unit 150 |  | Balcony checklist
|  | Zone 3 Unit 151 |  | Balcony checklist
|  | Zone 3 Unit 156 |  | Balcony checklist
|  | Zone 3 Unit 157 |  | Balcony checklist
|  | Zone 3 Unit 159 |  | Balcony checklist
| Level 2 | Zone 2 Unit 206 |  | Balcony checklist
|  | Zone 2 Unit 211 |  | Balcony checklist
|  | Zone 3 Unit 214 |  | Balcony checklist
|  | Zone 3 Unit 216 |  | Balcony checklist
|  | Zone 3 Unit 217 |  | Balcony checklist
|  | Zone 3 Unit 222 |  | Balcony checklist
|  | Zone 3 Unit 223 |  | Balcony checklist
|  | Zone 3 Unit 225 |  | Balcony checklist
Balcony checklist
|  | Basement |  | Balcony checklist
| Common Area |  | Entry/Lobby
Stair 4
|  | Lift car |  | Common Area checklist
|  |  | Lift car | Common Area checklist
Level 1
|  |  | Café Terrace | Lift Car checklist
B-14 Bathroom
Balcony checklist
Apartment Checklist

## Checklists
checklist | Apartment Checklist
Section | Substrate inspection
checkpoint | All prior works done
Substrate has no damages and sound
Floor grinded or free from any latent, contaminants or cracks
Wall Square and Plumb
Wall stopped and lined
Ceiling installed
Section | Screed works to shower floor
Checkpoint | Planicrete and Mapecem Slurry applied prior screeding as a bonding agent
Mix no 3 Sand to Mapecem 3: 1 ratio
FFL confirmed and Screed to correct height
No lose sand on top of screed
Section | Soundproofing
Primer Applied
PE Foam tape to all relevant substrate
Installed Soundproofing
Apply floor levelling compound (FLC) max 5mm thickness on top to cover under floor heating cables
Section | Waterproofing
Checkpoint | Apply Mapeband SA to all changes plane, penetration, and floor waste area
Primer 3296 to all relevant substrate
Aqua Defence waterproofing 1st coat
Aqua Defence waterproofing 2nd coat
Water test performed and passed
Section | Tiling
Checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Skirting Tile Installed
Vanity Splashbacks Tile Installed
Section | Grout and Silicone
Checkpoint | Tiles adhesive cured and clean properly
Grout work properly into all joint
Silicon applied and tolled to a neat continuously finish
Section | Final check and Sign off
Checkpoint | Tiling Completed
Photo Taken of Completed Area
Sign off and Handover
checklist | Balcony Checklist
section | Substrate Inspection
checkpoint | All prior works done
Waterproofing completed
Section | Screed works (Level 6 only)
Planicrete and Mapecem Slurry applied prior screeding as a bonding agent
Mix no 3 Sand to Mapecem 3: 1 ratio
FFL confirmed and Screed to correct height based on site measurement and to be agreed on site
No lose sand on top of screed
section | Balcony Deck Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Nurajack NM used with Nurajack Maxi Leveller, Spacer and appropriated shims
Tile lippiness checked and to acceptable standard
Tile interlocked with each others, stable and not moving/rocking
Section | Final check and Sign off
Checkpoint | Tiling Completed
Photo Taken of Completed Area
Sign off and Handover
checklist | Common Area checklist
Section | Substrate inspection
checkpoint | All prior works done
Substrate has no damages and sound
Floor grinded or free from any latent, contaminants or cracks
Stair Tread and Riser dimension consistent and within standard
Section | Tiling
Checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Stair Tread and Riser Tile installed
Stair Nosing installed
Section | Final check and Sign off
Checkpoint | Tiling Completed
Photo Taken of Completed Area
Sign off and Handover
checklist | Lift checklist
Substrate Inspection
All prior works done
Substrate has no damages and sound, suitable for tiling
Section | Tiling
Checkpoint | Setting out tiles according to construction drawing / Site confirmation
Correct primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Section | Final check and Sign off
Checkpoint | Tiling Completed
Photo Taken of Completed Area
Sign off and Handover