## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
15fdfc7b-7664-55e8-a29d-209b3beb0a79 | checklist | ITP - Earthworks Cut 10 Rev 1 | itp | ITP - Earthworks Cut 10 Rev 1
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
b8036728-618f-5223-862b-4d5d9b7392e7 | checkpoint | 1.01 - Approved CWP
bc48be59-51d4-56fc-b21d-7a6cb32fcbb5 | note | Method/Description - Document Review
dc0a6241-08f5-5c95-960a-d5199205bd29 | note | Test frequency - Prior to personal starting
7c42040d-74de-5270-b68b-c1618021f0e1 | note | Contractor - H
80550d88-1d7f-5a42-9ba4-9e6c647bf9bb | note | Designer - H
a797a1da-89a8-50fb-ab97-d5078decec53 | note | Verifying Records Checklists, Test and Supplier Certificates - signed off CWP
51d56764-a670-51be-8dcc-3653ff33619e | signoff | AUTHORITY HOLDPOINT
8bba7d2b-c99b-5bc4-a108-87b749bd8128 | checkpoint | 1.02 - IFC issued
bc16f5f6-413b-51b4-8db1-afe7fd453105 | note | Method/Description - Document Review
3d2aeafb-ab58-50b2-a8b9-32eeae3f32b6 | note | Test frequency - Prior to starting
39ebb796-c4ac-576f-accf-8e47210028e4 | note | Contractor - H
5b02bdf0-5912-5b65-9208-f8c1e4a2f866 | note | Designer - H
7fcc791b-9643-54dd-99d2-d144648ea7fa | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
10b2478d-ece7-5388-8d8d-bec83e587bde | signoff | AUTHORITY HOLDPOINT
c1036124-090c-538f-921f-e077596a4d48 | checkpoint | 1.03 - Approved SCWMP
eeb04c0d-9228-58fc-81ab-814eaff9ad7e | note | Method/Description - Document Review
68794616-9729-53eb-9736-d3d07a7198b0 | note | Test frequency - Once prior to works commencing
f069ea47-c3ce-5ebc-98a9-b33acf4dce0a | note | Contractor - H
2217b11f-b651-5ef6-abfe-21507bdc77fb | note | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
f362954b-2464-58b7-a905-79e3c3f4cfe5 | checkpoint | 1.04 - Investigation testing (Pre-construction)
ea26347c-2af2-517c-832f-7bc7df459ac2 | note | Method/Description - Test
8ebaedae-4203-553a-b1db-684bd02b5413 | note | Test frequency - Pre-construction
90e847ae-1e62-5a4e-9d90-3d50b8a16068 | note | Contractor - H
b2d2e9e0-28de-511b-94f8-92e2b757890d | note | Designer - H
0b107e6b-f491-5fbc-b744-969075a018cb | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
74832774-9e1a-5606-96fe-e669dbf341ec | signoff | AUTHORITY HOLDPOINT
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
63689242-1966-5c9d-913e-14ac0387199f | checkpoint | 2.01 - Order of anchors / rock bolts, including grout and headworks components
b29182e6-ce13-521b-975d-f05d3a4ed441 | note | Method/Description - Approval
98439c06-c1b1-50ee-b46e-2d678c7891d1 | note | Test frequency - Prior to commencing
ca107507-23a3-5fb3-a917-b15510ae1661 | note | Contractor - H
b1cb9936-c0fd-5ad6-94cc-681fd50c37a3 | note | Designer - H
2cbf214c-1a23-50ca-8a13-30126135f510 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
730274bd-2f0c-5926-9a40-689f95a479d3 | signoff | AUTHORITY HOLDPOINT
d271e33e-cbd7-5f21-861b-08080d9a211b | checkpoint | 2.02 - Headworks
caacb4c2-e2af-5c5f-966f-446a419bdb90 | note | Method/Description - Submit
e6c64625-15c9-569b-91f3-457de9310719 | note | Test frequency - Prior to commencing
e2c45304-13c7-5e6f-90ef-4849fb4c07f0 | note | Contractor - H
3323592f-f20f-5c36-9fd2-c8f57c65f5e2 | note | Designer - H
1c2cf481-15f2-5917-ab5f-c5c1df96591c | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
03ff086a-a973-5c55-a22d-52f3836e0b04 | signoff | AUTHORITY HOLDPOINT
5af9b2d7-4843-50a1-9ca9-a420493d5b94 | checkpoint | 2.03 - Grout
2ddf9aac-ab29-5b48-a266-c8920c391f0f | note | Method/Description - Submit
a1069b04-92e8-5b54-9a75-907e1515f459 | note | Test frequency - Prior to commencing
b0f8e3c3-5180-5637-8e1b-2bfbde201efc | note | Contractor - H
a8237714-3a0c-5e47-8678-c0f6edd847c1 | note | Designer - H
98bd1ae0-b97c-530d-a23f-442ae1599340 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
b02f7a44-b739-5bec-b542-aebe4f318592 | signoff | AUTHORITY HOLDPOINT
0845b341-76d9-50c4-86d1-14c1932cce6f | checkpoint | 2.04 - Drapery Mesh
2043331d-4e02-5ece-806f-9b046f12bb4d | note | Method/Description - Submit
ee5eb793-3804-5db7-8799-1527cceefac5 | note | Test frequency - Prior to commencing
658b2b4b-f9e9-593a-aec8-02d04986b78e | note | Contractor - H
2aa2134a-8bb2-543d-8534-56d66d96f99b | note | Designer - H
9c0103f8-a314-5fc3-99a0-09d91e972638 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
dbfa5453-a0a5-5652-a6f9-89a517345572 | signoff | AUTHORITY HOLDPOINT
2b8ec929-6a8e-5031-9305-df14d084b07a | checkpoint | 2.05 - Steel Wire Ropes
c222faba-076b-5ef9-9206-7f46eee888aa | note | Method/Description - Submit
e1cf51d9-487e-5e40-ad8f-ef6f0f6ed23f | note | Test frequency - Prior to commencing
5c5383cb-755e-5a80-99f0-8abc151ca831 | note | Contractor - H
dff4e656-7f6e-5f03-bed9-3babed98a051 | note | Designer - H
247f70b2-d0d4-5909-b444-81de3eb54825 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
4613a13a-4057-5618-8565-0a63abce1c0e | signoff | AUTHORITY HOLDPOINT
30d3cc73-6917-5006-902a-97840ab9b918 | checkpoint | 2.06 - Wire Rope Fittings
a64d4fba-6142-598d-a820-54614c22b38f | note | Method/Description - Submit
c23bc1ae-8e3f-509f-9d51-2bb55d7f6418 | note | Test frequency - Prior to commencing
fa39926a-48bb-5d65-b91b-4dae4ad64cce | note | Contractor - H
77304c76-b859-5f5c-8773-454838e20149 | note | Designer - H
bd29d91d-c1ce-50f3-8b51-7eb339840f02 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
72cf4203-3940-55e0-ace1-3f8b7d600eb8 | signoff | AUTHORITY HOLDPOINT
e46abdef-03eb-5f62-acfc-609cea849bdf | checkpoint | 2.07 - Delivery of all rock drapery system components
30cb1773-68a4-54e2-bbcb-2e1fb0987ded | note | Method/Description - Visual
8ca37bc3-5f0b-5fb6-bd1e-ae05a5c8671c | note | Test frequency - each delivery
b6e1c79a-2b55-5507-80d9-72a27aa4ea79 | note | Contractor - H
7026e32b-94ac-5e4a-8b4a-d5bd0f2aaa12 | note | Verifying Records Checklists, Test and Supplier Certificates - Dockets, Test Certificates, Material Inspection Checklist
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
e50a2b37-ca62-57e7-96ab-eff525762a41 | checkpoint | 3.01 - Set out extents
d6756d55-6134-5739-993a-77ebccd3b557 | note | Method/Description - Survey/visual
48d9c281-149a-5151-95f4-698240731b96 | note | Test frequency - Prior to Commencement
4bd37f01-e1de-528a-ae6f-8b5ebe3a3ce4 | note | Contractor - H
36357efa-9810-56b4-8445-9f7b034509b5 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
01747703-c742-5b7d-bcc9-4e49f238ffcc | checkpoint | 3.02 - Verify Machine Control
11c8c659-be31-5bee-a305-af616377bbe9 | note | Method/Description - Survey/visual
567910c2-704b-5c77-8bf3-948b742202cb | note | Test frequency - Daily
169b49e4-68ce-571a-92c4-3da3a085f1d5 | note | Contractor - W
bf065234-73f4-5fbf-a31e-a43a64c25caf | note | Verifying Records Checklists, Test and Supplier Certificates - Plant Pre Starts
b4cd666f-df12-5060-bb1c-024a617295ac | checkpoint | 3.03 - Assess Crest detail
d724ec64-4a7f-5c12-8cf1-cb4d39b9b3d5 | note | Method/Description - Hand augers/ slope assess/Window Samples
7fe631f2-4690-5dc5-8265-81a3fee74f0a | note | Test frequency - Prior to Excavation
2f744cc2-0493-5c8e-a26e-a0611772f549 | note | Contractor - H
311e340e-f363-5d8c-923f-7b2c12fc2abe | note | Designer - H
8565cf56-b4f1-53ce-834b-2558b850c840 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
2805d6d1-7869-5723-afbf-2c796cc8b838 | signoff | AUTHORITY HOLDPOINT
8380eeb1-fcdd-5cc7-a2a1-09f2bb38b8fa | checkpoint | 3.04 - Install crest detail - Soil Nailing
dbeb6aa0-2509-5992-aa06-e3eb68fbad0f | note | Method/Description - Visual Inspection
73ba9fa3-0be6-5fdd-a45e-d2e85f4ad512 | note | Test frequency - Prior to cutting rock slope
0a069931-8c38-51ce-876c-ca95ad696eb9 | note | Contractor - H
fa86e6e2-0840-5c5d-a248-5b3f8d6bed22 | note | Designer - H
5c055a2e-d963-593a-9470-5dd11276c074 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
d49f20db-ad3e-5724-8fce-6cc6a9f7810b | signoff | AUTHORITY HOLDPOINT
320cb4a8-017c-583e-939a-9a80bfd044a9 | checkpoint | 3.05 - Install crest detail - Erosion Matting
a0dc14e4-7a45-55ea-bd6a-0e756dbffefe | note | Method/Description - Visual Inspection
f9bcf0bf-54b2-558e-be72-ccaa0f4ec009 | note | Test frequency - Prior to cutting rock slope
e1d62ee2-e516-5b83-8290-0942e1e2bff6 | note | Contractor - H
d525aafa-4931-516d-98db-29fdc014b49d | note | Designer - W
c68a8a4e-b6af-569d-9c18-1abe607ff29c | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
1376efe9-4b80-5a65-b9a3-b1d7d3598a44 | checkpoint | 3.06 - Install Rock Fall Protection
ce3f94e2-b6c6-5064-9dec-c3925caba8f1 | note | Method/Description - Visual Inspection
65ccdd21-0290-5baf-994e-d6fedc21086d | note | Test frequency - Prior to cutting rock slope
f81f6583-0fb2-59e7-9a9c-5c251bbe9f51 | note | Contractor - H
c1f83483-110d-5d12-aa71-501c7e9710ff | note | Designer - H
26bcfd9e-f2df-5ec0-89fe-2bb2d8a209d3 | note | Verifying Records Checklists, Test and Supplier Certificates - Ground Nail Check List
880084b6-045d-579f-8915-dbdd7e8e30ec | signoff | AUTHORITY HOLDPOINT
a961364b-e40c-5018-a6bc-d5e01720ede4 | checkpoint | 3.07 - Cut Face inspection - Cut Face inspection
ab0107bd-47bc-548f-9be0-0962f33b20ea | note | Method/Description - Survey check by construction team, visual inspection by designer.
30cf4955-7959-5dc8-aadb-68ac4a615cfd | note | Test frequency - 100m2 or maximum 5m vertical cut
32dccfc6-8b78-5974-8a87-d7f7149ce8e4 | note | Contractor - H
8d765b57-f1a2-5c8b-adec-2c849667e6a7 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, Survey record, As-built
01653db1-5675-50b5-aeb3-796794446c29 | checkpoint | 3.08 - Cut Face inspection - Cut face material verification - Geo mapping
de65aaa7-f253-5fd4-a707-c06a0fe48e13 | note | Method/Description - Geo inspection and face mapping
44080c6b-a0bb-59b1-9e51-070947693f1e | note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
167377c7-9603-548e-ac33-108b6fccad22 | note | Contractor - H
05c39219-b111-592c-84ce-08db95400085 | note | Designer - H
38c35d7e-4527-5422-9d6e-442b94bb881b | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports, Face map from geotechnical engineer/geologist
c64c22d8-2986-56cd-9eb5-93377238fa26 | signoff | AUTHORITY HOLDPOINT
8dce7ee4-3ae3-541f-b516-bfd835c7f05b | checkpoint | 3.09 - Install Rock Drape - Set out drape anchorages
bbe89ff4-e5c0-5761-b20c-56af651b86ab | note | Method/Description - Geo walk over
b56caee0-030e-51e4-b4cc-bb19d0701d87 | note | Test frequency - Prior to drilling
e7798dc6-55d3-5e7a-a901-f228d2198fe5 | note | Contractor - H
b28c1acf-8222-51dc-811f-7a0af3cb20c6 | note | Designer - I
6514984a-1bce-528f-9f0a-dfa9564e1f09 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist
45815ed2-4da5-501e-bdc2-45802043d9e5 | checkpoint | 3.10 - Install Rock Drape - Install anchors
0867b240-7ac3-5d85-8357-58a4165f24b3 | note | Method/Description - Drill and grout records. Stressing records.
6a68e547-ce55-50ac-8a9e-e6abda03ad42 | note | Test frequency - During construction and at end
82e98677-e901-5710-962b-899c3416ae25 | note | Contractor - H
b4ebf5f9-01a4-522c-b4f7-9e49fccb9491 | note | Designer - I
180fa315-5040-58ee-9abc-495cb5f943c1 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Rock Drape Checklist
fad8a95a-7ed3-5a16-8ac5-7c8ed329706d | checkpoint | 3.11 - Install Rock Bolts
6950d28c-b7ad-552e-b3ce-b7ae395241d9 | note | Method/Description - Drill and grout records. Stressing records.
65be1cfd-bff7-519d-b19a-2dc5a00f8fcc | note | Test frequency - During construction and at end
fa476613-9f3d-5dff-af3d-d7b8b201f97d | note | Contractor - H
c5249786-eb84-52c6-97c2-5a728849d713 | note | Designer - I
d7811f68-4817-5ce6-aa4e-8a0175875c10 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Active Mesh Checklist
01c2045c-902e-55c8-8357-16af6b3918ab | checkpoint | 3.12 - Install Rock Drape - Install Drapes/Active Mesh
d37957f8-af67-54fe-9dfa-05654a4064e1 | note | Method/Description - Visual inspection
903c96bc-0a29-5d80-a17e-7a4234fd04f2 | note | Test frequency - During construction and at end
88cc6d7e-c60e-5151-a779-7f4423f9dd6e | note | Contractor - H
573d6107-e166-52dc-81bf-56c22e95716c | note | Designer - H
dd246132-a20a-598d-b0d9-5307ef6d7e0a | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist, Active Mesh Checklist
af7b5775-7448-59f1-8656-cf536cc8b8a6 | signoff | AUTHORITY HOLDPOINT
0d2040a0-a854-5b9d-b033-e62b53e18096 | checkpoint | 3.13 - Production nail acceptance tests
063e759f-d207-50ac-a156-71e0d6536ba1 | note | Method/Description - Test
9e78a5ab-6e70-52a8-89b9-2fd74cff39fe | note | Test frequency - At Completion
547b6478-a091-5734-b750-bfe6d9216e62 | note | Contractor - H
53d51e2d-892d-5f18-ab4a-7606f93e9ad2 | note | Designer - W
99f330d7-3913-5de9-9a07-ed7415c7931f | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
6f4b4ee3-606e-5dd4-8015-c231650ad84f | checkpoint | 3.14 - Production drape anchorage and Rock Bolts tests (acceptance tests)
ba2564ac-5a67-54dc-ace6-dccf2135dd58 | note | Method/Description - Test
1492d707-b4a4-5bf8-9dfd-623ca88ef711 | note | Test frequency - At Completion
edcbcb33-6400-5d42-b32a-9c619f425866 | note | Contractor - H
b357e6c0-6487-5a5c-bd81-b26f06dd44cc | note | Designer - W
643b3edd-725c-5027-9152-6480eec66be2 | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
7f46e4b9-5c20-53b4-a42e-f99aaf2164d2 | checkpoint | 3.15 - Catch Ditch Inspection
e1df5724-8dde-5ca6-baed-6653236a9d84 | note | Method/Description - Visual inspection
adbd8ec3-cd96-50d8-abc8-9f9b6cbe684f | note | Test frequency - During construction and at end
c310cfe2-0203-597c-8190-0f82442c175f | note | Contractor - W
f3eefe7d-4082-5338-8485-60d33d680e0e | note | Designer - I
7addafad-14ef-5c21-8c85-6aa6f47879e6 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
09a3152f-ae50-532c-bdbc-f38642adf899 | checkpoint | 4.01 - Throughout construction period prior to road opening
e587f083-cf5b-5612-b3d4-c63a37476462 | note | Method/Description - Monitor
055d9e05-b296-559d-a78f-04d733932121 | note | Test frequency - At least once during construction, A minimum of 5% of the rockfall drapery system anchors shall be monitored throughout the construction period prior to road opening
59570868-cb1b-5195-8856-a2dd4cb65fae | note | Contractor - H
a47a72c3-5612-58b0-86d3-2825f6f8160e | note | Designer - H
9e00c7d4-adde-5450-9b0f-5eac4f84e78e | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring report, photographic
b44868f2-c57e-5d38-b8d7-c113e4f21511 | signoff | AUTHORITY HOLDPOINT
37e1199b-cda8-504b-8df9-24e893afed46 | checkpoint | 4.02 - Red Line Mark Up Drawings
b97c3437-d842-5f3a-b53d-995594dc84bd | note | Method/Description - Submit
e3f02c82-98e2-50dc-8829-7d38a8bf2d63 | note | Test frequency - At Completion
c302beeb-9096-5042-8195-29e7b3d0796d | note | Contractor - H
2da5465e-6715-5ecf-9eeb-edfed38638b6 | note | Designer - R
eacfc4f6-5364-5c00-8b3b-5fce3ac23ff3 | note | Verifying Records Checklists, Test and Supplier Certificates - Red Line Mark Up Drawings
165c7067-43c9-5a52-b41c-8c7612d7b156 | checkpoint | 4.03 - Operation and maintenance report
e840c5a0-cba9-505f-ac09-dda1b691da53 | note | Method/Description - Submit
d08c5825-98d6-540e-ad04-20ff9e0ba7f5 | note | Test frequency - At Completion
bda34d95-cb97-5812-9c75-e7801a3561d8 | note | Contractor - H
12b07137-0306-5cf9-8fea-4dec86993b57 | note | Designer - R
4a85c651-09b9-5f67-8c37-496562268e86 | note | Client - R
21c1bcf2-76be-504f-8bd5-ea358e17ba13 | note | Verifying Records Checklists, Test and Supplier Certificates - operation and maintenance report
ddebe8d5-1f5e-54b7-b7d3-e3cd9dc9e681 | checkpoint | 4.04 - Final Handover Package
ce6ef1e6-8b6c-5de2-a841-d3c2041784ed | note | Method/Description - Submit
0a02195f-9d74-5b77-b17b-7ebc0d5c04b2 | note | Test frequency - At Completion
f826b970-e166-5f89-9e18-b56274ec617f | note | Contractor - H
cc7a9247-ee97-5cbc-aba2-9388c24af2fd | note | Designer - R
399da181-4075-53d1-9d05-62ee6e41e7db | note | Client - R
46eea58d-5e20-56f7-aaf6-c87db6654af1 | note | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
e778d075-3e93-4a95-9b30-0003ced93ea7 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
e0b92828-92dc-4214-b035-1e805ee48ab2 | checkpoint | ITP Close-Out by
98709db6-a75a-5539-aed0-acdd295c1c7b | note | Site Engineer/Project Engineer
9f52930b-1ac0-5794-9b7a-753d7bb1aa62 | note | Zone Manager Approval
f79c02fe-ecf7-5e64-9e25-8af63271ea78 | note | Construction Manager Approval
a4528e21-81b7-50ce-8687-87190cfa7282 | note | Quality Manager Approval
9107c5df-153b-5498-9a24-a36ff2fe578c | date | Date:
db74876f-5ff4-4c99-9e76-362daf8c5d0a | signoff | SIGNATURE
c12e5dd5-07ed-5099-8efd-444e6e200aae | checklist | ITP - Earthworks Cut 11 Rev 1 | itp | ITP - Earthworks Cut 11 Rev 1
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
b8036728-618f-5223-862b-4d5d9b7392e7 | checkpoint | 1.01 - Approved CWP
b1fad7ff-803a-5ccc-b08e-3b08fe1b815e | note | Method/Description - Document Review
4f82afcf-2cb3-5178-bdef-5b8636599910 | note | Test frequency - Prior to personal starting
477bfc6d-e1b2-59f6-91fa-b5b729c7fb26 | note | Contractor - H
fc53c781-f93f-5a8a-8af2-150459cde80e | note | Designer - H
4669ba5a-f722-55d4-88da-a7c8ee26b0c4 | note | Verifying Records Checklists, Test and Supplier Certificates - signed off CWP
51d56764-a670-51be-8dcc-3653ff33619e | signoff | AUTHORITY HOLDPOINT
8bba7d2b-c99b-5bc4-a108-87b749bd8128 | checkpoint | 1.02 - IFC issued
7414cd06-bfd4-5b08-8d9c-868882f1f7c6 | note | Method/Description - Document Review
df232622-82aa-5c8b-a064-bab6a9ac5128 | note | Test frequency - Prior to starting
5c031128-5597-5328-ad19-aaaad5b47d11 | note | Contractor - H
e808207a-ec6a-5faf-b001-52cce87cfc1d | note | Designer - H
856e1b23-4389-5c76-81a3-79952ddaf593 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
10b2478d-ece7-5388-8d8d-bec83e587bde | signoff | AUTHORITY HOLDPOINT
c1036124-090c-538f-921f-e077596a4d48 | checkpoint | 1.03 - Approved SCWMP
8302d758-3507-51c7-bd74-3fec1fca8ec9 | note | Method/Description - Document Review
2fa7a5c0-9c3c-5968-9c3d-c460cfb90f98 | note | Test frequency - Once prior to works commencing
8984bc8b-322e-56cd-84f3-0b3f390fff7d | note | Contractor - H
1d52618e-7d5c-5fcb-81cf-4b6f4cf08183 | note | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
f362954b-2464-58b7-a905-79e3c3f4cfe5 | checkpoint | 1.04 - Investigation testing (Pre-construction)
acb1b279-f036-5da2-a737-22110f1915e7 | note | Method/Description - Test
44cfdd2c-83ec-5966-bc4b-03a1d86ff765 | note | Test frequency - Pre-construction
9081dcad-a9eb-5219-a16a-6e66b01bfe8c | note | Contractor - H
b345e757-6a76-5429-bdf4-513eafc3f085 | note | Designer - H
271f2d58-979d-5cb5-9c52-91f520d57b2c | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
74832774-9e1a-5606-96fe-e669dbf341ec | signoff | AUTHORITY HOLDPOINT
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
63689242-1966-5c9d-913e-14ac0387199f | checkpoint | 2.01 - Order of anchors / rock bolts, including grout and headworks components
ca6f43b8-9627-5249-ac3a-7305be9de7ed | note | Method/Description - Approval
5c644dff-933a-5303-be66-5d1dc457643d | note | Test frequency - Prior to commencing
5ab56e3e-572e-5589-a779-91794d6a8f3a | note | Contractor - H
cce6611a-8d3c-5ad5-b38f-f63fd4c364bb | note | Designer - H
1a88f3cb-fb91-5e16-9dec-f83d12be280b | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
730274bd-2f0c-5926-9a40-689f95a479d3 | signoff | AUTHORITY HOLDPOINT
d271e33e-cbd7-5f21-861b-08080d9a211b | checkpoint | 2.02 - Headworks
d9de3895-65d3-5102-9c12-f6cbe933a946 | note | Method/Description - Submit
a54b1b4a-b37b-586f-8a52-a59b0e3b6b45 | note | Test frequency - Prior to commencing
9420614b-c948-599a-b388-0c00c2f6d975 | note | Contractor - H
ae5bb703-3a51-5555-ba0b-3cdea91e7c34 | note | Designer - H
3be8ddbe-17f7-5542-b701-a14a414ba984 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
03ff086a-a973-5c55-a22d-52f3836e0b04 | signoff | AUTHORITY HOLDPOINT
5af9b2d7-4843-50a1-9ca9-a420493d5b94 | checkpoint | 2.03 - Grout
4a770ebe-19e6-5c27-8934-c6cdfafea7f2 | note | Method/Description - Submit
8705f591-481d-5c5f-ac71-36307f1e3849 | note | Test frequency - Prior to commencing
16b7000c-65c1-5474-9720-6c422c7c742a | note | Contractor - H
bc0b3552-4452-5d37-a664-1c8f76e47c3b | note | Designer - H
4a11efe0-1eea-52d0-a966-bbc29bb1a3a0 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
b02f7a44-b739-5bec-b542-aebe4f318592 | signoff | AUTHORITY HOLDPOINT
0845b341-76d9-50c4-86d1-14c1932cce6f | checkpoint | 2.04 - Drapery Mesh
acd84c6d-7554-583c-ac9d-75cba1301815 | note | Method/Description - Submit
681f141f-b4ea-500a-914c-0a354544fff4 | note | Test frequency - Prior to commencing
04a39f40-71eb-54d0-8306-4145b014d292 | note | Contractor - H
34a77a80-27df-5e08-8c36-d2d1766240bf | note | Designer - H
4a9d731e-8a58-5e33-b68a-f1a186a350d1 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
dbfa5453-a0a5-5652-a6f9-89a517345572 | signoff | AUTHORITY HOLDPOINT
2b8ec929-6a8e-5031-9305-df14d084b07a | checkpoint | 2.05 - Steel Wire Ropes
3c1b16ad-367e-5955-b0eb-ff8929f2ca71 | note | Method/Description - Submit
3266bd59-f3e7-513a-8f67-2b97573bc11d | note | Test frequency - Prior to commencing
464b5fb2-74d5-5bad-8a35-87c94bb02f73 | note | Contractor - H
07410b86-7042-5a21-9404-87a223af013e | note | Designer - H
cc8b2eb4-b347-5003-a896-beffe655bbe6 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
4613a13a-4057-5618-8565-0a63abce1c0e | signoff | AUTHORITY HOLDPOINT
30d3cc73-6917-5006-902a-97840ab9b918 | checkpoint | 2.06 - Wire Rope Fittings
106f13da-3692-56c2-ab2b-55339fd12add | note | Method/Description - Submit
bccfcd0d-fee1-56cc-9046-b749b1a4a7f6 | note | Test frequency - Prior to commencing
98bd4566-9caf-5297-b1e0-b392ec747ae4 | note | Contractor - H
86d7c5e5-f969-5ce7-b561-16d2c84f11d9 | note | Designer - H
a415d7d2-cb44-5a57-8ee3-5620fed597c5 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
72cf4203-3940-55e0-ace1-3f8b7d600eb8 | signoff | AUTHORITY HOLDPOINT
e46abdef-03eb-5f62-acfc-609cea849bdf | checkpoint | 2.07 - Delivery of all rock drapery system components
988ad208-1991-53ea-9e22-52194473970b | note | Method/Description - Visual
7367c886-66da-5c98-bb24-84e42834d071 | note | Test frequency - each delivery
e65c8cab-bb0f-54e5-a8e7-b9d1c1e3643b | note | Contractor - H
98e02821-4d13-5a72-8867-d446ccb95ac2 | note | Verifying Records Checklists, Test and Supplier Certificates - Dockets, Test Certificates, Material Inspection Checklist
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
e50a2b37-ca62-57e7-96ab-eff525762a41 | checkpoint | 3.01 - Set out extents
49cd5c1e-60bc-5f82-a464-c6e0f2b7d2e4 | note | Method/Description - Survey/visual
8fd8400d-40ab-5fa1-a4a5-911f2da2a6de | note | Test frequency - Prior to Commencement
2483fe1a-04aa-56b5-8d38-44e41150008f | note | Contractor - H
54e6359e-a127-5298-b127-d24b16dbf314 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
01747703-c742-5b7d-bcc9-4e49f238ffcc | checkpoint | 3.02 - Verify Machine Control
75ba54b3-be2d-5f79-a5bc-5d777d4da1d5 | note | Method/Description - Survey/visual
7057cfed-7cb0-5096-b32b-5146720b38c5 | note | Test frequency - Daily
c04e23a6-f2a9-5a31-9d60-f02093f7fbd7 | note | Contractor - W
193da519-1119-5eaf-9b24-a9daf8b62723 | note | Verifying Records Checklists, Test and Supplier Certificates - Plant Pre Starts
b4cd666f-df12-5060-bb1c-024a617295ac | checkpoint | 3.03 - Assess Crest detail
0e1f3103-223a-5bd1-a5c2-3e0887e92c18 | note | Method/Description - Hand augers/ slope assess/Window Samples
40f432c3-865f-57eb-9480-2b866436de34 | note | Test frequency - Prior to Excavation
eee1da58-0e15-5ce8-9080-b12b6b5e369c | note | Contractor - H
6b462512-412e-5e21-9186-2bc6fcb4402a | note | Designer - H
c9a6d1ea-20c6-5127-95cb-7b7b3b8989a1 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
2805d6d1-7869-5723-afbf-2c796cc8b838 | signoff | AUTHORITY HOLDPOINT
8380eeb1-fcdd-5cc7-a2a1-09f2bb38b8fa | checkpoint | 3.04 - Install crest detail - Soil Nailing
bd5f6714-437c-5e0b-8fa0-2ac1abb95130 | note | Method/Description - Visual Inspection
09bd57a7-386e-54ea-8aea-eb89ae180256 | note | Test frequency - Prior to cutting rock slope
47308621-5616-569f-8467-12109682e986 | note | Contractor - H
5ba23382-806e-576f-9e66-d665079a48c4 | note | Designer - H
1e6ec9af-863a-56a8-b01b-07653c1016a0 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
d49f20db-ad3e-5724-8fce-6cc6a9f7810b | signoff | AUTHORITY HOLDPOINT
320cb4a8-017c-583e-939a-9a80bfd044a9 | checkpoint | 3.05 - Install crest detail - Erosion Matting
56fa8d6b-ff1b-50bc-ba83-87d3e4e74c0a | note | Method/Description - Visual Inspection
f591bc59-356f-5fb3-8495-b834eaeb9571 | note | Test frequency - Prior to cutting rock slope
16d26ec6-8894-5b24-a272-ade1f595619c | note | Contractor - H
54c900c2-b267-578c-b3d1-1f4a6c28b5e5 | note | Designer - W
8c744a2b-2505-5585-a998-9fb4b689b3dc | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
1376efe9-4b80-5a65-b9a3-b1d7d3598a44 | checkpoint | 3.06 - Install Rock Fall Protection
ea4cb283-b495-579e-baf8-4271b0d30dfd | note | Method/Description - Visual Inspection
a674cd62-4918-58e0-b211-e2995f85d3d2 | note | Test frequency - Prior to cutting rock slope
ef52c3d5-3cef-5eb7-8830-13f5aa3832de | note | Contractor - H
3edd6dbc-3f15-59d3-91d7-50b27d5a8db3 | note | Designer - H
96245b6d-0b21-582d-a684-28ddfba09100 | note | Verifying Records Checklists, Test and Supplier Certificates - Ground Nail Check List
880084b6-045d-579f-8915-dbdd7e8e30ec | signoff | AUTHORITY HOLDPOINT
a961364b-e40c-5018-a6bc-d5e01720ede4 | checkpoint | 3.07 - Cut Face inspection - Cut Face inspection
4bc41b04-010c-567b-b5a3-5e423813fdd7 | note | Method/Description - Survey check by construction team, visual inspection by designer.
75f8e66b-fa38-51ed-a727-d4e3df0842db | note | Test frequency - 100m2 or maximum 5m vertical cut
20d1d63c-34a5-51c5-96f8-cd5bcde77f5e | note | Contractor - H
6f77a6b0-a4ab-54d1-9071-3c5112fa9551 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, Survey record, As-built
01653db1-5675-50b5-aeb3-796794446c29 | checkpoint | 3.08 - Cut Face inspection - Cut face material verification - Geo mapping
537f4c6d-7354-5888-8cd4-20c5992041c4 | note | Method/Description - Geo inspection and face mapping
5601228e-f9d1-5341-bcd0-d4be9e7d2f25 | note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
d958c49d-aab8-53fe-91ca-ed57d41e11d7 | note | Contractor - H
d414aeb5-c69a-5fd9-aeae-6cbe2b711898 | note | Designer - H
b20dd8cc-529a-557c-8f0f-3c2dfbf6d988 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports, Face map from geotechnical engineer/geologist
c64c22d8-2986-56cd-9eb5-93377238fa26 | signoff | AUTHORITY HOLDPOINT
8dce7ee4-3ae3-541f-b516-bfd835c7f05b | checkpoint | 3.09 - Install Rock Drape - Set out drape anchorages
c7d53db2-e394-53ca-af70-3dd26c659092 | note | Method/Description - Geo walk over
5608c886-1c2b-5c96-a9e4-2903b884aab0 | note | Test frequency - Prior to drilling
6f1302dd-c012-512b-bc95-607a2d33c64f | note | Contractor - H
cb0d9175-8427-5480-b122-f9fb089251eb | note | Designer - I
6060d47a-0fdf-51b3-8c9e-02d0b9ec0e10 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist
45815ed2-4da5-501e-bdc2-45802043d9e5 | checkpoint | 3.10 - Install Rock Drape - Install anchors
27be02ff-ed41-5ae7-9005-275aa0aa64ed | note | Method/Description - Drill and grout records. Stressing records.
d945a3b2-c620-54ac-a922-8a5070b921d2 | note | Test frequency - During construction and at end
8e6327c7-ac9f-5e0c-b4cd-f0f0619f2c59 | note | Contractor - H
ca733476-b29c-5587-8443-f3efd8b15d6e | note | Designer - I
5e333f46-cd10-5082-8f46-e9e69c3664df | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Rock Drape Checklist
fad8a95a-7ed3-5a16-8ac5-7c8ed329706d | checkpoint | 3.11 - Install Rock Bolts
c350baa5-ff11-5131-9afc-26a5d5a36913 | note | Method/Description - Drill and grout records. Stressing records.
148250f7-0f3a-53da-8e53-f1f037f2bfad | note | Test frequency - During construction and at end
1ca6b708-0311-5960-bb83-065267ef316e | note | Contractor - H
29a5a25f-a94e-5ab7-b8d8-b1a96f6b97f8 | note | Designer - I
972ed810-2c08-5f16-8142-850443ee8ef7 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Active Mesh Checklist
01c2045c-902e-55c8-8357-16af6b3918ab | checkpoint | 3.12 - Install Rock Drape - Install Drapes/Active Mesh
23811254-3126-518a-b5be-52d3a0f38975 | note | Method/Description - Visual inspection
b8416c23-dc9d-5221-9455-201a0f193fab | note | Test frequency - During construction and at end
d2dfdf2b-78aa-56a3-b4b9-2fdd54c60688 | note | Contractor - H
e539b1e1-f155-5080-ace3-2b173d13d54c | note | Designer - H
c65d67f4-ebc6-57f8-a5c8-46c0cbea90fa | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist, Active Mesh Checklist
af7b5775-7448-59f1-8656-cf536cc8b8a6 | signoff | AUTHORITY HOLDPOINT
0d2040a0-a854-5b9d-b033-e62b53e18096 | checkpoint | 3.13 - Production nail acceptance tests
ad3791a9-5701-5f4e-a992-9e3a83362044 | note | Method/Description - Test
6ab205da-96ce-571f-98bc-01e88d7e6d6d | note | Test frequency - At Completion
0fabf57d-cf44-59d8-bc64-e29bd882d222 | note | Contractor - H
8e339fc2-cfc8-521e-acd8-1daacdd978e2 | note | Designer - W
1c6ed97e-7a3a-5b9a-a09a-d7a252afe358 | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
6f4b4ee3-606e-5dd4-8015-c231650ad84f | checkpoint | 3.14 - Production drape anchorage and Rock Bolts tests (acceptance tests)
709895e6-45da-5aae-afb3-5e34093e26dc | note | Method/Description - Test
b2c8f36f-51aa-56d7-87b9-70cb9bbff5d9 | note | Test frequency - At Completion
94b101c3-9207-5216-8279-f080112ad4dd | note | Contractor - H
feebd5e9-b22d-57cb-86f6-17a3b934734e | note | Designer - W
1489c9d4-5f23-52e2-ad0a-6bdd6596ff7b | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
7f46e4b9-5c20-53b4-a42e-f99aaf2164d2 | checkpoint | 3.15 - Catch Ditch Inspection
3ccf1c46-1927-5aa3-9c46-9d03592b571c | note | Method/Description - Visual inspection
37479323-9a9e-5f99-8ae8-1790884d2960 | note | Test frequency - During construction and at end
49046ca7-dd7e-5db5-9858-7a74bf1199ba | note | Contractor - W
a80f656a-a39d-5c07-941f-49d7b2657fb3 | note | Designer - I
5e3f2a42-8a79-59ca-acc4-1d727bf6aebb | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
09a3152f-ae50-532c-bdbc-f38642adf899 | checkpoint | 4.01 - Throughout construction period prior to road opening
89173973-a9e7-5c1c-a2c2-3f9f94544d8c | note | Method/Description - Monitor
f1d1b15f-b628-53ae-9b89-7f213ceba39c | note | Test frequency - At least once during construction, A minimum of 5% of the rockfall drapery system anchors shall be monitored throughout the construction period prior to road opening
70c05cd3-6064-5a80-9bbc-dec525798450 | note | Contractor - H
08c3d0bf-a1c4-547c-8892-4a2e766e11a9 | note | Designer - H
afc5c1a9-481b-521c-a78f-b29dfc05b253 | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring report, photographic
b44868f2-c57e-5d38-b8d7-c113e4f21511 | signoff | AUTHORITY HOLDPOINT
37e1199b-cda8-504b-8df9-24e893afed46 | checkpoint | 4.02 - Red Line Mark Up Drawings
0e4e143a-586f-57b0-a93b-bb161f194936 | note | Method/Description - Submit
d4cd4b5c-b538-5063-8453-5d789a3296a0 | note | Test frequency - At Completion
232ba076-fe42-5073-9541-fcf35a3d56f8 | note | Contractor - H
d6b22be6-3cc6-5995-ab19-7d14eaffa301 | note | Designer - R
94e9bb2e-c40b-5e0e-b41d-8dd39a542c04 | note | Verifying Records Checklists, Test and Supplier Certificates - Red Line Mark Up Drawings
165c7067-43c9-5a52-b41c-8c7612d7b156 | checkpoint | 4.03 - Operation and maintenance report
d9db6970-c2a7-5ad7-9935-26f2a7560e87 | note | Method/Description - Submit
04165cb4-b18f-5f44-937a-19c3fd6fbf8a | note | Test frequency - At Completion
1282451b-59fe-5a7c-9dcc-91015835a4c3 | note | Contractor - H
75292e76-3431-59b5-954c-a4de7ab28c72 | note | Designer - R
bdaf33fb-87c3-50cb-a1fb-db2b88ad2acb | note | Client - R
776511f7-6a04-55c3-a70a-df7ad701ad28 | note | Verifying Records Checklists, Test and Supplier Certificates - operation and maintenance report
ddebe8d5-1f5e-54b7-b7d3-e3cd9dc9e681 | checkpoint | 4.04 - Final Handover Package
afa7a847-29b9-591c-8c8d-216dc16fe10c | note | Method/Description - Submit
06b2cb67-a71c-512a-87de-a950c359f8ae | note | Test frequency - At Completion
fbe6a94a-920e-5a3b-908c-88b77ccd6cb3 | note | Contractor - H
32d9d3d3-fbcf-5f38-8f70-4f777f2f583a | note | Designer - R
db1a03b0-e403-5962-b6f4-78d6f0bf21a0 | note | Client - R
61137bd5-866e-5fb8-888d-97b6e2bf7547 | note | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
2744793d-25aa-4474-8850-d21d94b09375 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
bc33c08f-08c4-46de-b26b-aa687c6f5901 | checkpoint | ITP Close-Out by
0c6c874b-30b7-5b45-b694-4a5c677492ef | note | Site Engineer/Project Engineer
3d713ec2-9d8d-507c-b47f-85ed11fb4cad | note | Zone Manager Approval
d110c85b-c85e-505a-9873-38b11e793a1a | note | Construction Manager Approval
d8ce17e5-c0dd-563a-a331-a9af62b5155c | note | Quality Manager Approval
b89ead96-446c-5490-9936-68acc4a46889 | date | Date:
a0101ccb-42d9-4a45-8669-34e39bc8aa01 | signoff | SIGNATURE
f8cddba7-5810-585f-8107-eed9dac6aaed | checklist | ITP - Earthworks Cut 12 Rev 1 | itp | ITP - Earthworks Cut 12 Rev 1
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
b8036728-618f-5223-862b-4d5d9b7392e7 | checkpoint | 1.01 - Approved CWP
3efe6b64-0cae-5f56-91bd-8b053d6de10e | note | Method/Description - Document Review
56d95657-bc0c-5a4b-b493-d5d5b454d783 | note | Test frequency - Prior to personal starting
d9b1c55d-c388-5f0c-afc7-2298eb608508 | note | Contractor - H
a874ef3f-0686-5233-ab40-53f345ff2862 | note | Designer - H
b582bfc2-90ee-5ddd-aafe-873ad3a95a5a | note | Verifying Records Checklists, Test and Supplier Certificates - signed off CWP
51d56764-a670-51be-8dcc-3653ff33619e | signoff | AUTHORITY HOLDPOINT
8bba7d2b-c99b-5bc4-a108-87b749bd8128 | checkpoint | 1.02 - IFC issued
ffd8d6db-0dde-58af-9f5b-b9f306450bc7 | note | Method/Description - Document Review
bfba68a1-ca80-530c-8f55-81e25f916eee | note | Test frequency - Prior to starting
c6d27184-2a15-51f9-bfc8-0f7d0ad05211 | note | Contractor - H
fc92d2f3-e27d-51c9-9935-89166ef2627c | note | Designer - H
f5c2d42d-10d5-5e42-8e13-a2c408fee1e1 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
10b2478d-ece7-5388-8d8d-bec83e587bde | signoff | AUTHORITY HOLDPOINT
c1036124-090c-538f-921f-e077596a4d48 | checkpoint | 1.03 - Approved SCWMP
b1092132-339a-5159-86b7-34f096569c4d | note | Method/Description - Document Review
76a1f0d1-29c8-5dc3-8213-abbaaa6c458b | note | Test frequency - Once prior to works commencing
e80831aa-a0f8-5ae7-8950-d657efac192a | note | Contractor - H
869d78eb-ddf9-5cc5-956d-1aa1991e99d5 | note | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
bb2b1fb1-8ba5-5507-819a-4df4d6e7a599 | checkpoint | 1.04 - Investigation nail testing (Pre-construction)
3f4df789-9220-575b-bb17-1409a14820ba | note | Method/Description - Test
c2ce1e29-ad95-5752-8ded-a4a4da270140 | note | Test frequency - Pre-construction
2692082b-52ae-5ed0-9e77-066d18c9f87c | note | Contractor - H
5666f0a2-bd9f-5331-b33d-69d0c7136d67 | note | Designer - H
b2716bc7-2b2b-5c63-a20f-d4da916588b8 | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
4421deb2-42dc-51c8-8938-a23522d9c82e | signoff | AUTHORITY HOLDPOINT
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
63689242-1966-5c9d-913e-14ac0387199f | checkpoint | 2.01 - Order of anchors / rock bolts, including grout and headworks components
9aaebe36-fec7-5e87-ba8c-bc904afbd061 | note | Method/Description - Approval
2056cce0-f4da-56da-b4ac-a6306e91a59a | note | Test frequency - Prior to commencing
ca819f3d-b27c-5448-a4f6-365ba626636d | note | Contractor - H
94de48b4-0802-55ae-951f-7b7453686504 | note | Designer - H
7bc3829b-189e-59d8-8519-0854822be3ae | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
730274bd-2f0c-5926-9a40-689f95a479d3 | signoff | AUTHORITY HOLDPOINT
d271e33e-cbd7-5f21-861b-08080d9a211b | checkpoint | 2.02 - Headworks
818682a9-dd56-5f6d-88bf-a6cf6c88a74b | note | Method/Description - Submit
778e1366-9e9a-5206-973b-30f25c9cedb1 | note | Test frequency - Prior to commencing
3a707d86-7ad1-5d63-bf2c-c08a45fe5f7d | note | Contractor - H
f2f0b058-d477-5677-8ea6-23f5842fc60e | note | Designer - H
829fdb22-4a08-5104-b9c1-6f0c7d90cada | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
03ff086a-a973-5c55-a22d-52f3836e0b04 | signoff | AUTHORITY HOLDPOINT
ec2696a5-f64f-517a-9cc7-31c63b59f9ac | checkpoint | 2.03 - Drapery Mesh
c9253dcb-0539-5e78-b054-3dfe0ead24af | note | Method/Description - Submit
a583f7a9-5565-59b0-aea8-72a46b299822 | note | Test frequency - Prior to commencing
d8bf1fdf-adcb-58b6-b757-c0ef52a63e5d | note | Contractor - H
6a93acb3-8306-5593-af84-e1501f32c4d3 | note | Designer - H
8ce2853a-a572-52bf-ba91-02d368a19858 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
c6ce221c-cb42-557b-966a-425f3878585c | signoff | AUTHORITY HOLDPOINT
e1179b52-a79d-5bc6-a9d5-48ff14f60ada | checkpoint | 2.04 - Steel Wire Ropes
325ba659-cd11-564e-adcb-38d6662c24aa | note | Method/Description - Submit
f6f04053-9c17-550e-9d91-f980f4108af0 | note | Test frequency - Prior to commencing
fd811330-6392-5d3b-a31f-4fd438aad467 | note | Contractor - H
3ec32774-e468-51eb-b1e1-c9c324284826 | note | Designer - H
6b344dc9-04e7-5af3-907e-8fadb450bff6 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
2511025d-aead-58bd-8c4f-49a7e01ca2f3 | signoff | AUTHORITY HOLDPOINT
0bc697f7-80d1-50b1-a28f-664872862133 | checkpoint | 2.05 - Wire Rope Fittings
e5bdb7ce-52c3-5164-bf09-f9b930e01459 | note | Method/Description - Submit
0cf5c283-b69f-5aeb-80c8-f0cd813ff775 | note | Test frequency - Prior to commencing
36084907-a7bc-5845-9934-0327e291a235 | note | Contractor - H
4b9d6ee1-02a2-56e2-84be-53ae90216560 | note | Designer - H
4a1bc91e-4af8-5cd3-8520-0ad7ac0a1ee2 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
b160c85b-6830-5050-927e-2493b5dfa91b | signoff | AUTHORITY HOLDPOINT
0a7d85a6-a75f-528f-83cd-198ef0e3e5c1 | checkpoint | 2.06 - Delivery of all rock drapery system components
2b176abd-8d22-5fbc-bdc6-45ec1ce7900b | note | Method/Description - Visual
4e301c2d-fe9d-5a4e-bc7e-a095676464cf | note | Test frequency - each delivery
a92ec3d7-da46-5e43-8b5b-aa345efedd1b | note | Contractor - H
7a3199c3-5288-5986-bc39-0052c607bd13 | note | Verifying Records Checklists, Test and Supplier Certificates - Dockets, Test Certificates, Material Inspection Checklist
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
e50a2b37-ca62-57e7-96ab-eff525762a41 | checkpoint | 3.01 - Set out extents
e106bd1f-4306-5870-b3d2-667c2a24fa5a | note | Method/Description - Survey/visual
049b5c38-ee48-5188-a825-af3aaecb776c | note | Test frequency - Prior to Commencement
72769698-5b7a-5e02-9331-c0202e9a9b88 | note | Contractor - H
78770c6e-ba0d-5f1e-a043-e42182eb29aa | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
01747703-c742-5b7d-bcc9-4e49f238ffcc | checkpoint | 3.02 - Verify Machine Control
87a7806c-676c-5cbd-90e0-11a548d3b85e | note | Method/Description - Survey/visual
06efc53a-344e-56a9-a597-3e676c00533a | note | Test frequency - Daily
7b41747a-82b6-573d-9b8c-8fe086847088 | note | Contractor - W
bb8e2174-714d-5cf2-a2bb-1244a5d70269 | note | Verifying Records Checklists, Test and Supplier Certificates - Plant Pre Starts
b4cd666f-df12-5060-bb1c-024a617295ac | checkpoint | 3.03 - Assess Crest detail
f67aa20f-f2f5-5033-923d-2e406e883d55 | note | Method/Description - Hand augers/ slope assess/Window Samples
2a6a6d79-8f3f-51b5-bf89-c2889c129a44 | note | Test frequency - Prior to Excavation
bb61d5cf-a574-5343-9064-275999803d35 | note | Contractor - H
c892e452-9e76-50b4-866a-131190ddc367 | note | Designer - H
6f112e26-4ce3-5ba1-b908-db74ecc0ff60 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
2805d6d1-7869-5723-afbf-2c796cc8b838 | signoff | AUTHORITY HOLDPOINT
8380eeb1-fcdd-5cc7-a2a1-09f2bb38b8fa | checkpoint | 3.04 - Install crest detail - Soil Nailing
dd599ae3-a242-54b1-bc9e-d9999c14b2e1 | note | Method/Description - Visual Inspection
ceb63161-3852-56ad-9be3-dc2eaf00cb1f | note | Test frequency - Prior to cutting rock slope
ec72dbc6-ebae-50c9-bcb2-4cc55f1ab03c | note | Contractor - H
96c552d5-88e8-59e4-850e-4d0c54067ce2 | note | Designer - H
9b7cf0b4-383b-55a0-95b1-cb6e5c011808 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
d49f20db-ad3e-5724-8fce-6cc6a9f7810b | signoff | AUTHORITY HOLDPOINT
320cb4a8-017c-583e-939a-9a80bfd044a9 | checkpoint | 3.05 - Install crest detail - Erosion Matting
9474781f-06fd-56e4-a7c5-befb7c2105d6 | note | Method/Description - Visual Inspection
c9d975e8-c720-5f8c-9967-9b5c4cd716fe | note | Test frequency - Prior to cutting rock slope
a40d6db2-2903-59f1-baa3-26467f66e916 | note | Contractor - H
8f0633ec-555e-5739-b7de-3cb73df0a505 | note | Designer - W
0fd75df9-1d0a-56cf-a92f-9b178441431b | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
1376efe9-4b80-5a65-b9a3-b1d7d3598a44 | checkpoint | 3.06 - Install Rock Fall Protection
02afa65e-e8c4-54d7-b7f8-12c8ea3fb152 | note | Method/Description - Visual Inspection
b3d247aa-dcac-5a03-a5f1-b23ad4236296 | note | Test frequency - Prior to cutting rock slope
1fe5f770-2540-5f71-8f9c-9d1d5a4dbace | note | Contractor - H
8ac0bc2b-c8ee-5c53-89e0-243694841347 | note | Designer - H
5b0b0f48-d268-5ad1-8a3f-0331bd62e55c | note | Verifying Records Checklists, Test and Supplier Certificates - Ground Nail Check List
880084b6-045d-579f-8915-dbdd7e8e30ec | signoff | AUTHORITY HOLDPOINT
a961364b-e40c-5018-a6bc-d5e01720ede4 | checkpoint | 3.07 - Cut Face inspection - Cut Face inspection
7ef0006b-ac0c-572d-a530-b00272e07578 | note | Method/Description - Survey check by construction team, visual inspection by designer.
78351530-3306-51d8-9e36-40dc3580daac | note | Test frequency - 100m2 or maximum 5m vertical cut
58ace8aa-7a56-5d41-a1dc-a7ffec549a6f | note | Contractor - H
2f21b288-1034-57c3-8b21-d943bba0c1ab | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, Survey record, As-built
01653db1-5675-50b5-aeb3-796794446c29 | checkpoint | 3.08 - Cut Face inspection - Cut face material verification - Geo mapping
f1d39dc9-4ce8-5e57-8f57-c2c27aebe7ac | note | Method/Description - Geo inspection and face mapping
ffcdeba8-7195-5d45-851f-13b523f68050 | note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
105202e6-8b08-5cb8-bca3-eb2d393a0f7f | note | Contractor - H
2b1199e8-aa29-5e36-9a02-ee5ccfd8d791 | note | Designer - H
4c2fa667-ce75-5130-885a-7655db44f92f | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports, Face map from geotechnical engineer/geologist
c64c22d8-2986-56cd-9eb5-93377238fa26 | signoff | AUTHORITY HOLDPOINT
8dce7ee4-3ae3-541f-b516-bfd835c7f05b | checkpoint | 3.09 - Install Rock Drape - Set out drape anchorages
680268c3-3fe8-532f-9c49-4989df86452c | note | Method/Description - Geo walk over
b6f2952a-2fe0-58b0-887e-a2e336c28419 | note | Test frequency - Prior to drilling
828188e2-af4a-55e2-b4a9-227ccf06c3bb | note | Contractor - H
447a7f1f-1210-55d2-991c-e61f54fffbd0 | note | Designer - I
1ce4f5b1-a6ac-5798-b8db-b1c1a821bef8 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist
45815ed2-4da5-501e-bdc2-45802043d9e5 | checkpoint | 3.10 - Install Rock Drape - Install anchors
90e8b3f4-c92d-50e9-b1a7-3082fa9f90bd | note | Method/Description - Drill and grout records. Stressing records.
edd662e4-1b9a-5246-8257-b3492b94e908 | note | Test frequency - During construction and at end
d4371f53-7f78-5745-858d-d644f95c31d8 | note | Contractor - H
81bb9c2c-11d2-5e18-ad8b-57de5bd843ad | note | Designer - I
069c774e-7920-51e4-885b-0b2202351ca1 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Rock Drape Checklist
fad8a95a-7ed3-5a16-8ac5-7c8ed329706d | checkpoint | 3.11 - Install Rock Bolts
e1c22199-934d-5036-a747-074bf893429d | note | Method/Description - Drill and grout records. Stressing records.
c090af7a-cdb7-5e61-b4cc-b148c10778be | note | Test frequency - During construction and at end
bc8aca19-9fe7-552b-9e1e-d7394d3bdd58 | note | Contractor - H
fba800f4-210a-5d11-acc7-d3319e99f901 | note | Designer - I
4316e0a9-8a3e-5fe5-be29-7a9e2a763464 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Active Mesh Checklist
01c2045c-902e-55c8-8357-16af6b3918ab | checkpoint | 3.12 - Install Rock Drape - Install Drapes/Active Mesh
b4e11c60-1242-57b8-bff0-b6dc684811e1 | note | Method/Description - Visual inspection
a77e8a32-4ff1-5ca7-9408-ece86918e143 | note | Test frequency - During construction and at end
cd91ed5c-beaf-5e80-bcdf-c26a05401e57 | note | Contractor - H
9d905484-5974-5f03-9eb8-f0f6a40de14b | note | Designer - H
95ec2e35-cabc-5187-82ba-269d95e3cb30 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist, Active Mesh Checklist
af7b5775-7448-59f1-8656-cf536cc8b8a6 | signoff | AUTHORITY HOLDPOINT
0d2040a0-a854-5b9d-b033-e62b53e18096 | checkpoint | 3.13 - Production nail acceptance tests
2671a527-cbc9-54fe-8c2b-67c05fc7165f | note | Method/Description - Test
fe2d9c26-623d-5c67-8fb7-400ac43e4dbf | note | Test frequency - At Completion
f7ea9e21-ee7d-5e75-bf16-1d76858570ac | note | Contractor - H
f4338cf7-27bc-5c67-a468-1dc78bd2f98b | note | Designer - W
8807d8e9-07ff-56bd-8f48-cd0a243331d9 | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
6f4b4ee3-606e-5dd4-8015-c231650ad84f | checkpoint | 3.14 - Production drape anchorage and Rock Bolts tests (acceptance tests)
6462b49b-cce3-57a5-9300-98f2a334fa25 | note | Method/Description - Test
a74d7e1b-59e7-5759-a923-2abdd3cab414 | note | Test frequency - At Completion
e4c9dd82-60f6-5476-81d8-1f5ad42c6779 | note | Contractor - H
26b4afb6-a4f7-56a8-a20e-e66a4e28d31c | note | Designer - W
47c6ae03-c613-5493-8c67-8252d324f4a0 | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
7f46e4b9-5c20-53b4-a42e-f99aaf2164d2 | checkpoint | 3.15 - Catch Ditch Inspection
ef010779-5d60-58db-80d6-94fed44e9677 | note | Method/Description - Visual inspection
457f6c5b-084f-5378-abe8-06f172f26160 | note | Test frequency - During construction and at end
c773fbb2-432b-5bfb-ab7e-3216eab28511 | note | Contractor - W
116167d6-660e-5b7e-ae4b-d721318708d6 | note | Designer - I
8c3519ae-c7cc-5e51-b390-6ce00a86c61e | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
09a3152f-ae50-532c-bdbc-f38642adf899 | checkpoint | 4.01 - Throughout construction period prior to road opening
b2f5804b-eebc-5e0e-b806-f93835a69ea7 | note | Method/Description - Monitor
cc2474d5-1d10-5d48-a1c8-35ddf04d515c | note | Test frequency - At least once during construction, A minimum of 5% of the rockfall drapery system anchors shall be monitored throughout the construction period prior to road opening
2cef5515-6aa1-5265-beea-d049c52adb9d | note | Contractor - H
5c30ce6b-c9e3-52aa-811f-99ad3fe48a68 | note | Designer - H
522850e2-1ec2-5392-b29e-850e4ae23c3f | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring report, photographic
b44868f2-c57e-5d38-b8d7-c113e4f21511 | signoff | AUTHORITY HOLDPOINT
37e1199b-cda8-504b-8df9-24e893afed46 | checkpoint | 4.02 - Red Line Mark Up Drawings
bf52eade-eccc-56aa-91fb-0251acc214d2 | note | Method/Description - Submit
fcf86572-73f9-5631-b937-2515e81c22ab | note | Test frequency - At Completion
2a3da0e6-0a6f-5b2e-870f-4120a58a8550 | note | Contractor - H
e0c36a09-33f8-5e55-ac50-06101691701a | note | Designer - R
9abe176d-9fe6-55fd-823a-fd38554839de | note | Verifying Records Checklists, Test and Supplier Certificates - Red Line Mark Up Drawings
165c7067-43c9-5a52-b41c-8c7612d7b156 | checkpoint | 4.03 - Operation and maintenance report
d61801bf-268f-53bb-b851-955fae9b9f6a | note | Method/Description - Submit
9b7241be-5cd2-5016-a00f-3de723a0e749 | note | Test frequency - At Completion
303c4980-8a96-5596-bdb9-b11cd795babc | note | Contractor - H
2e65953f-db31-5613-873d-9c11fc01212c | note | Designer - R
069b5355-3572-5c43-afd2-1aa16abe76d1 | note | Client - R
92b8c26f-d011-5257-90bc-3ffe802905a7 | note | Verifying Records Checklists, Test and Supplier Certificates - operation and maintenance report
ddebe8d5-1f5e-54b7-b7d3-e3cd9dc9e681 | checkpoint | 4.04 - Final Handover Package
48452e55-2798-57b5-abe3-35913521b644 | note | Method/Description - Submit
9be7946d-4d71-559c-a26a-eec294827515 | note | Test frequency - At Completion
558d0b33-24eb-56eb-8b64-8ddf77c40bfe | note | Contractor - H
43fb7a75-2b1f-5d47-8da8-dd0a47bfa5f1 | note | Designer - R
873c2aa2-186e-5ea7-8750-62416f26f0d3 | note | Client - R
d9a6db20-64fe-5288-a650-d5ade0882c72 | note | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
6c971726-524a-48f9-a29d-08c04ebf69a8 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
28efb6ee-61b7-4f62-b086-d16c79e74efb | checkpoint | ITP Close-Out by
de787460-e857-5b5e-9f8d-e1552756c11e | note | Site Engineer/Project Engineer
e004b373-472c-586a-a83f-514a16a118a2 | note | Zone Manager Approval
055e5c9b-c12e-56f0-812f-54f676f17298 | note | Construction Manager Approval
8b8b45bb-3026-5a61-922c-8c67b6406e06 | note | Quality Manager Approval
1c9a97d6-dbc9-588a-a80c-8fa2865ca98a | date | Date:
e770c7a8-79c6-431b-b0e5-f4f9fc2a1a59 | signoff | SIGNATURE
a111629d-c2e8-5525-92ad-fd98879a9059 | checklist | ITP - Earthworks Cut 13 Rev 1 | itp | ITP - Earthworks Cut 13 Rev 1
046a1aba-5615-526e-93b5-56ba0137143b | section | 1.0 Pre-Construction - Preliminary Inspections and Tests
b8036728-618f-5223-862b-4d5d9b7392e7 | checkpoint | 1.01 - Approved CWP
eed1b6cf-e479-571b-bb99-79b4096972d1 | note | Method/Description - Document Review
507b46c4-9ac0-59f0-adca-89d757bc43b0 | note | Test frequency - Prior to personal starting
24d94a01-9ba8-5ffb-be87-1d6e12cc7af9 | note | Contractor - H
a9269f85-9357-503b-a70a-f7d5ee65b4c9 | note | Designer - H
2d814f51-dc0c-5387-a98f-7ea92a01c959 | note | Verifying Records Checklists, Test and Supplier Certificates - signed off CWP
51d56764-a670-51be-8dcc-3653ff33619e | signoff | AUTHORITY HOLDPOINT
8bba7d2b-c99b-5bc4-a108-87b749bd8128 | checkpoint | 1.02 - IFC issued
872aef0b-9989-532a-b1d1-31b4921a20bc | note | Method/Description - Document Review
c024714c-a691-5f19-b98f-0c2950505801 | note | Test frequency - Prior to starting
ea585226-a881-5310-bab1-e065bd9acd02 | note | Contractor - H
33adef82-d674-5e00-91fd-b1ff9f19a476 | note | Designer - H
769018f3-dd52-5f8d-a6a9-48fe905486b9 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
10b2478d-ece7-5388-8d8d-bec83e587bde | signoff | AUTHORITY HOLDPOINT
c1036124-090c-538f-921f-e077596a4d48 | checkpoint | 1.03 - Approved SCWMP
b5495171-f50c-5079-9639-b0ab1e339d24 | note | Method/Description - Document Review
5171a6e0-1565-5233-9dd0-f5dd13fbe4ed | note | Test frequency - Once prior to works commencing
9d69f938-f864-5022-ac23-9b676d2fd71a | note | Contractor - H
24e42651-5ea9-57fc-a08d-dbffb7648f1a | note | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
f362954b-2464-58b7-a905-79e3c3f4cfe5 | checkpoint | 1.04 - Investigation testing (Pre-construction)
2af71c12-b64c-5882-9464-12676fad18b7 | note | Method/Description - Test
46a71513-4571-5979-bf6b-4d0e4316b7ff | note | Test frequency - Pre-construction
1b0c08ea-baf8-5aa3-bdf9-fa78eddaeda8 | note | Contractor - H
dd8a9d49-3f3e-5ac8-ac31-a6205ac6b659 | note | Designer - H
5bf7ef1c-2c03-54b4-ad61-72b1a3c34a32 | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
74832774-9e1a-5606-96fe-e669dbf341ec | signoff | AUTHORITY HOLDPOINT
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
63689242-1966-5c9d-913e-14ac0387199f | checkpoint | 2.01 - Order of anchors / rock bolts, including grout and headworks components
378adcff-6c88-5753-a967-70255c0a29a0 | note | Method/Description - Approval
6d1572bc-acdd-5ffe-9763-43e2a6535950 | note | Test frequency - Prior to commencing
0984a3f6-43bc-53f0-8886-77916b946e09 | note | Contractor - H
35240077-2023-591e-b65f-1a2ca1c7e28d | note | Designer - R
a9ff20bb-0f7a-58bb-8eab-02e6eea9d2d6 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
d271e33e-cbd7-5f21-861b-08080d9a211b | checkpoint | 2.02 - Headworks
d30bcd22-b098-5d6a-98bc-2850031d9596 | note | Method/Description - Submit
d33358d8-e5a1-599d-94f0-58e931c77d5c | note | Test frequency - Prior to commencing
0a02e738-dd3c-5f96-a5e9-291002eba195 | note | Contractor - H
6158e3c3-412e-5ede-a650-2a10aa62c464 | note | Designer - R
6a54a9e1-0b12-51be-91a3-04df35f79a73 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
5af9b2d7-4843-50a1-9ca9-a420493d5b94 | checkpoint | 2.03 - Grout
52fab8a9-1cb3-564c-b36e-04c9a2785991 | note | Method/Description - Submit
42a90897-b82f-5e8f-832c-4be92d57e126 | note | Test frequency - Prior to commencing
75ef4340-6a04-570a-9344-efebe5961264 | note | Contractor - H
ddf6d5d5-93b6-544b-b426-17b5f396bc77 | note | Designer - R
ed3c882f-2b50-5b77-8c74-1c45341edf78 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
0845b341-76d9-50c4-86d1-14c1932cce6f | checkpoint | 2.04 - Drapery Mesh
dfd8994c-1f5e-519a-bb30-9d76ee592a8f | note | Method/Description - Submit
ddd020bf-5639-5195-801c-bbcbd775584a | note | Test frequency - Prior to commencing
da9a4907-0f98-57bb-ac16-9b7fc948e4f4 | note | Contractor - H
20d621ae-2254-5ce8-a3ff-27a15c9cac53 | note | Designer - R
7a946617-e909-5cf8-86c2-cc7dbb6e7ad5 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
2b8ec929-6a8e-5031-9305-df14d084b07a | checkpoint | 2.05 - Steel Wire Ropes
5500d061-6899-5067-ad24-3231bc7b5ced | note | Method/Description - Submit
6d930fc3-6a4a-5b6d-9671-a1254053d3df | note | Test frequency - Prior to commencing
9b62ec1a-1016-50da-825f-0dc071bdc696 | note | Contractor - H
3f0b47f5-007a-53dc-a3a1-ae3fd87c9c8d | note | Designer - R
c74e0c24-7ae7-5871-9465-a3524f457f47 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
30d3cc73-6917-5006-902a-97840ab9b918 | checkpoint | 2.06 - Wire Rope Fittings
50147cc6-aafb-5003-8b8a-4c39b93488f2 | note | Method/Description - Submit
231354e0-7e58-555c-a369-20bdc862462e | note | Test frequency - Prior to commencing
9bc12dd6-dbb6-5714-80db-7f14b311a799 | note | Contractor - H
7244b931-4425-557a-a924-566996986e68 | note | Designer - R
8cc73ad4-a91e-5513-8738-f89ebcceea87 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
e46abdef-03eb-5f62-acfc-609cea849bdf | checkpoint | 2.07 - Delivery of all rock drapery system components
4fe78c29-963b-51c6-99fe-4376d5200688 | note | Method/Description - Visual
cdebc857-4af8-520c-829d-68e9a2ab3742 | note | Test frequency - each delivery
c8738a73-52c1-5243-abe0-e95fae39dc6b | note | Contractor - H
84dd7195-0151-5e81-83cd-d68dd87c5296 | note | Verifying Records Checklists, Test and Supplier Certificates - Dockets, Material Inspection Checklist
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
e50a2b37-ca62-57e7-96ab-eff525762a41 | checkpoint | 3.01 - Set out extents
30d1277e-5f53-5f67-9f24-6d2e44d41958 | note | Method/Description - Survey/visual
f8df1e2e-b22d-5ba8-8df2-8aeb3eae9945 | note | Test frequency - Prior to Commencement
12f25c57-5bc6-5dbd-8fc5-ace5dd82c86c | note | Contractor - H
10f0207d-c3f0-54eb-8242-778aeecce50e | note | Verifying Records Checklists, Test and Supplier Certificates - Survey record, GPS model, DSR reports
01747703-c742-5b7d-bcc9-4e49f238ffcc | checkpoint | 3.02 - Verify Machine Control
2be83fd9-0095-5f8c-8d84-e1dabb67ae99 | note | Method/Description - Survey/visual
b976a3bd-c38d-5c03-8d9c-6891cd40ea22 | note | Test frequency - Daily
36c4a451-840f-584c-8ebe-28503c203558 | note | Contractor - W
6960833a-a021-5eb3-93de-9889b724ca1a | note | Verifying Records Checklists, Test and Supplier Certificates - Plant Pre Starts
b4cd666f-df12-5060-bb1c-024a617295ac | checkpoint | 3.03 - Assess Crest detail
38d873d3-87f7-51ff-a087-58d9e6c7cc75 | note | Method/Description - Hand augers/ slope assess/Window Samples
1af85e4b-d5c7-5ccb-b531-e0e05abf3178 | note | Test frequency - Prior to Excavation
0b4d7ead-e31c-5bb4-afe1-42ac6d8f4cdc | note | Contractor - H
96811c8a-de1f-51dd-aabf-fadad72d46ff | note | Designer - H
90a88811-a4e9-5d89-ab61-c523ffb19535 | note | Verifying Records Checklists, Test and Supplier Certificates - DSR reports
2805d6d1-7869-5723-afbf-2c796cc8b838 | signoff | AUTHORITY HOLDPOINT
02398fd7-157b-53fd-8e3f-0ec30df40b2a | checkpoint | 3.04 - Install crest detail - Ground Nailing
c33e7d1a-63bf-54ae-96ac-cc1d8a00b47f | note | Method/Description - Visual Inspection
2631f2b7-c58a-59e0-b59e-4488b3dce1b1 | note | Test frequency - Prior to cutting rock slope
f653bffc-bc8b-5e69-9f53-27d19051a0fc | note | Contractor - H
5dc6bbdc-77d2-5428-aad5-bec6c9ff2fb8 | note | Designer - W
4b1cd3d7-95f2-58c9-8ee0-5ac89d41b644 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Checksheet
320cb4a8-017c-583e-939a-9a80bfd044a9 | checkpoint | 3.05 - Install crest detail - Erosion Matting
3d5686b3-48b9-5e41-a99e-d2a1e5ca5208 | note | Method/Description - Visual Inspection
fe622eb1-2538-5437-879a-5e257e4323fd | note | Test frequency - Prior to cutting rock slope
69181bcb-4c68-553d-9096-2dfec4555ff5 | note | Contractor - H
b871b156-daaa-50c0-be46-6ad742780de3 | note | Designer - H
b419e9ea-3944-5ecd-9901-bd8328975465 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Checksheet
161aac8b-3d72-5fa6-a430-8d2d3574d753 | signoff | AUTHORITY HOLDPOINT
1bd73293-91b2-59d2-a294-263abfe46c61 | checkpoint | 3.06 - Cut Face inspection - Cut Face inspection
b878b553-1429-5007-bec4-070c86953d8b | note | Method/Description - Survey check by construction team, visual inspection by designer.
382e90c0-fe7c-52f3-b95e-12238a4d73c7 | note | Test frequency - 100m2 or maximum 5m vertical cut
dbecb281-e09d-5150-840c-a011c372a139 | note | Contractor - H
8a9ac5ae-7971-5ff2-b621-f1e64a2d701d | note | Verifying Records Checklists, Test and Supplier Certificates - Survey record, As-built, DSR reports
f7475140-93d1-5cc8-9ea1-3a8dd237ec30 | checkpoint | 3.07 - Cut Face inspection - Cut face material verification - Geo mapping
d42b795d-811c-5150-a57a-2d505d22426c | note | Method/Description - Geo inspection and face mapping
9c8b7fcd-4cc7-5003-8e82-1082f7b21236 | note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
54a3310c-5e11-5cbf-80f2-69b19045b971 | note | Contractor - H
5164e1fa-6b12-5d95-8bbc-1db9d39dc25b | note | Designer - H
ffe42c6b-466d-5589-ae59-59937a014c4e | note | Verifying Records Checklists, Test and Supplier Certificates - DSR reports, Face map from geotechnical engineer/geologist
fe777dee-5aa6-5b17-b674-4a56517f8037 | signoff | AUTHORITY HOLDPOINT
6a46bf7b-2668-5cc2-b2c8-64112de2793d | checkpoint | 3.08 - Set out extents of drapes
2b36bd41-6f3c-541f-9f13-330801351e31 | note | Method/Description - Survey/visual
653c909b-f4b9-5502-9df2-50cf2c34a842 | note | Test frequency - Prior to drilling
98acd023-57a1-53d7-9e9c-3aac784f16e6 | note | Contractor - H
a4eeb4bf-950c-5a62-901c-368fdbe2c7d1 | note | Verifying Records Checklists, Test and Supplier Certificates - Survey record
be3e5932-29f0-5513-8926-d034d60af6f8 | checkpoint | 3.09 - Set out drape anchorages
b3940203-55e5-5f81-99f5-ed153d9bac53 | note | Method/Description - Geo walk over
73cb2840-4dc0-5223-9870-6076188534a5 | note | Test frequency - Prior to drilling
dc74833f-327b-5da1-a14e-7581fe182b1e | note | Contractor - H
81ac7177-a358-5d4e-b804-bdf817334812 | note | Designer - H
4757f814-cc28-5be7-960d-7609780d3bcc | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checksheet, DSR Report
71afebc3-33e1-5acb-adb0-15feb2ee97e6 | signoff | AUTHORITY HOLDPOINT
2563d54a-10c6-5d49-9c8c-738061e39ee0 | checkpoint | 3.10 - Install Rock Drape Anchors
64e67bdc-91c9-587e-b256-b29b67985f77 | note | Method/Description - Drill and grout records. Stressing records.
b978851c-a58a-57e2-9ce1-68a6c76be15d | note | Test frequency - During construction and at end
5ec66e97-37d1-5c1b-a281-e12511eed8ba | note | Contractor - H
8a46a560-5b3a-5bd1-b7e3-14a899b78d69 | note | Designer - I
aa104c30-ca26-57d0-aa45-1de550cf558d | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checksheet
c16bb1aa-bb54-5b62-b5fe-822cd410d7bc | checkpoint | 3.11 - Install Rock Drape Mesh
a1c1300a-3f4d-5845-a7a5-3fb9568ce0bf | note | Method/Description - Visual inspection
f3e60537-a9fe-5667-81a7-f9c9d03bddb5 | note | Test frequency - During construction and at end
9fc9f4c4-cd73-587f-8332-8fe66334d735 | note | Contractor - H
8f66cdf9-ce5c-5147-9622-9d81c6f4b37f | note | Designer - H
c0fbbc76-03c9-51c9-aae2-dbebc6f8ff54 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checksheet
b77f8687-8a82-5fff-8448-efbb1fd830dd | signoff | AUTHORITY HOLDPOINT
c311088d-e928-593e-a7be-3742031e7de1 | checkpoint | 3.12 - Production nail acceptance tests
083e804c-a4ae-549b-8f7f-808482a5d1d5 | note | Method/Description - Test
4ab1ba71-cf86-5bb3-aa83-bf9281b544ef | note | Test frequency - At Completion
cad908a8-a6ad-5f98-aa03-ec7035204e9a | note | Contractor - H
0051c18b-c39a-5819-b4a2-b836ac3a81f1 | note | Designer - W
ffd95a96-04b7-52eb-a728-d8ce99f5e52e | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
25aae6f7-ce4c-59d6-b8b1-bd0539507d50 | checkpoint | 3.13 - Production drape anchorage acceptance tests
b2f076e9-1599-5657-b92e-083693c23fca | note | Method/Description - Test
cca86add-5595-5272-8dd6-f4bbff6acdec | note | Test frequency - At Completion
b3c36ba9-f8b4-59fd-a656-310aef7e38e9 | note | Contractor - H
a9257863-f820-514a-846c-32dc60ed966d | note | Designer - W
4f97957d-cb46-55f4-b81c-7d29407057c9 | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
7213b24c-fa13-5c65-a374-ddaaff2ae800 | checkpoint | 3.14 - Catch Ditch Inspection
545f860e-0e02-5db9-90d8-299cbfcac9e1 | note | Method/Description - Visual inspection
76f05349-625b-5ca4-9678-6a12d02e58ec | note | Test frequency - During construction and at end
683f2628-7539-5e9a-91a6-c05c482410e2 | note | Contractor - W
f4206ae3-dba0-500a-a2c9-7ef32c3669c3 | note | Designer - I
50a7513a-2b06-502c-b6d8-a078073cd7b6 | note | Verifying Records Checklists, Test and Supplier Certificates - DSR Report
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
09a3152f-ae50-532c-bdbc-f38642adf899 | checkpoint | 4.01 - Throughout construction period prior to road opening
5b04568b-2a10-5c36-905c-95890d8e4b38 | note | Method/Description - Monitor
747ea1e3-ba3b-53b6-a273-e3913510cbeb | note | Test frequency - At least once during construction, A minimum of 5% of the rockfall drapery system anchors shall be monitored throughout the construction period prior to road opening
3cf8644f-8507-5cec-91bf-a8c8abcb0ca4 | note | Contractor - H
40fb4d5d-4370-56ac-b080-9b9a057dafef | note | Designer - H
fa01d2a5-9066-5793-af2f-e3497fe1b93b | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring report, photographic
b44868f2-c57e-5d38-b8d7-c113e4f21511 | signoff | AUTHORITY HOLDPOINT
37e1199b-cda8-504b-8df9-24e893afed46 | checkpoint | 4.02 - Red Line Mark Up Drawings
e4a9954d-13a0-547e-b1aa-da6c437e1fdf | note | Method/Description - Submit
148d849c-509c-5a78-aa31-7dc24915a9cf | note | Test frequency - At Completion
c7288e5d-2c2d-5f71-b556-5b4d7bab4679 | note | Contractor - H
88e85a0b-bee2-50ec-95f5-49ca68e0c6cd | note | Designer - R
9f8c6d7f-c624-5a11-9aa5-48df9ebef8d0 | note | Verifying Records Checklists, Test and Supplier Certificates - Red Line Mark Up Drawings
165c7067-43c9-5a52-b41c-8c7612d7b156 | checkpoint | 4.03 - Operation and maintenance report
b5d541b8-527f-5ea2-984d-3327af45feeb | note | Method/Description - Submit
cf8dc90c-a89f-5828-bf45-1b31f5ee233b | note | Test frequency - At Completion
0ea9e841-cd0d-50ea-8ee5-53c8b81bd6ec | note | Contractor - H
5887b4e7-22e0-5bec-b1f0-97ed1302f017 | note | Designer - R
faf8532f-d537-50c1-8423-f5c6e910b818 | note | Client - R
49d9660f-c27c-5818-a541-576a823362a0 | note | Verifying Records Checklists, Test and Supplier Certificates - operation and maintenance report
ddebe8d5-1f5e-54b7-b7d3-e3cd9dc9e681 | checkpoint | 4.04 - Final Handover Package
4b469d41-4fa7-5992-9d57-bacb428d5df7 | note | Method/Description - Submit
df4c8928-96c9-5153-b74d-beb73c43fd71 | note | Test frequency - At Completion
fab5ab65-25d2-5a89-b458-15ed37755857 | note | Contractor - H
25c8e52d-2dec-54ca-8f68-d9c476aa6f99 | note | Designer - R
f0a3f0aa-7a08-5937-bf3f-7c6bb15d890f | note | Client - R
7af2e595-d0ea-5337-8172-29c5248813ff | note | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
c0476176-b420-462b-b971-8d3ae18751a8 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
2849c234-47f3-41a8-880f-9f5e9d970957 | checkpoint | ITP Close-Out by
596bc65d-82fd-554e-8fb1-cfb71e29d4bc | note | Site Engineer/Project Engineer
57906231-1cb4-5a7a-83d8-fa17a6e464bc | note | Zone Manager Approval
e2a4c6b1-bdf0-5d51-9aef-a9843105e0b0 | note | Construction Manager Approval
37d8b9c6-e3bd-5803-bd39-de98f414afd0 | note | Quality Manager Approval
78c02b21-9f82-57ad-b3a7-de485340f67c | date | Date:
2aeff830-d391-4793-bbad-435194419b3e | signoff | SIGNATURE
f24ba49b-420b-5260-bfde-e086e72f211b | checklist | ITP - Earthworks Cut 14 Rev 1 | itp | ITP - Earthworks Cut 14 Rev 1
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
b8036728-618f-5223-862b-4d5d9b7392e7 | checkpoint | 1.01 - Approved CWP
548a2689-3446-5cbe-b5e2-1078c8dfa1de | note | Method/Description - Document Review
a18fd996-6414-52e9-8ee2-4ba5d2ee747b | note | Test frequency - Prior to personal starting
19444607-a513-53b9-ac8a-980e09e3752f | note | Contractor - H
c9d349ed-c2c6-55f7-8eb9-d5848bb97e8a | note | Designer - H
aee810a3-e661-5e0d-aee2-e94597333497 | note | Verifying Records Checklists, Test and Supplier Certificates - signed off CWP
51d56764-a670-51be-8dcc-3653ff33619e | signoff | AUTHORITY HOLDPOINT
8bba7d2b-c99b-5bc4-a108-87b749bd8128 | checkpoint | 1.02 - IFC issued
4fc278e2-aeb2-5a00-9b46-90270df461a2 | note | Method/Description - Document Review
f5a2d1df-090a-51b8-bf38-6a4d3925a26d | note | Test frequency - Prior to starting
d5fb4f8d-930d-52d4-96e3-ef7e9f8a43f9 | note | Contractor - H
f86889c1-ec03-5c34-832a-c5c9562faae4 | note | Designer - H
5f6530b4-b9ed-5e47-b19c-5c972bc4905b | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
10b2478d-ece7-5388-8d8d-bec83e587bde | signoff | AUTHORITY HOLDPOINT
c1036124-090c-538f-921f-e077596a4d48 | checkpoint | 1.03 - Approved SCWMP
e793d48a-93f6-5b35-89db-e247dbbe05af | note | Method/Description - Document Review
fd5f16c0-537b-5485-993b-c126833a2c10 | note | Test frequency - Once prior to works commencing
f57c505c-0ec8-5fd1-9a51-4df203165993 | note | Contractor - H
0eff3c79-90bb-5a35-b2df-7c25f2f21d71 | note | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
bb2b1fb1-8ba5-5507-819a-4df4d6e7a599 | checkpoint | 1.04 - Investigation nail testing (Pre-construction)
545c391b-fd03-52db-9909-f85dae577c1a | note | Method/Description - Test
7aced001-32e9-5241-8fc7-b5b5eaa5c8a6 | note | Test frequency - Pre-construction
e49c0fa1-4f01-54e3-be39-f53c4a35dfec | note | Contractor - H
952cabcc-9b2c-59aa-81dc-2421ee022f83 | note | Designer - H
b501d4a3-d464-5aaf-88bd-bb1e696d5ca2 | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
4421deb2-42dc-51c8-8938-a23522d9c82e | signoff | AUTHORITY HOLDPOINT
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
63689242-1966-5c9d-913e-14ac0387199f | checkpoint | 2.01 - Order of anchors / rock bolts, including grout and headworks components
f9d77d65-766e-5bf6-9bd6-1e24409a0a62 | note | Method/Description - Approval
e65b0936-d13e-5322-a481-a7bb7f2b6a1b | note | Test frequency - Prior to commencing
aafd78f8-41f5-5054-aa71-e5a5570c6eb7 | note | Contractor - H
b231d560-7ae6-5b1b-a92b-b74f5f3f3dbf | note | Designer - H
89da99bb-d60b-515d-b6f6-3a17ea741a7c | note | Verifying Records Checklists, Test and Supplier Certificates - Material Data Sheet, Material Certificate
730274bd-2f0c-5926-9a40-689f95a479d3 | signoff | AUTHORITY HOLDPOINT
d271e33e-cbd7-5f21-861b-08080d9a211b | checkpoint | 2.02 - Headworks
745eab7b-d5b0-541e-accf-b4efd626088a | note | Method/Description - Submit
d26a0032-b6da-5ee0-80b2-8f8dca35c12a | note | Test frequency - Prior to commencing
49503f22-f601-5a83-a030-0a819abb7755 | note | Contractor - H
e8b4d60f-bcc3-5a8e-9b65-df08b4f22ae6 | note | Designer - H
be185258-2759-58bf-944a-4b1783fddd37 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Data Sheet, Material Certificate
03ff086a-a973-5c55-a22d-52f3836e0b04 | signoff | AUTHORITY HOLDPOINT
ec2696a5-f64f-517a-9cc7-31c63b59f9ac | checkpoint | 2.03 - Drapery Mesh
88bbb89f-295a-547d-bc53-8af9c3772028 | note | Method/Description - Submit
e8854e1b-400f-5505-b1f6-eac7733efc38 | note | Test frequency - Prior to commencing
2c285710-2799-5241-a7b2-0bf92cfc34bc | note | Contractor - H
b8dbbb04-518e-5c0a-bf62-9fbc12481d4f | note | Designer - H
48fa8bda-2bae-5c92-a9e4-5dbd34826009 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Data Sheet, Material Certificate
c6ce221c-cb42-557b-966a-425f3878585c | signoff | AUTHORITY HOLDPOINT
e1179b52-a79d-5bc6-a9d5-48ff14f60ada | checkpoint | 2.04 - Steel Wire Ropes
e85cb0a9-0fbf-5fea-8d3b-1971674aad80 | note | Method/Description - Submit
e3aa7e32-cb09-59ea-a81c-d09dbabb1a6b | note | Test frequency - Prior to commencing
18fb0832-3d48-5e5b-8080-8ee9f8d9105c | note | Contractor - H
0bf019b2-7449-571f-b0cd-66f1d8940793 | note | Designer - H
59b00ece-84f9-53ed-9384-fa4bab9c3e6f | note | Verifying Records Checklists, Test and Supplier Certificates - Material Data Sheet, Material Certificate
2511025d-aead-58bd-8c4f-49a7e01ca2f3 | signoff | AUTHORITY HOLDPOINT
0bc697f7-80d1-50b1-a28f-664872862133 | checkpoint | 2.05 - Wire Rope Fittings
6cebc112-3deb-564d-97ce-25508ef4b686 | note | Method/Description - Submit
5edd2824-ff5f-5e49-922a-3cf00a93ac27 | note | Test frequency - Prior to commencing
eb3f4705-cba7-5697-889d-9208e4b20cfb | note | Contractor - H
31dc58e3-a58c-591d-8cb4-5531963cf864 | note | Designer - H
751f285f-75f5-5578-a673-0166d3232cf8 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Data Sheet, Material Certificate
b160c85b-6830-5050-927e-2493b5dfa91b | signoff | AUTHORITY HOLDPOINT
0a7d85a6-a75f-528f-83cd-198ef0e3e5c1 | checkpoint | 2.06 - Delivery of all rock drapery system components
1359a359-5784-5c59-b705-bb29aac5973f | note | Method/Description - Visual
802ce491-8fff-5e5f-b0da-9cf11ea52bd0 | note | Test frequency - each delivery
53869ae2-6a8d-50fb-a99d-3f0866eddcd7 | note | Contractor - H
1ccf124b-17f4-54d2-af1b-4d4555879ecb | note | Verifying Records Checklists, Test and Supplier Certificates - Dockets, Test Certificates, Material Inspection Checklist
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
e50a2b37-ca62-57e7-96ab-eff525762a41 | checkpoint | 3.01 - Set out extents
2953b571-55c8-56d8-acda-edcca8fbf21c | note | Method/Description - Survey/visual
23749f7e-1c80-5245-8832-90d6e7dd10a9 | note | Test frequency - Prior to Commencement
799a93a8-fe14-50f1-890d-b52193b9b8d1 | note | Contractor - H
8f050015-8c43-55bc-9386-e84a348caed3 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
01747703-c742-5b7d-bcc9-4e49f238ffcc | checkpoint | 3.02 - Verify Machine Control
98c22281-eb09-5383-997f-771dfd96c274 | note | Method/Description - Survey/visual
71bc40d5-4357-53a5-9fc7-7bcde16ed9ec | note | Test frequency - Daily
fba62b8a-8498-578a-947f-a023e98d40d2 | note | Contractor - W
3d9d49f7-487a-579e-be78-0834e1f4e4ae | note | Verifying Records Checklists, Test and Supplier Certificates - This ITP
b4cd666f-df12-5060-bb1c-024a617295ac | checkpoint | 3.03 - Assess Crest detail
ee1b8d72-b6af-50c3-bd9e-2ccea0d60d41 | note | Method/Description - Hand augers/ slope assess/Window Samples
8cf2f84f-d4db-5fbe-bda0-6ea9be157d45 | note | Test frequency - Prior to Excavation
44994600-747a-53a9-9b7a-8482444d907e | note | Contractor - H
e36af01a-7b49-56c9-820f-0dc894394a97 | note | Designer - H
51f4f821-2bde-5809-9b80-78ca89789893 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports
2805d6d1-7869-5723-afbf-2c796cc8b838 | signoff | AUTHORITY HOLDPOINT
8380eeb1-fcdd-5cc7-a2a1-09f2bb38b8fa | checkpoint | 3.04 - Install crest detail - Soil Nailing
cd475276-4c70-52fe-8746-65b7ee1ee1df | note | Method/Description - Visual Inspection
e48cec80-019d-59a0-ae3f-6406a12f8843 | note | Test frequency - Prior to cutting rock slope
67ab3785-9b58-5fe3-972d-2ccb0f7ea3ed | note | Contractor - H
c830daf7-28bb-5895-aec8-5b5ac31d0130 | note | Designer - H
dc16720d-7446-5239-8aab-0fcd2141285b | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List
d49f20db-ad3e-5724-8fce-6cc6a9f7810b | signoff | AUTHORITY HOLDPOINT
320cb4a8-017c-583e-939a-9a80bfd044a9 | checkpoint | 3.05 - Install crest detail - Erosion Matting
96f199eb-4d0c-5712-bbe6-2747ef651a51 | note | Method/Description - Visual Inspection
b244e36d-0f86-5a16-ab10-e2e493924d6d | note | Test frequency - Prior to cutting rock slope
4e47663a-39fc-5e7b-ba14-4cd5e36ed743 | note | Contractor - H
0905b9fe-c836-50e0-a319-8a9c91cd25ee | note | Designer - W
0b8a7be7-6ee4-5c96-9860-0ef9e34789ef | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Check List/ RFI
1376efe9-4b80-5a65-b9a3-b1d7d3598a44 | checkpoint | 3.06 - Install Rock Fall Protection
0d8315ab-c481-5d4e-b868-2038ac45e992 | note | Method/Description - Visual Inspection
4dd7e5e0-6d13-5a76-9cfa-76f11548d6e2 | note | Test frequency - Prior to cutting rock slope
96ffa15e-6f93-5a4e-9f85-224eef62c202 | note | Contractor - H
e227632d-c61e-530c-a1ec-e141a8871900 | note | Designer - H
5e9203de-34c9-5453-bd95-6ed299d73e8e | note | Verifying Records Checklists, Test and Supplier Certificates - Ground Nail Check List
880084b6-045d-579f-8915-dbdd7e8e30ec | signoff | AUTHORITY HOLDPOINT
a961364b-e40c-5018-a6bc-d5e01720ede4 | checkpoint | 3.07 - Cut Face inspection - Cut Face inspection
094bf5b2-d26e-5ef8-bb88-16a86b3abd2b | note | Method/Description - Survey check by construction team, visual inspection by designer.
fdd7b3c2-a6a1-5760-baf9-10a7cb4060f2 | note | Test frequency - 100m2 or maximum 5m vertical cut
847f3dc0-2b15-5c05-b4bb-319894aaed5d | note | Contractor - H
d918c711-8c9d-5668-8bcc-5ac69699aba7 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, Survey record, As-built
01653db1-5675-50b5-aeb3-796794446c29 | checkpoint | 3.08 - Cut Face inspection - Cut face material verification - Geo mapping
c3e3345a-2678-5c1f-a061-eaae080e8fec | note | Method/Description - Geo inspection and face mapping
3a2690f3-3315-5a7f-b0b2-158485713453 | note | Test frequency - At soil-rock interface, Each 100m2 or maximum 5m vertical cut
0dbc2fd8-fb48-56e3-87f1-0ca03706f461 | note | Contractor - H
fd80def1-bf34-57cc-a8be-94ac1926ebe1 | note | Designer - H
d0f610a8-a301-50a4-b105-e7cc9f167f30 | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist, DSR reports, Face map from geotechnical engineer/geologist
c64c22d8-2986-56cd-9eb5-93377238fa26 | signoff | AUTHORITY HOLDPOINT
8dce7ee4-3ae3-541f-b516-bfd835c7f05b | checkpoint | 3.09 - Install Rock Drape - Set out drape anchorages
02bc5b55-58f0-58e5-acfa-2ab95b85047c | note | Method/Description - Geo walk over
69562007-8aaa-574f-8828-001e0e7026f1 | note | Test frequency - Prior to drilling
ec496d3b-fdde-5a98-8d43-4f749efae90f | note | Contractor - H
6d9d1d33-c6c2-5c82-b3b7-1be804766732 | note | Designer - I
b5aa0889-2e23-532f-bf6a-a592b5b8917e | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist
45815ed2-4da5-501e-bdc2-45802043d9e5 | checkpoint | 3.10 - Install Rock Drape - Install anchors
156d36b9-917c-58b4-9cda-9f2af303c594 | note | Method/Description - Drill and grout records. Stressing records.
ebd8d991-8fa8-5c2c-bff8-3d919ba1558f | note | Test frequency - During construction and at end
b650b5ec-9f7d-5fcf-89e8-ba3cf1de9674 | note | Contractor - H
a8679019-4581-59f2-bf71-66106f028f9f | note | Designer - I
1bdfcee7-8061-53e3-8a6a-0d3d7dc0ee6d | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Rock Drape Checklist
fad8a95a-7ed3-5a16-8ac5-7c8ed329706d | checkpoint | 3.11 - Install Rock Bolts
af802c58-eae5-55fa-b8fc-feaa9e4ddc1e | note | Method/Description - Drill and grout records. Stressing records.
52e2b077-b622-54a1-8664-4490dd6acd0b | note | Test frequency - During construction and at end
3a3112ef-8d52-5ab7-8c4f-a37e30cf6653 | note | Contractor - H
d30b7741-acf7-5073-acee-957e0ae8f878 | note | Designer - I
6e1704d0-e2db-5c9d-954b-7ba15dd9e440 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Calibration certificates for stressing equipment, Active Mesh Checklist
01c2045c-902e-55c8-8357-16af6b3918ab | checkpoint | 3.12 - Install Rock Drape - Install Drapes/Active Mesh
9e14d0d6-c661-5952-8e98-e354c2a5cf6a | note | Method/Description - Visual inspection
5ff306fb-e65d-5695-b2f7-872ba384898b | note | Test frequency - During construction and at end
d61b9948-92ca-55c6-9aeb-03b3ce621655 | note | Contractor - H
d731ee67-23e2-5e7a-a50b-c8c3834d0b6b | note | Designer - H
2c3873a8-c3bf-5a40-b33a-a7da85eb2389 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checklist, Active Mesh Checklist
af7b5775-7448-59f1-8656-cf536cc8b8a6 | signoff | AUTHORITY HOLDPOINT
0d2040a0-a854-5b9d-b033-e62b53e18096 | checkpoint | 3.13 - Production nail acceptance tests
8b580bb9-1256-5445-b1be-94c5b1b4b94f | note | Method/Description - Test
c798f016-3f0c-5986-bafb-857850d4bf10 | note | Test frequency - At Completion
86e1f9a5-eb40-5c7c-8099-a8442b9cf421 | note | Contractor - H
c7382783-488a-5481-ac99-728e60cbb6cf | note | Designer - W
17d5c55c-5bec-5bde-ad8f-4255904792fb | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
6f4b4ee3-606e-5dd4-8015-c231650ad84f | checkpoint | 3.14 - Production drape anchorage and Rock Bolts tests (acceptance tests)
556fbb82-70a4-571d-a2cc-c06772cbe4db | note | Method/Description - Test
bcf9cc05-5a41-5c4c-8811-097f0425c8bc | note | Test frequency - At Completion
94f1e0f3-c218-532c-9cad-326036c8d02d | note | Contractor - H
54b6d5d0-4a84-59ac-af1e-2c3e724367a8 | note | Designer - W
6c515cda-98ca-58fa-8b16-9638b45bc2bc | note | Verifying Records Checklists, Test and Supplier Certificates - Test results
7f46e4b9-5c20-53b4-a42e-f99aaf2164d2 | checkpoint | 3.15 - Catch Ditch Inspection
3bc81bfe-f8ca-5874-aa70-3a36b8e3c19c | note | Method/Description - Visual inspection
6591a1a2-a4f4-5d80-81f0-52f304bfa7b2 | note | Test frequency - During construction and at end
bf75b45e-e158-5b90-b063-0f36181b3fae | note | Contractor - W
1a6dedb3-7f2a-5fff-8eee-ceeb49adb010 | note | Designer - I
922c023c-8333-5eac-88a2-62a5bf9c081f | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks Cut Checklist
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
09a3152f-ae50-532c-bdbc-f38642adf899 | checkpoint | 4.01 - Throughout construction period prior to road opening
a0d6d38c-697b-54cb-9687-a845e0846bc7 | note | Method/Description - Monitor
451c3b4e-6bb5-5b5f-8d5b-8f16f987d73d | note | Test frequency - At least once during construction, A minimum of 5% of the rockfall drapery system anchors shall be monitored throughout the construction period prior to road opening
4bf59c76-faa3-5941-af05-cd2e4b84c3c4 | note | Contractor - H
77d4330d-61f9-5ab0-a66b-88bf8fb510c0 | note | Designer - H
28e36483-a29e-5f52-b23f-8042f8ac3ae0 | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring report, photographic
b44868f2-c57e-5d38-b8d7-c113e4f21511 | signoff | AUTHORITY HOLDPOINT
37e1199b-cda8-504b-8df9-24e893afed46 | checkpoint | 4.02 - Red Line Mark Up Drawings
dbf459a1-6040-5721-81ac-6db9d7de3f7a | note | Method/Description - Submit
e7047806-8a5a-5141-baa0-037319244bf6 | note | Test frequency - At Completion
7850ed49-3905-50d4-9ee3-da38a9bc9940 | note | Contractor - H
e8259853-8598-5000-948b-17d65b065b84 | note | Designer - R
a4877652-f389-5445-975d-d0316fb7fb40 | note | Verifying Records Checklists, Test and Supplier Certificates - Red Line Mark Up Drawings
165c7067-43c9-5a52-b41c-8c7612d7b156 | checkpoint | 4.03 - Operation and maintenance report
c479fb98-dd0e-5bff-94dc-929616e70747 | note | Method/Description - Submit
bd630073-0de0-5a01-9554-b4dc79cb428c | note | Test frequency - At Completion
a500b4b3-21d8-589a-8b44-0957500ce9b5 | note | Contractor - H
b8389d31-7198-5f5e-aa97-4eef21df24be | note | Designer - R
49b4726f-0ee7-591b-af1f-91bb4b22195a | note | Client - R
17706908-05a9-572e-b866-1eacbb91578e | note | Verifying Records Checklists, Test and Supplier Certificates - operation and maintenance report
ddebe8d5-1f5e-54b7-b7d3-e3cd9dc9e681 | checkpoint | 4.04 - Final Handover Package
60f80013-c7b0-56c3-af8a-e61873733297 | note | Method/Description - Submit
acd2048d-7e93-59b3-8ce0-9ba64ac1042d | note | Test frequency - At Completion
317658b0-94f0-525b-8c81-071dbb80e9ba | note | Contractor - H
b4434f65-a290-5277-b45a-5ded9e503375 | note | Designer - R
5dff87c2-1437-5e9f-8b85-3c20c5728035 | note | Client - R
2e373b2c-cc8b-50ce-ad46-3d99d98e6786 | note | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
901ddb0f-a03f-4b02-9b0e-86b53c1a93f5 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
87a29dee-8313-4f1a-b841-3e435ad9eee4 | checkpoint | ITP Close-Out by
31103acd-80ba-5f64-887d-2dc5b516353d | note | Site Engineer/Project Engineer
13f28cce-c929-5da7-9da1-7c3b34a537fb | note | Zone Manager Approval
cadbaf9c-a377-53f0-81b9-3e881b436780 | note | Construction Manager Approval
980c1939-c8bb-57a0-a2b5-f368775937d4 | note | Quality Manager Approval
14d8586b-5ae8-5faa-873d-1e4e13958f6e | date | Date:
cb01da1f-62e4-46b6-a5e6-c327d2676754 | signoff | SIGNATURE
d4e2e832-8638-5880-a666-c697690c36fa | checklist | ITP - Fill 12 Rev 2 | itp | ITP - Fill 12 Rev 2
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
c9e7969a-5007-57ec-ba14-7e88241a4737 | checkpoint | 1.01 - CWP
fb664a72-e171-5e36-ab8f-f6dd3f949cc1 | note | Method/Description - Document Review
70a83330-58e8-552d-9db8-6e56a9f87f94 | note | Test frequency - Prior to personal starting
b2748313-849f-5c1d-a688-1bd896297d75 | note | Contractor - H
d60c4887-6495-512a-afd2-3c4705407f86 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
5c6d3d2d-8b90-5b45-ac77-8cb3e4b937f4 | checkpoint | 1.02 - Design
7cdccebb-a505-5b78-8c70-2d5f8e33a186 | note | Method/Description - Document Review
f88efe67-5095-54d0-9559-e85400613b4c | note | Test frequency - Prior to starting
032f22ea-2f61-5b1a-a7b8-de57a55a0cb8 | note | Contractor - H
37114cda-cee2-52db-9234-258f921175c6 | note | Designer - H
84355d15-0176-5fba-ad0a-13a6efb89feb | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
7bd1fe4b-029d-5a22-999a-91130e63165b | signoff | AUTHORITY HOLDPOINT
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
c5860170-7555-5902-b6a0-5e5af09b61c9 | checkpoint | 2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural fill Material
4e14b593-e8c5-5f41-b65e-9c1a1b8b0100 | note | Method/Description - NZS 4402:1986, Test 4.1.2
918ef461-7d0b-5f06-a12e-7fc437daad2d | note | Test frequency - 1 test per 20,000m3
fe4c6413-b11f-5e42-992d-c6b4016deb38 | note | Contractor - H
3afd822d-a24e-52e3-b04d-661e9e006270 | note | Designer - R
019bcf3b-5907-5727-b8ca-876deaacd2eb | note | Lab - I
ceca5d14-9f6f-5202-87a6-8613faa41e7c | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
235d1d5d-9af2-5bc5-ae7f-3fd0f28baa68 | checkpoint | 2.02 - Atterberg limits test for Structural fill Material
58bc7ded-605f-5ae4-8e79-ac3e1568cd4c | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
34f7af07-687b-5d9d-81f0-e4aa6911831f | note | Test frequency - 1 test per 20,000m3
b53ce078-1a14-5c00-bd74-3087694449d7 | note | Contractor - H
3b2bf412-28d5-5583-b405-ca86a6ac91f1 | note | Designer - H
476cf28c-b97f-5e4e-bf91-e3841eba7299 | note | Lab - I
5f39c429-9592-5afc-bed4-a1a09ca98814 | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
293db33c-cb61-566d-bafc-5f8ae2ab4a45 | signoff | AUTHORITY HOLDPOINT
7f582d98-61ec-5278-8c11-9dc43d59f9f2 | checkpoint | 2.03 - Determination of the dry density/water content relationship (Heavy Compaction) for Buttress Fill Material
8229c3c3-194f-5458-8656-69e0deca6813 | note | Method/Description - NZS 4402:1986, Test 4.1.2
d1c50a0e-d542-5d29-92df-fb27fa05e7d2 | note | Test frequency - 1 test per 20,000m3
6cdee1e6-6ba4-502e-b0db-152707a2a453 | note | Contractor - H
fb48c7b3-3a05-5343-ab12-1d03b9ce7a39 | note | Designer - R
cde610eb-b31c-5424-9437-354c64efa368 | note | Lab - I
788032a3-8edf-5798-894c-acf2894dd69c | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
7d6904fa-05eb-5017-88ff-f9f456e0acf7 | checkpoint | 2.04 - Atterberg limits test for Buttress Fill Material
ecede97a-bb51-5139-90b7-4aec966801ed | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
83ea8ac5-cbd4-5551-85a2-ef5bc097eaa5 | note | Test frequency - 1 test per 20,000m3
3bb2114a-3298-5538-b54e-a5a7dbc717b7 | note | Contractor - H
959d599b-6d0b-5bb4-8d5e-bc81be994f6e | note | Designer - H
23584793-154a-5099-bc08-bf32dd8a9c3e | note | Lab - I
06b25e96-b8c4-519c-be9a-281fea0b69a1 | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
4102e8ea-397b-58f8-b887-3bfbfdb96db5 | signoff | AUTHORITY HOLDPOINT
eaa4bde7-3333-5990-8dc2-4ced4d650c06 | checkpoint | 2.05 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material
5c67c79c-eda3-5a80-af91-266a53016298 | note | Method/Description - NZS 4402:1986, Test 4.1.2
3d6c8533-a8c9-59b0-8065-ed6c30448435 | note | Test frequency - Source approval 3 no. tests
4d0b44ac-5f02-5a7b-8ec4-38f0438c1bcd | note | Contractor - H
9f8b930e-e131-58d9-8296-278ed51836d9 | note | Designer - R
394945aa-6a62-5263-b960-3c85ec182505 | note | Lab - I
63cf6667-fdb1-5df9-aa09-64c03b058d22 | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
3cdaa73e-31f8-5bf7-b4d2-bda5d46ff56a | checkpoint | 2.06 - Particle size distribution (PSD) Test for GAP 65 material
289936c9-0928-53a9-8157-8a6a6d5be5fc | note | Method/Description - NZS 4402:1986, Test 2.8
1b90de68-5d3e-51d7-9e82-96a6afe82106 | note | Test frequency - Source approval 3 no. tests then every 2000m3.
32401c7b-2015-5381-b8ad-9c4a78018e8a | note | Contractor - H
eba1b39a-a2da-58cd-a305-8ac1bdbaa710 | note | Designer - H
f9f8baf0-13dd-5d7c-8735-6a1ef668bc16 | note | Lab - I
3266ecdf-daa0-57ee-bb87-a1062f4eacae | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
e451af1e-f752-5a54-a441-a4e522577541 | signoff | AUTHORITY HOLDPOINT
4c70cee2-b353-538d-9f04-883677264fe7 | checkpoint | 2.07 - Permeability test for GAP 65 material
b47bf4cb-a33e-5f42-8ef9-f866aa45b068 | note | Method/Description - ASTM D5084 - 16a
57a8715e-b4f2-56cc-9ee6-337041097a14 | note | Test frequency - Source approval 3 no. tests
096f8fc5-5724-5c2a-a820-075005b5e38b | note | Contractor - H
de432b98-93d3-5771-9f55-4df77b372aa8 | note | Designer - H
e427fa78-6276-512e-9a42-c2a4e186e3e3 | note | Lab - I
48318e62-673f-5308-a0f2-7db6ebc91ceb | note | Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report
6732cb05-6996-515f-bdee-b84ec622ba5a | signoff | AUTHORITY HOLDPOINT
39b08672-8e77-55f3-b312-9ca6941ef427 | checkpoint | 2.08 - Large Shear Box test for GAP 65 material (Minimum 3 normal stresses)
456169af-8390-51c1-9c4d-fb72b54001b7 | note | Method/Description - BS 1377 Part 7:1990 Test 5 Determaination of shear strength by direct shear
2866340d-6b9d-5813-b5c3-9c6c91bc7d78 | note | Test frequency - Source approval 3 no. tests
33b93899-828a-5ea3-891e-de9c2bab628d | note | Contractor - H
8307e1e3-531c-5d41-bfa9-bddd24713831 | note | Designer - H
8d1fd2f3-763f-54f1-9384-932dbe97ca5b | note | Lab - I
d0b928ce-801d-55f2-a5be-39fd2537bd34 | note | Verifying Records Checklists, Test and Supplier Certificates - Direct Shear Strength Test Report
b17bc04f-f801-5254-b66f-20b0b5af172a | signoff | AUTHORITY HOLDPOINT
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
f80e3859-9837-5795-b26c-edce867f3449 | checkpoint | 3.01 - Set out extents of fill and check against design
c52def2f-2109-5b5c-ad95-4ea04e9cd97b | note | Method/Description - Survey/visual
ac031b91-f2a4-5881-b693-4c63e95ab9b6 | note | Test frequency - Prior to Commencement
4d47c5f7-a2f8-508e-abf7-93a59ae0c335 | note | Contractor - W
9a2366ea-dde1-5a1f-aa20-31976fcfcac4 | checkpoint | 3.02 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
de7d798d-cb48-5672-a148-0d3cb7eb1e29 | note | Method/Description - Survey/visual
6a08abb5-2286-5fa3-a65b-566f57916f22 | note | Test frequency - Prior to Commencement
18576264-457f-5a5f-97ef-4fcc327ce8b8 | note | Contractor - W
ad7cde9a-ab42-5a9a-a9cd-4dd8a4d67d81 | checkpoint | 3.03 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots. Except for Fill 12 and 13 where the fill height is >=5m.
9c885834-2a05-552c-ad4a-10775f4aa66f | note | Method/Description - Survey/visual
1ceb6a75-efde-52cb-aab8-ec863ba203b1 | note | Test frequency - Immediately prior to earthworks beginning in all Fill areas except Fill 12 & 13
4dd8fc92-344e-5f72-92a1-ea2932f02d9e | note | Contractor - H
79d08386-5ae6-5d2a-87a1-43a4158e7c94 | note | Designer - H
17d1c2e6-e9c3-5e33-a7f6-8f49d770a6ac | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
7c1023a7-79db-5bcd-a3bb-3fd56c97e2da | signoff | AUTHORITY HOLDPOINT
968214fd-11f9-5702-8296-7a714958f524 | checkpoint | 3.04 - Designer witness of in-situ subgrade prior to filling
ab7f8317-43eb-555d-9d3d-183b9214d086 | note | Method/Description - Inspection
3f7d1430-d594-504c-aac6-943df5437658 | note | Test frequency - Prior to Filling
51613f83-605d-528e-9a08-5935151d273c | note | Contractor - H
065766cc-d893-5902-ae2a-664ea598f82a | note | Designer - H
d0438fd8-b2a6-5373-83e4-a55ab09c708f | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
0df5fe88-5f22-57d6-b8f0-47988d704f9b | signoff | AUTHORITY HOLDPOINT
9337de40-bb4e-5c4d-869b-d8f3bcf1a9cc | checkpoint | 3.05 - Undercuts
6a247c14-a5c4-5160-a781-6ddbb0a7f70f | note | Method/Description - Visual inspection
4265eefb-8165-5c9f-9e1a-9c717668d00f | note | Test frequency - 100% of works area
2797ee5c-bba2-5334-9268-d825f5e4da7b | note | Contractor - H
cf71ba8b-b7c3-514a-99fd-c213c2509fc5 | note | Designer - H
9745ef4d-ec00-5cb2-a244-7f1f1ef8f98e | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
b0f007b2-da0e-5103-a4d5-29026850c2cf | signoff | AUTHORITY HOLDPOINT
580053e5-baa8-5405-9489-549ebcfb830a | checkpoint | 3.06 - When required Undercuts (cut-to-fill operations)
debe45a7-584d-5ce1-bdb4-557f0c8e813f | note | Method/Description - Visual inspection
7f2fcffa-1eb3-5998-8842-b8555461cc30 | note | Test frequency - Prior to Filling
1e376a62-1752-5cf0-ad5b-f226ae1548cb | note | Contractor - H
75528299-e470-532b-bc26-4b56da0a037c | note | Designer - H
6c6ea7d9-c62a-5c00-8c93-8166ab29cfd9 | note | Lab - I
6c418ec5-1ac1-5285-95a1-488379d4d2d2 | signoff | AUTHORITY HOLDPOINT
2552f911-8442-52c0-9af0-728f86ec61c8 | checkpoint | 3.07 - Sub soil Drainage
9163e960-06f7-557b-ade5-7365b9f79677 | note | Method/Description - Inspection
4069e98c-35fd-55bf-a8dc-cf3314e4c29a | note | Test frequency - During subsoil construction
4dde36bf-f539-506a-94a6-f6e2dcbde0bc | note | Contractor - I
e0263c49-b0ae-55a4-bf49-42c986dbf85f | note | Designer - I
f625f46b-68d8-5844-ba1a-6dce0b346fc2 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
98241a54-b8c7-5bd4-959e-35df3ae73c33 | checkpoint | 3.08 - Monitoring Equipment
f4f5f137-94c9-5c26-89a6-d1bf1ee418ab | note | Method/Description - Survey/ data logging
62f2a2ca-798d-5954-bcba-857dc1448c1d | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
0e5bcbc9-f14c-5bec-b825-5cc6b24e042e | note | Contractor - W
ba8609b5-b6f3-52fb-bc2b-7ca53f0cc70a | note | Designer - R
bfc9acba-a2ce-588d-a11d-32c1a4a10b6f | note | Verifying Records Checklists, Test and Supplier Certificates - Drill logs
ec83abcf-a19b-5853-bcb4-61fa99665448 | checkpoint | 3.09 - Filling operations
ad955907-2159-56a7-8ffd-e5fc9b963359 | note | Method/Description - Visual inspection
3063d0e1-0dad-5ccc-9e61-40b4b412bae1 | note | Test frequency - Daily
815ba075-215a-55b7-a1ee-12e673279413 | note | Contractor - H
06bc61c0-efb8-5497-a238-d391f2538cd9 | note | Verifying Records Checklists, Test and Supplier Certificates - checksheet
b1bff344-bc71-52de-be11-9a49585bc454 | checkpoint | 3.10 - Filling operations
ccb4e9e9-985f-5567-8cf0-7417da9199d0 | note | Method/Description - Survey/visual
f58a6b83-69c5-5f2e-af40-913f6472c40f | note | Test frequency - Daily
98674dd3-9591-57cd-8f92-407b743cb7b0 | note | Contractor - H
cf0e763c-bc9c-532f-a6fd-bf9bdfa25665 | note | Verifying Records Checklists, Test and Supplier Certificates - checksheet/ Survey Report
fde1ce1d-6645-5ebc-ba18-97117995efc0 | checkpoint | 3.11 - insitu fill testing-Plateau Test
c8325e1d-71f0-54c7-9b55-da598b924065 | note | Method/Description - Plateau Test
44ca0705-bfc3-5ce7-8998-9d50c1df2bd8 | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone, except where outlined in RFI0057
96d040cf-8859-5075-8f0e-01bf68b5104b | note | ○ Buttress Fill - 1 test per material type per earthworks zone
91e3c67d-0b5f-5115-82ed-3836ffe881a5 | note | ○ GAP65 - 1 test per material type per structure / location
1f0198bd-718f-5132-8231-ec9730b5cab0 | note | ○ Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
756ffbfb-684f-5370-9056-ec58078d83b2 | note | Contractor - W
0b2c8187-1723-5aaa-87e5-7cc1338ca595 | note | Designer - I
580cdb20-596d-5c03-a60d-786bf6b109c3 | note | Lab - I
bef97d2e-e20c-566e-a03d-b4ff4d647f52 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
59fa6d4f-9210-514c-8b0f-d81a5b525263 | checkpoint | 3.12 - insitu fill testing-In situ moisture content and density
13c0b8c3-eb11-5e71-b617-e58d0c38662c | note | Method/Description - In situ moisture content and density
d87458c3-88c7-5964-8504-18840501bee4 | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057
3c8ed8fe-1536-5781-a749-b19c2caa3f85 | note | ○ Buttress fill - 1 test per 200m length Average
87b6b8d5-400e-5379-8453-1da5111e6bbf | note | ○ GAP65 - 4 tests per lift per structure○
bd7b717a-be9b-54b2-b65c-c33acc8e1815 | note | ○ Subsoil Drainage Back fill - 1 test per 500m3 ,
feaaef30-3805-5931-b1be-8418dd08f651 | note | ○ Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
271a6dcc-edf0-519f-b566-d119ec88da08 | note | ○ Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
0c1c9d43-6351-5e28-b282-d337e1cf7cd9 | note | Contractor - W
5781d64a-7557-50bd-a333-23ad16e2c5c6 | note | Designer - R
73ecea43-0c6a-54f4-9c71-3a9ef68da5a2 | note | Lab - I
cfea635d-453e-5f1b-8948-d0c9b0642071 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
de9398e8-a388-53dc-a93f-ca29f461df80 | checkpoint | 3.13 - insitu fill testing- Undrained shear Strength
c67d69b2-0d36-59d1-a44f-2965981ca06a | note | Method/Description - Undrained shear Strength
35e33ec8-b0d4-502b-9b3c-5f693e9d0d0c | note | Test frequency - Structural fill - 1 test per layer per 1000m2
8605b40b-f9a5-5de7-9d8a-787e59bbfc77 | note | ○ Buttress Fill - 1 Test per layer per 2000m2
142930a3-34b1-5e8b-a82d-2c05debb1a78 | note | ○ Cement Stabilised Structural Fill - 1 test per layer per 500m2
204714da-422a-5f73-b5e1-ab5eb713eb52 | note | Contractor - W
8c058d99-dbee-56a5-bcdf-33376a9f1d94 | note | Designer - R
e2c32b3d-c756-5aac-8e96-77eb10bc9e74 | note | Lab - I
7c4d522e-83e7-5da0-a0e7-5bafbe3b47bb | note | Verifying Records Checklists, Test and Supplier Certificates - test report
94db9489-fa95-59c4-81f4-1b1869b18e9b | checkpoint | 3.14 - In-situ moisture content and density (and/ or air voids) testing of compacted for fill material Subgrade
ef3a1542-01ba-574c-bc5d-6fe2da870f41 | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
f194cada-3f64-5c37-923f-9ffdfc6d0121 | note | Test frequency - Fill 12 & 13 - 1 test per 0.5m lift per 50m length for 1.0m subgrade depth
ce865698-0f30-5f20-acb7-16b2237e1698 | note | Contractor - W
44e69cbf-2958-5994-93c8-9daba860050e | note | Designer - R
88e54547-4107-57ba-85b7-460d6e8d29ff | note | Lab - I
0ba11cab-23e5-5f19-af10-01da722e5a80 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
c5bdb7ee-403e-5550-9d7d-933aa522812d | checkpoint | 3.15 - Carry out deflection testing (either Benkelman Beam or FWD) at the subgrade
9963858c-e44c-541d-845f-e7fe7d723ba4 | note | Method/Description - Benkelman beam or FWD Testing
df745ad1-d40a-5377-93b6-a56c6ee3617e | note | Test frequency - 10m interval in each wheel path at the following levels:
3cc424d3-bc2b-5f6d-8472-76874d61d352 | note | 1) 1.0m below Subgrade Formation Level
f1691c7a-289b-5d8a-8427-59487e1e72fb | note | 2) 0.5m below Subgrade Formation Level
751460d3-f6e5-5fb6-b5ed-d2ab65971b2c | note | 3) At Subgrade Formation Level
aea5ee05-c9e1-5db9-ae96-2435e30c7d53 | note | Contractor - W
23a271da-052f-5930-ae65-ae4819fc7f03 | note | Designer - R
a4c69df8-622d-5f26-bf5e-f508e6b73255 | note | Lab - I
c09331bc-9246-505b-8909-d0307c4bf60b | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
a22abca3-0365-576a-95d5-c65bbd5e33bc | checkpoint | 3.16 - Laboratory Soaked CBR testing for Subgrade Fill
308ea3c8-956c-5a07-8845-28536f3c7ff1 | note | Method/Description - Laboratory Soaked CBR
d1a1d32d-7efa-5432-a906-6b92e6f40d65 | note | Test frequency - Test per 5000m2 at subgrade formation level
bc63d8ee-326f-55d3-8c6e-182f7a4d288b | note | Contractor - W
4f4c3482-f302-5c56-b3bf-4f7eb416a27b | note | Designer - R
2a2d4a16-7759-54ab-8439-88ee29bdbc09 | note | Lab - I
c79ffa2d-f9fe-5179-9408-72979631322d | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
de153151-2496-515f-a86e-a71e4ea85abf | checkpoint | 4.01 - Monitoring Data
1e78f3e9-37d6-51df-8954-24ef9578207c | note | Method/Description - Data Recordings
9b23dc58-c1d3-5020-9f1d-4c0885a3b15c | note | Test frequency - During construction and at end
89d77eed-cc7f-5f86-bfba-8c92a63eba04 | note | Contractor - H
47f11da2-c16a-5301-a57d-48f62e4d2853 | note | Verifying Records Checklists, Test and Supplier Certificates - monitoring Data tables
96b27424-f2a1-51a5-ba79-d8a2e76ef901 | checkpoint | 4.02 - Survey As-builts
cffa44b3-1ced-5a9d-b1b2-02a09d533f3e | note | Method/Description - Survey As-built
58eb9d98-438e-5754-8a7b-6da27f2ea094 | note | Test frequency - During construction and at end
0e92b21d-6520-585e-a748-0b15cea0394c | note | Contractor - H
9eb2cdf3-6e3e-5573-8c9d-aec197727b05 | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
5c0732e6-58ca-5568-815f-7eb40f0c0149 | checkpoint | 4.03 - As-builts
700f7a4f-3aea-5967-82cd-4b4d18452424 | note | Method/Description - Red Pen Mark up
4b3d0966-9800-58be-9613-1a8ad7a7bbe6 | note | Test frequency - End of Construction
1190487e-55ab-5617-b4e2-deccdecdf745 | note | Contractor - H
7d929f3e-2cfc-56fd-b23f-966a85871ec2 | note | Designer - H
acde1e63-8cb9-592d-9aea-47c02d5b8758 | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
da8801c3-a745-57ae-8ee9-97e0c79c7f28 | signoff | AUTHORITY HOLDPOINT
e1d6c126-3a30-4107-a192-87c2e46e0af3 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
fc94ca57-b61e-4c6e-927b-45a866f435f2 | checkpoint | ITP Close-Out by
8f4e4e65-89d3-5ff0-ab34-da9837e3b3fb | note | Site Engineer/Project Engineer
41377e3b-5e70-5dcd-a671-24c0d70f014a | note | Zone Manager Approval
f7c362a7-3e48-577c-985d-4433c9c1006b | note | Construction Manager Approval
226b7d49-3f7e-5169-906f-5b0618ec4803 | note | Quality Manager Approval
a3fb3ae0-994a-51cb-91a7-e6b3dad5403a | date | Date:
42ee6ce2-5268-4642-8bf8-f6d37a15b9af | signoff | SIGNATURE
8ab99207-4683-5b71-8702-be1afb4c1b5d | checklist | ITP - Fill 14 Bored Piles | itp | ITP - Fill 14 Bored Piles
42f478fc-2189-5924-ba07-4baaf8f6299c | section | 1.1.0 Pre-construction approvals
c6325e1f-98cf-5dd9-a024-c2741f8830c3 | checkpoint | 1.1.1 - Construction Environmental Management Plan
61f29001-2f6b-5f44-89ee-d3b6c75a68c3 | note | Method/Description - Document Review
1979e6b6-2b49-5aab-a971-55eb8ec20d46 | note | Test frequency - Prior to work starting
542bdc72-8916-5c27-9f28-b39a18838a6e | note | Contractor - H
55483e7d-69c6-525e-a54c-5057482cf97f | note | Verifying Records Checklists, Test and Supplier Certificates - Signed CEMP
ee7771bc-2366-56f9-836d-696e37f5e599 | checkpoint | 1.1.2 - Construction Work Plan
7e2b4418-314b-5306-b852-0e4e8ebc5a50 | note | Method/Description - Document Review
e8e1bed6-d40a-5654-8031-a3e78ea8fb19 | note | Test frequency - Prior to work starting
a31a4aec-69e1-5557-9d93-1d36e6eae9a4 | note | Contractor - H
ed40b710-a115-5a72-be30-2b3aa015cb9f | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
80997794-398e-58e2-88f5-b742e9843f56 | checkpoint | 1.1.3 - IANZ accredited testing organisation
a0c6841f-08e1-5aab-8422-463014b24441 | note | Method/Description - Document Review
7955328a-9d87-521b-8490-bc968db8e258 | note | Test frequency - Once prior to works commencing
ec5fdf51-9b3e-5d73-8111-94b406304b45 | note | Contractor - H
d0cf77e1-01be-5dfc-8714-1d5ca8f01a0d | note | Designer - H
b7437ca6-4dd4-583b-b6a7-135edcb68c09 | note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
1b40a37a-e607-5a69-894d-892e8bd1f5d4 | signoff | AUTHORITY HOLDPOINT
5c26f7c0-d87d-5f8a-b002-622bcc6a25e7 | checkpoint | 1.1.4 - IFC drawings
d92449ef-a0e2-57b9-ba4c-0ef09385e607 | note | Method/Description - Document Review
adef6486-4c99-5e70-bf30-db4a260e3350 | note | Test frequency - Once prior to works commencing
1bb47dfe-220b-53f5-acb7-f57a3786599c | note | Contractor - H
c5038424-94de-503b-a6d5-a0cee48147f5 | note | Designer - H
9394898e-12e1-53a6-a288-6ce480077786 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
f5c6768c-5850-51c5-a577-949a3f3372ea | signoff | AUTHORITY HOLDPOINT
f6507096-e97a-53b9-a5e3-94b665bc0f52 | checkpoint | 1.1.5 - Survey Set Out
89b1451d-6032-5004-ad56-d50d10a1da2d | note | Method/Description - Survey Set Out
19afcdaf-ebb2-5ee7-8a54-c780b1bf4329 | note | Test frequency - Prior to work starting
10693596-1e59-58a5-bdfc-1ea2f43cac45 | note | Contractor - H
2c5cbfcb-b67a-5693-94f6-f65e009615e3 | note | Designer - W
1f781704-c6db-5c5b-881c-b0caa840a4c2 | checkpoint | 1.1.6 - Piling Platform
123101ef-c100-51d0-8864-da9ac1295cda | note | Method/Description - Temporary Works Design Engineer to sign off permit to load prior to loading
84d51347-9381-5962-b1ef-520ae16a07d3 | note | Test frequency - Prior to works commencing
83f82ca9-6b2c-552a-be05-aa15582e7ff9 | note | Contractor - H
ddc1f0b2-79e2-56b9-a123-fbb0e7d8c8ff | note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Load
00d31ada-1efe-57f8-860f-8e3ddba5922b | checkpoint | 1.1.7 - Method statement and piling programme
bf779b64-86ce-5d67-a9fa-c4bc5bc49546 | note | Method/Description - Document Review
740302f8-2624-506c-9d2b-3d0aab501916 | note | Test frequency - At least 1 week prior to work starting
35917cb2-238b-5625-a3b2-526c61c44dac | note | Contractor - H
ff98f96d-5c76-5cc2-ab40-cc31f3e01460 | note | Designer - H
a980ef0a-75f8-5ef7-be04-32bad9eb5d39 | signoff | AUTHORITY HOLDPOINT
66ebdf9d-06d1-5c5b-9131-0fe3ddb647bc | checkpoint | 1.1.8 - Piling supervision
7433a21a-8085-568b-a6ee-2eca876e0a49 | note | Method/Description - Nomination
9a563578-bf0e-5e15-a3da-b3df15c9360e | note | Test frequency - Before construction and as necessary until the end of works.
ad5daf7b-e249-52fa-b4a4-cd93dac11087 | note | Contractor - H
efd0317d-2630-5f8a-81ae-c8d302a5a62f | note | Designer - W
7073aea4-221f-5ac0-8bd0-195a220994b8 | checkpoint | 1.1.9 - Observation
210e898e-ec94-503d-8632-89ae8e068efc | note | Method/Description - Contractor to provide adequate notice to enable DSR inspections
794890df-a9e1-50bd-80da-db0266d6eaa2 | note | Test frequency - Daily during works
705e9a5a-190f-5494-9709-fed5821feb54 | note | Contractor - W
c36d910e-1336-5133-b7c0-e60b9a76429d | note | Designer - W
a07a770d-1834-559e-bed8-d3126ac906bd | checkpoint | 1.1.10 - Tremie check
19ac1f51-a21f-5f49-b25a-a9d2d422855a | note | Method/Description - Confirmation of tremie sizing as outlined in section 2.1.5.2 of the specification.
29b8670f-b6a5-568a-aa15-7fcfa7ee91e6 | note | Test frequency - Once prior to works commencing
2894aacd-7fa9-55dc-a24e-c88a1582d48a | note | Contractor - H
4ff67e2d-67d0-582e-87ca-9a340aad4c9d | note | Designer - W
fe747f01-0a46-5e2c-a367-ef3d708d8f2c | note | Verifying Records Checklists, Test and Supplier Certificates - Record
721f4e1b-f234-5c95-9878-fb33f8ec166d | checkpoint | 1.1.11 - Design of temporary casing
f9033219-e97a-556f-a9c0-aa9efef5c441 | note | Method/Description - Contractor to complete detailed design of temporary casings
c0307b7e-179a-512b-a284-ce910aed44a3 | note | Test frequency - Once prior to works commencing
6102ec7f-db98-598c-a226-440d95c8251e | note | Contractor - H
e28a844e-26a4-50d0-b2e6-83e38df40ce6 | note | Designer - W
0163946d-ab1c-5072-99de-f4721af2f050 | note | Verifying Records Checklists, Test and Supplier Certificates - Record
0f3f7c86-5e36-5d1b-a6d0-ea9aff9da0d5 | section | 1.2.0 Material compliance
1dffec80-bf0b-57aa-b31d-6736773df50b | checkpoint | 1.2.1 - Concrete Mix Design
cf2648d0-6b87-5ce4-b8b8-1d3056a62246 | note | Method/Description - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 1 week prior to placing concrete and approved before placing concrete
784a5273-6bac-5abe-8bb5-d89827971949 | note | Test frequency - Prior to commencement
0aa927b5-4394-5714-8115-cf509b018f72 | note | Contractor - H
1df17266-2625-53bd-8b62-0d8f8eb4036f | note | Designer - H
e75e3944-7847-51a4-b7be-c0f97bfb7542 | note | Verifying Records Checklists, Test and Supplier Certificates - Mix Design Certificate
5b32e886-f5c4-5152-8af5-0790ae1b8f68 | signoff | AUTHORITY HOLDPOINT
5884f24a-10f9-5181-b9bd-7a700c1a73d1 | checkpoint | 1.2.2 - Steel Reinforcement
026db90b-3cf1-5d38-9422-b7eb53d1afa8 | note | Method/Description - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings
f82df01f-6a5e-5434-93ea-d10acb7a27bb | note | Test frequency - Prior to ordering steel
55186262-1c98-5e23-9be7-89901af2d985 | note | Contractor - H
a606cafa-bb69-5e0c-9c10-aaff2ea67011 | note | Designer - W?
eb21abb0-a29c-5168-9558-21ad6f0b90ba | note | Verifying Records Checklists, Test and Supplier Certificates - Mill Certificates, Detail Sheets
3150f70b-2e79-578c-a60b-e2d571037503 | checkpoint | 1.2.3 - Welding of Reinforcement
c66861a3-8187-5b7b-bddb-ab4ba160dd4f | note | Method/Description - Any welding or mechanical splicing to be approved in writing by the Design Engineer
cbeba099-6de1-57f0-9082-d4acd05e3ac8 | note | Test frequency - Prior to welding or splicing
cb48a9f1-34ae-5bc4-b0db-6b963baf4d23 | note | Contractor - H
0942976b-6654-55b2-82f7-355f8f978c42 | note | Designer - H
cce9ce8d-89d8-5ddb-82d2-6b08fabd5d05 | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built
02a5e853-5471-5e8b-95da-79851fb0c9c9 | signoff | AUTHORITY HOLDPOINT
1662121c-4b0a-5400-a9f0-471682f8bdce | checkpoint | 1.2.4 - Welding of Reinforcement
6b2f537f-f13c-5bd0-ae12-ecac410b0c1e | note | Method/Description - 100% Visual Scanning of all welds
e3104864-ddab-54a7-81be-dd81f128505f | note | ○ 100% Visual Inspection
4227338d-84f0-5668-98b9-5646c15de346 | note | ○ 10% magnetic particle or liquid penetrant
34e0972a-e00f-52d9-ba4a-97a653933e68 | note | ○ 10% radiography or ultrasonics
802bc5e1-ff2b-594b-af26-22a542622511 | note | Test frequency - Each Weld
269fcb9f-d7a1-5f17-82d8-86945d5a2211 | note | Contractor - H
ad057760-ba2f-5992-ac93-d5f145482b7a | note | Designer - W
180ede67-7f2d-567b-9c92-58a37a63cb9e | note | Lab - I
2cc856a7-52dc-54f4-a3f8-c0c4e5c22850 | note | Verifying Records Checklists, Test and Supplier Certificates - Weld Inspection Report
4deb37ea-497f-5969-9860-35554b568aec | checkpoint | 1.2.5 - On-Site Bending of Reinforcement
e015a632-52fb-57ce-913c-cea81e7d9b7b | note | Method/Description - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer
a9652896-3b1a-5b20-8921-063950d0576f | note | Test frequency - Prior to cutting or bending onsite
249fa559-c356-5e19-b5bd-00b4516e4612 | note | Contractor - H
a81f906e-f877-515f-b27c-c1e4835f201a | note | Designer - H
518f5f73-dceb-5f88-86a5-f9fb48661e7a | note | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI
2cbb4984-676e-5974-a230-4d87cee79bbf | signoff | AUTHORITY HOLDPOINT
88b14db8-13ce-5de2-b493-7a2caecdc527 | checkpoint | 1.2.6 - Storage of pile casings
6a32837c-260a-57a8-9e58-aaad559d2421 | note | Method/Description - Pile casings shall be stacked on suitable supports on firm ground
67217de3-3fd4-597d-bca1-799705667ba4 | note | Test frequency - Prior to commencement
69d905f7-3cfa-531e-9bcf-eb0f54a4a9ba | note | Contractor - H
7c3bd17e-a93a-5ec4-b725-380e09bf3c8e | note | Designer - H
84bdca34-9ccd-59bc-a741-1d1b4acac040 | note | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI
d3f310e2-8d6f-516a-9755-b369caa9a3fd | signoff | AUTHORITY HOLDPOINT
9f486cc5-1250-5507-a82e-8b56157debe7 | checkpoint | 1.2.7 - Concreting placement methodology
a0e8d5f4-7e51-53f1-9e49-b23fab9ec3fa | note | Method/Description - The concreting methodology shall be reviewed in advance by the Engineer, who will require to be satisfied that the method of placing and the concrete mix design will result in concrete fully compacted in place, possessing the specified strength and having the necessary density, integrity and durability.
23068f9a-838b-537d-bb2f-45d3f1a08ea8 | note | Test frequency - Prior to commencement
6a8946f7-0c11-580f-85f1-6813b0e6cd6f | note | Contractor - H
05e0fe15-3130-5624-8978-e0f1ade310fe | note | Designer - H
7807e1f7-1165-5cbd-a2e5-15dd2278c17b | note | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI
8a9c629d-668f-563b-b539-b741341acc04 | signoff | AUTHORITY HOLDPOINT
1f263482-98ed-5f1f-8702-e929d463c795 | section | 2.1.0 Drilling
51cb8c8e-78f4-5635-bbed-7b46aba9ccbd | checkpoint | 2.1.0 - Installation/Removal of Temporary Casing
e5e39352-4182-503d-85fd-bcd423e45289 | note | Method/Description - Vibe temporary casing to rock level, Extract Casing immediately following concrete pour.
616bfc43-385b-594f-8043-b9ca36835132 | note | ○ Sufficient quanitity of concrete to be mainted with in the casing during removal to ensure external pressures are exceeded
c272e1ff-9b7d-594d-be3d-7dddc43f7cd9 | note | Test frequency - Each Pile
8f764521-a207-570a-af61-ee189f8db68d | note | Contractor - H
9c5d7dfc-80d5-5885-9b7c-b1b28f92fe16 | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
16962cd6-5de6-58f0-99be-b917c38536d9 | checkpoint | 2.1.1 - Drill Rig Set Up
434d24a1-dc97-5915-a8e6-8279e2b4d15d | note | Method/Description - Check drilling performance, verticality and position. Drilling equipment must be capable of drilling into inclined rock surface
03b63dcf-b96f-523a-8c92-226e3274d14b | note | Test frequency - Each Pile
64dd3aff-8ba9-5a1e-a122-086fcf86097a | note | Contractor - W
c887d275-828b-5a52-8404-182dcd99a816 | note | Designer - W
d962cd1d-9fe4-5a3b-aae0-6897fa07103e | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
72420940-6c94-5853-84d0-ca9f6784713a | checkpoint | 2.1.2 - Pile Bore and Condition Log
163a9a8d-f94e-5161-b0a2-e1c688932e7d | note | Method/Description - Inspect pile bore condition, pile depth, rock socket length, toe level and ground water level.
a42bbf65-5257-5d86-98d7-d6b328558640 | note | ○ No Pile shall be left open for greater then 24 hrs; pile borehole to be checked and cleaned if open more than 12 hrs; Concreting shall be done on the same day
e9e2b6ac-8ef0-5e17-a079-6e307e243b14 | note | Test frequency - Each Pile
5cf1ba70-4ca5-50d8-b785-2a1fafe1ca62 | note | Contractor - H
6244beaf-9f4e-52d4-b6cc-ea64738d8c7f | note | Designer - W
34a02caa-42bb-5e57-8a56-e0842d7f6822 | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
001cd35d-a2e6-5801-b901-c0b24d896818 | checkpoint | 2.1.3 - Rock Socket
3d595554-70b4-5e40-af15-5d5d629a5ee7 | note | Method/Description - Each bored pile excavation shall be inspected by a Geotechnical Site Representative to ensure that the material at the base of the pile complies with the design requirements (i.e. founded in Mt Messenger Formation rock). The pile construction record shall be signed by the Geotechnical Site Representative to say the inspection has taken place and that the founding stratum meets the design requirements.
d845e343-678a-52dc-a8b5-4617ab235da7 | note | Test frequency - Each Pile
46cf72c9-65a0-578d-8a08-331f7361b13c | note | Contractor - H
d1f18c3c-e1a3-5d86-ada3-99b70a57bfc1 | note | Designer - W
e8368c44-2223-56b7-8c71-30e0f99e1846 | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
4e2e097f-227b-5fae-b825-66c3abdd8597 | checkpoint | 2.1.4 - Cleaness of Pile Base
8b196130-a19e-560c-95cf-24262d3e3b0c | note | Method/Description - All loose material to be removed from the bore using appropriate methods. Details of cleaning equipment to be submitted to the DSR at least 7 days prior to use onsite
a4cbabe9-4cad-5567-bf55-bc29a739c242 | note | Test frequency - Each Pile
512ff111-3def-58e6-86ff-381f3912d327 | note | Contractor - H
27c9ff9e-5bd3-5039-b777-bc234ee4752c | note | Designer - H
b01cab69-f2ad-5820-b74e-2472fc7cdf53 | note | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI Bored Pile Record
74f8d711-e252-5404-945d-783e60d7f50a | signoff | AUTHORITY HOLDPOINT
d859d740-8de4-5940-8513-84ae40b4d442 | checkpoint | 2.1.5 - Base Hardness
45b5d5d6-1444-52ca-9926-9795f9a3aeb3 | note | Method/Description - Base Hardness Test to be undertaken immediately prior to placement of reinforecemnt cage.
3c2f88fa-1cdd-5e2e-a1fa-3a0e72445dc9 | note | Test frequency - Each Pile
3030d30d-d51d-562c-8501-6c75dbcf48c7 | note | Contractor - H
1c0ee038-80d1-5f03-a769-1053e03f664e | note | Designer - H
761cf2dd-50cb-5fd3-ac39-e2eea04f9819 | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
ba9e50d1-9a58-5add-bcaa-04fc3b970c87 | signoff | AUTHORITY HOLDPOINT
3fe61457-c7a3-5905-893b-05727c2501cf | checkpoint | 2.1.6 - Pile bore
e2f98442-b168-5276-9077-42fcf8749b95 | note | Method/Description - Observation of geotechnical conditions encountered and confirmation of key design assumptions. Contractor to inform designer at least 1 day in advance where pile observations will be required.
5fb71b29-3a53-5269-acc5-ace0fbf004b6 | note | Test frequency - Each Pile
5705d8f2-0dba-5d5d-a7a9-a625e88bb700 | note | Contractor - H
da560292-0aba-5859-a830-25ac50c11dd9 | note | Designer - H
b967f971-f311-5a6b-a9a5-e3cb409faba8 | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
079fae18-d6bf-56b9-9480-a9de588f8877 | signoff | AUTHORITY HOLDPOINT
15b3ab22-de85-53d6-a47b-fe7569441936 | section | 2.2.0 Construction of Pile
a38cdc90-8170-590d-852e-69c0c057416e | checkpoint | 2.2.1 - Reinforcement Cage
3c731cbe-39ca-5139-8216-38c01d483ad5 | note | Method/Description - Visual Inspection to check supply and installation of reinforcement cage.
7d63756e-20b0-52b9-b489-56280ae54cd1 | note | ○ Confirm cages have been supplied as per detail sheets.
2f93728d-97fd-5b2b-bf7a-ac6f9bd2e70f | note | ○ Confirm Grade, Size, spacing, lap lengths and weld postions are as per IFC drawings
48efa758-33f1-51cb-8dbe-2b9b7f5666f7 | note | Test frequency - Each Pile
70406586-1a84-5dbe-b8b5-774991f960b5 | note | Contractor - H
412683d6-1ce3-5b24-8c92-5767d73ed4f9 | note | Designer - H
a306dfb9-721b-5d91-b3bc-26505cf333dc | note | Verifying Records Checklists, Test and Supplier Certificates - Detail Sheets, Bored Pile Record
01644df0-61ee-5b77-a7a6-e1281568f7c6 | signoff | AUTHORITY HOLDPOINT
bbd90189-a77b-5a15-88a4-ae663ff5c883 | checkpoint | 2.2.2 - Pre Pour Inspection
3f349e28-a76e-5812-8860-09ada24ed9ff | note | Method/Description - DSR to inspect and sign off each pile prior to concreting
ae4caaa6-798b-5fae-9a52-7c641bb869c5 | note | ○ Visual check of socket cleanliness inf dry
e352a3f2-9fc6-5726-beef-651ba6fb2c32 | note | Test frequency - Each Pile
6e03debc-e7ff-5657-9f1f-85f112946a08 | note | Contractor - H
7b568c6d-527c-5b59-8aad-7671a3ff215e | note | Designer - H
35fbf134-f0f0-544f-941a-a2c7f41fb7ed | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
86c2ee52-0e08-5dd8-b6f6-227bd61cd72c | signoff | AUTHORITY HOLDPOINT
52149fc6-5677-5694-89c9-fddd23f7e3b8 | checkpoint | 2.2.3 - Concrete Supply
39881190-3486-55cc-9f6b-19374001d32b | note | Method/Description - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
c1feb23d-cd6a-5746-a9e6-e54a78b3c4d9 | note | ○ Concrete dockets checked for correct mix and concrete site testing undertaken.
12b9a291-63bb-520d-8904-c9a9612b6edd | note | ○ One set of 3 cylinders to be taken for each set of poured piles
97cdcd82-77b9-5c78-a065-feefe0dcb7bc | note | ○ Onsite Slump Test
3f606efa-957c-55e4-988f-1d61d500049c | note | Test frequency - Each Delivery
5b2ea29c-9a96-5fe2-bbc7-baef22f64cf8 | note | Contractor - H
0cf20d9d-6ac9-52dd-9455-17200684d567 | note | Designer - W
2b14a1e4-f409-5140-8490-4362e553291f | note | Lab - I
958d0b06-9920-5dfc-831d-c564e53ef9f4 | note | Verifying Records Checklists, Test and Supplier Certificates - Concrete Dockets, Bored Pile Record, Concrete Test Results
ed1cc3b9-0a51-529c-b645-ec96a4561bd9 | checkpoint | 2.2.4 - Concrete Placement - Placing concrete under water
28bd2adf-8d09-5ea7-9e5e-91cf91e35aa4 | note | Method/Description - Should either:
9856054c-6a2b-5919-9994-9a2c516db30f | note | ○ the depth of water at the base of the pile at the commencement of concrete placement exceed 75 mm; or
123b8409-bacd-55c4-af35-681ce6d067ad | note | ○ the inflow of water exceeds 200 mm of bore depth per hour; or
cf7460d8-a7e2-57a1-afe7-e814ff44e602 | note | ○ the use of drilling fluid prove necessary to maintain excavation stability,then concrete shall be placed using a tremie and a methodology that meets the appropriate requirements which are stipulated in this specification and the recommendations that are described in the publication “Recommended Practice Tremie Concrete for Deep Foundations (CIA, 2012) and/or Guide to Tremie Concrete for Deep Foundations (EFFC/DFI, 2018)”.
3250e8de-d24a-57e1-abd2-ae658b514e7a | note | Test frequency - Each Pile
8fd14542-ec25-53c1-a980-22df7ae05931 | note | Contractor - H
dfd826d3-5841-5e53-817e-a29d8c4285c7 | note | Designer - H
00bad930-79ad-568d-8123-2c56f0c6a814 | signoff | AUTHORITY HOLDPOINT
3ace9467-faa2-59da-a1b1-42477683c7a3 | checkpoint | 2.2.5 - Concrete Placement - Dry Pour
7958f68e-2be6-5ff0-94d5-b38ad8245f3c | note | Method/Description - Concrete height to be no greater than 10m.
e2d07f19-c240-52db-95a1-744c8cc11fe3 | note | ○ Concreting of piles shall be carried out continuously so no segregation occurs.
637eccd8-0fbb-5dd4-b54f-3a2d8e94d4ef | note | ○ No concrete shall be placed when there is any danger of adverse weather causing damage to plastic or partially set concrete due to movement of pile casings.
c5e05f60-2a69-57a4-b033-cab785fa1dda | note | Test frequency - Each Pile
ffb29a09-e17e-5ada-b4d4-d20a65a76053 | note | Contractor - H
fe1e1c0e-4637-59aa-a0bf-99296cd10d0f | note | Designer - H
82fb5a82-0577-5ee4-8a9a-318cfc236d7d | signoff | AUTHORITY HOLDPOINT
66d9428f-52bf-5dcc-95c5-363f6e233c91 | checkpoint | 2.2.6 - Post Pour Inspection
73c4a54a-ce54-5e8a-966b-db36f18ddb0a | note | Method/Description - Complete Survey of Wet concrete level to ensure pile is poured to correct height
ae71bbe5-2943-5f17-bfa7-02f59e51c623 | note | ○ Confirm finish is as per IFC Drawings
3445d5a7-2b6e-5b57-96d9-fdf065f2248c | note | ○ Record of pile length
bc67c0cd-6512-588f-a363-13d84944907e | note | Test frequency - Each Pile
c589a28c-f998-53de-b8a1-bffe9f99cb9f | note | Contractor - H
27dd3a5f-97ae-59cf-be50-15b51bd3ac65 | note | Designer - W
2ed9b603-8fd4-5a0d-b595-e09ecb835857 | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
ae6986c9-2111-5ba2-81b6-5e51b86e536b | checkpoint | 2.2.7 - Reinforcement cage support during installation
b2bf07e7-de59-591b-9adf-4ce60bc5088b | note | Method/Description - Reinforcement cage to be adequately supported at all times during construction
30da34d1-27d4-588d-b2cb-065452302ae9 | note | Test frequency - Each Pile
b2aba53b-c1af-54d3-8fc7-dd77303cb667 | note | Contractor - H
b215a48f-b1ec-5de8-a4ca-0f156e543c16 | note | Designer - W
a47030ba-4e72-5ac7-8006-dbab43d6a1e0 | note | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
d5545795-84a2-5564-99ac-44165c0761fb | section | 3.0 Post Construction
be98c092-01d5-5b90-971c-8c4da0244e2b | checkpoint | 3.1 - Survey/as-builts
0be11f26-6501-5401-af5a-485caa5a6fca | note | Method/Description - Survey final position and top R.L. of each pile, produce As-Built drawings including stated measurements of pile lengths; record bedrock level
e7230960-6281-5419-babc-742bc3b0e56b | note | Test frequency - Each Pile
476d5ccf-f296-5076-a37b-991ab9817b50 | note | Contractor - H
dad7c6c1-2120-58d6-81cd-c89890d69515 | note | Designer - R
51811888-795b-5aaa-9b66-8897a27cdde8 | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built
9f0e8a71-a4df-5fbf-ac8d-1e79564455eb | checkpoint | 3.2 - Red-Line As-built
b5be7e63-e421-5979-9242-19ba72e10a18 | note | Method/Description - Draewings updated to reflect any changes during construction
28c6a7d4-4e5f-5dcb-980b-9d81776d456e | note | ○ Any RFI's and NCR's noted on drawings and closed out prior to drawing re-issue
d29fc432-22f9-5d01-9c44-ad341f8b5ea6 | note | Test frequency - On Completion of Works
81e3220b-ff4c-5cd3-88d5-9901367a1cd8 | note | Contractor - H
7ed51bf0-b157-5800-9d29-a1c74d781ebe | note | Designer - R
3419a46e-9ba6-50d9-83ac-d6712b6d1019 | note | Verifying Records Checklists, Test and Supplier Certificates - Red-Line As-Built
d954572d-81b5-4dc3-bc61-1106e8903b36 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
26e83392-2e71-495f-a71e-2dda635774e8 | checkpoint | ITP Close-Out by
ed4255d2-0cda-51f1-a3e8-639ec853a26c | note | Site Engineer/Project Engineer
265eeef4-96f6-5d5a-818d-66f3538c160a | note | Zone Manager Approval
eaf0913e-b8e6-5913-8e08-63dc877be4a4 | note | Construction Manager Approval
b7598025-9a66-561e-b62d-ff6c15925483 | note | Quality Manager Approval
9a6857bf-b413-5cc4-befd-a9d8f378bdf8 | date | Date:
9ea4c714-c982-4c21-8931-e5cb2f1c9018 | signoff | SIGNATURE
09d5f768-4640-5b85-8523-711a80e08596 | checklist | ITP - Site Preparation and 2023 Planting Season Rev 3 | itp | ITP - Site Preparation and 2023 Planting Season Rev 3
046a1aba-5615-526e-93b5-56ba0137143b | section | 1.0 Pre-Construction - Preliminary Inspections and Tests
4cd4a400-1f83-5f50-bbdd-d05ed0b9c0d9 | checkpoint | 1.1.1 - Provide work plan to the Landscape architect.
502ed3db-9ab6-5ee0-9423-95c4199ec997 | note | Method/Description - The builder will produce a Landscape Treatment Programme Plan listing polygons from MMA-DES-UDL-E1-DRG-1000_1017 that are ready for planting, and assign approximate planting dates to each polygon.
b41cc882-fabd-5424-ae2e-825cd3647cf2 | note | Test frequency - Annually - pre planting season
c370880e-cc1d-50d1-9122-5f40fe890491 | note | Landscape Architect - H
7d1d8317-b6ec-5653-ad2d-32c57f449b22 | note | Verifying Records Checklists, Test and Supplier Certificates - Work programme signed off by Landscape Architect.
3d82a333-c271-5e6a-8045-7a9afcb7aac4 | signoff | AUTHORITY HOLDPOINT
ccebf4eb-bd07-5e67-8ea8-4a8370cdcd45 | checkpoint | 1.1.2 - Plant selection
0809f703-6875-5d44-9aa7-ecfa0067fefd | note | Method/Description - Plants selected are reflective of the specification and approved by the Landscape Architect.
fdb812d9-5d11-5a9f-b70c-a2da00b4f214 | note | Test frequency - Annually - pre planting season
5510d9ac-3124-5ce4-8ed4-1130458eab80 | note | Landscape Architect - H
5ad72ad6-5fbe-53e8-9cec-17dd391f631e | note | Verifying Records Checklists, Test and Supplier Certificates - Plant species memo issued by Landscape Architect to confirm eco-sourcing. Planting verification checklist signed off.
10e5cc85-39f8-5eff-bff1-ff52367e847c | signoff | AUTHORITY HOLDPOINT
b4dd9b86-62ad-592e-8b40-bdb110064e2d | checkpoint | 1.1.3 - Boundary fencing installed
c9a517d3-0857-5fef-9d0d-6e28b9f6bdf8 | note | Method/Description - Planting areas identified near property boundaries are to be stock-proof fenced prior to planting.
c32bdff1-fd17-53e9-94e4-ed7347218355 | note | Test frequency - Prior to planting
02572bb1-f0e2-557e-beed-714930f1011e | note | Contractor - R
770103f8-6be9-573b-83e6-64b042317d33 | note | Verifying Records Checklists, Test and Supplier Certificates - Boundary fencing plan review MMA-ENV-DEP-37319 and relevant property agreements. Planting verification checklist signed off.
ffd8c6dd-dd92-5811-9834-14d8f139c82b | checkpoint | 1.1.4 - Vegetation clearance complete
0df7ff4b-1c9f-5d04-9512-9737189750ab | note | Method/Description - Ensure all vegetation is cleared and removed (as required) from the planting area.
3e1446c7-4ec8-57d7-b504-f4704328d5c8 | note | Test frequency - Prior to planting
b61fc960-cfcb-53c4-9aa2-67fa7212464b | note | Contractor - W
95940d25-a0b0-5ef0-a248-ec20ac73537f | note | Verifying Records Checklists, Test and Supplier Certificates - Planting verification checklist signed off. Approval from ecologist required?
0e9c7ff2-8303-51cf-a6c0-d6eaf4c8197c | checkpoint | 1.1.5 - Plant and animal pest control
62666065-56b2-501a-a1e5-ca8f077a72c7 | note | Method/Description - Invasive plant pest and pest animals to be controlled where required, prior to planting per polygon.
e8d00337-681f-5da5-9d90-b4df7e1a133e | note | Test frequency - Annually - pre planting season
315fe849-1c69-5154-b286-a6fbd12934c1 | note | Contractor - W
92a1bea4-dd52-5fc4-9b76-45311090d8d7 | note | Verifying Records Checklists, Test and Supplier Certificates - Fencing ITP reviewed for nearby planting locations. Planting verification checklist signed off.
b8b1179c-9b0e-5c90-8cb4-ddcbc6c133c8 | checkpoint | 1.2.1 - Plant Acceptance: Inspect plants at Nursery
887def15-dd9d-500e-aa17-c5461dd9cbce | note | Method/Description - The Landscape Architect and Contractor will inspect the plantings growing in the nursery, prior to delivery to site.
49aafb10-d0b5-52e3-9296-45e7a8643312 | note | Test frequency - One visit during the propagation stage (propagation nursery, Jan-May)
608c955c-b45c-5950-aca4-73eb3941521e | note | ○ One visit during planting season (growing nursery, July-November)
3229cdff-6441-5d92-bf32-c6f26ebbb962 | note | Contractor - W
65d91c04-f15d-5cd4-b5a6-8c9bc7777250 | note | Landscape Architect - W
2a63b929-638b-5bf8-9330-aaff6edb379d | note | Verifying Records Checklists, Test and Supplier Certificates - Nursery inspection report from the Nursery detailing propagation and eco-sourcing records. Planting verification checklist signed off.
d5c2963d-b099-5e7b-aa43-513c85b9ece3 | checkpoint | 1.2.2 - Plant Acceptance: Inspect plant delivery
6eabdd31-2ae2-5a15-8e70-5e4044826a01 | note | Method/Description - Inspect plants on delivery to site, prior to planting. Reject plants based on incorrect species or health of the specimen
675d65e7-1ef1-5699-8423-ee6942678409 | note | ○ Inspect the plants on site following transport to confirm they meet the works requirements.
124c3c91-7d67-5608-84ef-933f6969c10f | note | ○ Any plants that are dead, dying, not true to name or size as specified, or not in satisfactory growth or have a matured root ball as determined by the builder shall be removed and replaced
715ba8ab-6741-5ebf-a484-ec097a6fdb11 | note | Test frequency - Per delivery
dea295e7-d1cb-5e75-8ab3-7e03d95f836f | note | Contractor - H
5d9e9f2e-41ad-54ea-8f91-9147a8ddec4e | note | Landscape Architect - W
c0eca5d6-ebe5-531a-8211-a2e33723cf00 | note | Verifying Records Checklists, Test and Supplier Certificates - Plant delivery dockets. Planting verification checklist signed off.
ac9f2bda-6d65-549c-822d-9fd7fe98f912 | checkpoint | 1.2.3 - Imported Growing material
1f61a35f-d800-5afd-8874-083f4ea49e7c | note | Method/Description - The Contractor shall notify Waka Kotahi (via the OIM) to confirm the need for imported material. The Contractor shall then confirm with the Landscape Architect required volumes of imported growing media for each treatment area, prior to sourcing and importing.
3b7d08b9-7b8e-58c8-8d70-108d783ab0fc | note | Test frequency - As required
fb6d3a79-d22f-59b9-88f7-ef0aaa5a8f30 | note | Contractor - H
68992708-ba16-5f57-ac26-efb3ad7221c5 | note | Landscape Architect - H
3a03f14a-f575-550d-9480-893a808ee0a9 | note | Client - H
9718bb44-8b0c-5021-b5b9-7317403dbf9f | note | Lab - R
7fb94e27-bb4d-5e5c-b1d5-57e46fd6a10e | note | Verifying Records Checklists, Test and Supplier Certificates - Test report from an approved soil testing agency
18273ea2-f1af-52c2-9814-0f37000a1fbc | signoff | AUTHORITY HOLDPOINT
744638b5-cf0a-5a17-80f4-e36e9a533305 | checkpoint | 1.2.4 - Grass seed mix
cf2311fa-f0c6-57f0-8fb9-ba4cc1f76ea1 | note | Method/Description - Grass Seed shall be as specified by a turfgrass specialist. Different seed mixes will be required for different types of sites.
883d64f4-c6d2-550f-bebc-b761e5607f1f | note | Test frequency - As required
dbd89441-dd40-55c9-a47a-7dc4fd572455 | note | Landscape Architect - H
f5a3af51-b819-58b9-b1d0-8eb12bd1d1c3 | note | Verifying Records Checklists, Test and Supplier Certificates - Approval of Grass seed mix by the Landscape Architect
ea1a1307-cfd8-5084-b4b6-cde6de983144 | signoff | AUTHORITY HOLDPOINT
da1840cf-2033-5059-9826-3cae8015d4f1 | section | 2.0 Construction
03b80add-5c88-5f0b-8723-f0ee16192fc2 | checkpoint | 2.1.1 - Planting set out
8952d28c-bec2-5f48-810c-7e1d7ffec5f2 | note | Method/Description - The builder to do a visual assessment of the plant layout, ensuring spacing, species groupings, and species placement are acceptable and meet the environmental conditions that each polygon provides, prior to planting.
dfcc8d7b-af81-51f9-adf8-76177c483ddb | note | Test frequency - Per planting polygon
b9522717-4613-50e4-b480-605d2a431221 | note | Contractor - H
944baf1e-d254-59dd-94fa-d836b1bca402 | note | Landscape Architect - W
f9cc2101-cd28-584a-87de-aa147a91521c | note | Verifying Records Checklists, Test and Supplier Certificates - Planting verification checklist signed
122c6685-0c39-5da6-859f-f067d192a4fb | checkpoint | 2.1.2 - Hydroseeding and grass establishment
28e5e6e9-050f-5d16-9c7c-4632d52b8890 | note | Method/Description - Grass is established as per sections 8 and 9 in the landscape specification.
ef55ff10-ee32-5e9f-aab4-26b9535e6a30 | note | Test frequency - Per Grass polygon
a1712e39-07cc-517a-a3ac-13317477ea89 | note | Landscape Architect - W
6eb231a0-ff6c-55ca-93bb-89c50a8b3be7 | note | Verifying Records Checklists, Test and Supplier Certificates - Planting verification checklist signed
ed343649-df20-5925-ab52-d5a7ebc82f95 | checkpoint | 2.1.3 - Practical completion
e14c574e-b6aa-5765-a9dd-ef0b61548968 | note | Method/Description - Information to be sent through to designer, illustrating design implementation. Correct species, planted correctly as per specification standards.
d253bf2d-d5df-51d3-ab96-0d60d60f9170 | note | ○ Tracked via photos, verification checklist, and onsite inspections
9c946a4c-89a3-5d2e-94b2-20b42968f962 | note | Test frequency - Per planting polygon
7ba385c7-9c26-5299-bfa0-e42c6bf895cb | note | Contractor - H
827dcf38-e86e-52f2-8a68-7d70c559580f | note | Landscape Architect - R
f2b7f9bc-c00d-5a19-8fbc-5962d2281ae3 | note | Verifying Records Checklists, Test and Supplier Certificates - Planting verification checklist signed off.
734d6856-675d-41e2-820f-46538a596c79 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
7aae9d2d-2cd1-4224-a8b1-264c19a65b29 | checkpoint | ITP Close-Out by
64d6b04e-1da0-53ea-839c-363c9f2ccd97 | note | Site Engineer/Project Engineer
2db7f5f1-05e0-516c-9f39-d2338c370b1d | note | Zone Manager Approval
676fef29-72fb-59be-a461-edb46bbb62df | note | Construction Manager Approval
02c2b15e-4d63-56e1-9ed3-ed6fb46d42c6 | note | Quality Manager Approval
a98994f8-396e-5017-8b26-a3c697180d58 | date | Date:
d58cc199-0a80-4851-9cda-fc4e6b87800a | signoff | SIGNATURE
7d73d3c4-00cc-4919-9bd5-76d05a6893cf | checklist | ITP - Tunnel Construction | itp | ITP - Tunnel Construction
d1f5c76e-936c-45d8-a740-8048ea4bdb09 | section | 3.1. Excavation
69f9d624-bf7f-4ca9-aebd-c2d498ff88a9 | checkpoint | 3.1.1. - PTT
1ffbc93c-3958-5e2c-9c30-a28164226a6c | note | Description - PTT shall define the planned excavation limits and support types (RESS) prior to each defined period of excavation in each heading or bench face.
12e1cfb7-3a0c-5f79-a68b-bf1665c68ff4 | note | ○ Tunnel excavation shall not commence on a shift until PTT has been signed off
14c96b10-0a4f-5040-b326-8322bc2a1d56 | note | Method/Description - PTT form
bdeaf7f0-54b1-5691-952f-5e40a6c88cfb | note | Test frequency - Every advance or as agreed in DRM
00fb9425-b1b6-513a-a0b1-777d83d1129c | note | Conformance Criteria - N/A
49b48eb5-2111-5958-bee3-52fd9b2b2c9d | note | Constructor - H
bef1c692-420f-52b5-b394-cd0a7f056f21 | note | CPS - H
7cdba770-cd4a-5c61-8592-76b786a20f1a | note | Verifying Records - PTT
89eb2806-d3f8-4ebc-9ccc-2b36faf230b9 | signoff | AUTHORITY HOLDPOINT
47fe0e79-4c45-4b74-bc57-c249b9ab4d49 | checkpoint | 3.1.2. - Face Mapping
db7b5dad-dc0a-5d23-826d-3b2028be29a6 | note | Description - Recommend the required support type based on the Actual Ground Conditions.
994c6fef-38e6-55a8-be79-f481002bf170 | note | ○ Determine any corrective measures required to ensure safety and stability of the excavation.
502ac59a-143e-59d7-9916-bc5ca17993b5 | note | ○ Identify if the ground conditions depart from the expected range of conditions for which a support type has been designed and notify the Designer if new design is required.
245057d4-3bd2-5253-bdbb-58c88b8820a6 | note | Method/Description - Geological mapping record
874b445a-10d6-5370-8622-dc0e8d50a67e | note | Test frequency - Every advance or as agreed in DRM
3423d1e3-9433-5988-84dd-5a2a4a172860 | note | Conformance Criteria - N/A
f60821a2-d779-51d1-896a-8127330a1595 | note | Constructor - H
e9e470e4-cdc7-5637-af9c-c7fe46e58757 | note | CPS - H
21d0e1eb-594e-5faf-92f7-a0b9efddc459 | note | Verifying Records - Required Excavation and support sheet
409b00ed-8874-4e93-8383-e6590381e40d | signoff | AUTHORITY HOLDPOINT
c779146e-d91d-41e6-a378-fb045f26ee1e | checkpoint | 3.1.3. - E-line control
6c33199d-a3bf-5d46-b14c-aaae1fb6471f | note | Description - Control the E-Line before, during and after excavation is finished
7a2ad99a-8b3c-5af8-8315-0abb21986145 | note | Method/Description - Surveyor to set out and record as built. VMT system to provide e-line guidance
f166a8c8-287a-5fe6-b9a2-cbb770dcff27 | note | Test frequency - Every advance
738706fb-4a23-5574-8e5b-2c4514b67613 | note | Conformance Criteria - Over excavation tolerance -0/+150mm
33f22df9-751d-5c7f-8359-540bfbdd38d5 | note | Constructor - H
a239a9d2-9dd0-56d9-b5a4-0725f9ff605b | note | CPS - W
b8eb98b1-0800-5487-9b20-8e5582c66183 | note | Verifying Records - As-built Report
95ec9b42-4fee-4b5f-b787-ec8270c69c9d | section | 3.2. Shotcrete
a2bc2193-7f9e-4ddd-9820-eafd5ad317e1 | checkpoint | 3.2.1. - Delivery docket Check
dd28c764-9c66-5bc6-94ad-aa6d96e53b0b | note | Description - Check delivery docket to ensure the mix used is the correct mix
bac23667-c0d9-52d2-81a8-e36be885320b | note | Method/Description - Document Review
813f6969-32f2-59a1-b4ab-444b64837a43 | note | Test frequency - Prior to any shotcrete application
4a87f013-e664-547d-b08c-142df460f42d | note | Conformance Criteria - N/A
7b82e7a4-f187-55dc-8353-b47213acc76f | note | Constructor - H
91b655dd-6c8c-564a-a485-b68948b9ea6a | note | CPS - R
c50407be-fc67-5f46-88a6-2354ae636349 | note | Verifying Records - Delivery docket
c7986b49-66a5-4b8f-b22a-309872d57691 | checkpoint | 3.2.2. - Rock Surface Preparation
3a7ffdb0-cd2e-5784-a691-0214e557ea4e | note | Description - Prepare all surfaces to be shotcreted prior to application of shotcrete
7006a971-4057-5276-ba74-618bd7ec0aba | note | Method/Description - Visual Inspection
0d46d02f-afd0-5150-9422-af5369e282e5 | note | Test frequency - Prior to spraying
1aea9e1c-33b0-5da9-b66c-0b6c26f2c5fd | note | Conformance Criteria - Surface clean and free of loose material, pre-wet surface immediately prior to spraying.
d8122b02-e221-5b33-b2ea-18f25c7a803a | note | ○ Any residual flowing or seeping water shall be controlled using channels, chases, pipes, or other approved means.
0ada6814-e092-5c05-a3a6-422d75dabeee | note | Constructor - H
36bfe690-c180-592d-a2d3-0499bffb6134 | note | CPS - W
9635359b-33be-5843-ba08-884ddc6cb66e | note | Verifying Records - Cut CheckSHeet
5003c3e6-f3d2-4bc0-8a29-62e552af035e | checkpoint | 3.2.3. - Shotcrete Surface Preparation
91fb0155-dadc-5514-af6a-c10901b1c590 | note | Description - Prepare all surfaces to be shotcreted prior to application of shotcrete
a86f9363-23a6-55cc-b3c1-92f11d4686f7 | note | Method/Description - Visual Inspection
d7b25572-0d74-5835-a6e4-8c9d57fb40a0 | note | Test frequency - Prior to spraying
857aba21-1226-5c43-a92d-7b17dca82a38 | note | Conformance Criteria - Surface clean and free of loose material, loose shotcrete rebound removed. Pre-wet surface immediately prior to spraying. Spalled, cracked, loose or contaminated shotcrete removed.
3e88535c-ef97-5681-a50f-a18a5e1592a6 | note | Constructor - H
0e7ad38b-f2e2-5b56-8fa0-855a1d0cfe20 | note | CPS - W
5a701b86-b357-5d5c-8ce0-954f50a93762 | note | Verifying Records - Cut CheckSHeet
60c19e31-1e58-4373-a4a7-24d4e072f585 | checkpoint | 3.2.4. - Temperature check
d0b607d3-e4bc-5b87-9abf-20c9b100e8a8 | note | Description - Check the temperature of the shotcrete is within acceptable range between 5°C and 35°C.
25112b89-578f-5daf-ad05-f3ec81bceff2 | note | ○ The ambient temperature shoule be more than or equal 5ᴼC.
128da12a-82d7-5cba-a63c-58cbe9da6e15 | note | Method/Description - thermometer
c96df600-cc00-5ef6-8b2d-55c0a6c6983a | note | Test frequency - Each mixer truck prior to discharging
38cb3a00-b2a5-5db5-b7e4-66abceb183b1 | note | Conformance Criteria - Between 5°C and 35°C
8e31f9bd-acda-5126-8303-907569a34f4d | note | Constructor - H
1d385ed0-3bfe-5485-b607-5fe99ae916ac | note | CPS - R
45d6ac1c-1864-5f07-82a1-205d4e978f6d | note | Verifying Records - Shotcrete Installation Record refer to Item 3.2
0308a42a-4d33-4539-a11c-aaf0f2189aa9 | checkpoint | 3.2.5. - Slump check
ef8323e5-73cb-5fc1-a802-990a60cb5d4a | note | Description - Slump to be within the alocated tolerance
2643eaef-7758-5054-8c34-b6c4a448f971 | note | Method/Description - slump test
557da2f7-bc33-5229-a42d-adc4f09d7f0c | note | Test frequency - Each delivery truck prior to discharging
c700c8db-37b5-58d4-a7d8-65feda72eca6 | note | Conformance Criteria - 220mm ± 20mm
dfac7482-1c76-5479-a69f-a0b6565bb451 | note | Constructor - H
17f80b4f-02f8-5b82-a63a-5a373108c71a | note | CPS - R
1c02a4c7-a5a1-5b12-b5db-f452e78ab4cc | note | Verifying Records - Shotcrete Record
8762a54e-25ec-45ad-8af6-04f9896c52e4 | checkpoint | 3.2.6. - Personnel Entry
549b2de9-c5a2-5ad0-9cd0-cff4f50cf158 | note | Description - Test prior to each personnel entry and/or face advance.
48968587-f7f4-59f9-9e03-fb8de7a33397 | note | ○ Test results must be verified once a month during construction.
1ccec117-f0a3-544c-8c18-60aa1d67c940 | note | Method/Description - Penetrometer test
f54f771e-56be-5bd8-9f26-c827f3aa3c6f | note | Test frequency - Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction.
e36625e0-d55c-52cf-9196-3311bd52e410 | note | Conformance Criteria - Min 1MPa for man entry (providing the shotcrete layer is 75mm thick, rockbolts have been installed and the rockbolt grout compressive strength is min 3MPa)
fd617403-bd03-5d98-9c1d-3a8174249165 | note | Constructor - H
fd29a3f7-5ffc-570a-b416-8ef5fbb5fc1b | note | CPS - W
6171eeea-07fd-5e35-a3e0-02dc77903ba2 | note | Verifying Records - Penetrometer test results refer to Item 3.3
5dc95a4f-a604-44d2-92af-c06ea49577e9 | checkpoint | 3.2.7. - Beam End Test (early age compressive strength)
02d99cd3-3108-5f4d-8dac-82142d550de5 | note | Description - Safe shotcrete strength before next advancement to max. advance length
d31dafb3-6521-50e7-ae08-e8fa872f86c4 | note | Method/Description - field test
faac1007-bb64-58c4-be4e-893df098d1c0 | note | Test frequency - Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction.
de79e842-a8ed-5316-8ce2-0fcd9a516fbd | note | Conformance Criteria - Min. 1.00 MPa at 3 Hours
f7650381-25b6-58a6-a374-b37cebcdc57e | note | ○ Min. 5.00 MPa at 6 Hours
e0667f8d-ac78-557e-b1d5-e16c3c8777c5 | note | ○ Min. 7.00 MPa at 12 Hours
45fa55a0-5dc6-59a0-ac69-43261a109189 | note | ○ Min. 12.00 MPa at 24-36 Hours
fe725a26-e5a7-5613-9291-27020c81dfa6 | note | Constructor - H
4f759522-1d7a-52c1-916e-5e170818d1b0 | note | CPS - W
4515c082-12a6-5b39-a554-a88d43cadbe2 | note | Verifying Records - Beam End Test Results refer to Item 3.3
5870f82f-8746-453c-ae8c-1f106ec59548 | checkpoint | 3.2.8. - compressive strength (cast sample)
b1971745-a440-5896-ac15-63a632b84f91 | note | Description - To prove compressive strength compliance requirement
ac7b5bca-2f72-5187-9b30-01dd4eee792f | note | Method/Description - certified lab test
23b79a6f-c505-5c77-9e57-34c42615288e | note | Test frequency - 1 test (I test shall include 4 cored specimen, 3 tested and 1 spare) for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
95b5507a-bcfc-598a-9da2-342fb690ff53 | note | Conformance Criteria - Min. 35 MPa at 28 days
df934790-e2cd-5a3c-8817-525eb7a35199 | note | Constructor - W
e9b9fe8a-641f-568c-8869-758ff79d6242 | note | CPS - R
cd7484a8-aacb-533b-b4aa-0c6664d535d3 | note | Verifying Records - IANZ lab test report
fb4c260b-f9e4-49c1-969f-0e3e31189d73 | checkpoint | 3.2.9. - compressive strength (cored sample)
09a689f5-ed8f-510c-b157-8711d9b94da0 | note | Description - To prove compressive strength compliance requirement
5e68fd8f-ccbd-55dc-bb33-c6b95c4f285b | note | Method/Description - certified lab test
6b5eabf1-d0ff-5cde-8f50-3235d80857c2 | note | Test frequency - 1 test for every 50m3 of sprayed shotcrete
ba6b961e-912c-5099-906e-bc8d44583a10 | note | Conformance Criteria - Min. 20 MPa at 7 days
2bf84f32-6726-52ef-ad47-e09cf520ba2a | note | ○ Min. 35 MPa at 28 days
1dd91ea8-c999-54d4-b6b5-eefe4591368b | note | ○ Min. 35 MPa at 90 days
3cd393c1-5d73-52c1-aba1-7307d2595acc | note | Constructor - W
3fc3292d-14e3-5ee6-bf17-419d4f8afbf7 | note | CPS - R
28108188-e42c-5ed0-8442-086f3dea541f | note | Verifying Records - IANZ lab test report
ade9dd5a-8ce7-4707-a23d-0ce63e749a65 | checkpoint | 3.2.10. - Residual Flexural Tensile Strength
fa96cc58-02f6-5585-967b-9c7b5ffc0fd5 | note | Description - To prove compliance with flexural strength requirements
5793c477-f325-501e-bead-bc07a4a89123 | note | Method/Description - certified lab test
710b3416-eeca-56f3-9dd6-99e9864d480a | note | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter
d14debd2-8358-53f7-8d3c-6745d7fb472c | note | Conformance Criteria - Min. FR,1 of 1.25MPa and FR,4 at 1MPa
a6f6a5c3-b015-5cfe-a382-98d0d8a53502 | note | Constructor - W
6b640b68-bf98-5244-94a4-9a15c9a4eeaf | note | CPS - R
4e0cf657-c36e-5de8-81ea-d2507a6e71c8 | note | Verifying Records - IANZ lab test report
35b47abf-78fc-4eca-ba46-967a44922f34 | checkpoint | 3.2.11. - Drying Shrinkage Testing
194a3fba-1bbd-58ad-a345-9a96e7f06b79 | note | Description - To prove compliance with shrinkage requirements
1fdcd920-ed5b-5b26-b747-ea9b2c8d0f8f | note | Method/Description - certified lab test
257012ef-cbcb-5460-979f-1216f35858fd | note | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
fab72172-091e-5df8-aa0b-dd6ca455fa35 | note | Conformance Criteria - Max 850 micro strain
f8e72f61-ba8b-5964-89a2-34b96f61f88d | note | Constructor - W
fd409d88-aa68-50e9-8de6-3f8b596725db | note | CPS - R
65ca088c-cf15-5775-ad6b-67948059a8df | note | Verifying Records - IANZ lab test report
6979ec79-0db8-45c8-b418-2083987948ff | checkpoint | 3.2.12. - Permeability testing
8d4c538d-b1bd-5f33-b070-ac2f7ba4c8e3 | note | Description - to prove compliance with permeability requirements
5dc277c2-a351-52e5-a3ea-56a3be27fef1 | note | Method/Description - certified lab test
1c2333bc-67f8-5ce0-921a-e68280178067 | note | Test frequency - 3 tests for the first 50m3 of shotcrete then 1 test every 1 month thereafter
f64c222a-2e27-5922-81d0-062aa8ca36c8 | note | Conformance Criteria - Maximum allowable penetration 25mm
1024a19e-bcc1-50c3-83cf-a260f25319c0 | note | Constructor - W
8d5f8bb9-87c8-595a-967f-f1b908102529 | note | CPS - R
4693816f-dd27-5e09-aaa7-ca4b0d2b73f1 | note | Verifying Records - IANZ lab test report
cf3d58b7-1e4a-4348-a36c-c18fad26d43a | checkpoint | 3.2.13. - Steel fibre content
4ee3a365-3cf9-5d6f-be49-c86ca6d9d957 | note | Description - To prove compliance with fibre content test requirement
9a355225-4c01-5f4f-b1bf-651a41d66003 | note | Method/Description - certified lab test
a630006b-7525-5fa8-bc74-ef4995133ad6 | note | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter
cd4b3ecb-bbad-5fd7-8faf-a247aadf4f93 | note | Conformance Criteria - Minimum 35kg/m3
973ac8fc-7a0d-5078-93db-b4c8535be5d6 | note | Constructor - H
0ab84ce5-f2e0-5ec4-ae2a-6625e8fb972c | note | CPS - R
4e21016a-7ab2-5baa-b468-dccb2284f862 | note | Verifying Records - IANZ lab test report
fa3b59ff-32c2-4503-842a-ac5a8fff163b | checkpoint | 3.2.14. - Relative density
70aca86c-048e-55eb-a371-8e9b621f4461 | note | Description - To prove compliance with the relative density requirement
a9248702-7890-56ef-84d1-cb4b40c7813b | note | Method/Description - certified lab test
d48fd688-0259-5951-b33c-12e2712e69fc | note | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
9b469aa2-ff24-5c57-a9c4-5c710ec99ca6 | note | Conformance Criteria - Minimum 98% of the density measured from base mix
a6bbd174-a33c-5e35-aa17-8397b8331c9f | note | Constructor - H
9f56813b-f536-5486-8293-373aba3ffaf9 | note | CPS - R
b8dc470b-ab8d-59cc-9df7-b091437ea31f | note | Verifying Records - IANZ lab test report
6b6ec979-fb96-45e1-8622-6508dcd857fc | checkpoint | 3.2.15. - Layer thickness, Tunnel Lining Intrados, C-Line
25c99a96-bb77-5ed4-9035-5b6f5dd5e306 | note | Description - Provide control means to verify the thickness of final shotcrete layer
b8e461f3-a8ca-516a-b527-6ff0bfd89aaa | note | Method/Description - Survey scans, deep pins
86f4e837-5803-570a-8790-988a6eafa240 | note | Test frequency - As-builts shall be taken of EACH layer of shotcrete
ff7fde7f-c642-5961-b3aa-936b83144722 | note | Conformance Criteria - Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8130 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8119
93f6ba61-8f9d-52ed-b28c-89d3fad5b497 | note | Constructor - H
53516d11-96d6-58a7-9acf-b5361598a1c8 | note | CPS - R
a084fb0a-b19d-50ca-ad9d-03a629971f77 | note | Verifying Records - As-built Report
c4aeb4f3-a2f2-4382-9fd5-cdd76a14f5c6 | checkpoint | 3.2.16. - Construction joints
5dc2d9bc-9c2e-591b-bf98-f5423d32e8e6 | note | Description - Construction joints in the shotcrete lining top heading/bench shall be inspected by the Designer’s Representative as required by the Drawings.
6aab6676-ea8d-5279-adc4-78f0b3b51047 | note | Method/Description - Visual Inspection
9fb149e9-6847-50e8-b526-c93adf0ab26e | note | Test frequency - Every Construction Joints
c0b71ae0-b776-5bdf-82e2-362d189558e5 | note | Conformance Criteria - Hold point released by CPS
69453327-b6c2-5d2c-bce6-4709f29261b6 | note | Constructor - H
bb74a312-8427-5b6d-abc8-e009dd79bdf0 | note | CPS - H
7dc9e0be-46eb-5204-8470-ce70934be712 | note | Verifying Records - Site Inspection Report, Shotcrete Checklist
f2a04767-5cea-44bf-9e4f-b01c5082cee4 | signoff | AUTHORITY HOLDPOINT
9d9cd4de-a108-46b8-857f-6d2260690ec7 | checkpoint | 3.2.17. - Curing
d2faa440-4389-5683-bd94-85b9e370e6a6 | note | Description - Curing to be carried out in accordance with the Specification
0ab2ccf7-81ec-58bb-94d1-17f326b18b26 | note | Test frequency - Each Spray
5e0e38a5-b09b-5fae-aa42-d2483a02fdaf | note | Constructor - H
826cd2f1-2293-557c-8174-ba2089bc1e97 | note | CPS - R
3b6eb9d9-93da-598a-a5e3-0943baea20a2 | note | Verifying Records - Shotcrete Checklist
e32184c3-6771-4c53-afbc-ec7444166b39 | checkpoint | 3.2.18. - Defects and Repair
05268b67-e612-5389-831c-82ec47ad3835 | note | Description - The final layer of shotcrete shall be inspected for any defects and repaired accordingly.
dc738454-ea31-5d81-a8bd-2fbd96528d2a | note | ○ At the completion of the lining, all core holes in the lining (resulting from testing or inspection) shall be backfilled with non-shrink mortar of an equivalent strength and fire resistance properties unless otherwise specified. The surface of the restored hole shall be similar to the surrounding surface in texture and colour.
0ba2d7b5-35dd-532f-98c0-54f78f2453e8 | note | Method/Description - Visual Inspection
a5dd448f-b5df-5ec1-847f-730305a518af | note | Test frequency - Every defect on Every advance
e5c76ae6-b06b-5d2a-8c89-18453a9e054b | note | Conformance Criteria - Crack <0.5mm ,Crack >0.5mm -Non corformance report
fd876417-29aa-5017-9c1e-e3aef16b2338 | note | Constructor - H
69eac2b5-4f10-5911-ad35-84d0b4a5012c | note | CPS - W
135cfe1b-f938-5ba6-9caf-fc5e83413b08 | note | Verifying Records - Post spray inspection record
166e5964-0c53-4b67-aeba-500b4a0b1302 | section | 3.3. Reinforcing mesh
bad082b5-4879-4311-b68c-b81e14817ff5 | checkpoint | 3.3.1. - Reinforcing mesh for primary lining
1dbdbdb3-f973-5c3f-b390-5a6467ac9e08 | note | Description - To prove position, cover and overlap are achieved
2c9b89a3-1418-5e78-b264-c6861efeb413 | note | Method/Description - Visual inspection and survey
7918df37-9ca1-5b50-a530-a088375ca567 | note | Test frequency - Every advance
fbde0c66-315c-50d8-b911-483f67f28ff9 | note | Conformance Criteria - Longitudinal and transverse overlap of 250mm (one mesh square plus 50mm)
f7b69ad6-f9c9-50c5-a747-4ce9dda9470b | note | ○ Min. cover 65mm at the extrados and 85mm at the intrados
5a1242f3-c50e-5894-8d67-832e2ee85ec9 | note | Constructor - H
b6949101-5f0f-50dc-848d-cde1f70aac44 | note | CPS - W
7027e27c-3288-537a-bada-b4a83364763f | note | Verifying Records - Check sheet
1f40dbfd-1789-4709-aed3-a276d6434e84 | section | 3.4. Rockbolts
2857ce25-0dc3-4cf0-aceb-e9795a668543 | checkpoint | 3.4.1. - Drilling
2e3b9be7-8c25-541c-a2f4-6dd5cfb982bd | note | Description - Bolts shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
e23294ec-3e59-5d81-98a4-2e66fcd92a33 | note | Method/Description - Survey
973cd2dc-fce4-5c04-b3eb-8906810cdd2a | note | Test frequency - Each bolt
20113c20-aac2-54c2-b1dc-8d52ed00f9be | note | Conformance Criteria - Rockbolts shall be installed perpendicular to the excavation face unless stated otherwise.
dc47c0d3-f649-5afd-9b51-e28e7df0035e | note | ○ Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular.
a077bbf9-ed94-5e37-8ed2-f0add3720dea | note | ○ Position Tolerence +150,-150mm
eabdef3a-a6d4-59f2-bd43-d73ddf0aeaa2 | note | ○ No overdrill tolerance
57c8c397-e87a-5de4-accf-3eaf3a531c21 | note | – The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
f9bada0a-85fe-50f0-8b42-14b34e5c2d64 | note | Constructor - H
79bcaa3b-7e14-5f6e-994e-f67685a86bc4 | note | CPS - W
b19a376e-5372-5a6e-b3bc-5228ab40e86b | note | Verifying Records - Drilling log
d8b7c5bc-3971-4d52-bb38-f1cb99c08be2 | checkpoint | 3.4.2. - Installation
e72e7d1c-f0d3-5bb2-9a4d-e31da948f0fb | note | Description - Record all information on installation (position, hole length and dianeterm length of the bolt…)
7f61d4d4-aa5c-5ab8-9e69-103e6fd981da | note | Method/Description - Review
5d5a7fcc-020a-582b-9647-b95026d9dcb0 | note | Test frequency - Each bolt
39541f7c-b8a9-5dba-bced-ad89045dec13 | note | Conformance Criteria - Rockbolts to be clean and free from rust or any other physical damage at the time of installation
02c50956-ba5a-5053-80df-424688fdb62d | note | ○ Type of bolts, diameter, length, location, spacing and orientation according to detailed design
7f3db31b-1e27-51df-ab35-5a90bd9a3ea2 | note | ○ The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
4001bb7c-4d4f-57c0-bff1-7401ea715d8c | note | Constructor - H
d96eec28-9807-5bc8-92ad-d77da269dd09 | note | CPS - W
fd1a9976-80eb-5f47-85c0-f09eb946b968 | note | Verifying Records - Drilling log
831c8e90-411f-4c16-9d64-1c689551a9d6 | checkpoint | 3.4.3. - Grouting mixing
560a8c79-9989-5e9a-9ca2-798e97806ac4 | note | Description - To ensure correct practice
2b9c6d68-b464-516d-8708-44d45e97c4f7 | note | Method/Description - Review
f294d5bc-9949-558f-924b-57ace36bae46 | note | Test frequency - Every batch prior to grouting
c7ecb0ef-df66-52e4-bd55-bea35807408a | note | Conformance Criteria - Target w/c ratio as per MAR
ace0de62-a0d7-5b47-89ee-43193a5bdf29 | note | Constructor - H
260fe3e0-ed6b-5c0e-984f-fea174d9293f | note | CPS - W
b2804ca3-08cb-5831-84ad-8fd65077b8da | note | Verifying Records - Grouting records
5fd690f3-b2eb-41f5-bed4-f5d2590851aa | checkpoint | 3.4.4. - Grout test
ccb4636a-91ec-5647-82b7-a0419ba1c921 | note | Description - Testing specimen to measure UCS
1fdb4b64-0953-5a2f-903c-9f8802a59196 | note | Method/Description - Compressive strength test
ad5fd519-d632-50cb-af66-01ed07f4a01b | note | Test frequency - Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
3562f703-4185-573d-b6d0-6fca6974f475 | note | Conformance Criteria - min 20MPa at 1 day
88ea524a-d3ec-57ef-8a7a-d4d44dbdd65d | note | min 40MPa at 28 days
bc22be38-ff58-5ffd-a1bd-00b10aa92a07 | note | The average compressive strength determined from any group of cubes shall exceed the specified characterisitc strength by:
7559328c-cc65-5307-8fa9-01a2cc02a92c | note | ○ 1MPa at 1 day
f1632ac8-f74b-56a5-a354-efcf2b2369fa | note | ○ 3MPa at 28 days
01ea6831-ba11-55f7-b783-b81bd276a478 | note | Constructor - H
79fa90fc-59a3-57b4-aa14-05b3a70177de | note | CPS - W
688b6830-1d3d-577d-80c1-bdd163f107c5 | note | Verifying Records - Test results
4d3808e6-3d4c-41ba-879d-db991d68c53a | checkpoint | 3.4.5. - Resin
415528ba-f0b6-5c1e-896e-ed73eeca1eef | note | Description - To ensure correct practice and full encapsulation
7d797715-92cd-51e4-af26-38b355a91413 | note | Method/Description - Review
172d76fd-1f1b-56b1-8553-21f2b93973c8 | note | Test frequency - Each bolt
88a49903-b7e2-5f1b-9c2c-182567bb752a | note | Conformance Criteria - Sufficient number of resin cartridges to be used with each rock reinforcement installation in accordance with the approved project specific procedure developed during the trials.
7bccc6aa-1552-5060-8f2b-adcd04d2f9e0 | note | ○ daily records of all grouting works to be kept
dc245bf8-e523-5605-ae34-3ef813db47bc | note | Constructor - H
13e96784-c946-5f50-8e72-72e6c7277706 | note | CPS - W
2d726126-ee10-5a4f-8f86-fc242d1a5092 | note | Verifying Records - Grouting records
f3b9def2-a9a9-42d9-aac6-9d6354d97a69 | checkpoint | 3.4.6. - Pull test
c1b0077a-c230-5c78-87ce-4adb691e08b7 | note | Description - Demonstrate that the installed rock reinforcements can provide at least the design working load capacity.
2ecdd7e1-ef71-59ac-bff1-bfc547c2ee1d | note | Method/Description - Test
ac38ba5a-195a-5a47-a322-86c0fe9d49c8 | note | Test frequency - 1. First three installations of both rock bolts and rock dowels in each ground type as present in production.
94c2e7a7-2326-5285-9b4d-ed51e93c5b4d | note | ○ 2. 5% of the next 100 installations of rock bolts and rock dowels, proportionately throughout the ground types presenting.
90acc4eb-f9e6-5be7-8dfa-72dfed3ed2ef | note | ○ 3. 2.5% of the remaining bolts and dowels proportionately throughout the ground types presenting
5af6429e-8a6a-5657-8b73-abff4ff3525f | note | ○ Note: 3 neighbouring installations of rock reinforcement surrounding a failed rock bolt or dowel test (and test frequency to revert back to 5% for the next 100 and 2.5% for the remaining installations)
b3f118d8-b609-5f2d-8abe-d0b447e11d97 | note | Conformance Criteria - The bolt or dowel is deemed acceptable if, during the cycle, the displacement of the bolt or dowel head relative to the measuring datum (after allowing for any temperature changes) does not exceed the criteria for 100% of the working load, as set out in Table 6.4 of the specification.
f70a1225-ac1d-52b9-a751-8f918ecb1113 | note | ○ Failure criteria: 2% Maximum Permissible Displacement or failure to maintain specified loads or ongoing creep of the rock bolt or rock dowel
8745415e-e137-5e90-b953-0cb0200ecc33 | note | Constructor - H
d248668b-a8f1-50c7-a4da-693f6806d949 | note | CPS - W
a0e448fa-b6c9-59f9-bdee-42cb9cf0b104 | note | Verifying Records - Testing records
d72161d1-fd99-4653-9629-6d7ca47a8787 | section | 3.5. Spile installation
5983bfed-a166-4056-b27a-26864d782d19 | checkpoint | 3.5.1. - Drilling
b86b26f1-84c4-5841-acfd-c13acb678881 | note | Description - Spiles shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
ad1830f6-47d8-5e2a-a0f5-a0cc9947f12e | note | Method/Description - Survey
b4ba9014-5c58-5604-92ff-152504fd77cf | note | Test frequency - Each spile
0966c50c-a6b3-5ea2-9d6e-b773243af295 | note | Conformance Criteria - Positional tolerance of portal spile bars not to exceed 25mm in any direction
1fd4af6e-2c69-58db-8c8e-6b4c824d6764 | note | ○ Setout angle shall be as per drawing. Max. angular tolerance not to exceed 1 in 60.
ef62770a-886f-5f84-9037-fb5f91f523d1 | note | Constructor - H
0940bc7a-c9cc-5ae2-b7d7-9ef5fd748cd0 | note | CPS - W
60674146-463e-5e99-b189-62ea1aa84279 | note | Verifying Records - Drilling record ,Survey Report
e5970d03-915a-4685-a29c-2ce8c51a30ef | checkpoint | 3.5.2. - Installation
e1ec67fe-67cb-536d-b1fb-d5964c2e7c9f | note | Description - Record information on installation.
9e44ecaa-1ea0-5590-b512-a19ab1014576 | note | Method/Description - Review
0767264b-f74e-5924-a481-07f4aadc3d6d | note | Test frequency - Each bolt
3761167d-25b7-51ea-bdef-55518ade8976 | note | Conformance Criteria - Spiles shall be free of dirt, detrimental rust or any other deleterious substance.
83b71860-db3d-5bcc-944f-55ef02f54b10 | note | ○ Type of spile, diameter, length, location, spacing and orientation according to detailed design.
9177fd3b-4668-5560-9f78-210f73da0cac | note | Constructor - H
b2f9a9b7-0ba8-5365-b4ce-b6bd3f866c0b | note | CPS - W
35ef32ef-3cad-5bb0-94ea-68725f8cff35 | note | Verifying Records - Rock Bolt Installation Record
b9a0a913-2cca-44d6-8998-492e9cefcdd1 | checkpoint | 3.5.3. - Grouting mixing
d96cf3cd-04bf-58d9-be8b-d59fb3725fa4 | note | Description - To ensure correct practice and w/c ratio check
6235cead-fddd-5f09-837d-be255b255ef3 | note | Method/Description - Review
a924bac0-a5fc-5f3b-8447-f036f865f6b4 | note | Test frequency - Every batch prior to grouting
28042afc-7548-596c-9c07-206687eac5a2 | note | Conformance Criteria - Target w/c ratio as per MAR
35c7b876-37bc-52d1-bf94-8c201e9d3df0 | note | Constructor - H
69641d47-d479-5146-93aa-e34233f717ae | note | CPS - W
d4277988-03f9-5411-aba5-f5b35923992b | note | Verifying Records - Rock Bolt Installation Record
0f8f4901-5c16-4507-935b-4bc81f4d31d0 | checkpoint | 3.5.4. - Grout test
43b2703d-6042-55cf-a8fa-f3f815d01b7c | note | Description - Testing specimen to measure UCS
58b25577-0239-5134-93dd-8972b8edd2a7 | note | Method/Description - Compressive strength test
90c759e9-c2cc-5013-86d1-f6467ffb8b63 | note | Test frequency - Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
b0b0bd96-51d1-5697-81a6-78297c178230 | note | Conformance Criteria - min 20MPa at 1 day
5f03a781-a565-5a1a-9269-f4098ca803fb | note | ○ min 40MPa at 28 days
ad89b907-5098-50c2-b691-4f31abdda16e | note | The average compressive strength determined from any group of cubes shall excess the specified characterisitc strength by:
9616bd41-5696-51ed-8833-c092aebb49d3 | note | ○ 1MPa at 1 day
070f8e47-8848-5bce-9700-5996a3a77d46 | note | ○ 3MPa at 28 days
fe16e955-9f68-5178-b161-32efe24bf1ef | note | Constructor - H
aaff1db2-fba5-513d-99d6-cba9f64ad9dd | note | CPS - W
7b2151c9-b987-55ee-9edc-0525ca96d2db | note | Verifying Records - IANZ lab test report
5f0e955f-f549-496e-82f4-3a0f9252db0c | section | 3.6. Face dowels
41ebc9a3-cf21-4c5d-b7d7-cdcfd8d7c3f2 | checkpoint | 3.6.1. - Drilling
f64e4c1f-62a9-597a-97d6-6156310d651f | note | Description - Dowels shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
c015f6fb-6551-566e-98e6-48f9ebafdcf9 | note | Method/Description - Survey
a151f2fb-b8cc-578c-a993-c4b995752d1e | note | Test frequency - Each dowel
9e283a0c-85dd-5591-bc73-427e2dee8dc0 | note | Conformance Criteria - Dowels shall be installed perpendicular to the excavation face unless stated otherwise.
65b8378c-1e74-5fcd-9a44-5ddf4ccb6329 | note | ○ Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular.
6ea9b42f-1bbf-581d-a782-066f6ff8b5c1 | note | ○ Position Tolerence +150,-150mm
c6bc019d-fbb8-596d-aa3d-5b906d5276b2 | note | ○ No overdrill tolerance
3485a38c-a863-53d3-b019-21a6a645d9fb | note | –The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
74451fa6-cc58-5660-a7a5-cbe06099621e | note | Constructor - H
6c4723c9-e3d0-5eb6-af23-fe353ffdd752 | note | CPS - W
536f71c6-6784-5fd3-becd-b874618a2976 | note | Verifying Records - Rock Bolt Installation Record/Check list /As built Survey
880df168-701f-4238-a145-f96157a83850 | checkpoint | 3.6.2. - Installation
e213a835-180a-560a-998c-405517feb4d6 | note | Description - Dowels shall be installed to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
1b394d0d-9c76-5da2-93df-6d28091a2d58 | note | Method/Description - Review
af72e69e-5192-5f24-bcd9-95e232324998 | note | Test frequency - Each dowel
8c97b79c-8585-57a9-8e93-cc69ed8e9670 | note | Conformance Criteria - dowels to be clean or any other physical damage at the time of installation
29f3afea-8108-5b86-b004-c93b764f4544 | note | ○ Type of bolts, diameter, length, location, spacing and orientation according to detailed design
e2fe24c8-bd16-5fd7-85f6-eca207ff3ca5 | note | ○ The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
82cede42-c029-5093-a334-bd26a48db27f | note | Constructor - H
d5b20130-0f19-595f-bd24-6460099988ea | note | CPS - W
ba8f37c5-3550-5359-8332-eab3a419f313 | note | Verifying Records - Rock Bolt Installation Record
3ae4c154-529c-4e8c-93f2-ffcfd84edad8 | checkpoint | 3.6.3. - Grouting (1)
a750bc28-7292-5499-8a9c-a3d83d9af40b | note | Description - To ensure correct practice and w/c ratio check
6bde90db-f6fd-5fa0-bccd-0cc916a41ce1 | note | Method/Description - Review
0ff93f97-b0a0-5212-8f5d-d83506b275e1 | note | Test frequency - Every batch prior to grouting
cd9eeb56-5f9b-574f-85ba-75d6ae504b77 | note | Conformance Criteria - Target w/c ratio as per MAR
071e4190-e9f8-5d51-a03f-d247044451ac | note | Constructor - H
2093bc22-3953-575a-9f07-a889f7ef822d | note | CPS - W
a1050c40-c028-5490-8ff6-558cd11b7bfe | note | Verifying Records - Rock Bolt Installation Record
1767b2f8-ce9c-4128-bc50-3adc4be36336 | checkpoint | 3.6.3. - Grouting (2)
cb92de8b-e882-52ec-98ad-07939f1d209a | note | Description - Testing specimen to measure UCS
d9f4ad14-4532-53c2-8713-9f4aea148020 | note | Method/Description - Compressive strength test
409e6310-5c0f-5552-9939-651b97c96d02 | note | Test frequency - Every batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
4e4a67b5-4fa8-58a6-9afe-488e51607ad7 | note | Conformance Criteria - min 20MPa at 1 day, and average to exceed specified strength by 1MPa
7de34afd-6dd3-5085-b340-99c64d98afdd | note | ○ min 40MPa at 28 days, and average to exceed specified strength
e6874c44-3209-5a7b-b70c-903c058c4537 | note | Constructor - H
d0cc40e3-5f63-5fe0-a6b8-958330e779f5 | note | CPS - W
cb607df8-d810-5984-b120-47add2335ceb | note | Verifying Records - IANZ lab test report
080043be-0f80-4b5b-999b-5376c30b9578 | section | 3.7. Probe holes
afde7e40-6f87-4776-87c2-be2020a8a7b0 | checkpoint | 3.7.1. - Drilling probe holes
27bfb4ef-ad66-5519-a2a0-3dd377b25ce0 | note | Description - Record information during drilling
fcb30bfa-34fe-51d6-b2b8-d950f7078ff3 | note | ○ Check the water inflow during and after drilling
c5ff959a-7556-5c3b-9528-9fa65069008c | note | Method/Description - Geological monitoring
1f81fbbb-ea6d-53bf-a300-847fb93eb95e | note | Test frequency - Maintain minimum one probe at 20 m ahead of the face at all times
77cadac8-d949-5fee-ad50-df11cbbd38c4 | note | Conformance Criteria - Hole diameter minimum 50 mm
50362068-c940-5df6-a5dc-7d61bc4aeec5 | note | ○ Not less than three probe holes shall be maintained a minimum of 6m ahead of the excavation face at all times and with at least 1 probe hole maintained a minimum 20m ahead of the excavation face at all times
097cc8ed-8fb9-53c0-ac10-d83ca8244264 | note | Constructor - H
a21c12be-9706-5eb5-b74d-ac301bf8e91e | note | CPS - W
42eb91c5-e1cd-5384-a400-1e8e0bc9757d | note | Verifying Records - Probe holes record ,Survey As built report
f3deea79-ff69-4e97-a4bc-7a5bf3472eab | section | 3.8. Monitoring
809468d3-f8ed-465e-881f-3c31f1a22b0f | checkpoint | 3.8.1. - Tunnel convergency (Extensometer)
1184e1a6-4d0f-5474-ac2e-3f87b02014fd | note | Description - Monitoring and reading records of the tunnel extensometer
03e76a92-5627-5dcc-b7ca-7598ceb6b3dd | note | Method/Description - Review
63bb1987-ea11-5aae-b856-07af0726ea9f | note | Test frequency - from excavation face
9deb5ae9-d6ff-529d-b86c-dff309985c18 | note | ○ >100m = Monthly
05870ca7-2300-5ed6-9465-08400727359b | note | ○ 40m-100m = Weekly
04124743-7360-5df9-a36d-62929d8dbe47 | note | ○ 15m - 40m = 2x weekly
4ac2d7a5-e96d-5af6-bc9d-35e20089ebd9 | note | ○ <15m = daily
b37250e7-c12a-57d5-89fe-49ca01bde399 | note | Conformance Criteria - Refer to drawings MMA-DES-TUN-E1-DRG-8180
837ec41f-35a4-5b92-912f-eedc1193170a | note | Constructor - H
783aa7ca-e854-5498-b55a-7dd539582c13 | note | CPS - R
7a21a699-184d-52e3-8b3a-35b17ccad752 | note | Verifying Records - Monitoring Report
c650add2-54ec-4890-a002-43e6e3425ac4 | checkpoint | 3.8.2. - In-Tunnel Optical Survey Convergence
f1448831-6609-5912-9eb3-c7bd2a21cca1 | note | Description - Monitoring and reading records on the tunnel optical survey targets
4c2f9af3-6dbe-569c-b725-06de9617cd47 | note | Method/Description - Review
e806bfe7-b638-5acd-8fd2-943119e749b2 | note | Test frequency - from excavation face
451f6d95-fd43-5b37-82f8-86b71500fca5 | note | ○ >100m = Monthly
f19fd8ec-1a7f-51c5-b8da-eb2371c1af06 | note | ○ 40m-100m = Weekly
73b24297-7beb-56e8-ace6-dfe5ec7c66dd | note | ○ 15m - 40m = 2x weekly
b83cc22f-d668-5f0b-9d30-7d8094d102ec | note | ○ <15m = daily
8bbc3f28-08aa-59a0-aa0e-77fb95bd3781 | note | Constructor - H
12447b67-0bc8-56e4-be13-4cd99747ce5f | note | CPS - R
a33f5c7c-d7f8-505a-b691-59ee771dd91c | note | Verifying Records - Monitoring Report
c4333506-3eca-4008-9add-637ccda63a54 | section | 3.9. Ground water control
4f1599d4-3670-4ea5-b3cd-328ba5120327 | checkpoint | 3.9.1 - Strip drain installations
8e0ce96f-b387-58c9-bc8b-2a06d5311a1e | note | Description - Record location and ensure correct installation
2a205f5d-0e8c-51bd-909c-2265e2571090 | note | Method/Description - Review
6cb87176-27c8-5e34-9dd6-ae072b5fec95 | note | Conformance Criteria - Location and quantity of the strip drains shall be as instructed on site by the Designer's representative
1b336ea6-4be8-5294-9e1b-7aa45aa02043 | note | Constructor - H
1d132881-09ba-588b-bc51-4d3d1fa74b75 | note | CPS - R
59716672-a7ef-5dd6-9fc7-e444dea663cf | note | Verifying Records - Excavation and shotcrete check sheet,Survey as built record
26245e76-d936-41a4-b43d-742dc0cd7c07 | checkpoint | 3.9.2 - Groundwater (rectification)
a23fcad6-9d7c-5289-bdbd-66cc7a4f627a | note | Description - Where the inflow into the tunnel exceeds the design criteria,appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative.
f0be4c48-8953-545b-bdcf-dc110e8e3778 | note | Method/Description - Visual Inspection
a7d1ee34-6534-5bae-bed3-b6816bb1c931 | note | Test frequency - Ongoing
caf73a78-5310-5eb6-a8c8-53288d3fe832 | note | Conformance Criteria - Shall not be exceed 3L/m of length/day averaged over a 100m length of tunnel. Where exceeded, the post-installation groundwater methodology is to be followed.
39a8d660-82af-562d-94e4-e8ca2a419251 | note | Constructor - H
2594f7a8-e465-5437-af12-ad317b49de96 | note | CPS - H
a8360be7-c6ff-5c3c-ac04-00edeb551214 | note | Verifying Records - Installation Checksheet
a8ec8024-a9e3-48c1-a429-4f7a2cb32dd5 | signoff | AUTHORITY HOLDPOINT
215af2f8-8280-4501-801e-5869ab0b03af | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
4f97a1c8-6ccc-496f-9cd6-3b6534f88522 | checkpoint | ITP Close-Out by
d25fc0c7-7e79-5f09-869e-9b2c43b1a71b | note | Site Engineer/Project Engineer
7cf6bb0c-28b4-53df-af63-3f1c8bb84274 | note | Zone Manager Approval
304baf03-6f26-53cc-a100-79842cc3732a | note | Construction Manager Approval
2e7dcfa9-7818-5ace-aba4-adfeee5dd859 | note | Quality Manager Approval
d96dc3f2-36a6-5abb-818f-bb37851cc8b2 | date | Date:
853ad45a-e689-46f2-8b60-4b8f5211ee44 | signoff | SIGNATURE
c4c87e6d-7ded-4b0d-b99e-3db45c62476b | checklist | ITP - Tunnel Material Compliance & Approvals | itp | ITP - Tunnel Material Compliance & Approvals
42977315-e6e6-43b5-b3dd-37026f813bb5 | section | 2.1. Shotcrete
758c7e2f-b71a-4929-81e1-5048133d7487 | checkpoint | 2.1.1. - Shotcrete base mix design
0ee51089-59e5-5df4-aedc-e4fb5633e095 | note | Description - Compliance with Technical Specification - C0651 - Tunnel Shotcrete Clause 4
8c013b68-1bc4-55ce-9320-d9ce4293a257 | note | Method/Description - Material Review
e4cdeca6-ec66-55ca-b3d9-e0fb907ede68 | note | Test frequency - Prior to the commencement of the excavation work
3a25a030-7c8e-5d11-b32c-20c04016f1f0 | note | Conformance Criteria - as per Technical Specification - C0651 - Tunnel Shotcrete Clause 4
5a2228df-0fb2-50bd-8f5e-9100ccff1f5c | note | Constructor - H
70e13d31-816a-5243-aba1-b42caa79c3f0 | note | CPS - H
7f8c1d11-9a99-5706-979c-b1b369bf3939 | note | Verifying Records - Material Approval Record
76cf7835-0cf7-4372-ab34-55e063fb2b98 | signoff | AUTHORITY HOLDPOINT
8fbf1d32-4456-4ebb-a3a5-b3beba2a23b9 | checkpoint | 2.1.2. - Shotcrete Accelerator
83d86ba2-6ecb-52d3-b3be-60fcddaedb57 | note | Description - Type and dosage of shotcrete accelerator shall conform to the requirements of the Specification
d3e422f3-7b11-55dc-837a-8a56145e71bf | note | Method/Description - Material Review
0e3c777a-9d3e-557d-8d34-02bfba8c1757 | note | Test frequency - Prior to the commencement of the excavation work
641b7031-f17a-5ac8-ad10-61e379800025 | note | Conformance Criteria - Material Approval Record
fe7407ac-91f5-5835-86d2-7f0dee9ed8c4 | note | Constructor - H
696127d3-e9e5-5226-9387-a7f5e0066076 | note | CPS - H
c332e1bf-215c-5391-89ba-64387cf58d9c | note | Verifying Records - Material Approval Record
d83c98e4-f96f-46ae-b220-91f4f0e86178 | signoff | AUTHORITY HOLDPOINT
2c1d60ba-2731-46d8-89ae-ae96dcae7783 | checkpoint | 2.1.3. - Nozzelman Certification
c83fcafb-c560-56de-9a17-445d6ef5e90a | note | Description - Nozzelman shall hold a verification of competence (VOC) issued by the constructor
3f382e94-6e88-5ff8-9779-78196462d6d5 | note | Method/Description - Document Review
52ac4df4-2af5-586b-b648-4dc3b07b30fc | note | Test frequency - Prior to trial
8464be43-5fc5-5662-8367-b1efcd31c43c | note | Conformance Criteria - Ensure only personnel hodling VOC are operating the shotcrete robot on site.
24c91302-dfec-5e2a-8377-80de56525f65 | note | Constructor - H
2d71f73a-c4e4-527b-9b49-eaecd8154bc2 | note | CPS - R
0a434283-1cf7-52ca-8a88-3a71ad20b102 | note | Verifying Records - Nozzelman Certificate/ VOC
6bde3b2c-718a-4b4c-a77a-13401d7c85db | section | 2.2. Reinforcing Mesh
e24fb5e6-213c-4509-9065-c50c8367fde2 | checkpoint | 2.2.1. - Reinforcing Mesh
2928c936-5104-5840-a5a4-6c3b6c4d465e | note | Description - SE92 GR 500E mesh
91964662-12d2-5093-9cce-adda4278d7c7 | note | Method/Description - Material Review
7d8e2fbf-8bd8-567e-a193-8fc4dbf2a6e6 | note | Test frequency - Prior to the commencement of the excavation work
4e2d0edf-2f39-51bd-8e23-55df22140cfb | note | Conformance Criteria - Material Approval Record
a6b41d56-faf0-5de5-9fa5-36639501cd12 | note | Constructor - H
2346faff-d5d0-5ba0-8b57-54c07707ecf4 | note | CPS - H
3d8c3cbb-dc76-524f-a443-dbe66a1b08af | note | Verifying Records - Material Approval Record
39a9594a-56ac-47b9-90f0-7a76070b6278 | signoff | AUTHORITY HOLDPOINT
fa412562-1a3c-4801-87df-82bfb75c7366 | section | 2.3. Rockbolts/Dowels Bar
294572d4-a8d6-4d41-a013-f73bc7138e30 | checkpoint | 2.3.1. - Tunnel rockbolts and plates
b5a09c47-f75f-5896-bb0e-0d4c8cc4086c | note | Description - rockbolts material and corrosion protection
db41ced8-fc6d-5d8d-b0da-ceb500f17aaa | note | Method/Description - Material Review
04e05e05-13f9-5f24-902f-ac0b3b2f4c63 | note | Test frequency - Prior to the commencement of the excavation work
c5873350-1a4d-5a38-8c85-b47072ee1011 | note | Conformance Criteria - Grade 500N, galvanised HDG to AS/NZS 4680 Material Approval Record including mill certificate
9ee63db9-c857-5aa6-97b9-be5bec8d45c9 | note | Constructor - H
ba8108d7-2872-5e0d-84ff-c5cb56057465 | note | CPS - H
6bce580b-2bfe-574b-9816-cca15247ebb2 | note | Verifying Records - Material Approval Record
a4666734-b196-4f41-a0eb-81f1e0aba900 | signoff | AUTHORITY HOLDPOINT
bc9531f0-fdb5-46c8-97a9-3b4da843a5fd | checkpoint | 2.3.2. - Face Dowels
e5b092fa-4e7a-5c85-bb95-f4fd004eea99 | note | Description - glass fibre reinforced face dowels material
619a1708-6afb-50a5-ad9e-eaccf2d36220 | note | Method/Description - Material Review
17f97c14-091b-594f-b384-e8a1c714d79f | note | Test frequency - Prior to the commencement of the excavation work
8e471dc0-dd9b-58bc-be80-18ebb90e8ba6 | note | Conformance Criteria - Material Approval Record
55c2eadf-b10b-5215-9856-ec338504b3cf | note | Constructor - H
baff018b-4a23-5a5a-9b7a-1afd49799234 | note | CPS - H
3ac7b908-52bb-5a77-b674-537a3fce4c76 | note | Verifying Records - Material Approval Record
ab8c9640-e118-4a6b-a5dd-239b6939141a | signoff | AUTHORITY HOLDPOINT
27cb2f15-df82-4f0a-af54-64884a342280 | checkpoint | 2.3.3. - Delivery acceptance
21ad53e5-9f62-5a8c-aa51-ca427953f777 | note | Description - Inspect fabricated rock bolts and rock dowels prior to installation
9b29d0a1-e054-553d-bad0-e02b8bfa0241 | note | Method/Description - Visual Inspection
ee6e7ecb-bff4-5e60-8419-9ab1b2524904 | note | Test frequency - upon delivery
dfc39e0b-2805-57ee-9d03-dde81a80430e | note | Conformance Criteria - N/A
bc7e16f9-9500-5973-a7e0-a5de9b6a866c | note | Constructor - H
bfd957c9-63e0-5249-9097-07e0ab9cb5f6 | note | CPS - W
52859502-d872-503d-bb87-2cc42a45f677 | note | Verifying Records - Delivery Docket/Mil Test cert
693a6aa3-a511-47af-bee7-c20075dc2c13 | section | 2.4. Spile bars
a87be114-133b-4ba4-81cf-3e6c751ed95b | checkpoint | 2.4.1. - Spile bars
02c94d36-26ee-5663-83e8-9383f4f71af4 | note | Description - spile bar material
d86a518c-a2cb-590a-90b9-63d457ec9653 | note | Method/Description - Material Review
2d195474-1aa7-55dd-9d8e-ab651f112c2c | note | Test frequency - Prior to the commencement of the excavation work
2645a38b-9568-5b31-85f4-eae918ced494 | note | Conformance Criteria - Material Approval Record
ff9e5890-3172-500b-b1d4-7301633bdb97 | note | Constructor - H
37882e1d-231f-5803-abe2-b225a333ba48 | note | CPS - H
7cd5e9e5-d6e5-5781-ad56-dc8ba9aec098 | note | Verifying Records - Material Approval Record
fdbe5a14-8661-4245-be43-9c101f19d5db | signoff | AUTHORITY HOLDPOINT
addc2478-d049-4147-88ff-65b5b63b2a9d | checkpoint | 2.4.2. - Delivery acceptance
ed3dee88-a27e-5058-b3e1-097562703459 | note | Description - Visual confirmation of delivered items
b93eb539-259f-5e12-8f27-dd9eb5bfdd32 | note | Method/Description - Visual Inspection
fe7d3572-f115-5d97-8bbd-15e168304a7e | note | Test frequency - Upon delivery
daa6958c-fbdd-54e6-b9c3-fd6778c9f30c | note | Conformance Criteria - N/A
52fcb76f-a327-51bf-89b1-c41a90fb0135 | note | Constructor - H
a0c944e3-b6e9-5c15-be57-c640280ced1f | note | CPS - R
44b73ca2-3c38-5e45-a302-75af2e9fcc3f | note | Verifying Records - Delivery Docket/Mil Test cert
36bae66d-a167-4449-b70a-188c2b149231 | section | 2.5. Cement grout for rock bolts, dowels, spiles
49746313-3272-4737-b9d5-a61250d2a5dd | checkpoint | 2.5.1. - cement grout
b1815ffe-7af4-5f6f-90ad-5a0400b3285b | note | Description - grout material and properties
ab8877d9-39ec-5988-a9e2-f50365b31472 | note | Method/Description - Material Review
f8c524ca-e5a8-54a0-b9ff-6016612023a6 | note | Test frequency - Prior to the commencement of the excavation work
3f5c3f48-84e6-56ea-ba15-3c785ca2894a | note | Conformance Criteria - Material Approval Record
6d2ac037-e6c9-5be2-ac1b-3afbf4d10ceb | note | Constructor - H
05b61db4-e3f6-54f6-9582-b1dec3366f06 | note | CPS - H
4247cc61-28b7-5397-b10c-21512f79b977 | note | Verifying Records - Material Approval Record
82c2121d-e04b-4bdc-b043-a97f66a24fb0 | signoff | AUTHORITY HOLDPOINT
ac965c7e-cac5-4c5f-af06-d1e75280a762 | checkpoint | 2.5.2. - Delivery acceptance
3ff7e694-c631-52a9-8f38-165d209d7af7 | note | Description - Visual confirmation of delivered items
045daf3a-d8cb-5660-a0c7-4e0c09f60892 | note | Method/Description - Visual Inspection
38894234-298f-5ea0-9d78-bada24f47377 | note | Test frequency - Upon delivery
7c86bcb1-0e0b-5791-8c07-256f1108aa83 | note | Constructor - H
09227c49-7565-5296-972e-63dbcc184ae8 | note | CPS - R
e4b4d5cd-58bc-5194-8682-cad273559d6d | note | Verifying Records - Delivery Docket
abd021e1-066c-4a5c-aff7-f91dc056f92f | section | 2.6. Resin
bc5f8264-8912-465a-b8db-ec46446fba0a | checkpoint | 2.6.1. - resin grout
c0010370-ff07-55c6-8f77-1505ddea2d51 | note | Description - grout material and properties
dcdff1d1-9a32-5e3a-b86b-a44cefa1adfe | note | Method/Description - Material Review
2bbc7474-c316-59d7-9dfe-f95b2564f64f | note | Test frequency - Prior to the commencement of the excavation work
47078289-cecd-5894-a42c-149c9c898c92 | note | Conformance Criteria - Material Approval Record
df684973-4bcc-580c-a3ea-9b77ce5f282a | note | Constructor - H
4536db47-87cd-599f-a225-81a019faf330 | note | CPS - H
abe1bdeb-9dcf-5d8c-bb9c-4465d58cc345 | note | Verifying Records - Material Approval Record
454d7611-d45b-4532-9e72-74a3749b41ff | signoff | AUTHORITY HOLDPOINT
78fd0941-71f7-4d67-8b1c-8854b81ec4c6 | checkpoint | 2.6.2. - Delivery acceptance
1a089bc2-9cbb-5da5-a027-3a6bdd985007 | note | Description - Visual confirmation of delivered items
bf7b8db8-cd7d-5f11-a2a4-62e096ca6459 | note | Method/Description - Visual Inspection
889b6b84-ce25-5a14-9f60-d0a1331d9795 | note | Test frequency - Upon delivery
222e5049-8899-5c21-bdb4-44a2f00fa1ac | note | Conformance Criteria - As per accepted MAR
0c93a2f1-1a7b-5fd5-8866-45aa5754b1aa | note | Constructor - H
8b899ebd-9f7e-578e-9c43-b19b740fb89e | note | CPS - W
f7123c6c-bca3-5af1-9663-eaf6ab83733a | note | Verifying Records - Delivery Docket
25b35576-dccc-4266-87b3-76c440c3857c | section | 2.7. Monitoring Instruments
0983b495-e3e9-4829-9f25-4ec6e5584117 | checkpoint | 2.7.1. - Monitoring instrumets
47fd2cc6-fc71-5e8d-9136-e440aad2b32b | note | Description - Compliance with Technical Specification C0660 - Tunnel Convergence Monitoring
57d0e381-b7f4-5206-a0ba-40f524a2f6ff | note | Method/Description - Review
4f563b8d-937d-5c0f-b807-84b7ef2279be | note | Test frequency - Prior to installation
8ab732f1-cb19-5d0b-bef1-78b8c31d0fe8 | note | Conformance Criteria - Designer’s Representative Approval
c8e4a4b5-ae97-521f-b10f-beabaeca3749 | note | Constructor - H
38df1f14-8f02-55af-91c4-03d91643b0ee | note | CPS - H
5e5c83d2-a3d1-5965-be46-3a1921a9f46a | note | Verifying Records - Material Approval Record
94850752-caee-404c-82ba-2acd086f677f | signoff | AUTHORITY HOLDPOINT
bffbf701-25cd-4c38-aea8-7e14dfdfa289 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
897536c6-74c9-4e7a-99c3-f6815e1a8e20 | checkpoint | ITP Close-Out by
1cb543f3-48dd-589c-9e3d-64bf426d915d | note | Site Engineer/Project Engineer
0b452d01-ffd5-553c-b039-e0523361323f | note | Zone Manager Approval
4374f389-a293-59cf-b425-69f32fa58ecb | note | Construction Manager Approval
675146b5-2e19-52eb-a236-c1551fab01a3 | note | Quality Manager Approval
759e164e-a571-5cff-a628-9a4b0e5cbf5f | date | Date:
193cdc6f-d088-4c43-9ca6-8c3f14047656 | signoff | SIGNATURE
15250872-4c5d-46b7-afe7-783f232fcfba | checklist | ITP - Tunnel Post Construction | itp | ITP - Tunnel Post Construction
a5442c93-3947-4422-92c9-c9958615a0cb | section | 4.0 Post construction
9ac5d02e-765d-48b3-a31c-facec84a2988 | checkpoint | 4.1. - Red Line Mark Up Drawings
2780714c-d955-5921-804b-29035642d29f | note | Description - As-built drawings to capture any deviation from the IFC drawings.
9775fc9d-7de8-5b3d-ae5e-687b8c10a2ef | note | Method/Description - Submit
f5531757-7958-5902-bce9-fccfefb0bcdf | note | Test frequency - At Completion
7b0815e5-adbe-5237-a3f7-2606fde56e8f | note | Constructor - H
69bb3d76-1fae-5313-ae31-2fc91eb58c35 | note | CPS - R
537d63a1-2395-5464-8011-f49c8630552f | note | Verifying Records - Red Line Mark Up Drawings
ce284ee2-2f3d-4ac1-a698-554e6d6f756c | checkpoint | 4.2. - As-built Drawings
f3b93f32-5bad-5f8b-a852-cc2d0d35b884 | note | Description - As-built drawings to capture any deviation from the IFC drawings.
7a486206-2472-5702-b803-07f998bd6431 | note | Method/Description - Submit
fcbbd6f2-a7b7-5b1f-b638-8220a083a224 | note | Test frequency - At Completion
d50f9083-1416-561f-9672-0cff4059bc3d | note | Constructor - H
30dd740e-de52-5758-951a-02b005087fe1 | note | CPS - R
376f8b13-fdd0-5152-a940-cdd1a6633450 | note | Verifying Records - As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements
221ae9ab-1998-42da-b629-7f11faf8ad83 | checkpoint | 4.3. - Tunnel Operation and maintenance report
65b4b53f-84c2-5dad-bcd9-ca62e0bf7b7a | note | Description - Tunnel Operation and maintenance report to detail the maintenance frequency and maintenance procedures.
98a92476-81a3-5709-9b7c-43c99d3622ee | note | Method/Description - Submit
5984283e-85be-5bb4-ab5c-c012a141717f | note | Test frequency - At Completion
b1cbb43d-ea49-597a-a0ee-b9852ba30edd | note | Constructor - H
957d0f28-cf4b-590f-9970-c846b556fd4c | note | CPS - R
37ce19b7-7c4f-5e8a-b281-2c3ca5fe8ca0 | note | IOM - R
a45f118d-7dcb-5378-9851-3190b6d0bdbe | note | Verifying Records - Tunnel operation and maintenance report
d6d31fb7-a9d8-4ad4-bb1c-31e87de2a18d | checkpoint | 4.4 - Final Handover Package
11ef914b-d625-5960-830a-fe8728e04446 | note | Description - Collation of all QA, as-built drawings,as-built records, installation records, PTT, testing and monitoring documentation. Provision of asset management operation and maintenance report to NZTA, including Producer Statements.
b4dcd80a-d12a-5b4e-80b9-f3a34d43ec0a | note | Method/Description - Submit
2309e79c-12cb-5f7e-9b10-c55bae563b19 | note | Test frequency - At Completion
74d54729-1f91-58f8-8648-cb38148f2457 | note | Constructor - H
1fac3fd8-017b-5caa-b441-5b3a0a4adb50 | note | CPS - R
a25a3ada-2890-596a-82ca-7a6e1af568ee | note | IOM - R
74f2a164-6053-54e0-9554-fb975b63369d | note | Verifying Records - As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements
a66b95fc-d140-4fa5-b5c9-dedb6bfd41ed | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
f507ece0-d919-498d-9af8-32dd70ec5c96 | checkpoint | ITP Close-Out by
17923c3e-bb2d-51ca-9654-014f2c295b39 | note | Site Engineer/Project Engineer
e94f2114-79f3-5185-a956-30262f20a281 | note | Zone Manager Approval
b9018e41-a57f-5d0b-a59a-6f81ce59a8cb | note | Construction Manager Approval
a80f2fc6-60bf-53e4-a6b5-f4ed9e2ee7ff | note | Quality Manager Approval
a0a1bfa8-daab-5f8c-a588-b377b5b4f8c7 | date | Date:
ea9d52f2-1ab3-423e-beec-c76578683c9d | signoff | SIGNATURE
48d2f298-c653-4899-99a9-6caf29d2f9df | checklist | ITP - Tunnel Pre Construction | itp | ITP - Tunnel Pre Construction
1b3e1262-9722-4002-9121-fcc006abcf4d | section | 1. Pre construction
20288397-e418-4a30-96a7-16f37937a173 | checkpoint | 1.1 - CWP for tunnel excavation & support work
461aeccd-1150-52e4-9824-cefb0278a09a | note | Description - Approved CWP
597a52a4-36cd-5e7b-b1a2-149e67498de7 | note | Method/Description - Submission
814ba2de-15ae-5ef7-bb80-8af508a10e3c | note | Test frequency - Once prior to works commencing
3f596944-dac4-5aa2-aa9a-1ce3edde753e | note | Conformance Criteria - Approval CWP has been transmitted via InEight
99ce0126-15af-574f-894d-db633c2ffe23 | note | Constructor - H
82dc77ce-c14a-5ee0-9da8-ba869b9630fe | note | CPS - H
c78dd42e-c188-5f40-947e-ff9ba022fdcc | note | Verifying Records - Approved CWP
aeb6338b-a230-49e0-9cfc-cd3918cf2192 | signoff | AUTHORITY HOLDPOINT
41982e9d-bee3-4213-aefa-0ca8d3de01bf | checkpoint | 1.2 - ITP for tunnel excavation & support work
f8ecbb07-912d-5207-a6b4-e46f43ca86f6 | note | Description - Approved ITP
9fab528b-822c-545d-932c-79273255fda7 | note | Method/Description - Submission
3212c43a-6ea4-5c6b-9e4e-e1c4e2a85946 | note | Test frequency - Once prior to works commencing
431c93bf-2f53-5089-bf75-80752c9dbe14 | note | Conformance Criteria - Approval ITP has been transmitted via InEight
efd00e47-8feb-5600-9558-9abae4ea2e1a | note | Constructor - H
d46bd974-8f6d-5a68-8e27-ff0ee99faa16 | note | CPS - H
8dbaf7e0-8423-54b4-9505-cb0bce16427c | note | Verifying Records - Approved ITP
4115d8f0-2762-4a4d-a2e1-474e9aaac02d | signoff | AUTHORITY HOLDPOINT
98fc5c0c-bb3d-4d44-8ac4-e7423390a042 | checkpoint | 1.3 - IFC Drawings
21eb5159-84b8-5d5e-b976-e78041728d97 | note | Description - Approved IFC Drawings
1b5ba414-4acc-5823-9beb-90012f806d7e | note | Method/Description - Submission
be77b63b-cd89-5994-b01c-6b0dbcd6037d | note | Test frequency - Once prior to works commencing
8c07f531-7b87-5c04-9818-1ea2654616a2 | note | Conformance Criteria - Ensure all drawings are approved and transmitted Via InEight with IFC status
54ff4d6a-95cf-5359-8b03-a8c7f8db31c4 | note | Constructor - H
da2555b4-affd-5021-a08f-749a538b8c4d | note | CPS - H
829ed969-76e9-5f3d-848c-e09cf9f4712e | note | Verifying Records - IFC Drawings transmitted into InEight with IFC status
c937353e-c6e9-41eb-8c33-82981e3649d2 | signoff | AUTHORITY HOLDPOINT
0754b9cb-b843-4742-bc7a-aeaae3a505e1 | checkpoint | 1.4 - IFC Specification
525cfa99-8107-5d07-825e-0fe139157f72 | note | Description - Approved IFC Specification
8b443ee6-0e87-5e5f-a2ce-c40cbef2fcb6 | note | Method/Description - Submission
cd7574fc-f345-5b47-a873-ce9223861220 | note | Test frequency - Once prior to works commencing
acddd444-9b14-58aa-9d1e-d23fa922e82f | note | Conformance Criteria - Ensure all relevant Specifications have been approved and transmitted Via InEight with IFC status
dd07429b-50df-5c36-b25d-b3cb1cef696f | note | Constructor - H
067afc96-f407-5d96-8e3f-ea5300e88096 | note | CPS - H
b3defbf3-7dac-59ac-92bd-e56d84ebe9f3 | note | Verifying Records - IFC Specification transmitted into InEight with IFC status
0e15f213-16f7-49ac-8da7-34c040d72ac3 | signoff | AUTHORITY HOLDPOINT
a78832ee-f22f-4eb1-ae40-0de1f0c09ec3 | checkpoint | 1.5 - Permit to tunnel/excavate template
5b8696e7-1f9c-50f7-99e2-4c058955a8ea | note | Description - No work shall commence until a valid Permit to Tunnel has been signed off for the current section of excavation
1daec1c6-8b32-57ef-a6be-f2f1d3a96f9f | note | Method/Description - Submission
06bede12-71da-55b8-8056-a0f5b7ced66c | note | Test frequency - Prior to the commencement of the excavation work
2063bd5a-ee30-5875-b0ff-5836d710524b | note | Conformance Criteria - Valid permit to tunnel
42ba9fd4-1cdb-5522-b980-d10566982d07 | note | Constructor - H
22ffeafd-4dce-5733-b7d5-70438a2e7a0c | note | CPS - H
a8d6fbfb-b764-556e-9773-240d6e26bcde | note | Verifying Records - Permit to tunnel signed off by all nominated personnel
0f21be05-0172-4467-beba-1a3d5ee2d901 | signoff | AUTHORITY HOLDPOINT
07464445-f218-4be1-b0ac-1062300e039e | checkpoint | 1.6 - The groundwater control system Methodology
aa2a70e7-b1a1-5537-b1d9-7ec442d4fb48 | note | Description - The Constructor shall propose a method for a preconstruction trial of the groundwater control system and submit it to the Designer’s Representative for review.
aac07c8d-b2a6-529a-a606-b4e5fe0503d2 | note | Method/Description - Submission
b5ebcd94-317e-5d5b-9b6a-2147e86d2af9 | note | Test frequency - Prior to the commencement of the excavation work
b8fe062b-2c25-5b06-92a6-48aba8ecb621 | note | Conformance Criteria - Designer’s Representative Approval
52dc133f-0509-5ab5-ae6b-48caf71912b1 | note | Constructor - H
b4b8225e-cb57-525c-8eca-fca496748596 | note | CPS - H
adf87985-7671-51dd-b7e6-27df28c31b39 | note | Verifying Records - Groundwater control system methodology
6b49a55e-1d0d-41ae-b0c8-8fc21331f9dc | signoff | AUTHORITY HOLDPOINT
f7e27097-2c4c-4909-beba-3b2359993de9 | checkpoint | 1.7 - Post-installation Groundwater Control Methodology
a376c6ea-a5c4-54e3-9b21-32b0f53ecff1 | note | Description - Where the inflow into the tunnel exceeds 3L/m of length/day averaged over a 100m length of tunnel, appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative.
c22bd3ba-3601-5c07-98d2-e43033e0f037 | note | Method/Description - Submission
b9689a10-9646-5fba-9374-a95813048ac3 | note | Test frequency - Prior to the commencement of the remedial work
8c1caae4-57e8-59bc-a4a9-b94e64c01015 | note | Conformance Criteria - Designer’s Representative Approval
cccea32c-1971-54c1-87d5-ca4149072d6d | note | Constructor - H
6dcd57fc-4a2a-5b54-a2fb-206f58532d96 | note | CPS - H
9f57ce28-91bd-545c-827f-929eedd287c5 | note | Verifying Records - Post-installation groundwater control system methodology
27206447-2667-4216-941c-e3dd5ec1efe5 | signoff | AUTHORITY HOLDPOINT
3dffa3f4-ed12-487b-bad2-6d7411453ffc | checkpoint | 1.8 - The groundwater control system Trial
0ce7a56f-de4a-5726-973b-ff0c42007cd1 | note | Description - A preconstruction trial shall be carried out by the Constructor to demonstrate the effectiveness of the connections of strip drains from the top heading to the bench, unless using approved manufacturer's recommended connections installed to the manufacturer's specification.
10e4f846-6948-5052-9da8-9f9735ae2ce7 | note | Method/Description - Trial
9f327206-a1d4-536f-9bab-7b2566456cae | note | Test frequency - Prior to the commencement of the excavation work
98595162-a01f-5f4b-bce1-8fbe3bd7c841 | note | Conformance Criteria - Designer’s Representative Witness
54d331f0-00a9-5a31-b5b5-0c6adc62a037 | note | Constructor - H
9a380d60-f418-5f55-8c2e-35ead29eed2a | note | CPS - W
c5a79f40-b486-5d63-889f-f2e035cf06f6 | note | Verifying Records - Groundwater control system Trial Results
b3eafc48-774f-468a-bb57-fb23e4ec58f4 | checkpoint | 1.9 - Cement Grout Encapsulation Test
e3a8439f-f02a-59a2-91b8-6e6bbf049dd0 | note | Description - A pre-construction trial shall be carried out by the constructure to demonstrate that the proposed grout used is able to fully encapsulate the bolt using the proposed installation method
82924bb0-1f50-5f75-9dea-cea8c685bf9e | note | Method/Description - Trial
5c8606a5-7171-5112-b5ce-30a1cf4d31e0 | note | Test frequency - Prior to the commencement of the excavation work
d2216a50-fdb4-539c-b714-f13fb2acc2b8 | note | Conformance Criteria - Designer’s Representative Witness
aaa9e610-1fe9-5c95-9484-5fde94033c3d | note | Constructor - H
4173ad38-4d4f-5162-831c-e085099f07df | note | CPS - W
e7690170-2dd8-533f-a06d-c8d90f7e24e1 | note | Verifying Records - The rock reinforcement Trial Results
f7f219cf-d1ac-49ae-a3a1-7f4aac1ff834 | checkpoint | 1.10 - Investigation Tests
edbe8078-406c-5723-803e-cfc32d5bbb98 | note | Description - The Constructor shall conduct a Investigation test (pre-production) on sacrificial rock reinforcements and tested progressively to failure. Investigation load test rock reinforcements are to be installed at locations, agreed with the Designer’s Representative.
7a184750-cc27-5938-bc39-c6a4f8acb29f | note | ○ The Constructor shall notify the Designer’s Representative with a minimum of 48 hour notice.
8df396dc-8cb6-5851-8571-c6485b84c213 | note | Method/Description - Trial
df11dc99-cb68-593f-ae86-7024e5bfe45f | note | Test frequency - Prior to the commencement with A minimum of six investigation tests shall be carried out for each type of rock, grout mix, and rock bolt or dowel orientation, or as agreed upon with the Designer’s Representative.
c1aeb695-800f-5b96-beff-8ac54ee68454 | note | Conformance Criteria - At the end of the third Load Cycle the bolt shall be incrementally loaded at intervals of not greater than 33% of Proof Load
1f7e81fc-89e8-5153-95f6-803f8aead438 | note | Constructor - H
3776baf9-df06-5456-a7e9-e02650504d21 | note | CPS - W
53fa1c11-9ee1-5f71-afe8-11ebfeab35c2 | note | Verifying Records - Investigation test results
c042ca2a-ad52-4e0d-a108-da184d31da57 | checkpoint | 1.11 - End Anchorage Tests
6b18c184-efce-54de-b298-c0d43d33222d | note | Description - The Constructor shall conduct end anchorage test with a minimum of six rock bolts per proposed rock reinforcement system shall be tested in each ground type. For acceptance of end anchorage, all individual bolts shall achieve the pre-tension load shown on the Drawings.
7bfd9cc6-f39c-54f1-99f8-6a5bfdd1cffc | note | Method/Description - Trial
b7ce8db6-34f9-5ca4-8bd3-f579b39e682c | note | Test frequency - Prior to the commencement with A minimum of six tests shall be carried out in each ground type.
2f266a54-9208-5ded-9764-80e97d7d986e | note | Conformance Criteria - All individual bolts shall achieve the pre-tension load shown on the Drawings.
c8ac52b4-a5cb-5478-ab66-c5d24d3b5474 | note | Constructor - H
0ea1fa7d-3082-53af-833d-1959170fd607 | note | CPS - W
6acf4685-2f62-574c-948e-892722dbc4d3 | note | Verifying Records - End Anchorage test results
5cb6f8bf-44e8-4f0d-b94e-4f0e36613a53 | checkpoint | 1.12 - Approval of shotcrete equipment
d2c105a6-a825-5362-8d2c-03e1c38b9d11 | note | Description - Details of all equipment to be approved by the designers representative
36d06578-6673-5ab3-826f-3f9ab1a136ae | note | Method/Description - Review
b6733aea-7f5b-553a-a406-e87c02084524 | note | Test frequency - Prior to the commencement of the excavation work
95894af8-e999-52d6-bd38-3e8561de410f | note | Conformance Criteria - Designer’s Representative Approval
65191446-defb-5fd1-acb5-a506639ecac4 | note | Constructor - H
c32d0da2-a1c1-52d4-ba9b-c2ba6445186d | note | CPS - H
f9d9326f-4301-51a9-a3d4-47a4bf92a942 | note | Verifying Records - Equipment Technical Data Sheets
1503a547-7fef-4d50-ab20-433be9c05e74 | signoff | AUTHORITY HOLDPOINT
18cd7d69-daee-4dcc-b0ce-13f67fdf462a | checkpoint | 1.13 - Probing ahead trial
2301a8c3-42ac-5d6b-b280-1b20c4957a37 | note | Description - A trial shall be carried out in advance of tunnelling activities to identify optimum drill bit, drill diameter and flushing and percussion rates
3cef0b5d-4a8a-55dd-baeb-81948600f9f4 | note | Method/Description - Trial
e5ee7167-b89b-5133-8d52-9a172d136c6b | note | Test frequency - Prior to start of tunnelling
a13a6577-b0b9-5798-85ea-d5109595847b | note | Conformance Criteria - Designer’s Representative Approval
f5d1eab2-2944-5122-a3cb-b700ae36dda6 | note | Constructor - H
57dd8d62-02f4-5f56-86bb-93f3636e5ab0 | note | CPS - H
c496807b-78eb-5002-988c-2275b7fa0c0a | note | Verifying Records - Probe hole trial result
a9e1e324-86b8-451d-8f79-33f424579090 | signoff | AUTHORITY HOLDPOINT
93e683d6-38f5-4115-bb5c-0576a108442b | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
bf1c9a7f-0e8c-464e-9e30-7405df981bc2 | checkpoint | ITP Close-Out by
3a016a42-312f-5d68-b25c-939f56eea9d3 | note | Site Engineer/Project Engineer
4fe1fb7f-2d73-5d0e-9f16-71845587c3a0 | note | Zone Manager Approval
d45aeefc-7004-5403-89ab-35610cdbc5f7 | note | Construction Manager Approval
714114bd-83c0-50d9-b693-41d1fab7ac5f | note | Quality Manager Approval
d9dc876a-20bb-5e65-9ddd-c950021a6b6f | date | Date:
a06699ac-d215-437c-989c-8a4407d19fe9 | signoff | SIGNATURE
d167176a-1e73-5c56-afe1-a7eb9b55d75d | checklist | ITP-001 - Cableway Works | itp | ITP-001 - Cableway Works
bae2c9a3-0ab5-5bde-9400-1e4e0e914acf | section | Construction - Earthworks
f25b820d-6bae-5ecd-bdd4-706241f01c7d | checkpoint | 3.1. Removal of Topsoil and Vegetation
f446cf7b-05ab-5495-b466-d0e3f249c2b2 | note | APPLICABLE STANDARD OR SPECIFICATION:
ec3ddf8c-a3c9-52f8-8775-6d2cca7e1bfa | note | • Drawings
cac61a98-1105-52b7-8330-64b1c149b435 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
be59532d-0bce-5d68-a579-86de718394d0 | note | • Confirm when topsoil and vegetation stop
fd443fef-f2fa-5125-a828-8a3f9f1f1c29 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
ca7b77a7-17eb-5284-9e68-c6070efbe9aa | note | • Visual Checks
c6cb625f-26e7-5493-9885-07b84061c5f5 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
28d53178-2f58-5162-b80d-5635e3d0af6f | note | • Ongoing
7164c0f2-90aa-505e-aa41-e419fcf72d86 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
ede6a507-f4b6-5208-97b5-5af4aeac3162 | note | • I
2ec9688f-0f10-5bbb-89cc-2c906031f137 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
3d5d285e-29dc-5daa-a838-a987095bfe17 | note | • PE
a2f07ebc-f767-5e05-8044-56b1eff727d1 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
776b06e8-64a2-5150-9dc5-cd04b81dd42f | note | • N/A
9a036470-15ef-54ea-8557-29816678c21b | checkpoint | 3.2. ESC Measures
4d4ffe01-b599-5b6b-82b6-824b347e03a7 | note | APPLICABLE STANDARD OR SPECIFICATION:
82292996-b39c-5ed4-a138-b810503877a0 | note | • ESCP
8bad29e3-4d28-5493-bc0a-8b544875b442 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
a30b8b7b-d84a-5844-a587-ed0c3ffa6d47 | note | • Environmental controls to be installed as per ESCP prior to removal of topsoil
93f53a88-385a-54cb-9546-4521a3c6e60b | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
baa5ed11-4caa-55bc-8af3-5bd3a312b479 | note | • Visual Checks
9dc30442-9ae1-5f90-9128-052248c5b8b1 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
bfa81637-972e-51ea-b882-71d5ec2e5d09 | note | • Ongoing
4cde16de-d88d-5bfd-b964-527759515c17 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
2b931c43-0234-57fc-af3d-50e0cc58101a | note | • I
4bbebaee-9383-5324-81ae-ed66caee389f | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
21f20ff1-be2f-5168-a121-46e8abd20700 | note | • PE
327ea502-e626-5cd3-a9a0-34daa5fab716 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
152632e1-ec83-5423-9f93-15f4c4abd00b | note | • N/A
1e94c506-eddd-5c00-bd6f-17c3a5a30bc9 | checkpoint | 3.3. Cut to Waste – Bulk earthworks removal
0510bb34-6df4-5870-abc2-89ccc0403d62 | note | APPLICABLE STANDARD OR SPECIFICATION:
9c193eba-96de-54d4-9cfd-ed4fa5e1e486 | note | • Drawing
4419470d-b4f2-5f20-b5d5-1a66505409c5 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
27f704c8-9c2f-569d-ad98-860f1bc6dd5a | note | • Level of cut matches drawings
4286bfef-2f98-5c8d-90e9-c0151e943636 | note | • Global Position of cuts
2fab4e7a-a63a-59c0-81c7-cd2d0decab8a | note | • Inspection by MSQA
a101317d-a0f7-542d-a4c3-edd010a4e5b0 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
c49f0e1c-f813-5234-9b6f-6e0739b07e5f | note | • Survey Checks
5e0d5509-497e-5e6d-94d6-319756479af2 | note | • Survey Checks
8c09e4f8-fbcf-503c-b199-d7c00108b718 | note | • Visual Inspection
1d66461a-ac73-5e07-bf97-0e5dbf767e3d | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
72f9bf49-645c-5327-9ac2-1732b2da362a | note | • Daily
5262752c-8f0c-5cc8-bbb4-beb1f3735c5a | note | • Daily
75520e72-e460-5cfb-8583-dc2516cbbf52 | note | • 3 x visit per location
a05d2171-63cf-589a-8700-718a8cded3b8 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
eb19f1cc-37ea-5378-b2ec-0593f107c724 | note | • I
45572226-71db-5e36-9629-5b05bce0eced | note | • I
b940d53d-0a6f-5ef4-9bcc-99d8b8e8c167 | note | • H
2460b0db-4b5e-530e-9a99-fb65d15b0c6e | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
9d6c1ef6-d405-5b4b-8a40-889aae36dfcd | note | • PE
3f88913a-2237-5d6f-a898-90c98f633c5a | note | • PE
e460ac10-0540-5e72-8032-8f75dc3f0660 | note | • MSQA/DSR
45d7d401-1fa1-5a4c-9d94-910ad6b6e783 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
7c1e5d85-5363-5c79-88b1-8d58082e778c | note | • Survey Records, As Built (3a)
52f748fe-7bd2-5df8-9ad9-48659fefbc66 | note | • Survey Records, As Built, 3D mapping to be provided (3b)
b6dfe628-0696-5d97-a540-c23c13ff339c | note | • Site Report (3c)
a1c53a01-c8d3-5e0f-a010-ae4aedde5508 | note | CERTIFIED COMPLETE (DATE, RELEVANT CHECKLIST TITLE/LAB REPORT NUMBER ETC):
82369f8f-e107-54a5-b4a9-72301c63afa5 | note | • 3a No details received
bd803e80-891b-538b-83d9-8cdb241614e0 | note | • 3b No details received
d078bc43-14b4-5371-8d99-6d40d8c17934 | note | • 3c Tower Site – 13/10/22 Three site reports uploaded for Tower Site. NAB – 1 site report unloaded – missing two reports. SAB – missing 3 reports
ab260d51-7d3c-54f8-ab54-1cce2ff41f98 | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
0fe373b4-0959-5cf2-b964-2160ac31f964 | checkpoint | 3.4. Install Fill Retaining Area (North Anchor Block only)
840a6f4e-0865-5376-9ed4-d869c2acda83 | note | APPLICABLE STANDARD OR SPECIFICATION:
a37abe55-c354-5eae-8953-bdd1442b7205 | note | • Temp works design
f7ff324d-6507-5178-83fa-3bf2bd551a42 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
90e3fe80-68e6-5ab9-b243-dec4d653ca1d | note | • Level and Position
043a4502-27b6-5a30-9ac4-f2db912fb991 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
5e7daf55-28a1-5d7c-8fe4-d5dbcebc706f | note | • Survey Checks
4abcb998-7f41-56e1-a4a4-363a101e8366 | note | • Visual Checks
1740af0e-2138-569b-9cf9-080baf8ba77b | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
61454d78-ea80-5e74-846b-15bdd8c4b7be | note | • Each Temp works
a73b3217-fa40-5fcc-b8d9-20054ba77a6a | note | • Daily
00e50aa8-482b-5895-a0cc-205550e5eb9a | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
088757b5-4143-5eb5-8a05-524e45d4d9e1 | note | • W
fb2ef8bb-a07a-5f36-b6d6-62eba00575f8 | note | • H
ba5a3fdd-2817-53c4-8335-a93692b4d48c | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
b9ef9355-211f-53cf-a356-223417b31981 | note | • PE
5c162536-dca0-59b9-901e-831b66d85f98 | note | • PE
6d575111-72a8-586f-933c-36605f13e4cd | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
6d45613a-bb68-5f34-b156-58bdc7b2d1c1 | note | • N/A
acbf9c61-30e4-5fdf-92b8-5270aebc6b65 | note | • Temp works sign off
cf423a19-51b9-5d3d-8b8d-a9a3af82a8d1 | checkpoint | 3.5. Cut Access Track (South Anchor Block)
0296bd65-109e-5d79-b43e-b4009a94f08c | note | APPLICABLE STANDARD OR SPECIFICATION:
a12a652b-0f65-5cb0-8fa9-9f57231899b3 | note | • Temp works design
aab5b90c-c035-5999-92eb-d1b5213888bc | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
d9742b39-3681-5a5b-8d54-bfdf52b656b1 | note | • Level and Position
d69fab44-7e58-5638-bd1f-ebffa08a1c12 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
020df4c0-11a8-51d2-a117-53a4a05b47f0 | note | • Survey Checks
e7ecf537-f50f-5644-bc27-70d23628939d | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
21e30579-e39a-527c-a516-1e0da9178352 | note | • Each Temp works
f1a916d3-4afa-5783-b1b9-3db7e7e5fe8f | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
8985f5ca-a61b-5372-ad05-c61547e5bdde | note | • W
d4326e56-ca63-5431-b4c2-6936bc93cc82 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
481b3d24-3215-5ccf-aae1-67394e8c29eb | note | • PE
14678cf9-b4a9-5e8b-9c08-6c45f8e29346 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
a6cd570a-5685-55f3-b313-c872e93774d1 | note | • Survey Record
438622c7-336a-59f7-b993-9e74484b4fb6 | checkpoint | 3.6. Trim to Grade (Compound Only)
3ee56e6b-42c2-5339-8748-879019ed37b0 | note | APPLICABLE STANDARD OR SPECIFICATION:
f501d13f-57af-52f6-b501-c5860e0719b0 | note | • As required
e590f687-6a3c-58ec-83fd-9d7e7c2d4495 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
2058ee40-5d46-5f4e-940c-223f46af7195 | note | • Grade to control water
e5025be0-b307-5e95-99e8-6c22f692732b | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
c1d4efff-4179-5e33-8780-97d947731499 | note | • Survey Checks
7b973601-3e06-52eb-b452-6624a3d50ff7 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
9702a9bc-2888-5a6b-9092-dac49f0e4e16 | note | • Daily
f6951156-71aa-5b0e-b76c-dfccfcf34119 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
376a2884-bd16-59b6-9979-9238d964fce8 | note | • W
e05ef43e-4a01-5008-b875-d5ea0bc83558 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
04535899-7df2-56bf-af7d-db315fe74ae5 | note | • PE
9d28e230-8b83-53f2-8f3a-cc6c155ac7dc | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
94a96841-0e6a-5b30-8ef0-5f93887a3fc8 | note | • Survey Record
cdb1cb4b-07b8-5ad3-a9d7-a806740a6be4 | section | Structures - Piling Works incl Micro Piles (Central Tower Only)
348054a4-0785-5034-9d49-feddf88c6b4a | checkpoint | 4.1. Set Out Piles
afbd161d-f768-56a1-a6f4-8a258594fab8 | note | APPLICABLE STANDARD OR SPECIFICATION:
8fe47ac2-b682-5cd1-87eb-b0e34e56cd9d | note | • Drawings and Survey Model
97026ff4-3e7a-5d16-b8f9-237a5c6679fa | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
194ac4fd-8e04-5d74-b6e6-be0e13778478 | note | • Position and Depth
eeccdd2c-6a6c-520c-9057-2d3d5087f2f1 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
3dc1eb25-1611-543a-8e4e-50cd5dcc0b9f | note | • Survey
0eae9148-16b2-56d2-904a-f1649d4c9a9b | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
24664740-5fc9-5a15-bf27-68086cf75d01 | note | • All Piles
e6fbd6e6-0e6a-57ad-b708-82ca60820dd3 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
69b9c6b2-90bb-53e5-87ac-9fd51ff7ebe4 | note | • I
a7f71cae-cad6-5195-8a30-3f1565a36c29 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
10de8b3f-31a9-5787-b03e-55bd6891d1a3 | note | • PE
1fe6e74d-0dba-5d6d-9735-dec1fef67ae1 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
9291c85b-437a-5819-96fa-c513e9eff3a3 | note | • Pile Record Sheet
fffffe3a-e8d7-5d3a-93ee-99b714450303 | checkpoint | 4.2. Drill Piles
23798a48-4725-5c1f-bab3-6deebb12d0f9 | note | APPLICABLE STANDARD OR SPECIFICATION:
4d4abece-2e3c-5c6f-b4c0-049b4ee53daa | note | • Drawings & Spec (TBI)
8aefd90a-16e1-5fab-a300-b52b85776714 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
627500fa-3900-55b6-adf8-cdf8b5384bfa | note | • Piles drilled to set and/or required depth as per design drawings. Location within +/-75mm. Verticality of 1 in 75
67baab02-bfe7-5953-b897-fd184199ccd2 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
d20076ca-01cf-5084-8d3a-ca7cb10e6f88 | note | • Visual Inspection
939c8ee2-4718-5f89-9c24-b8d1c08d5f7d | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
4660e484-2661-5bac-ae09-95d6611551d8 | note | • All Piles
91a4fa9e-0f18-5e78-a76f-fa80826199ad | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
3dd45958-dbaf-59f2-b481-833edab21acb | note | • H
8f6e01f8-f9f6-5903-95d0-3e11d0c09ac8 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
371dea6e-2f33-5dbd-9e39-597b19897d06 | note | • PE, MSQA/DSR
a4f06133-2cee-5617-875e-a350359f65b1 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
b4f136b3-bb67-5879-9b2e-3e4f9e038ec7 | note | • Pile Record Sheet, Site Report
77d4ede4-ba4e-5eae-85ca-c8ee46690a89 | checkpoint | 4.3. Inspection of ground conditions
9fd8ea15-13d6-5181-be4d-9267f218548a | note | APPLICABLE STANDARD OR SPECIFICATION:
363d7832-a943-553f-b6dd-5526bcaa32dd | note | • Drawings
cdd3dd28-50c4-5826-91f9-b3934e53104b | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
8caf943f-be91-5ad0-8825-b2ef5bad38a4 | note | • Confirm as expected
e20e554f-2918-5536-a85d-7800fc2d0a67 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
066469dc-3222-55b1-a97f-79b11c01962f | note | • Visual Inspection
098c7633-e6e8-5391-84cb-b8adedf5f6c3 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
3c202d14-908f-56c1-8da8-0880ef639ec5 | note | • 1st Pile
7b92fd7f-a11f-5acd-a930-5020f9a73b14 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
bc11ca72-c34e-5270-bd06-3105af2dc58e | note | • H
3151e508-6076-5614-9787-8c1a844506ce | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
b5c0489e-7a77-5f88-8951-875812f435fe | note | • MSQA/DSR
0caf3356-58e2-57d0-bb0b-58fb6abb2564 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
80a34909-005c-564a-8953-9dde1fa82232 | note | • Site Report
6f98d386-84dd-51ae-92e3-7340badba35d | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
6e9cffa8-fba9-54f9-b1b6-53492f896d3b | checkpoint | 4.4. As-built
e9a13268-54f3-5368-8269-b9c81f1062b3 | note | APPLICABLE STANDARD OR SPECIFICATION:
c78357ca-bad1-5361-a2b4-d12da5e22572 | note | • Drawings & Spec (To be issued)
b3bb51d0-1c9d-5f2c-b8ce-be8c99631899 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
f50155e3-b1a9-5b0c-b4ea-a55a2e572385 | note | • Cut off level correct for follow on connections.
d2cc34b6-1aef-5321-b06f-481df0fe3702 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
be933e2c-b74f-546b-b3ef-5a01e0dffd8b | note | • Survey
09da8206-34ad-50db-b635-72b5f604388b | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
a0a5becf-062a-5308-8f16-dfd366665215 | note | • Once per pile
fd7c7df7-1b93-5615-84a7-617e11edd34b | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
9cdc8855-81a3-59a9-b90e-90dde8f01b6d | note | • I
cd2cd197-569d-5db0-a18d-e3cc9a4e3d65 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
965fad1b-6a56-5389-81b0-41c5df8986e2 | note | • PE
de74877c-cc93-544c-bfb9-e9692d42a6c0 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
513e6ee2-5918-5ef7-b24c-3afd002a43d2 | note | • As built, Pile Record
451b5016-f70b-5281-9f80-001932e218fc | checkpoint | 4.5. Install Reinforcement
736e31ac-9d22-5666-ace3-d1caa58396ed | note | APPLICABLE STANDARD OR SPECIFICATION:
d5995795-2ee3-5220-8459-28ee4dccd01e | note | • Drawings & Spec (To be issued)
9f622647-52eb-5ecf-abca-e258e6ba3b95 | note | • NZS3101 & NZS3109
b10b0c7b-72cd-5c6a-8f2b-f8524e272045 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
78caa8ef-cb4f-5e9f-b176-9858e56dde53 | note | • Reinforcement is fixed to design of IFC Drawing. Correct reinforcement used that is not damaged.
15d2ebbf-6a27-5a9c-b745-23f136700ffb | note | • All cover block/wheels installed to achieve minimum 50mm cover.
8fd03d2c-0c7a-52ca-8931-52c4a5c48049 | note | • Confirm all reinforcement matches drawings
18a79500-5aac-51bf-bf99-be7507a4f890 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
f8bc78cc-04f0-51f4-9842-1469aa65f0f2 | note | • Visual inspections
5593e5d4-47bb-55ec-aca3-8cb4bfc8fbd9 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
23a931eb-b7b3-5378-8151-25be5c2ddb47 | note | • Each reinforced cage
f255343c-5431-5746-95f5-bc5b16c0a62f | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
84dc1d8d-3110-5fc5-9e0b-3707717dc738 | note | • I
4d93497c-e78a-541b-ac0c-d278298f99b9 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
6c6afb15-71a1-5151-93db-3aabe0895b8c | note | • PE
5634a5b8-6036-5e74-b48c-b9512eb7e4fa | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
a0b0b318-81ec-5b54-aa86-0e4d5af72341 | note | • Concrete Pour Inspection Check sheet, As built
47f4ee34-a445-52ea-8fd4-18b30d9545c1 | checkpoint | 4.6. Pre-Pour MSQA Inspection
991448a5-f7c4-518b-a6c9-fda7e9c71929 | note | APPLICABLE STANDARD OR SPECIFICATION:
7ee8aa61-5039-55a9-ba07-9d63d8da4b85 | note | • Drawings
d7a9aaeb-772f-587d-9341-abf3f525ad06 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
3578c6a9-aba9-5255-9012-73b304e4e96b | note | • All above is as drawings
c2dd6fe0-b977-5bb1-8f64-98c46fdfa496 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
30a37170-aa7e-58e5-b22b-0d13e716705c | note | • Visual
b9b43c83-0fa1-5d58-88af-a21cc4c3f0fc | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
69b1aaad-2261-5799-9fb1-77993cb15767 | note | • All Piles
b04585fc-de7c-529e-82ad-1a1c4c657330 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
20c19885-3067-54d5-9155-b15cffa3bfb1 | note | • H
b18626a4-fc1f-5d66-97a1-772c797800a1 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
fe8bfa77-f048-5b10-9005-8caba3e4b7ec | note | • PE, MSQA/DSR
8cfb0014-4d79-50c6-8cc0-221b19e0512e | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
743327f1-b7f1-5649-9030-6312cc88b551 | note | • Site Report
4e422162-51c1-5d1d-a093-beb9f322b976 | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
5cc818d5-46ab-51e9-9431-55dba534b818 | checkpoint | 4.7. Concrete supply
032d7ce1-446c-5bcd-9bdb-73aea61448dc | note | APPLICABLE STANDARD OR SPECIFICATION:
198c326d-a8df-55cd-b082-80cc54a1765e | note | • Drawings & Project Spec
a3a3a402-9b0a-576d-a8d1-e6f233ecdec2 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
3a3d029f-44e3-5c15-bdc9-dd3f1df2dbb4 | note | • Request a minimum of 3no cylinder test on all structural items, 7 day, 28day.
9df9431d-e8f7-518f-abf7-f371eadf0235 | note | • Concrete cures to strength (40MPa).
b177ec3d-f8b7-5e16-aa9c-d5297962f6ee | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
dd300bb5-a65f-56a5-8af9-1d02cf1f9d8b | note | • Concrete sampling and cylinder crushing
20e582b9-3497-5c0b-afd2-ed5639635744 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
df076d07-f9be-5c33-9f53-fa9cb5b69cb7 | note | • Each Pour (or 1no set every 75m3)
39a3ae16-6e8d-5027-834a-210c838d75e6 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
6bb38144-a861-547e-b547-a088a83527b7 | note | • R
bbaf2431-6888-5d4b-b583-a54c097ce530 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
8b1d2888-4a38-5c93-b83a-297e33f88380 | note | • PE, MSQA/DSR, Lab
d974aa5a-dce8-56f0-b26e-6dad36f11747 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
3aac9b27-c56a-54ea-af54-d89c1dcbefe1 | note | • Concrete Test Result Register, Compressive crush lab test results
ae57c9e0-f040-52fe-9809-20be64478d8b | checkpoint | 4.8. Concrete Finish
47ccefd2-e8da-5149-b0d7-8f25ba2bbc82 | note | APPLICABLE STANDARD OR SPECIFICATION:
b6b84316-eb9b-57cf-80b3-f457094a344f | note | • Drawings & Project Spec
a80583c2-b41a-52b7-8ae4-fbe4521fcda6 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
05e35909-663a-536d-a71e-b6a5c66f70a6 | note | • As per drawing request, type B joint on top
f9296017-8b0e-5aa0-8c3e-4f0344ec24fd | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
d30945b0-ae45-5f1c-89c5-32998430dabb | note | • Visual
026b379a-9404-5aec-b923-f44daa7732b5 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
0a758f03-9a78-5023-9fad-2b528e3e777f | note | • Each joint
cf8ac7ec-7d07-5b45-a3da-0676f517c3b9 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
86775a06-2d8f-5601-b1b0-74897bf471c8 | note | • I
1706c6fe-4e77-5b21-befc-532b4e15e919 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
50a6ab0d-b797-5b6d-82bb-b570d7b224b9 | note | • PE
ec2ac623-2268-5e7a-a985-d935bafb15ea | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
9b187eee-9f51-5a22-a3c3-9ffecd673250 | note | • Post-pour inspection record.
b9eadffa-d58f-53ea-b2cb-2713e2a98dee | section | Structures - Formwork and Steel Fixing (NAB, SAB, Central Tower Footings, misc)
ef91c513-729c-5572-90df-00dd8db1542d | checkpoint | 5.1. Install Footings for Temp Works
e268598c-e2c3-5ceb-aae7-1c74d25d0420 | note | APPLICABLE STANDARD OR SPECIFICATION:
bb25648b-a534-5151-8012-d635744a7d70 | note | • As per Drawings
82ae4e69-304f-5a15-aeea-a204ee1b2eaa | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
071d7c61-b8ba-5c0f-aac8-0fb82a5d0255 | note | • As per the formwork design
835099f4-04a2-5773-a60b-d9c2e5b90c8c | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
5aadcd3e-6c6c-547c-b039-ae591594d07f | note | • Level Check by Engineer
a37b9509-747d-55ce-bd6e-9624718682ea | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
85be25e4-2789-5a6b-b76a-3e10c7723d90 | note | • Per Element
aef767e7-d43a-56ac-adf3-c8cb984f9bea | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
f9d38607-21fd-5b5d-a7b0-4a98281f9216 | note | • W
29378c0f-47a1-5d40-bdb4-1ad2c64be667 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
d28460d2-f230-50f7-b78c-5116c0ecd58c | note | • PE
bc3c2cf0-9a96-5533-a86b-4cf3b4686d56 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
43302cf0-dc16-5977-9414-dd20f968c0d1 | note | • Concrete Pour Inspection Check sheet
d5531cd0-ea33-56a6-b013-88860aab66a7 | checkpoint | 5.2. Install Blinding
c72f13d6-eb54-58fe-a99f-48afe95305b4 | note | APPLICABLE STANDARD OR SPECIFICATION:
68be54f4-b071-58d1-bf7d-f7d5ba7cdad4 | note | • As per Drawings
c8e891e7-8b36-5e2a-9bfd-0da017c7bcf3 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
87490d91-9d31-5c52-a23f-8ace31786cce | note | • Blinding thickness and level to be as per drawings/required
158fe809-1428-595a-9786-bb86b16a3443 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
983e1c19-1c1c-5015-8276-c5b04bb49f2d | note | • Level Check by Engineer
cd9ee49f-7b64-554e-bad3-28a6474caa41 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
c5d2add7-5a41-52e2-84cf-cceb93925b56 | note | • Per Element
f8a92c6b-1453-59b9-bdcd-fc702dcccdad | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
1277f853-ad06-5633-ae23-888008f6c7bf | note | • W
9e30256f-7c23-59d6-ac83-9cdbf1b1d30c | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
1acdf262-91dc-5312-9337-0c0105214596 | note | • PE
cc287c50-55b6-5772-bbc6-0e3d91dc7547 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
33413fbc-0a66-57fa-b08a-6fcf28067d7b | note | • Concrete Pour Inspection Check sheet
f4962dfe-3be1-5f1e-b692-07214e8f2cc2 | checkpoint | 5.3. Formwork Placement
437ac288-5afc-50e0-b536-17e189957f66 | note | APPLICABLE STANDARD OR SPECIFICATION:
99c7903d-4f94-52e4-b0bb-0f4097005717 | note | • Drawings & Spec (To be issued)
b17009a4-2672-5b40-bfb3-8cebee5a6517 | note | • Formshore Temp Works
7c24b5ee-aa45-5c1f-b32e-2e98994409c5 | note | • Doppelmayr Drawings
d55a4a42-32d2-58ac-92f1-2f524bef6a65 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
c8c24328-58a1-54fc-b6b8-e0484ecdb83f | note | • Formwork as per temporary works drawing if relevant.
5cb74200-be5f-5997-a786-25fa0a162793 | note | • Position, orientation, dimensions checked.
9eb9126b-690a-5345-9613-c6adb9a32e14 | note | • Oiled, Area cleaned of all debris, Cover correct as per spec and drawing requirements.
01f1f0de-5894-5181-a35f-03ab37d6cefc | note | • All inserts inserted, block outs, dross backs, bolt clusters etc See temporary works design.
87193310-b343-5bf7-a740-3a7dc30a38de | note | • Confirm any inserts are included as per drawings.
08bd278d-4ff4-59e8-bd57-858c914160f6 | note | • Ground anchor drossbachs critical – placement takes precedent over all over items.
a0254689-ac92-5c2a-96e3-b961893d7fce | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
c38c96e1-577c-56eb-8ed8-b672a6e0a46e | note | • Onsite Visual Inspection
f5b60228-a58f-5ff8-9ac8-cf88ac9a9f27 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
f4779be4-9e3e-516e-a49c-6c1a3d28ab38 | note | • Per Element
6f3df709-1078-59a2-9843-d3a50b60f224 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
8bf2f972-9d4d-50af-8faf-b21a1b6eb074 | note | • I, R, H
706351bd-ad7e-5519-a309-823eaac3bd86 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
89bea273-9eb6-5926-b1de-3a07caaa3dc0 | note | • PE
1ff3a2cd-bd8f-577e-b76c-c5ff172cce42 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
872e5186-1874-57c2-b18e-31e7f214d8ae | note | • Concrete Pour Inspection Check sheet Photographic evidence, Survey Checks pre pour
dfde3c4d-0194-5d89-bb7f-0cea3adafc81 | checkpoint | 5.4. Earthing
179068e3-2a4c-5050-ad92-ec72211b74d2 | note | APPLICABLE STANDARD OR SPECIFICATION:
13ac616b-7696-5169-8129-1e49a73a9baf | note | • As per requirements
85882a9c-8e2a-50e1-b886-37a4d15a627b | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
cd199acf-4057-5037-a5ef-8681a188eee1 | note | • Each concrete element TO BE ELECTRICALLY GROUNDED BY AN APPROPRIATELY QUALIFIED CONTRACTOR.
acda63c9-56d5-5be3-8d16-7565bb53496b | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
08cb715d-9cd4-509c-b48d-2a0d46bcef54 | note | • Visual Inspection
b073c7e5-2c9b-53ca-a309-f878fbac87c2 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
a82b1937-9954-53c7-9d88-932ce82ccd9c | note | • Per element
18275b99-0739-5687-9ab8-9eb8932ac79e | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
34a046d1-a132-521f-bdbc-592560056b69 | note | • H
9c407851-ae51-5cfc-b76b-3dd07870deee | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
fdb4f05b-c02f-5ecd-bd26-e39d88ddcc97 | note | • PE
ddda06e8-5cb8-5cfe-a748-5e7c766e3f8d | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
05f189fe-7ab9-53d0-a43d-3490a4320d9b | note | • Report, Photo
6b3a21cc-65c7-5e79-aa80-363c9e15e6d3 | checkpoint | 5.5. Reinforcement Placement
1f93b989-a739-528d-8023-8891866d3b48 | note | APPLICABLE STANDARD OR SPECIFICATION:
80c1e902-229c-525c-b0a2-8e419db5ab09 | note | • Drawings & Spec (To be issued)
692a076a-a433-556c-9562-e4df13363127 | note | • NZS3101 & NZS3109
287cba95-828d-5278-ac58-e7bf89bb2130 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
72145de4-044e-5cfe-885d-540a4693bf9d | note | • Reinforcement as per relevant design IFC and standards NZS3101 & NZS3109
abb37c2a-9c09-5a4b-bcf4-f4f74ae8ce97 | note | • Grade, number, diameter, spacing, starters, cover, welds, lap length and position all checked.
25452442-36f6-57cb-9122-c39da4f29266 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
ec69c584-4d8f-5989-bc6f-dc8946ccda1a | note | • Visual Inspection
ad63d122-cc30-5ff5-a30e-5f8ad3829f4e | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
b91d0cd9-51be-58a5-83a6-44d90f0518e6 | note | • Per Element
eb3461ef-4443-5a38-bcdb-df653a36a894 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
2d4a55ad-5626-538c-acac-c33926da3252 | note | • I, W
dfde7c5e-ba22-503e-8a3b-643a9d99db44 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
1925c479-78a4-5962-9205-9085d2d4db75 | note | • PE
7e1660f8-6df3-5f43-96a2-b5286df89802 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
60c4c56e-2ebd-59e9-9b10-2621c4f4f2fd | note | • Concrete Pour Inspection Check sheet, Photos taken and stored in QA File
25b24c52-4df8-5198-afe5-5dda9253c64c | checkpoint | 5.6. Cableway SAB/NAB Williams bolts
ff63ea0e-7e74-5f2c-a77c-43f6a0f24795 | note | APPLICABLE STANDARD OR SPECIFICATION:
962de1da-1433-5d3d-a61f-cd6041eb3ece | note | • IFC Drawings
57f40c0d-70fe-5905-ac38-e555e703df6a | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
dc5ef26c-ed66-5a76-8288-e1c95df3a4f9 | note | • Size, length and position of the bolts to be as per the design
cc07cdc5-1168-58d7-942e-3d44a7d83eae | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
4c890d17-0612-54d3-828e-728f104c6f91 | note | • Visual Inspection
4a060cbc-fbc2-52b4-9781-427a7115ceb9 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
58e64bad-afdc-5b60-9c53-067af7178010 | note | • Per bolt
fdcbbf4c-45da-5e28-ab77-50f9436daeec | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
3285f756-ade8-510a-8336-231ddbf8178c | note | • H
1688a166-2562-5e6b-b431-3f1b2881e9f3 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
d2fd7f3e-b593-54a9-bddf-93cc5f3bc1b8 | note | • PE, MSQA/DSR
06da6a19-9a5d-5ca1-b329-6267a070662d | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
7c609c0a-d5d6-5b01-9849-d723f3d59bf7 | note | • As-built
fbc13618-5854-5fca-8713-a7896198f388 | checkpoint | 5.7. MSQA Pre Pour Inspection
f0fd00fb-f614-5bbb-b393-5b5b8768392e | note | APPLICABLE STANDARD OR SPECIFICATION:
a83e7a70-62e2-5295-8ce9-9da4aa279e1d | note | • Drawings
efad27e3-2ea5-50f4-a82a-058d8b48909e | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
947a35c4-de07-5f19-b012-130c823a44a2 | note | • Confirmation of all above, reinforcement, dimensions, inserts, finish
10fa8e6b-d2bb-5993-8a1c-4daa73cff85b | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
78173002-645c-536b-8426-a8122f654340 | note | • Visual Inspection
ba33cce6-9010-5b7b-ba1f-97e9287fab3a | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
784da88f-3073-5688-9a83-756703e08c69 | note | • Per Element, Holmes provided 48hour notice to inspect.
b5f0f3a2-00f0-5d66-9cb0-7c8ef865f1e2 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
ebab0b2e-59c5-549c-90f8-cdc2e10a46a2 | note | • H
26a37a1e-52d5-520d-aec8-b51f5472d824 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
f231e42e-ffbd-59aa-a6e5-a4da3ca8a72b | note | • PE, MSQA/DSR
2f5e6ec7-a01f-5927-9409-922dd3abce84 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
970e3e1b-8f11-5d65-bcd0-a61cf8fc12fb | note | • Site Report
5f255159-4a7a-5083-a371-a88974327a25 | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
1c61e8dc-b663-5b7a-a739-a1548494f305 | section | Structures - Concreting
b87ad42f-cbc7-5588-af31-a86ce4f8e1a7 | checkpoint | 6.1. Concrete Delivery
c1789aed-752d-5bd2-9fa8-7f6e26d8479f | note | APPLICABLE STANDARD OR SPECIFICATION:
8cff6ca9-ffdd-5437-b8b5-2a4359cf00c2 | note | • Drawings & Project Spec
d962de97-cf50-5705-a665-8e17438dfcff | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
62afc40b-0f17-5ff5-bb22-7999bc82e126 | note | • Supply to match design drawings and specification.
e0aa8a2a-87df-59e2-8ff9-ea57e8e474a7 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
6a69ce40-44bc-53f1-84ea-afd0ec0dc72f | note | • Docket Checked on site for correct Concrete type.
b53c6379-44c6-5099-8dbf-41193b98a1a8 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
f65ab9f7-5d30-5c47-8b31-968d1642a461 | note | • Per Element / Per Pour (minimum)
13efd765-8cb9-531c-8620-601999e3dc04 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
df44e847-1b76-597c-bc87-656e923b49c0 | note | • W
730b32f6-7cff-505d-80e2-6714b3809052 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
b104134c-07a2-5880-808a-52b36bbbc7bf | note | • PE, Lab
cd96dd29-ebb3-5952-8104-2132e6d3e597 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
dab9479b-0ce8-524b-b236-d6bccd38b201 | note | • Concrete Pour Inspection Check sheet
9229eca3-4676-51db-88bd-2336528a83db | note | • Concrete Test Result Register
165fd99d-4e22-5d87-a174-3a99b38aecdf | note | • Docket checked onsite/Filed
b141108d-14b7-5030-a806-570d6b85114e | checkpoint | 6.2. Concrete Finish
7a43dcd1-75b4-58d0-a1c8-31083ef43fdf | note | APPLICABLE STANDARD OR SPECIFICATION:
c1b9ac54-cfa1-5a7e-8eba-39300a951b7c | note | • Drawings & Project Spec
e513370a-78e7-5dff-b612-c8af62b68437 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
800cd600-a0f6-5089-88f9-d5b618bbfb18 | note | • Concrete finish to be as per on drawing, U1-5 or F1-5 (inline with relevant NZS standard 3109 and NZS3101)
eba79f05-f6ff-5c2b-9281-c9c2fdfa9520 | note | • Concrete checked for any cracks and other irregularities.
79d65d07-b94c-5148-bf68-cac3093a321a | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
10986c05-633c-5bf6-8b4a-698ed892af64 | note | • Visual
4fc0f5a8-612b-5ae8-a2b4-bdf32fadaa41 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
84d13530-4021-596b-98f4-d027207f78f5 | note | • Per Element
01768efc-f44b-5d12-9e99-961b35ab1c09 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
dac6bf88-0de5-5b72-aaff-97e40cea1409 | note | • W
8b2daeee-6ec1-59a7-ba98-3379c9a69a32 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
83c92c0b-9e13-50ec-8712-9941cc778619 | note | • PE
b3482b89-e1f9-5e36-b7f5-ad24cba35ff3 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
dc5a2134-8e17-5e5a-bf5c-f2f79bfe507e | note | • Concrete Pour Inspection Check sheet
68e6f27d-a7a8-524c-80fa-5988171d0177 | note | • Photographic evidence
915e7242-b501-5d05-a6db-61488ac3811b | checkpoint | 6.3. Concrete Strength
b59f4473-1956-55cd-ac57-24b6f3691f8a | note | APPLICABLE STANDARD OR SPECIFICATION:
dc6b6518-9f1a-5aa9-8839-2b15f5a56822 | note | • Drawings & Project Spec
92dafc3b-8539-5339-be15-199674041e7d | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
ef077e8a-cf7d-5140-94ee-665f8390ecd6 | note | • Compressive strength results to match design drawings and specification.
b2f17c9b-9fa9-50f1-ae14-d8b764a37cd0 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
c3bee8e5-931b-5614-a3f7-e78fdc3a6344 | note | • Review of 7day and 28day strength results.
7664085e-0ad9-5afe-a6fa-1fdaba8509c1 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
0b714584-2c8f-5d11-b77e-403ce9fc0157 | note | • Per Pour (minimum) or 1no set of 7day, 2no 28days taken for every 50m3 +
c5f245c8-9d07-5904-bd60-784439c78566 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
c1bcadb9-0fd0-54d5-8331-0a9e949952cf | note | • R
307741a8-14fa-5925-89d9-63ff64446687 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
b27a237e-75af-5171-9f91-296b4ba3dbb5 | note | • PE, Lab
4b931d97-7f7b-5ea7-8599-ce3a17ef1bcb | note | • (MSQA/DSR)
d086303c-227c-5c34-bbfd-905145ed4553 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
ababe297-35e5-5845-b376-00c7e0d6daf8 | note | • Concrete Test Result Register
a2af986b-60a0-528b-8d8e-91a8d95d47f5 | note | • Compressive Strength Results.
85b22f05-272e-5170-9752-ea952653ca5f | checkpoint | 6.4. Construction Joint Creation – Type B
66fa461a-3d7e-56b8-995f-b8b2d3185212 | note | APPLICABLE STANDARD OR SPECIFICATION:
446dd4fc-c6e1-5c73-a3d4-0ee194655a1a | note | • Drawings & Project Spec
3ae21d96-bfbe-508d-aafc-f9dc50922111 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
46b15712-0fe5-59a6-a7e1-2a8c3cd88c0d | note | • Construction Joint type B
18993b11-2616-5315-b18c-9df955876458 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
0b49efa0-006f-529b-bdd5-933bd8b8d5f9 | note | • Visual
d53ea45a-2cf9-5bc3-9019-358c9f0ab8ba | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
6ee674f2-54c6-56cf-8499-4fcfcbeae9c2 | note | • Per joint
35d68d67-fed2-5471-856e-111861476888 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
46d89852-b12c-5cd8-b425-96072bb58693 | note | • H
70be5109-b57d-5b10-b483-479a8c628905 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
f7e42152-a1ac-516e-bddc-e4c434018461 | note | • PE, MSQA/DSR
d836dfec-aae4-52b3-bc7e-042c200a6571 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
2bdeed45-c32f-50f0-b4de-9a2bd7f66bf5 | note | • Prepour inspection
4f031999-21f4-5618-96c6-b371f6453876 | checkpoint | 6.5. Curing
b517d131-5c90-5b25-a0af-b3bd124b86f8 | note | APPLICABLE STANDARD OR SPECIFICATION:
329c82e7-812c-53ea-a1f4-52017db87883 | note | • Drawings & Project Spec
3f42da58-24ba-5053-b817-0cd15d173600 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
53ab0f8c-55e8-5770-a9bb-3227b010a6b0 | note | • Wet curing method or As per approved alternative curing method
d9d062a7-326b-5d2c-87fe-7cee618ea746 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
13ca13bf-6159-50eb-9bf6-48ee31032e40 | note | • Approved curing method
4d6cee37-7ac7-53e5-a701-9a4f16e1dc8c | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
b113d2a5-5382-5092-9574-cee6cf655f15 | note | • Per Element
0246f6ef-db3d-5ef1-b95d-1fc109622a54 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
4ddb561c-8deb-58a6-bd7f-23b17f7a7aaf | note | • W
60082181-85ea-5b99-a2df-be1336333d5f | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
136683cc-bc55-5fad-bff9-a67cebfd377b | note | • PE
fd3d84a4-e80c-5a67-a689-90c5ccc3d029 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
c624afa2-78cb-5343-b8a3-f018d67c10f6 | note | • Concrete Pour Inspection Check sheet
b5637e64-2a92-515d-83e3-95c61d687c15 | section | Structures - Anchor Install (NAB & SAB)
1beede44-e131-5de4-b000-5aa9015bdbf9 | checkpoint | 7.1. Drill Anchor Hole
2aef55d4-79c5-5e33-ad1a-fe0d8053e229 | note | APPLICABLE STANDARD OR SPECIFICATION:
b8a43414-7851-5480-9cfd-59d504cba5d5 | note | • MMA-DES-GEO-E1-DRG-4081
08cc91ff-fb7f-5e83-9ebb-e191a750e09b | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
78ef6b86-200b-5f0e-acbe-0ce2797c349b | note | • Inclination angle of anchor 13deg North & South
5bd92697-5430-521f-bacc-0172863d0fcb | note | • 4no Anchors at each anchor block – 2 contingences if required
d69ac742-df60-5202-896e-92d53d4d00a4 | note | • Length – 18m North (TBC), 15m South
5452b269-354a-515d-bd76-272f78102aa6 | note | • Tolerance on drilling angle is ±2° both horizontal and vertical.
247f4b9d-45f7-535c-b2da-f703f4aec4d2 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
c2e39778-54fd-5b6f-a57c-66104d497e46 | note | • Onsite Checks by Engineer
d3e17edf-011c-5b8c-9127-6405ef350076 | note | • Inspection by MSQA Checker
b9af2402-6f96-534c-8898-3dbe54e66d4e | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
30ae3177-9f5e-5af8-8aa7-db1fae16a78b | note | • All Anchors
d24ad75d-751a-530c-ade6-f493333b6800 | note | • One Anchor per anchor block
f0dc9fc8-b844-58e3-b1b3-20ded3a2e637 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
866c0e5f-b2b6-528e-8580-fdedf2dcc53e | note | • W
e4163eb5-36d9-5da5-9e01-e4c34d10516b | note | • H
eedc747f-62d5-5dfa-a31c-224f8ae10da1 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
817e8c47-282b-5b7c-bfbe-42fd7f566035 | note | • PE
c9cff728-416c-56c7-8160-ee88358f808c | note | • MSQA/DSR
d260c863-57d8-5c03-a5bb-2f0c1340670a | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
6d75ec59-5e93-5bf5-b96e-e8ac193c89f2 | note | • Drill Log/Anchor Install Check sheet
78314b2c-ceb5-56ad-ad34-a4384f9863b5 | note | • Site Report
e1236351-36b8-5838-9100-9414337ac2cc | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
f991a035-fb04-542a-abc9-995bfa8030b1 | checkpoint | 7.2. Camera/Inspection of Drill Hole
f0380a49-1226-5222-99a3-c055a8755c42 | note | APPLICABLE STANDARD OR SPECIFICATION:
84fafd66-469b-5dcc-9c39-d154c183da93 | note | • MMA-DES-GEO-E1-DRG-4081
a5e8c377-2b55-5522-b1c7-79630308f069 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
7378136a-227e-5ca5-b3ea-973d539f7c3e | note | • Anchor to be open and clean of debris.
2cce5180-9e36-5fa6-ad3a-12960324cff0 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
218f6e8f-6464-53fb-8ff2-c993bce8a696 | note | • Visual Inspection
fe7635e7-12a5-58fe-88f0-169f397358cc | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
89855936-c104-52d3-9ae7-f406c11233fe | note | • All Anchors
ac7c0fbb-16de-52fa-8d0c-225b8d13e5bc | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
d7478e24-e08b-580f-99e4-85a340a75dd8 | note | • W, R
40031843-f9fe-56e0-b760-221ff7373e9c | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
f8974acd-57c7-5c82-8f16-2fadfc9e97dd | note | • PE
f0718beb-3c24-5daf-ab2b-37e5ed7f9e5b | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
9cb75679-9c45-582f-9a30-535b4ee877fc | note | • Drill log/Anchor Install Check sheet, Video footage
d5e05520-e6c2-5a50-92eb-c6ffab1d62ed | checkpoint | 7.3. Install Anchor Tendon
d030f946-cd46-53bb-845c-e572b102ae58 | note | APPLICABLE STANDARD OR SPECIFICATION:
dc02220b-5b59-5e4e-b3e2-5299a3909efd | note | • MMA-DES-GEO-E1-DRG-4081
adeff8fa-6893-5717-9a4b-c732627587cc | note | • BS 8081:2015+A2:2018
0496b8c7-0cc8-5606-a86a-3d33295f49d3 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
ad16959f-a0ea-5183-872c-9c986a07e77d | note | • 11strand Anchor for North Anchor Block
f91b5c88-616a-5d69-9e10-241e65b21f6c | note | • 10strand anchor for South Anchor Block
3354f77f-ac93-5936-9b8c-07bef61836bf | note | • Anchors to be installed with fixed length and free length indicated on drawings. Centralisers (internal and external) should be in accordance with manufacturer’s instructions.
c1bf3969-bcf4-5c2c-83c4-42895f691e26 | note | • Anchors to be kept clean and free of any detritus materials. Anchor strand stick-out to be sufficient for wedge removal during future maintenance/re-stressing.
15697f23-09b7-5b97-b5af-e60c286b9737 | note | • Anchor corrosion protection in accordance with design drawings.
43666071-6870-51f0-a598-44a44cf60cb4 | note | • The anchor head shall be protected with a galvanised end cap, fixed to the bearing plate and filled with grease.
0de21082-e86f-5c15-b742-7905b82b8731 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
a3b7a33a-fb02-5c9b-964c-6b987b5aee92 | note | • Visual inspection
37f022bd-7611-5747-a1f7-5901868de2c1 | note | • MSQA Inspection
d59f08ba-f147-57b5-8a2e-4656f125c264 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
c0266762-d75d-5094-9c37-67b4faf9e786 | note | • All Anchors
15b87e7c-6eb2-5052-961c-1dd32b985056 | note | • One Anchor Per Block
5b04035b-0b7c-59b5-907a-a411975d254e | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
969bdf10-fe67-5d94-8218-6f61bc975539 | note | • W
b185fe54-749b-56cf-8f75-ea616383fc65 | note | • H
aa37b538-6bae-5aee-bf46-29c8ebbefded | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
28559f47-7550-5e89-8b8b-9ae9b64b15e7 | note | • PE
94fd321d-8f1a-5015-b7f7-70002eeb3804 | note | • MSQA/DSR
87af0cda-1e9f-5166-b764-6560d5ab172d | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
2e6bab53-3a6f-5f48-a363-f592a99bf104 | note | • Drilling log and Anchor install check sheet
2e5218f9-fef7-5ca7-88f3-124fda7b23c4 | note | • Site Report
2c278654-4b4f-555f-856b-c658af4e2510 | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
285705a3-4c7d-5a67-9b27-91b5c7cd3635 | checkpoint | 7.4. Place Stage 1 Grout
cfd5d6b2-5d25-559d-b101-b02cc8d7c4e5 | note | APPLICABLE STANDARD OR SPECIFICATION:
d9ccfc7a-850e-543d-aff7-1b32eb6cf5d9 | note | • MMA-DES-GEO-E1-DRG-4081
8a5b982a-205d-531a-a395-3fc2e970ee95 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
2daba3c6-44b2-5589-bc26-1ccb58744d54 | note | • Holes to be grouted within 3 hours of flushing hole/completion of drilling.
631221a1-0709-5345-8604-42291bef2d51 | note | • Confirm 10m Bond Length grouted and top of grout is behind anchor block.
51cc2083-34a1-5a0a-835e-f74d818ea09d | note | • Grout for anchorages to have 30 MPa compressive strength at 28 days and a maximum water/cement ratio of 0.45.
f6e35a24-3666-5f8e-b2aa-505427efd4e1 | note | • Grout shall not be used more than one hour after mixing.
c3968f41-c160-5fa3-89a2-cd4fcc482b09 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
9c2626c3-e7bc-54fa-94ab-f54120183447 | note | • MSQA Check
7d9245bc-bfed-5ad2-9b8f-39a0a4cc049d | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
b4ff0389-6088-5d6f-8df3-6c9c1da9e829 | note | • One Anchor per anchor block
8d935654-67dc-5a3b-8a81-54c64aa0f6c8 | note | • Take grout samples for each grout batch. Review laboratory documentation for all anchors
0bc609bb-0fdd-5971-ac72-f620f519d508 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
9b989be8-9847-5f57-964f-6e21d638d0e4 | note | • W
378cef99-2b3a-540f-9e63-6d7dba3faaa0 | note | • H
0e7f7dbe-bf07-5ffa-a16d-b08aa41477aa | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
bdd32e71-7359-547b-9b48-06f2ddf7b7dd | note | • MSQA/DSR
eb4d06fa-1ee2-51b9-8ea0-2759d456319f | note | • MSQA/DSR, Lab
ff5a0662-7e06-5a77-8522-cac2e7e8462c | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
378a9a58-2148-5ef1-981c-4d0a848712dd | note | • Anchor install check sheet
d9eb75a2-855a-5c0e-b379-37badb8142d8 | note | • Photographic evidence of grout pouring
ccc2c777-e386-51ee-8025-12031ec33797 | note | • Grout strength results
fa6057fe-f5c5-54ec-963e-38a1923cddef | note | • Site Report
f69f475d-e0e7-5cde-ad9e-2a2d9e961364 | checkpoint | 7.5. Stressing Jack Calibration
b13cc457-6418-5af4-899c-9e2f3eb2c6bb | note | APPLICABLE STANDARD OR SPECIFICATION:
d7cad1fb-9139-5a2f-ad0c-68f01dc3d6ea | note | • MMA-DES-GEO-E1-DRG-4081
67df6b19-334e-56a4-a1bb-d0e4ce5a4081 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
2c4ce277-193e-5c97-b7d8-9781c873255d | note | • All jacks and Pressure gauges used need to have current (within 12 months) calibration sheets.
89a5906e-f6fa-5418-ab9a-2629bc18bbaf | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
707340ff-c3f4-5d50-9091-a97d618d3a79 | note | • Contractor to get calibration sheets from sub-contractor
606df6f0-1adc-5958-a770-298fc210c086 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
686ce674-4c85-5423-aca4-0bb435c7a775 | note | • Once – prior to work starting
e0589f1d-d2f5-56d7-85af-6bc004a560cd | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
52e52f40-f0a7-5bc9-ad20-3d03cc6fe0a5 | note | • W
e9c22565-204a-5938-8a44-a10df4aea376 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
b0bce8de-00d0-56ca-bdd5-c8b9df61265d | note | • PE, Lab
b37f39bc-eba1-5d6d-bb33-5ba24c0fbc97 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
acabf496-9621-5f6f-b91a-c0e50a0d5952 | note | • Photo graphic evidence, Anchor install check sheet
5acb0ca1-0898-5a32-8e16-7991fc139ffc | checkpoint | 7.6. Smart Cell installation
c587e0f0-0df7-56b3-aeab-9de7e33ce9ea | note | APPLICABLE STANDARD OR SPECIFICATION:
41636209-9b21-5c37-8ceb-f80ae6797563 | note | • MMA-DES-GEO-E1-DRG-4081
b51ecf03-7be1-5f2e-b76d-fc9b194f4ac3 | note | • Manufacturer Instructions
7528b220-0abb-5b3a-8a8f-b2f537f87dea | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
ff75d6e3-dad9-57a7-b98d-001dd04be76b | note | • Need to be appropriately installed and calibrated.
77a646b8-defe-5d07-a66c-b1fed107335a | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
135bc391-c851-5155-84e3-6f6ab5dda88a | note | • Physical testing
5b6dbd0e-92f7-599d-9330-39f608d9ee08 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
72472d8d-6bd1-56f8-bd83-b65226d19a63 | note | • Prior to working and after pre-load
8bda275e-e5fb-57fa-b0b6-69ee10f9233e | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
309aa66c-d656-5f38-a49b-109ca669d2bc | note | • W
08928ec8-d72c-5c4a-ab29-5338cfffe03e | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
5c91c43a-150c-53ff-b021-62cfb705cfa6 | note | • PE, MSQA/DSR
6f3d67c5-be0e-51f2-9cfa-47086a0a11c0 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
f3d9636b-9d9b-566d-926e-e722ef9e9d61 | note | • Contractor records.
d172d617-0c02-5d9f-9d80-d6cb6496668a | note | • Site diary.
a4976a93-d71e-5574-ac39-ca6bd7bbc5f4 | checkpoint | 7.7. Stress and Lock off Anchor
5906d67b-db74-5030-924b-e7785fc513a7 | note | APPLICABLE STANDARD OR SPECIFICATION:
20b167d7-56e6-5821-8a52-98a5562f9f54 | note | • MMA-DES-GEO-E1-DRG-4081
7dee3307-8a96-5919-9af9-f296449ad657 | note | • ISO 22477-5:2018
b97ceb95-a716-5404-9026-e0a98a2fd661 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
3de7c8a3-aaf6-504a-bce1-e717932444e0 | note | • Confirm RC block concrete and anchor grout have achieved a strength of minimum 30 Mpa.
1c854980-d747-5deb-a7e4-9dff7408b35b | note | • All anchors shall be stressed and locked off at the lock off load shown on design drawing.
d1859baf-e3ef-5fe8-81b8-4ba521943633 | note | ○ Acceptance test Proof Loads:
e3105079-fea2-5529-baa8-a7eefb36d6e3 | note | – NAB -1500kN,
ff3528ad-3adf-51b8-aa57-3ed8ee14453b | note | – SAB – 1350kN
87171c6b-ffc8-572c-8b89-ddab3970c13d | note | ○ Anchor Lock off loads:
695e6527-c729-5eab-916c-2c1ce9cd095a | note | – NAB – 1350kN
95d00891-4484-5565-8f25-79b96b11ee5a | note | – SAB – 1230kN
3ed04603-4e2a-56ac-bf1f-0476a7112b61 | note | • All anchors to be acceptance tested in accordance with ISO 22477-5 and Table 2 of design drawing.
63b0dac1-6b15-55ab-890a-ccb1c6d82315 | note | • If anchors pass acceptance criteria on design drawing (displacement, creep, and apparent tendon free length) they can be locked off. If fail these criteria must inform Engineer immediately for instruction on how to proceed.
ad9051dd-ca79-526d-81fd-e5e65955a520 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
62b49a4b-5287-5cd0-9841-9559795f590e | note | • Visual Inspection, grout tests, stressing records.
4780e038-cdac-5fa1-b67b-eaec727e301c | note | • Acceptance test reports prepared in accordance with ISO 22477-5:2018 are to be provided to the designer's representative within 48 hours of completing each test. Results to be provided in electronic format, including raw data in .xls or similar format for ease of interrogation.
78d2b485-be50-5778-a8a3-7e11f2c83345 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
bc4eaa11-c6d6-56ed-a043-f74676da41a1 | note | • Each Pour by PE & One Acceptance Anchor per anchor block by MSQA
bcc9299f-82b3-543a-941a-8db0eb03759c | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
37593edc-5979-5039-b56f-35342c4d7d83 | note | • I, H
967783e4-b249-51a1-aa1d-34236ad160ff | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
b672ea79-c6a9-516e-89c0-a561b9f9dd4f | note | • PE, MSQA/DSR, Lab
b8311861-dba8-5897-8ff9-931068ee95d7 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
0eb6f617-0b62-5979-a99b-4742f4a887e0 | note | • Grout test Results
79cf509f-1ab9-56dc-98e3-7f9872d23e1a | note | • Stressing Acceptance Test
4f3b0a46-f968-50cb-82dc-231f6280c889 | note | • Stressing Record
643ead2d-aed9-5edb-a013-40314f3afd9d | note | • Anchor install check sheet
a8bf8ad9-7ecc-53fb-8e1e-a1d5ed2d48db | note | • Site Report
673fecfc-481c-5c32-94e8-b647aec8892e | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
c10a684b-92b2-53c4-89d6-31d297422dd6 | checkpoint | 7.8. Place Stage two grout
bbf7c506-da8a-5c80-abb6-3e42c4925cf1 | note | APPLICABLE STANDARD OR SPECIFICATION:
b8518063-fac5-5ec9-86ce-bea9a7653470 | note | • MMA-DES-GEO-E1-DRG-4081
6623cc7a-d7d7-519a-9b67-558b684b927a | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
62a79a77-60f5-5690-b865-223524faefe3 | note | • Grout for anchorages to have 30 MPa compressive strength at 28 days and a maximum water/cement ratio of 0.45.
ec11d289-5378-51d0-bb73-df2e47abab90 | note | • Grout shall not be used more than one hour after mixing.
51bdd483-e2f1-508c-a617-d24dce6cefa4 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
1d02b962-d66a-58dc-85b5-aa9c6cad3992 | note | • Visual Inspection - MSQA
a005cae9-5cc8-5b6f-9f30-af1744fdbb89 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
eed4cb44-e4be-5772-810d-623cbef249af | note | • One Anchor per anchor block
c381de70-8574-56ba-b087-3ac4f23d0813 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
25186918-2fa8-52bd-bd42-d6b82933f39c | note | • W, H
d64287c0-fa1a-5f25-9f01-d3e8298e775d | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
bf22cd46-6f72-52ce-a7c0-e809e516e914 | note | • MSQA/DSR, Lab
18c789c9-0215-5ccf-9840-f5cf2c2333f6 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
b3ea81cb-2545-553c-ad06-75bf4468dd2c | note | • Anchor install check sheet
3769a5e4-d7f9-55d9-bd53-06a66a210dfd | note | • Photographic Evidence of grout pouring
95f52c8c-6348-52c7-8e72-cf8f436eef3f | note | • Grout test results
eab18c75-2cc8-5315-9d6f-a9363ec71237 | note | • Site Report
f2c2b06d-4f5e-59bb-810f-04fd5ad96157 | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
078e7feb-86c9-5623-8d36-5b0db7e78c6e | checkpoint | 7.9. Finishing Works
21c60541-38e0-5569-823a-ba2f2d87a121 | note | APPLICABLE STANDARD OR SPECIFICATION:
26ba656c-5977-5a71-817d-f12ec653efb7 | note | • MMA-DES-GEO-E1-DRG-4081
a4d50a92-e93e-5bf2-b415-abc4ae5a3f2e | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
27bfc3da-c26d-5acd-aded-7dcdce3226b5 | note | • Install Rubber Gasket
1d432c2c-016e-58e2-94de-75e4d09fdb46 | note | • Strand to be left (100mm or more) as advised by contractor beyond anchor head to allow for wedge withdrawal and future re-stressing.
c3be627f-70b3-571c-8ddf-f29d6e0a12d8 | note | • Top Cap (HDG) Installed and Packed with Grease
484a31fb-3960-5f27-abc7-8993a7df516a | note | • Bearing Plate and anchor head detail to be in accordance with drawings.
e04409eb-4522-5a96-82dc-776499944d34 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
f34872d6-2b77-5f5d-b885-108dcc56c8c5 | note | • Visual Inspection
6d5a3526-3317-5c56-bb03-fac39f291c37 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
8a2711a4-024b-57fd-ac09-29cf6ad9f6fb | note | • All Anchors
08890ef9-298d-57d9-881a-d59de240404a | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
6a48b1e0-9780-5d01-b8b5-0688efa6154c | note | • W
89d411c8-30d3-59c9-9d43-5a6ab372a798 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
fe128b84-d8da-5f70-9c1e-1cdc23f0216e | note | • PE
ad2a9973-0231-55f0-97a3-d45531c1d6a5 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
fbfa9864-a7c2-5e8a-9c54-b8a8bb5486f1 | note | • Mill Certs for Plate
ae743f65-9b88-5edf-b4fa-cee3304b7b6e | note | • Anchor install check sheet
06c72694-5e8c-572b-a53a-d95e70a18592 | section | Structures - Structural Steelwork Fabrication and Erection (Drive Station Shelter Building and Tower Footings)
27ca9f99-86d0-5e46-9245-b89bb84dfca4 | checkpoint | 8.1. Weld Inspections
ba33134b-b330-5492-8650-4e42ead6ce9f | note | APPLICABLE STANDARD OR SPECIFICATION:
29616399-4a00-5a73-8581-9bbdf440b7c6 | note | • Structural Steel Work Specification, AS/NZS 1554.1
03643554-676c-5ac7-87f8-748ff4d630e2 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
cfe2939b-2a3d-5a28-8d28-095353e8f7c1 | note | • 100% Visual Inspection
9d941a0f-4d8d-519c-bfd2-3479cecf7c0c | note | • 100% Visual Examination
ef012016-c7f9-5899-b8b6-791affe790df | note | • 100% NDT (Ultrasonic or Radiographic Inspection) for butt welds
fa07419d-91e2-5a7b-b551-dc7d95ed8911 | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
1dad4487-b85e-5885-be19-770297a4d7b0 | note | • Visual Inspection/NDT
78ed558d-02b9-5cc7-9227-e62fdcdf1532 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
1d1b87d0-0ff9-50e1-8df1-d61f4dae2581 | note | • All welds
07c44b9c-3c41-550a-8131-44171d43db32 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
18e89607-1e21-5715-8620-65f18b8be1ef | note | • I
919f1b09-4615-5d3b-bb0f-74fc7ea020a7 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
7bb37fc5-ba5f-5e5d-b53f-9ea9cfd3ba23 | note | • PE
f90eb9f2-4cfb-546c-b44e-7a1aaaff8e75 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
42873eef-4ffb-5c35-9a10-50a4f5263668 | note | • Weld Inspection Report
bf91f9ac-29be-5471-8fa5-e44b23b5956d | checkpoint | 8.2. Weld Inspector
51362cac-edcc-5f3c-a9ac-f7f7e1232613 | note | APPLICABLE STANDARD OR SPECIFICATION:
f098dd26-72ca-51a0-9c27-29b3aeb6f1a3 | note | • Structural Steel Work Specification, AS/NZS 1554.1
0d7abdd0-1ce1-569b-9bde-708db5726aad | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
536bc3d0-5f13-57a1-a2ea-e135124e584d | note | • Weld Inspector to be independent of Fabricator
ff5cec3e-1f84-5e68-8011-8a0b0a8341fa | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
aaed8b71-a89c-56a4-82a0-4bf9b381431e | note | • Review of Qualifications
0b609d6a-dba1-5ca6-bc60-303f8f159705 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
ed036ab5-e9b3-5e59-8345-3089bc3802f5 | note | • Once
3d7104cd-9c89-5f98-a48e-bf3a34f6b04f | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
fe75674c-c24e-59bb-a9ad-6fc722a3c261 | note | • R
8b5b11be-d0a0-558e-b4dc-67540044f5a4 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
2d7065e5-d908-5878-92a1-2690af579243 | note | • PE, MSQA/DSR
2bf45c07-34cf-5a15-a8d5-c5b842afb4f5 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
7e31d082-d1ab-5ca9-b8fd-174e49b78e47 | note | • Inspectors qualifications/Certification
049dfc3e-0354-5442-9e53-f12d9df08b6e | checkpoint | 8.3. Shear Studs
af7e38e8-35e4-5e4c-9167-0e82438fe4b3 | note | APPLICABLE STANDARD OR SPECIFICATION:
880f7036-4f2e-528b-8585-4a9494c6052b | note | • Structural Steel Work Specification, AS/NZS 1554.2
0e16f785-688a-5979-844c-037c8e075dff | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
d6b639ca-af94-5e71-b696-0198c4fc4572 | note | • All studs to be ring tested in accordance with AS/NZS 1554.2
a49baf49-ec5b-5658-a536-7b98311d3224 | note | • Any studs that fail the ring test to be bend tested in accordance with AS/NZS 1554.2
d3fb0851-fb1e-5953-8ecf-472c9545f175 | note | • Bend tests to be performed on 1st and 2nd Stud from production run followed by 1 in 50 there after
45fb79ba-79a6-5406-a6c0-3e9b7bb290ac | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
ecfaaf52-669b-5d58-826a-cdf597b570b7 | note | • Bend/Ring Test
3f3260dc-d5d1-5bea-bf8b-5b1fa8fb6828 | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
bc875b9c-30a7-5d0d-a538-d40fee723d73 | note | • Ring Test all
87833d64-7573-59ab-ac24-f4bca4faee54 | note | • Bend test 1st and 2nd, 1/50 and then as required
989c6a7e-0d4f-5bd0-ab35-e9ae8184230b | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
8614e4ea-4fab-5657-88c0-0d6bbfc900a9 | note | • I
2001407d-e59e-5cef-8d54-a30f0918cf72 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
66c01beb-7341-51be-9e50-810186ffe5ec | note | • PE
c27ae4aa-7ace-5ebc-b38d-bdb728bb0289 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
c9ec53a3-c707-5a36-89fb-9f4ec07ebd69 | note | • Test Report
82735c26-e4ca-500b-87fe-590f226d5025 | checkpoint | 8.4. Inspection of Bolted Connections
ec93ce4a-1885-5af1-b394-c52cfafccbcd | note | APPLICABLE STANDARD OR SPECIFICATION:
d766a913-1736-5401-9d10-a683da132b0d | note | • Structural Steelwork Specification, AS/NZS 5131
f365f078-5c85-51fd-9047-d6391f374cee | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
7c8b58f4-06a0-5b5c-a7f5-994cc72d02b3 | note | • Designer/DSR to inspect min 10% of bolted connections
862c36a4-7f93-5c7c-a296-915bd8c49faa | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
15f6b036-abba-5f4d-bbce-272cd8225a50 | note | • Visual Inspection
a5930786-1323-5d61-908f-fb749c542cfd | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
504e92a3-bf88-531c-aeaa-faa2afa95e5d | note | • Minimum 10% but no fewer than 2 per connection
84c8e556-898b-5a5b-97d9-6f5c247ac4be | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
29dcb543-c5d0-5768-80af-a09f85e2b932 | note | • I, H
c5fdbd7e-a1ff-5143-b1a3-8037fbcb2a75 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
8b62a166-4173-5f0e-9723-9acf1a6a3773 | note | • PE, MSQA/DSR
4b3b6245-e8da-5404-89cd-2df87434c6d9 | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
d65f5e5e-af22-5226-858b-e027a3ed6bc2 | note | • DSR Inspection
b214ef54-3cfa-5826-b44d-3c4e60b19ab4 | checkpoint | 8.5. Inspection of Fabricated/Erected Steel Work
6cf27208-0f22-5b3b-bd83-b73e37abd4cb | note | APPLICABLE STANDARD OR SPECIFICATION:
5badd6b2-357b-5424-be4e-26c3089384a3 | note | • Structural Steel Work Specification, AS/NZS 5131
27764164-59ba-527b-9e4a-9e0c3f38a776 | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
7fada03c-f191-5c9d-9fd3-d5b5ffd07c13 | note | • Designer/DSR to inspect fabricated steel work
7bd67302-88c9-57c6-93b4-8c9a07f1ea9d | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
9bc0dfb8-3a79-5905-8937-073462e4629e | note | • Visual Inspection
2862460f-6615-584b-a674-3c471fec9d9c | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
120503d1-8084-5e0c-9e83-3f0b0cfef51b | note | • Per Element
b0de2df8-7e01-58ac-a71d-2ba4e0f2811f | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
57c3d65b-10cd-5ace-9b1c-a296d02e3a33 | note | • I, H
50c8b810-b818-5258-9e36-41eee8503b32 | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
b3c714eb-4657-51f4-92ee-d67da24e249c | note | • PE, MSQA/DSR
f89b1150-13e4-5c8d-910d-af87707f4baa | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
1dbc3972-f751-56af-a505-1609c9a82e42 | note | • DSR Inspection
72dafa94-a893-58c1-a85f-ddf3aecbde8d | checkpoint | Completion Verification
c7a84e57-84b4-5814-be7b-1eb68a616f55 | note | Work under this ITP has been Certified complete by:
e6f51531-700f-5aad-8a9b-7d0b7a0ed105 | textbox | Name:
9515b7c7-2d95-57bb-837a-4ab02bcb92f0 | textbox | Date:
55ad0b7c-ea15-57be-8f79-cfbb9b951cff | note | Reviewed by [as applicable]
264c0f64-8419-5254-bd37-d741f5f21c4c | textbox | Name:
a6ace094-bbec-5f6c-96f6-55b441411afa | textbox | Date:
d0d2fe25-b83d-5222-9413-d7d0836ea8fd | note | Reviewed by [as applicable]
c368c579-e632-5c5c-803b-ca915f223ff1 | textbox | Name:
b654b67e-a819-5afd-b5fa-cdef1b467410 | textbox | Date:
d7341bb1-1a59-5932-9451-25105159d29c | note | Approved by [as applicable]
33c84292-cfca-57e0-97dd-f5807986ed1f | textbox | Name:
dd952e5b-5f8e-541a-9e18-33c62baada87 | textbox | Date:
81d87bce-98da-4469-b286-398b9f1307a1 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
8ce50c3b-0d40-4916-8e32-12d6f61f8be6 | checkpoint | ITP Close-Out by
942f7a88-6405-5b92-85c4-a097be0157fb | note | Site Engineer/Project Engineer
84a6be8c-48a0-5a7b-87a5-82806ad7aced | note | Zone Manager Approval
3b3d6723-cc2c-5e38-8d25-ee42b5af18b4 | note | Construction Manager Approval
37f0ff8e-13a1-522f-8999-0575e01802e0 | note | Quality Manager Approval
e910a340-62ca-5f95-b851-85987ad22d0d | date | Date:
be4ab67d-488e-4ff9-ab66-6d46a88faff8 | signoff | SIGNATURE
b1599de8-3ca7-5ba5-a826-6545006121cd | checklist | ITP-003 - Subsoil Drainage Install | itp | ITP-003 - Subsoil Drainage Install
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
840d7178-b03e-537c-b111-82e872a14b9c | checkpoint | 1.01 - Confirm Method Statement Signed off
411bd5c4-b550-5426-8642-6e9d38cedd5a | note | Method/Description - Document Review
f6ff0115-1f4c-5d65-84e0-4a72c28bf9ca | note | Test frequency - Prior to Work, Once
b9764723-8ab4-5c67-9161-c65c2a44bca2 | note | Contractor - H
a3fc211d-6b84-5b39-a13a-b983ebbf904c | note | Designer - H
7e6343fc-ee4e-526f-9ad7-299d1c34eb9b | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Copy of Method Statement
42bc0245-639c-57f9-9f09-8f12305c24ce | signoff | AUTHORITY HOLDPOINT
5c8b235a-89c6-5bc2-95c3-af3747fcf89a | checkpoint | 1.02 - Confirm Compliance against Resource Consent & Management Plans
420fd7b7-423b-5959-993b-c73d42531c56 | note | Method/Description - Document Review
c0e5bc45-3814-5ff4-8b3b-a565b622cff6 | note | Test frequency - Prior to Work, Once
8bc82449-2207-5d7a-96f3-793f9ca06ac7 | note | Contractor - H
ee6e2cd8-d98a-5e50-8c59-1804da061700 | note | Designer - H
d9d381ec-bfa8-5bee-899c-969666ee4ecb | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Management Plans, Approved SCWMP and Approved CWP
80f44c70-59d0-5d07-bf6f-65b719d78da8 | signoff | AUTHORITY HOLDPOINT
a7abe052-25a4-5b64-9ac8-d2d5e962d5e3 | checkpoint | 1.03 - Confirm IFC Design is in place
5cbb18ad-918d-5405-baf8-81fe5da2b49a | note | Method/Description - Document Review
44f5de07-bec1-5e35-9c1d-3dbfd9464002 | note | Test frequency - Prior to Work, Once
3e53d722-fa25-56af-a398-678a5682fc0e | note | Designer - H
52e4814e-6fe0-54f8-8f1f-0538178473a1 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings Issued
124b501d-73e4-53df-a8f5-6b9175b379e6 | signoff | AUTHORITY HOLDPOINT
3e4ca7a6-fdcd-5bc0-9f74-9e85ab2206e0 | checkpoint | 1.04 - Complete Permit To Dig
6c102f09-b37e-5afb-9f26-f77c2b9aaf0b | note | Method/Description - Document Production
7fa5eb99-b91d-5ad4-a556-531062f8850e | note | Test frequency - All Excavation works
e699e163-c0cf-5681-8f18-b79553cb4f80 | note | Contractor - H
22edda1f-88cd-53b8-aea5-1fcfe52e7623 | note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Dig Form
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
e86f10e9-8b19-553f-804e-38c741e160bf | checkpoint | 2.01 - Order Subsoil Pipes
af305bec-6dca-5765-b4f2-db988afa71b5 | note | Method/Description - Ensure Pipes are ordered as per drawing
58b89afa-b730-5c29-8e64-326ba59444aa | note | Test frequency - All Subsoils
aaf13ecc-db2a-5c90-b8f9-81bdf5689aee | note | Contractor - R, I
4c61e2ae-16c6-515a-ae67-2009a7fad8cd | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Material Complaince Certifcate/Data Sheets, Material Delivery Inspection Checksheet
c73d4d38-f592-5050-beca-bb24f088b3c2 | checkpoint | 2.02 - Order Geotextile Material
89d6f497-7bfc-594c-8eb7-f5bf197f03de | note | Method/Description - Document Review
ed503d8c-d3ee-56a7-95a4-7d45becbd6f0 | note | Test frequency - All Geotextiles
6dab2856-732b-5149-bb06-32b809f5eebd | note | Contractor - R, I
f6b1b5ff-c92c-5653-ab33-115f67ed0fb4 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Complaince Certifcate/Data Sheets, Delivery Dockets
ab193b17-ff99-5108-8392-edbe34f38cb4 | checkpoint | 2.03 - Order Subsoil Drainage Backfill Material
622bff40-4a90-54e1-ac66-8edb6738428f | note | Method/Description - Laboratory Testing
c03b408a-b9c9-5dde-a71e-959b63c50f10 | note | Test frequency - All Material
6e3b59f8-2e8a-5963-b6e3-3d0ed4beccf3 | note | Contractor - R
fffe0c0f-4766-5f30-bcb7-3d94a3257e7b | note | Designer - H
06f57223-d4a2-5114-841e-5138808b0dbf | note | Lab - R
31c62d6a-1468-5b2c-a597-e96682946414 | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Results, Permeability Test Results, Crushing Resistance Test, RFI - Confirmation of Material acceptance from Designers
a40a5658-bcec-5b25-9610-992d44c8435f | signoff | AUTHORITY HOLDPOINT
a60c08ec-043a-5ac7-968a-e6a03c1faea3 | checkpoint | 2.04 - Order FarmBoss Pipes (Temporary Drainage)
30bbcc20-5408-5d2e-bbb9-6a5cc69851f3 | note | Method/Description - Document Review, Material Delivery Inspection
097d041c-1f47-517b-ba4d-56ce9da6c904 | note | Test frequency - All Pipe
54e4c6d4-86dc-5dc4-8573-38697687ca70 | note | Contractor - R, I
b2774fba-4484-5c97-9af9-b270674f6e74 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Docket, Material Delivery Inspection Checksheet
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
3e503167-dfec-5627-8b25-d5091f7b1f38 | checkpoint | 3.01 - Clearing and Stripping of Area
54a0b372-b788-5f8c-8fd7-89a9b8adf917 | note | Note: Fill 12 and 13 are exempt from Organic Waste Clearing and Stripping when >5m from finished ground level
7eba61e1-a678-5b88-9a49-d2db0087350f | note | Method/Description - Removal of Organic Material
bdb87169-5d7d-5d33-8552-99ef9253825d | note | Test frequency - All areas. Subsoil Checklist completed for every independent section and minimum 100m length.
8d14f524-c053-58df-8c51-56f43d393668 | note | Contractor - I
cce81a3b-409a-51fc-9e95-83e31b1880d2 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
3ffb03be-3168-5ad5-a602-7618f3bca33c | checkpoint | 3.02 - Formation Level Inspection
f3036a5d-b13c-5a63-88a3-3ad0e220544f | note | Method/Description - Visual
73ba8bc8-6bab-599d-880a-2e0ac03881d2 | note | Test frequency - At formation level before installing the geotextile. First section of pipe and then once every 50 m of pipe laid.
c5c8c29f-0e83-5d1a-bd36-890b925bcb8a | note | Contractor - H
12b260a7-1688-5966-a01b-82021a9ef5d8 | note | Designer - H
908813d1-8520-5971-8f63-9195c1247d12 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
264dba25-731d-5ed7-a78b-a7a629fa9437 | signoff | AUTHORITY HOLDPOINT
a6f1c758-656b-5240-862b-c139a4e5de79 | checkpoint | 3.03 - Lay Geotextile (BIDIM A29)
b0109de6-b404-5c76-83d0-ee683c2dfc73 | note | Method/Description - Inspection
8a80bde1-54b6-543b-b6c2-cda6cba54adf | note | Test frequency - All BIDIM. Subsoil Checklist completed for every independent section and minimum 100m length.
24ab384e-d96a-5aee-8fd9-df1dbc3afed3 | note | Contractor - H
ebdc72b7-9bbb-5a3d-a0bd-4a4bcb2818a5 | note | Designer - R
21353ae2-3c95-5f46-a40e-3f9a08d0b24a | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
64925617-a85a-5a43-bba0-7650792c7468 | checkpoint | 3.04 - Install Bedding Material for Subsoil
b1b5b860-f0e8-59d4-8346-be74e228a313 | note | Method/Description - Inspection
1932a309-a32e-55fc-93d9-935909f265bb | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
b5aa431b-d802-58d1-9bbb-f308f7575c4f | note | Contractor - I
9d45cff1-e3db-556c-af76-eccfe60a67a3 | note | Designer - R
a401c1cf-1d25-578f-a88d-dddeb91d97c4 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
48dfe27e-ff7a-521b-bae5-f5f55a05dd96 | checkpoint | 3.05 - Install Main Gully Subsoil
d93d3077-04f3-546b-b3be-ac4b4e79bcd9 | note | Method/Description - Inspection
674c2c76-db0e-5354-9d19-d1bba290b267 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
70ae588f-5643-5ac0-b22f-66abfa02029d | note | Contractor - I
6726ff69-0b15-5532-9c98-d9bc9e2801b3 | note | Designer - I
def36970-6afd-5238-9837-484c1143cf7b | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
90d6e7a1-cbd8-5795-bbe8-f63561ce30fc | checkpoint | 3.06 - Install 450mm FarmBoss (temporary Additional Drainage)
8b8f3e16-dd01-5675-92a4-435fab8755d0 | note | Method/Description - Inspection
8fbebcb2-31f7-5f10-b82e-ddee47f53f77 | note | Test frequency - All FarmBoss. Subsoil Checklist completed for every independent section and minimum 100m length.
6dfe1a21-1962-5a75-b326-ae092497b44c | note | Contractor - I
aed160f8-f5ac-58c1-a9fd-a2328f4a380a | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
4a8e29a9-6a51-5d0b-a0ba-a0530485b2f3 | checkpoint | 3.07 - Install Backfill Material
b4e7f7da-0ff1-5759-9d07-6a0864cfeec3 | note | Method/Description - Inspection
4b40a2a4-a5b6-5991-bf26-b9638cf60226 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
95d1b2f7-f730-57c0-9193-1e90daff09ff | note | Contractor - I
a058d4fd-902f-543e-a36c-8526c32e317e | note | Designer - R
41c9c328-47f6-593f-8583-164ac40798a2 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
c04adb27-0b59-522b-aa33-a966e3353cf0 | checkpoint | 3.08 - Install Vertical Subsoils and Connections
70d540f5-3674-5eb4-9939-8a266b433505 | note | Method/Description - Inspection
3025783b-2ad7-52b3-b7d8-46663eff93c3 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
593fd4d7-8d4c-5b1a-854f-d31948c4321e | note | Contractor - I
b0b52af5-2717-5265-adcb-6f49bfc656a4 | note | Designer - R
026816eb-1786-5f1e-961b-799c1ca2c9aa | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
a91430d2-3995-5e25-9013-6a3786f37df3 | checkpoint | 3.09 - Install Additional Vertical Subsoils
f73c7e64-4c1d-577d-8897-de04a5088be1 | note | Method/Description - Inspection
b698bbae-bbee-51e0-a8d4-9e6765faddd9 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
4bbb6a7d-4a4e-55e4-a0cd-1800f317b7d1 | note | Contractor - I
e6260eb6-b8f2-5558-8c53-26626c1ca0a2 | note | Designer - R
da5d75ec-f13e-5505-ba75-0d4508d09075 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs, As built, Formal correspondence
e938a91e-74a1-5e8d-a2f9-7fc1fe37cb86 | checkpoint | 3.10 - Wrap Geotextile
b951fc49-e9bb-5569-a949-395e600ee30a | note | Method/Description - Inspection
1c01c10c-9fa7-58ab-8b6b-3fb8505c1baa | note | Test frequency - All Geotextiles. Subsoil Checklist completed for every independent section and minimum 100m length.
8a4e6575-67ed-5e13-9a2a-850167260611 | note | Contractor - I
e073d395-68ca-51a8-8020-9c1788f97bb9 | note | Designer - R
f54484f6-89d0-5be0-90bd-3c34df2a0802 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
fae5e183-4e7a-5bc3-a094-f921f788ef4c | checkpoint | 3.11 - Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top
14bcfb28-8ee2-59d4-98f6-b3db43730e62 | note | Method/Description - Inspection
1860d7b7-3a54-5c3c-85ba-ecb2572989b9 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
dfea8ab4-fa9e-50fa-b290-3ce40295a690 | note | Contractor - I
d31434ef-14ff-5ac1-8c82-8d3cddfb7331 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
f761d223-9345-5a5d-b40f-3a06946049ac | checkpoint | 3.12 - Construct Outlet structures
5339cc5e-3443-5fec-bdd4-21e0f10d5a58 | note | Method/Description - Inspection
668a31e4-9a76-5145-8e78-0956646d97a8 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
78b9c36b-690c-5484-b0a6-77e3f0dc8fcc | note | Contractor - I
d6830253-1bb1-55e1-9676-884360d4f7bc | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
d2ef6b17-bd1e-5c35-a60f-ec686fb1ab1f | checkpoint | 4.01 - Completion of works
f02a4548-7e0b-51e6-a9f6-074e47f3d4c0 | note | Method/Description - Inspection
5cd33b37-6710-54c6-ad63-77e8e0294792 | note | Test frequency - All Subsoils
a0972601-b0f8-5893-800a-3405c5695e7f | note | Contractor - I
a7e369d4-7517-5cb4-953c-c8ee47bd25ca | note | Designer - R
3d4b2ee6-962e-5c38-9871-4f195c3114c3 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
5b8df720-9ca7-5ae8-a81d-997056d6c93b | checkpoint | 4.02 - Provide Maintenance and Inspection Report/As Built
cb221f93-58c1-52bc-8de9-adf7abe7dea6 | note | Method/Description - Maintenance and Inspection Report Completed
d7776e28-748f-5c55-bf04-2ececb274d93 | note | Test frequency - All Subsoils
d00a9801-7a1c-5d96-9a3b-1d01d832ceaf | note | Contractor - I
92feb325-2ac3-5e68-a22c-4ee3742ece37 | note | Designer - R
5ef0b631-7bc9-56bc-b929-46845b742467 | note | Verifying Records Checklists, Test and Supplier Certificates - As Built Plan, Redline markup
8988577b-06e3-4c5d-9434-98f4aebf6eca | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
402ed04b-d3fb-4805-9a36-1177bc9a14d4 | checkpoint | ITP Close-Out by
e1e42af9-f86d-5090-a5bd-50acb3197df0 | note | Site Engineer/Project Engineer
2a0b6b1a-c907-51b8-9a6f-01ae00f8e18f | note | Zone Manager Approval
692dfc8c-9271-52cb-9fb5-ce622485fadb | note | Construction Manager Approval
43aa297f-a844-5361-a200-b59af1c0399f | note | Quality Manager Approval
21047857-ddf6-521e-8c09-5675d752b655 | date | Date:
e7c888e3-5a81-409d-9492-92845afb5d32 | signoff | SIGNATURE
ec2ced02-0cc8-5290-961d-23702c6b21cb | checklist | ITP-006 - Temporary Culverts Installation | itp | ITP-006 - Temporary Culverts Installation
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
25cb42ef-7d50-5dca-89f5-4c29a78ce685 | checkpoint | 1.01 - Confirm CWP Signed off
8bcca5d2-2976-5a23-b405-c6d60403e2c7 | note | Method/Description - Document Review
596fcf40-f136-57c5-b157-a2026b0750f5 | note | Test frequency - Prior to Work
914272b8-2591-57ba-8b32-66cbde1c092d | note | Contractor - H
ce7bd977-6308-5ba0-8caa-bcb8124f28fe | note | Hynds - H
5cd0f26c-3486-5983-a10b-64ebfe083bb7 | note | Client - H
a70b1538-7ab2-5367-b91b-fbad9a2c2b0b | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Copy of Method Statement
90528568-7dbb-505b-b32d-75da79ee0256 | signoff | AUTHORITY HOLDPOINT
5c8b235a-89c6-5bc2-95c3-af3747fcf89a | checkpoint | 1.02 - Confirm Compliance against Resource Consent & Management Plans
34056558-ffa0-5201-9cbe-64991ed1eee5 | note | Method/Description - Document Review
960eba53-f532-5268-8712-6315c1f919c3 | note | Test frequency - Prior to Work
476a2b2a-cca6-5fe4-9472-b248f2e1ecc0 | note | Contractor - H
5d933087-1e33-57c8-9f59-ea2d8a93b731 | note | Hynds - H
08ecf120-7547-5d3e-9034-0795223f7415 | note | Client - H
2c0d4747-0a14-50bd-9c2d-5f8abe5c4780 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Management Plans, Approved SCWMP and Approved CWP
80f44c70-59d0-5d07-bf6f-65b719d78da8 | signoff | AUTHORITY HOLDPOINT
5e649741-08e8-53d7-90e2-13e62ad83986 | checkpoint | 1.03 - Confirm Design is in place
3fa3020d-d5fa-595b-8997-cbc3df6ab9a2 | note | Method/Description - Document Review
b55513d7-aff4-5d1b-b59f-448213c77dd9 | note | Test frequency - Prior to Work
270616d9-4f18-5544-8286-f403e79e2939 | note | Contractor - H
ace7769b-523d-51fd-822e-b72ceeef6121 | note | Hynds - R
f29e2e19-05a2-5629-a09d-20cc11a5c036 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings
3e4ca7a6-fdcd-5bc0-9f74-9e85ab2206e0 | checkpoint | 1.04 - Complete Permit To Dig
af02e228-acc9-54cf-9a3e-36242cec0f72 | note | Method/Description - Document Production
1f54f34e-5794-5d1a-bd82-926f0c86727c | note | Test frequency - Prior to all Excavation works
6d47b75e-8b10-57e6-bbef-dc38a33cad7a | note | Contractor - H
6150d923-7e62-5da7-ba68-907c67f93212 | note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Dig Form
ed3b9c61-8190-5c6b-bc78-3deea876281e | checkpoint | 1.05 - Survey
9730b2b4-d46c-5e42-a1ae-692deef46d6e | note | Method/Description - Record inlet and outlet heights for the stream diversion. Mark out scope of works
4d07a43d-8960-5c0e-b316-015a3e30f74a | note | Test frequency - Prior to Work
5309efbf-ad8b-5a9a-99a7-38d6467979c8 | note | Contractor - H
152f6c24-ecfe-5867-8f14-ad95ef1b88f1 | note | Hynds - R
223ffcb4-c380-5273-b0c5-44d06cace32f | note | Verifying Records Checklists, Test and Supplier Certificates - Survey Heights, Survey Mark-out
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
276596e5-622f-540a-b5fb-f058d6208be7 | checkpoint | 2.01 - PKS pipe (1400mm, 900mm & 800mm)
b06cb1e0-db13-5f81-b7cc-421395cfedb4 | note | Method/Description - Document Review
2de5d1f6-0b15-552b-9ae9-c60845cc3631 | note | Test frequency - All PKS pipes
271ef182-0804-5ac6-a12d-4e5c7b25e43c | note | Contractor - R
1e0c9aea-6f5a-5eea-b0d1-05f17118606e | note | Lab - H
dc5630ab-1c5c-564d-88fd-b67809ac8e65 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Lab Tests
2b0c4440-9e92-590b-8648-3562a3bdd6ac | signoff | AUTHORITY HOLDPOINT
437e53b9-8816-57a5-8687-f2b95e8eadd2 | checkpoint | 2.02 - PKS pipe fittings
f932ecbc-b8ee-5dd0-9a4c-7c567961ab1a | note | Method/Description - Document Review
dfbe90df-f533-5e42-a64b-e3f461674ef4 | note | Test frequency - All Fittings
83fd9542-eb46-5a0c-b6a9-0b911ecdc1d5 | note | Contractor - R
c374d92e-68f5-52a4-97cd-cc5468747a9c | note | Lab - H
603d3e25-09ff-5064-8c8c-ee2ec0a80ccb | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Lab Tests
c5f6844e-e2c3-5736-b591-d9b8a313842e | signoff | AUTHORITY HOLDPOINT
f0fafa0a-7d8b-52d3-a270-8e95cd73cf98 | checkpoint | 2.03 - Subsoil Pipe
1e2c4e12-4456-54ca-98ce-23e9afca0bd4 | note | Method/Description - Ensure Pipes are ordered as per drawing
df6de802-7bb9-50a9-8aa6-8d422b96aba7 | note | Test frequency - All Subsoils
37113ea6-9d63-5b69-9d08-41fe777895f4 | note | Contractor - R, I
a0d873da-bb0f-51c7-8c75-c371e5c812a7 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
18fcaed8-c292-5c18-b5e2-81222a052df4 | checkpoint | 2.05 - Geotextile
6abcee02-d71e-5353-9406-568821dc632d | note | Method/Description - Document Review
232e368e-b197-5f21-8168-2b48ba57e51b | note | Test frequency - All Geotextiles
b11614e8-3f0a-56f2-86b2-de669b5e7fc2 | note | Contractor - R, I
7b82b63b-2b35-561f-940e-4592ea2aa393 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
1c4ee408-b787-5f05-9623-9c6acb31d725 | checkpoint | 2.06 - Drainage aggregate
df6c7a2a-83f2-5829-9495-8dd85be80236 | note | Method/Description - Laboratory Testing
cdaaf44a-989d-5b0f-ae69-7240c3d030b4 | note | Test frequency - Embedment material
f58b17e0-177b-551c-9062-be0282493020 | note | Contractor - R
c099be62-f1b1-54bc-9c86-bc290562861e | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Results, Crushing Resistance Test, Confirmation of Material acceptance from Designers
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
3212d783-a144-5989-a497-6dc108eb26ac | checkpoint | 3.01 - Trench for PKS
3977f772-33d4-57e6-90b8-2feb495543bd | note | Method/Description - Inspection
e8a5eb11-0157-5a7a-8fba-cdf5b9fdcb59 | note | Test frequency - Prior to BIDIM installation
0d032c5e-9f49-589e-b2cb-52b52f4b433f | note | Contractor - I
20752364-a489-58c8-bc4f-5a04546530b4 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
aa967d00-f53d-5a11-aac7-dac3cb7ed00a | checkpoint | 3.02 - Insitu subgrade (foundation) Compliance
a8c0c653-f9d9-5249-9319-bfd0314824ee | note | Method/Description - Inspection
d3ba65cc-f58a-5014-9287-8ada3d77f468 | note | Test frequency - Checksheet filled in for every 100m section of drainage
4c222a4a-3879-512c-b4f2-6f94eba25e25 | note | Contractor - I
70fbe8e1-f018-5077-8251-bae2e11936cb | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
a6f1c758-656b-5240-862b-c139a4e5de79 | checkpoint | 3.03 - Lay Geotextile (BIDIM A29)
ebe45091-9fd6-522b-a2be-340c1bc986f1 | note | Method/Description - Inspection
bead50f6-cbb5-5b7e-8a8e-80b8190fa3e1 | note | Test frequency - Checksheet filled in for every 100m section of drainage
84d60d6e-d840-5b67-bb17-03d3c2d37533 | note | Contractor - I
f2c15657-8d2f-5f98-98ec-3739dee09921 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
49eaf908-2e12-581f-a669-34aeaf41b1ee | checkpoint | 3.04 - Install Bedding Material
3052fcf5-adac-5953-94fe-08aee1b89c9a | note | Method/Description - Inspection
8aa7b042-497a-5f83-84fc-56f7c3d1d02c | note | Test frequency - Checksheet filled in for every 100m section of drainage
9067b1fc-854b-53f7-bc24-12544cbb1ada | note | Contractor - I
6f7a9cd3-1457-536c-84c2-a59272032605 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
58e93f70-4a80-5048-aca7-98b095e4b403 | checkpoint | 3.05 - Survey pick up location and heights
040d3231-b354-5c54-9ce1-8a3565693a52 | note | Method/Description - Survey pick up
fa1e1bdc-a7c8-51c8-b34b-c0d3cebcc5bf | note | Test frequency - Picked up location minimum every 100m
aefefd22-5e33-55cb-9e46-25743eaee2a0 | note | Contractor - H
02914537-456f-5a3a-9ef0-03e65e99b61b | note | Verifying Records Checklists, Test and Supplier Certificates - Survey record
20ab2a1c-5777-58bb-b116-74a612dcf678 | checkpoint | 3.06 - Install PKS pipe
abf8ce50-12bd-500e-aeb4-df6600783a89 | note | Method/Description - Inspection
244d6350-dbfb-57e3-9156-80d9806181ee | note | Test frequency - Checksheet filled in for every 100m section of drainage. Hynds inspection once at start of Works.
d6a34e46-217e-5e8e-9213-f8842cf24615 | note | Contractor - W, I
7e620971-3b53-5329-af4f-f37450836102 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
c9866cdc-da9a-5642-919e-bc2cee48d5bb | checkpoint | 3.07 - Install side support embedment material
440be4b5-d534-50ef-a6c7-4f0b0b8d06e6 | note | Method/Description - Inspection
879f454b-bd86-5b94-9a4b-775d230bda64 | note | Test frequency - Checksheet filled in for every 100m section of drainage
0ec9c69b-8080-55dc-b629-314ab5f88c15 | note | Contractor - I
b06f40dd-10f8-5f79-a209-6ebfc55208f4 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
a21bcbfa-81b7-53c2-bdc3-81d407ba28a0 | checkpoint | 3.08 - Install overlay embedment material
5daa1abf-1d51-5d22-8d25-b2778c9e14b2 | note | Method/Description - Inspection
950c6c35-8e94-5d5c-b0af-42f73473c9a3 | note | Test frequency - Checksheet filled in for every 100m section of drainage
a3f368f2-6f89-531e-af54-4dab17c427e8 | note | Contractor - I
b25648b8-be95-5d7a-9ead-06d5d13d43ad | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
3b075c01-8664-586a-af05-3b593bc393d7 | checkpoint | 3.09 - Wrap Geotextile
f880db3f-6fba-5897-a26e-fd6c967d1fd4 | note | Method/Description - Inspection
1121fef9-fb6a-55e0-adc3-52a93be20d8e | note | Test frequency - Checksheet filled in for every 100m section of drainage
6fb29771-c5bd-5ccd-8242-6062b1db58bd | note | Contractor - I
28e60a39-7acf-5806-b945-d43365d7222b | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
85910491-7d0d-55df-8a28-bc8442b458f3 | checkpoint | 3.10 - Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top
dbd0b7a1-a2be-5ec2-b340-53cdc03d5b30 | note | Method/Description - Inspection
a81c3316-cd58-54b0-9aca-a135186dd12e | note | Test frequency - Checksheet filled in for every 100m section of drainage
f748059f-174f-5691-9e36-6d688ef30e5c | note | Contractor - I
5100807d-70d9-515d-94c7-ce73b075e195 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
768d3ea8-4aa7-5499-b4df-1095b7adf573 | checkpoint | 3.11 - Spat Rope installation
26fb15df-8f1c-5fc2-9927-977c0216bfd3 | note | Method/Description - Inspection
f389ccce-38c8-5466-a680-6cef979a2879 | note | Test frequency - Checksheet filled in for every 100m section of drainage
a3039d5f-16f3-5594-96cd-ad67855d4841 | note | Contractor - I
a32cb2d9-99d4-54bd-9179-a784e4a84c0c | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
5b2bf91d-9fc6-51c5-8e1e-5861949c524a | checkpoint | 3.12 - Construct inlet and Outlet structures
0debb97a-37cf-5e40-91c1-af9269a59654 | note | Method/Description - Inspection
96c1baf3-ef5a-5846-9dab-4d01f267ad65 | note | Contractor - I
a831b8a8-7715-514c-b650-4b7b6359cbc0 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
c815dfd0-5dcc-5cc4-9c68-7c8d5d947fd0 | checkpoint | 4.01 - Install culvert screen to catch debris
4ab8e6dd-0aab-5add-b907-365591572736 | note | Method/Description - Inspection
799d5670-42e5-56fe-abe7-2f3c64b5f83e | note | Test frequency - N/A
fee25ee8-e98b-522e-bb8c-9cd932df95ad | note | Contractor - I
5b8df720-9ca7-5ae8-a81d-997056d6c93b | checkpoint | 4.02 - Provide Maintenance and Inspection Report/As Built
d1d19c64-3d49-5249-b158-ed8c6fe54809 | note | Method/Description - Maintenance and Inspection Report Completed
d71fd21d-0ecc-5b3a-a2c5-bb49a68bac7f | note | Test frequency - All Temporary culverts
79b5c7e6-7a1a-52ef-9bcd-2c261e157190 | note | Contractor - I
ddbff481-7bcf-56e2-802d-cec814301f0d | note | Hynds - R
10203b48-48b9-5a03-b653-dfd45f5dc6ea | note | Verifying Records Checklists, Test and Supplier Certificates - Maintenance and Inspection Report including As Built Plan & Photographs
741efbb5-74c9-4c27-bc25-a0bd52daaa0f | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
b3a04313-6afa-49d6-ac06-d7ae47764ce6 | checkpoint | ITP Close-Out by
22671d76-a652-541c-b486-be35a8f7dc80 | note | Site Engineer/Project Engineer
a8ec4d71-3595-539f-a038-58dcc7dd264c | note | Zone Manager Approval
e1de0133-0323-56ac-9d25-4a7f264f3437 | note | Construction Manager Approval
4e61842c-d78b-5fac-a61b-9fe76f14e187 | note | Quality Manager Approval
12994945-4936-5388-b565-40c848e85f49 | date | Date:
c4bb368d-e955-42b8-8d5c-996ce0e3137c | signoff | SIGNATURE
4a460203-18a9-5aab-abba-728e69f32104 | checklist | ITP-007 - Palisade Wall | itp | ITP-007 - Palisade Wall
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
b8036728-618f-5223-862b-4d5d9b7392e7 | checkpoint | 1.01 - Approved CWP
ae17a6c1-46a2-550f-989f-9c932990bb19 | note | Method/Description - Document Review
bcd1878c-ec81-58b9-b27a-1f802258dcde | note | Test frequency - Prior to personal starting
b63f2dfe-8c01-55a8-9c21-3762471f75d1 | note | Constructor - H
ce694c1d-838d-5da9-9777-74c831c7d166 | note | Verifying Records - Signed off CWP
8bba7d2b-c99b-5bc4-a108-87b749bd8128 | checkpoint | 1.02 - IFC issued
a12e9e8f-e5cf-5a64-933c-a4ab68b11a93 | note | Method/Description - Document Review
275d9a3d-2ef2-5e00-807f-739d546ebe33 | note | Test frequency - Prior to starting
9fe09329-56f4-554e-8897-4b3f05a26fa7 | note | Constructor - H
54d14091-8a8f-5126-8232-9e3f864b7a16 | note | Verifying Records - IFC drawings or written approval from PAB
431dec39-58e7-5089-ad02-f482ccba3585 | section | 2.0 During Construction
03e9f38c-948b-5523-9053-8cf88235bb3d | checkpoint | 2.01 - Survey Set Out
574e2092-3e1b-5a23-ae41-33a3395a9869 | note | Method/Description - Survey/visual
7a8b15bf-ee6b-5822-835c-2ffe380d46ea | note | Test frequency - Prior to Commencement
845b40b2-6634-50cd-ad20-b6bbbd52089e | note | Constructor - H
42070937-0609-57f0-85d4-49af8090564e | note | CPS - R
93576e5e-0a0d-5b52-9177-bb00c38d04e8 | checkpoint | 2.02 - Steel Material Classification
49c343d1-8d3a-5617-a759-6b9b03da12cc | note | Method/Description - Document review
0bdcf704-3dc5-5dfd-9758-e40b18ea2d29 | note | Test frequency - Prior to commencement
c7124f4c-1414-5dd2-9fca-81711b642836 | note | Constructor - H
86f81fb8-5615-5ff7-acb6-502340cdcfc6 | note | Verifying Records - Mill Certificates
7d675098-7616-5045-9265-790e889e1f52 | checkpoint | 2.03 - Splicing Piles
609e5639-a411-5e65-9a85-5ce1ed07efbf | note | Method/Description - Document review
836aa4ef-df37-5c4a-8191-4a0a04bc45ee | note | Test frequency - Prior to welding or splicing
8fe8c025-d7b7-5981-a308-af506c729cbd | note | Constructor - H
2fa338d5-2aff-5cdf-a924-be7931f73c66 | note | CPS - I
b074dcca-8e55-52f2-9580-fdff20d1232f | note | Designer - H
50117185-46ad-5617-9629-7b0c8d66a701 | note | Verifying Records - Mark Up As Built Drawings
eea0a60e-d99a-5190-8b9b-d35e41fdb9ef | signoff | HOLDPOINT
7f72b698-8e98-53c0-b1c0-2010521647e3 | checkpoint | 2.04 - Piling Auguring
a58d2e99-2732-540a-9e33-b1d86b9debb3 | note | Method/Description - Visual/measure
25c77358-f9bb-5079-bd8d-d7b241f6ac49 | note | Test frequency - Daily during piling operations
a8e165a6-e92c-5566-9166-966a2cde014b | note | Constructor - H
b0c4c133-5a4d-51c7-8759-e095a769fb40 | note | CPS - R
ee118550-7f3d-5f53-9949-57f2eb6af069 | note | Verifying Records - Piling Log
e09a68aa-6803-5bfb-ae12-3dd342b52935 | signoff | HOLDPOINT
97f4a735-b0e2-5506-b0fc-498f884b8660 | checkpoint | 2.05 - Pre pour inspection
cd890e0a-16d7-5db5-992d-7ee3e7e785bb | note | Method/Description - Visual/measure Document review
74516db5-2926-57b9-8cc1-d714a10c2dad | note | Test frequency - Prior to concrete pour
57e77e17-00ea-50fb-92d3-b7dbbe2fd458 | note | Constructor - H
74c8cbca-d8c9-500a-bc95-1227dbe83612 | note | CPS - H
d7d31a2f-df96-55da-99ce-5a6184ad75b2 | note | Verifying Records - Pile Pre Pour Checksheet
e76b98ec-74d9-5ce5-a3af-c9842a1228d9 | signoff | HOLDPOINT
2cdd6bf4-e25e-517d-ac1f-a0ca3b0b6e4f | checkpoint | 2.06 - Concrete supply
c102baee-d0fc-5c70-b55e-c0354af76818 | note | Method/Description - Supply docket review
4ca7503f-abd8-5867-8ac6-19b7b07c2cca | note | Test frequency - During pour
9620206b-292f-5f63-b82a-73a8d94d872a | note | Constructor - H
e0c82c1c-6bb6-5431-b9a9-62c18e1f808b | note | Verifying Records - Concrete Delivery Dockets and Test Results
97fccb1f-4c5c-5856-bffe-be655d77653b | checkpoint | 2.07 - Concrete Testing
efac2b73-5a69-54fb-aa30-8f562bec462d | note | Method/Description - Test
454b7948-da88-53f4-9b2f-1ee141cda8ef | note | Test frequency - Each pour
9e5051a7-aa92-56b3-b603-008d66dcfacf | note | Constructor - W/R
5faeca59-31fa-508a-9a82-09c77ba029c3 | note | CPS - R
a6c78e55-806f-5458-ab23-6c2bca1e4f30 | note | Verifying Records - Test Results
cf535855-89ac-528d-8494-259620bf3c15 | checkpoint | 2.08 - Concrete Finish
6218332a-e90d-53ba-a680-c2f5fabdfc1d | note | Method/Description - Visual Inspection
2cf52b54-ad8d-59c0-a3e3-6ccd940ceadc | note | Test frequency - At the completion of the pour
c172a534-6452-5363-8ab4-4d5409225e3a | note | Constructor - I
1733cb90-9297-57a7-8abc-2a487cd2f169 | note | CPS - I
fa1fa30b-1dd0-5b3b-b4c2-8f5ef1c0ebca | note | Verifying Records - Pile Pre Pour Checksheet
d5545795-84a2-5564-99ac-44165c0761fb | section | 3.0 Post Construction
bc7e03f2-146e-503f-b07b-58c63156a49f | checkpoint | 3.01 - Survey As-builts
d99d2f77-4932-5a67-9f6d-0352ee5513ed | note | Method/Description - Survey As-built
51362fa7-a13c-5063-b8fd-296c51d5d96a | note | Test frequency - During construction and at end
1410dcdb-57c7-5baf-a8ef-46ae33e8422b | note | Constructor - H
663ee1a2-3f4e-575b-96c4-a8d2ebfc9dd7 | note | Verifying Records - Digital file
71192f4d-1392-5b74-a9ee-474026efaf0a | checkpoint | 3.02 - Red Line Mark Ups
c7075f55-1638-552b-a729-62475546a564 | note | Method/Description - Red Pen Mark up
56e64a3e-3b7f-55ca-a720-88be66b549d0 | note | Test frequency - End of construction
bce71672-cac8-54a0-90ce-2675fb082c98 | note | Constructor - H
0bbfadc7-18fc-5c80-83a3-a240ab238006 | note | CPS - R
0ffdead6-9ba0-56ee-9a13-ca3dcd9ee36f | note | Verifying Records - Red Pen mark ups
8919eff8-fed3-572c-bcf7-d24e7712e7ba | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
45524c2d-1de8-5e60-b52d-1f4484181dd2 | checkpoint | ITP Close-Out by
1def2dee-d138-50e5-be5d-74064ede6d0c | note | Site Engineer/Project Engineer
5555477f-fc70-5205-9277-4d8f264c7cb3 | note | Zone Manager Approval
485e9ce9-6db1-52fd-aee4-ec60ad1fa8d6 | note | Construction Manager Approval
756de4a5-a1b2-5d22-bc48-ab326e39aa73 | note | Quality Manager Approval
7c9edf51-2630-5d7b-af4c-a635560f280f | date | Date:
1dc2c9d0-048a-5501-9488-936d3248a797 | signoff | SIGNATURE
b3a4403a-1d50-56fa-9bd6-a5fde843bba2 | checklist | ITP-009 - Geotechnical Equipment Installation Rev 2 | itp | ITP-009 - Geotechnical Equipment Installation Rev 2
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
5db01920-7d30-5f29-9615-65837ccd9caa | checkpoint | 1.01 - Construction Environmental Management Plan
c1781c39-6cac-5686-bf54-d6edb8e4135b | note | Method/Description - Document Review
d179a05e-3643-5bc1-a50d-a3081f64eb5d | note | Test frequency - Prior to personnel starting
09cac770-3cd8-52a3-8bc5-2e8a80f8cafc | note | Contractor - H
c9edf3ba-d9d5-5c74-81bb-44dd40ee758e | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
1735e9e8-adfb-572c-9a8c-6517471a2e66 | checkpoint | 1.02 - Construction Work Plan
4e0b4904-362c-544d-a719-519af9756510 | note | Method/Description - Document Review
68d92397-5cc2-5989-980a-c1b77fa042d9 | note | Test frequency - Prior to work starting
996f184d-097a-5a25-b169-b2d8603b4679 | note | Contractor - H
5021dd96-64a1-550f-abbc-15231c330cd0 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
2ece2dea-0ece-5f8b-808c-1cdc710ec1da | checkpoint | 1.03 - IFC's specification
75236a7c-b6a6-5779-acfd-5a519a419c98 | note | Method/Description - Document Review
d571d8ab-9eda-5b36-ab0d-87d643deb4cc | note | Test frequency - Once prior to works commencing
67804dd6-5d72-5463-9386-41204f75d563 | note | Contractor - H
e7d5e4d6-4f1f-54e6-9527-013ad9dff627 | note | Designer - H
2f3480f7-88d4-5e28-b4eb-52e475865867 | note | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
4f53a227-7472-56ba-a5a6-4c3ac8e4c227 | signoff | AUTHORITY HOLDPOINT
9f3782d6-fcad-57e8-9f89-25cbd7e66940 | checkpoint | 1.04 - IFC drawings
570dcf66-8dcf-5ff0-a2ab-37d011c8b838 | note | Method/Description - Document Review
4f6d9c99-2ee3-5e87-ae50-79704bd5e962 | note | Test frequency - Once prior to works commencing
f3b9d3d1-e7e4-5dc6-af7f-93e427e7c2fd | note | Contractor - H
736e6f7e-2203-5986-9b6c-ce8718951ced | note | Designer - H
102d6008-12ee-5103-a889-cf3c4060e1a4 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
0a00808e-11fa-5083-96cc-194ed9762c58 | signoff | AUTHORITY HOLDPOINT
88046553-aa6f-52f9-90e3-e891d6407ce1 | checkpoint | 1.05 - Approved setout locations of instrumentations
1206e3f9-55f0-5149-b537-d0cb066f8a02 | note | Method/Description - Designer Confirmation
234615fe-858e-5b91-84b6-936b7919e60b | note | Test frequency - Once for every fill site prior to work commencing
4da0b8e2-90de-5038-a64d-46d5bab7e7ca | note | Contractor - H
087d1f16-fa33-5b3f-871f-0bc2341b77e6 | note | Designer - H
94210d6e-d13c-5b52-a77a-cfd32be10b92 | note | Verifying Records Checklists, Test and Supplier Certificates - Written Confirmation from Designeer
b44d7639-8d9c-55a4-9c83-b431678d98d6 | signoff | AUTHORITY HOLDPOINT
44a0d20e-8a4a-5ae0-aa01-d566f7bbd0e5 | checkpoint | 1.06 - Method Statements Approval
58043e0d-7a7c-5d6b-b0cb-2a5cb8308248 | note | Method/Description - Document Review
28484890-c6bd-57aa-a072-f138cd85aad8 | note | Test frequency - Prior to installation of instrumentation
84f1f6ba-afbe-56d4-b668-c6badf80a7ab | note | Contractor - H
0d9b24a0-379f-5029-8b3b-a9dce4fb710d | note | Designer - H
b89bb69c-dd07-50f3-9c05-2adf405273ab | note | Verifying Records Checklists, Test and Supplier Certificates - Method Statement
80c5463d-a41f-583d-8d84-d1acff384202 | signoff | AUTHORITY HOLDPOINT
bb35f236-5d4b-5379-8828-26d0db8da5a0 | checkpoint | 1.07 - Calibration of Read Out Equipment
5ce63ece-0744-5b28-8663-673fa4ec1110 | note | Method/Description - Document Review
15a52ad9-a3d0-55a7-9e72-8b6f88f00fbb | note | Test frequency - Prior to starting
90e5d4a7-3752-58ea-ba82-fda72e3a8599 | note | Contractor - H
1d0cd476-aa76-5660-b4ca-c6e7df0b0dff | note | Lab - I
4dea238d-d690-5ab4-9b25-df4fa7049db2 | note | Verifying Records Checklists, Test and Supplier Certificates - Calibration Certificate
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
887763dd-cf3b-5bf4-9f81-61012322a83a | checkpoint | 2.01 - Vibrating Wire Piezometer manufacturer specification
8508f579-26f6-5f9b-ab9d-ed5b0788bdab | note | Method/Description - Document Review
e2832465-6268-5839-a4ec-ae1f5f07a2e1 | note | Test frequency - Once
247fa4c5-f5b6-5c18-ae09-0393c9d95ff6 | note | Designer - H
83268092-d390-516d-9f97-e3d207dddff9 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
cb1e758b-2883-5843-9bf8-4649283796cb | signoff | AUTHORITY HOLDPOINT
c532d2b6-ed2c-54fe-aaff-6f5cf869c385 | checkpoint | 2.02 - Vibrating Wire Piezometer calibration
b7f5e511-5b4c-523e-98f3-9186391fa4a1 | note | Method/Description - Document review of manufacturer's calibration certificate of piezometer
fd59376a-761f-529a-b44c-0563362362cc | note | Test frequency - Delivery and acceptance of piezometer material; prior to installation
a55a6cf7-0e6a-5223-b682-9188a30e3f05 | note | Designer - H
9197808e-38e8-56aa-b5d1-141467cac314 | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
b15780a9-f82e-5493-ac0b-a891f5cbda1a | signoff | AUTHORITY HOLDPOINT
769dda50-5983-571f-b49a-508273809562 | checkpoint | 2.03 - Extensometer manufacturer specification
9bd24c8f-a7ad-56b6-aa41-95a90caf0ae4 | note | Method/Description - Document Review
7adb8326-68d5-5a2e-905f-7abd3abe33fa | note | Test frequency - Once
7b10df48-62e5-5e4c-b46a-9ee89ab0f16a | note | Designer - H
7aecb46d-b871-5133-ba74-0800c6d852fb | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
5646f79f-aaba-51a4-9dcc-c9ea3c293cc3 | signoff | AUTHORITY HOLDPOINT
8ad36448-96f8-5d2e-b971-9049b199376b | checkpoint | 2.04 - Inclinometer manufacturer specification
61c5fa70-bf23-5469-ac68-32ed9196b1df | note | Method/Description - Document Review
a8c594f8-15a5-5f7f-ab2a-0b605b319f00 | note | Test frequency - Once
4f4b3d8a-936d-55c9-b24f-1c47c5d15527 | note | Designer - H
e0a9a8b1-3235-57bb-9522-feee8457c568 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
d2fe9598-c4b4-57c4-bb29-979b45342e00 | signoff | AUTHORITY HOLDPOINT
9fcfa480-540e-56b2-bad2-0a68740152ad | checkpoint | 2.05 - Inclinometer casing material
8d049a49-da62-5946-8522-3ef97ebf2e26 | note | Method/Description - Inspection of Inclinometer Casing Materials
197696da-5ff4-5fc2-a53c-3efe9fd19852 | note | Test frequency - After Delivery and acceptance of Inclinometer Casing Materials; Prior to Installation.
b541f439-cf8c-5c76-ab19-e156a625e233 | note | Installer - I
51a32b4f-53df-507b-882e-d3af5dfe1dd6 | note | Contractor - W
d57118d9-7694-56ad-9862-2a885a9c809f | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
66bb8975-da17-572c-adb0-6d0713c4ca29 | checkpoint | 2.06 - Inclinometer grouting materials
786b931c-3c88-5ecd-a3fd-19727c3c31c7 | note | Method/Description - Review & approval of approved grout mix
f1b8de27-97da-5ca9-883d-dddb212c54c2 | note | Test frequency - Prior to Equipment Installation
1cb33d54-ad44-5e27-a7db-8487d8dd5b73 | note | Designer - H
fb59121f-6951-5c4f-99d6-54eff3ec4557 | signoff | AUTHORITY HOLDPOINT
aef98b18-565f-5f1b-bd7b-fa8585342fc2 | checkpoint | 2.07 - Inclinometer materials
e2fd1a81-73c7-565d-b853-c3111cd40f20 | note | Method/Description - Inspection of Inclinometer Measuring Equipment
0a2a2ef6-b16b-542c-94d1-90837bbb9950 | note | Test frequency - After Delivery and acceptance of Inclinometer Measuring Equipment; Prior to Installation.
273c8ca0-7b83-5e92-af35-22612739ccea | note | Installer - I
348eb6b4-ef01-59c4-a5dd-6542c1578102 | note | Contractor - W
37aeb6fe-099d-5cd6-bc9d-f1f22fc60d4d | checkpoint | 2.08 - Rod and Plate Settlement Markers
f1767a56-98cd-5161-b485-5858026a6851 | note | Method/Description - Inspection of Settlement Plate Materials
726e8b24-7574-53c7-9215-d1d151994374 | note | Test frequency - After Delivery and acceptance of Settlement Plate Materials; Prior to Installation.
3cf9b493-b1e0-5d9d-a648-c37d96e8394f | note | Installer - I
5a063c6f-4079-5503-8288-efc6fa7dd4e9 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
c17d86d9-8948-59d6-8cbb-73c7541fdc5a | checkpoint | 2.09 - Surface settlement marker material
31e46699-57c0-56a7-8109-4cccd4ab8ee3 | note | Method/Description - Inspection of Surface Settlement Marker Materials
2c9b7967-160f-536e-a28b-4bd1712851fa | note | Test frequency - After Delivery and acceptance of Settlement Marker Materials; Prior to Installation.
abeb4c4b-eee1-5237-9714-a27ffa8bd5b5 | note | Contractor - W
d2d208d3-d0d6-50b8-b83a-53c6c33b05c0 | checkpoint | 2.10 - Surface monitoring marker material
c4008508-cc50-5c19-be8f-4018488f2557 | note | Method/Description - Inspection of Surface Monitoring Marker Materials
d86f0420-126e-5a8d-88ff-7c3066693792 | note | Test frequency - After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation.
13ad65bb-3c90-5749-ade3-e6a0e787ead1 | note | Contractor - W
90de7fdc-f9e0-5b70-b111-31b226c72498 | checkpoint | 2.11 - Lateral deformation marker material
a7981613-659f-5d55-981d-5d3e613e1e42 | note | Method/Description - Inspection of Lateral Deformation Marker Materials
657d885f-23ab-5574-b5d9-a08ea4deb6ad | note | Test frequency - After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation.
2a2be6e3-afff-5414-b3ad-fa7767e0a6f8 | note | Contractor - W
5c0d8b58-428d-5557-8e39-979c18fbb503 | checkpoint | 2.12 - Profilometer material
70f4ec1f-91f0-564f-81eb-d3a72d163771 | note | Method/Description - Inspection of Profilometer Tubing & Backfill Materials
ec702f18-1775-5b9c-b45f-6b30324f79c6 | note | Test frequency - After Delivery and acceptance of Profilometer Tubing & Backfill Materials; Prior to Installation.
3d08e78a-3bd5-5c7d-b526-4aae589252f8 | note | Installer - I
a3b00f9c-02d3-5924-b8b9-bb65e7b7e852 | note | Contractor - W
81283718-b5f4-5ae1-bf42-f99eb026a96c | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
971af1b5-8ff8-59fb-a547-1d7e319a9029 | section | 3.1.0 Vibrating Wire Piezometer Installation
24a176b0-5ce0-5bce-8a87-8bba38e87836 | checkpoint | 3.1.1 - Piezometer location per construction drawings
97f06828-2caf-5cd7-a4a3-409b96e73e83 | note | Method/Description - Inspection of borehole location
08542b2f-5be8-5165-a9f4-80124dd5228e | note | Test frequency - Before borehole drilling
e01a595e-dee2-5b3e-bdfb-c83057676e35 | note | Installer - I
d52632ce-52de-55ab-b1d1-eb9d0b6463fc | note | Contractor - W
a05cd3a9-7117-5e95-b9e4-6461d8302100 | checkpoint | 3.1.2 - Borehole Drilling
997af7b4-aab4-5825-8684-2a5aaf387751 | note | Method/Description - Inspection of borehole
ab4b7269-2c4e-58b5-982e-0a1a4ee68169 | note | Test frequency - After borehole drilling
0b79cad7-6874-5b1c-8c45-1a37607add57 | note | Installer - I
fcfd834b-52e9-5fad-abc1-0c9deb9f9a2d | note | Contractor - W
234d71aa-d17a-5f15-a34b-1776293e0e26 | note | Designer - W
8be6940c-1648-52ae-9a58-c5101015ec9a | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
98900df6-8cc0-5705-a178-3e091b102f2e | checkpoint | 3.1.3 - Depth of piezometers
19339646-ac6e-5c9f-af2f-bbf5f09561d2 | note | Method/Description - Review & approval of depths of piezometer based on the results of the core logging
91b842e6-26dd-5935-824a-00c2399679f5 | note | Test frequency - After borehole drilling
5297a916-5715-5bd6-907b-5319098e1934 | note | Designer - H
8bd1f80c-5f69-5ed7-b9ef-d8e1feff3888 | signoff | AUTHORITY HOLDPOINT
0770b2f1-d660-5e90-86d1-f8d27d74a52c | checkpoint | 3.1.4 - Core materials
9554b4d3-c4ea-5dea-9d2c-0cd07e9bc21b | note | Method/Description - Inspection of all retaining cores
d3f129c9-1e47-59bc-83dd-9a69cd3fa3e9 | note | Test frequency - After borehole installation
bcfba8db-e93c-527c-bdfc-62d56597a233 | note | Installer - I
b3cbb2b2-caa6-54e8-97be-562e08e8f2f4 | checkpoint | 3.1.5 - Heavy duty connecting cable placement
ee72f1d2-f712-5ae6-8c68-294c2596e4a2 | note | Method/Description - Inspection of completed heavy duty connecting cable placement
bc9713f9-36ab-56f9-be37-524735907d41 | note | Test frequency - After placement of heavy duty connecting cable
2729dba7-b3fd-5cbd-af0e-2f6e4c777e68 | note | Installer - I
e54b085e-8565-5831-9956-3e783fbaff05 | note | Contractor - W
24654022-1160-5def-8779-eb7e0e827502 | checkpoint | 3.1.6 - Splicing of heavy duty connecting cable
0ee7fefa-c864-5e69-9cd5-30013489f77d | note | Method/Description - Review & approval regarding acceptance of cable splicing
e919a43b-93c1-52ae-9cff-a7a28a9573e4 | note | Test frequency - Prior to splicing of heavy duty connecting cable
edd93939-dc7a-56eb-86d7-51940cf19269 | note | Designer - H
d4911b86-e703-5d53-8d0f-540adbea9fe9 | signoff | AUTHORITY HOLDPOINT
60e399e9-99cd-5bb0-8962-74d694d85445 | checkpoint | 3.1.7 - Readout unit/data logger placement
1b610c73-588c-5083-bec8-876c667ca86f | note | Method/Description - Inspection of completed readout unit/data logger placement
6fefb079-9f32-574c-8ef1-8943af052b27 | note | Test frequency - After placement of readout unit/data logger
2db1dc4a-eea4-51fe-a4d3-f66abcd9afd6 | note | Installer - I
e31763d6-db63-58a6-be45-ea0b50234ba0 | note | Contractor - W
3e097bf9-1805-5301-85dc-12801b742648 | checkpoint | 3.1.8 - Ground surface finish of installed piezometer
6cbe5381-8918-5cd6-b52e-6485a9b4c197 | note | Method/Description - Inspection After completion of the installation process of Piezometer
5f058a59-0929-5775-a961-872daac29d9e | note | Test frequency - After completion of the installation process of Piezometer
27761d93-7b50-52d9-a0b2-3bc85df1f09c | note | Installer - I
79bf7090-19a2-5072-a267-555b01d9e09a | note | Contractor - W
e6b0e5c1-8bd5-57f3-a59f-bbf68736cab1 | checkpoint | 3.1.9 - Ground surface finish of installed connecting cables
4a8e6ed2-a4ed-55bf-9b16-50d3b59d7487 | note | Method/Description - Inspection After completion of the installation process of Piezometer
dcb90d5c-7062-5b1d-a38c-53435a0c5e18 | note | Test frequency - After completion of the installation process of Piezometer
b7afbdc8-5937-55d5-a73c-b756f25bfcdf | note | Installer - I
317758d8-ba30-5957-9ef7-e14079ebd6d5 | note | Contractor - W
bb1293a6-aac6-55e9-9921-f9dc6a422b23 | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
38532a6b-2739-5a67-9019-173101a0c2c7 | section | 3.2.0 Inclinometer Installation
17c32914-90e0-5a94-90ee-2f89cc1912fa | checkpoint | 3.2.1 - Inclinometer location per construction drawings
266d8360-3ba0-58e9-b0a7-a8db93ae308e | note | Method/Description - Inspection of Inclinometer Placement
ad89ab14-1762-543c-a9b7-a9706711ee0e | note | Test frequency - After Placement of Inclinometer
a68a3803-ebe6-5f40-aac2-735cdeb2d727 | note | Installer - I
8cd09675-fef7-51a4-8847-2123720ee558 | note | Contractor - W
b97b2a5e-d4e0-599d-a9fb-ea374b7f9702 | note | Designer - H
aee9c164-bf68-5320-84f1-322d6eec1d24 | signoff | AUTHORITY HOLDPOINT
60c35340-4236-532b-ac97-b34580edfc45 | checkpoint | 3.2.2 - Borehole drilling
ef57b910-6bac-547d-99bb-3d8ac65bb105 | note | Method/Description - Inspection of Borehole Installation
678a720e-e033-5fcb-a395-32f93a26ff9a | note | Test frequency - After Borehole drilling
94641131-d845-599b-9f75-11074bbc3bc0 | note | Installer - I
770c3480-2a1f-5472-997f-2d8de63c579c | note | Contractor - W
3c1064aa-7e3f-5bb9-98f1-8a341672363b | checkpoint | 3.2.3 - Depth of inclinometer
ea8324a4-cc97-5fcc-a8c6-96470d2fd7c6 | note | Method/Description - Review & Approval regarding depth of Inclinometer based on the results of the core logging
8aa05df7-b4b3-5cbf-b59b-4a670c41f60f | note | Test frequency - During Borehole drilling
ee8f1b46-f208-5c94-930f-9ff75aec8109 | note | Designer - H
192b06f4-6036-58a8-818d-a1d5ee91b978 | signoff | AUTHORITY HOLDPOINT
b32ccf54-24a0-5a46-814f-9839a82629da | checkpoint | 3.2.4 - Core materials
6f6c3361-01a9-5af3-b8c5-1f77923dba36 | note | Method/Description - Inspection of all retained cores
0d720a3c-ce38-5bcd-b087-ce24a5292585 | note | Test frequency - After Borehole drilling
ee833ebd-1609-5ba5-bcca-8fdb572fa472 | note | Installer - I
ca8a0db4-d3cc-5ca2-897b-adb297c7e6e6 | note | Contractor - W
ac3bdbda-290f-556a-a150-4ffc806d2714 | checkpoint | 3.2.5 - Grouting installation
c0addd41-8376-5dd4-8ed4-305fb1b1402d | note | Method/Description - Inspection of Grouting Installation
e5fd02fa-8c25-5462-ba69-1e7931a3b790 | note | Test frequency - After Grouting Installation
33a90bd8-e353-5005-946a-51d06a4ddc15 | note | Installer - I
56544afb-bc15-58cb-a996-18b3092a94b9 | note | Contractor - W
520e0250-aff0-5d36-801d-200c9817e38d | checkpoint | 3.2.6 - Ground surface finish of installed inclinometer
98208c70-480a-5133-be0f-a1a21a5ffefa | note | Method/Description - Inspection After completion of the installation process of Inclinometer
8f5b2dff-6126-5aed-b9d7-b97245f67267 | note | Test frequency - After completion of the installation process of Inclinometer
e46e9ffe-71a6-5e3d-9764-848f1e8e4ab5 | note | Installer - I
8ccbe5f1-3cf5-59b7-9647-963661ba9fd5 | note | Contractor - W
c4813869-485d-5bf3-8b0e-1dd22985442a | section | 3.3.0 Profilometer Installation
9b71cf4e-694a-56ae-b79e-748c235dd558 | checkpoint | 3.3.1 - Profilometer tubing levels and location per construction drawings
9e0f73d3-b9d3-5e14-82c0-eed9dfc2b27a | note | Method/Description - Inspection of profilometer tubing Placement
9e1c7723-acb4-5fca-9191-35f7196ecf53 | note | Test frequency - After placement of the profilometer tubing
7f3be2e5-d344-5eca-b438-40b7d865db39 | note | Installer - I
5a388a25-82a3-5b60-9b4c-ddfea206fa35 | note | Contractor - W
68bdb094-09bf-5488-ab94-1442a59c4090 | checkpoint | 3.3.2 - Profilometer installation
fef720e7-04ca-50fd-9d16-b8c1a341e50f | note | Method/Description - Inspection of profilometer tubing Placement
c6419f97-c873-565c-8a1b-7dc6efa71f46 | note | Test frequency - After placement of the profilometer tubing
6b2766be-0847-58cb-9cd6-95df8f7d30bf | note | Installer - I
5c9b39d5-3606-5511-ac86-fe246754d9e1 | note | Contractor - W
0ed39647-7669-5112-83ca-adeb671a24a3 | checkpoint | 3.3.3 - Ground surface finish of installed profilometer
727a19eb-7b56-597b-bb6f-a7ed93a2f355 | note | Method/Description - Inspection after completion of the installation process of profilometer
594d1ea3-ddb0-515c-b99d-e41c2aea2530 | note | Test frequency - After completion of the installation process of profilometer
f8dfe5e3-e0e9-5bfc-ac43-ed37c8b588e7 | note | Installer - I
37ffdf9e-e743-57ee-a470-334dbdd69142 | note | Contractor - W
8368603d-fcb7-5a19-96b9-661961066151 | section | 3.4.0 Rod and Plate Settlement Plate Installation
c4062047-40d7-596d-8c02-abbf2b1562ff | checkpoint | 3.4.1 - Settlement plate installation
8f2adc4a-81f7-5727-aa98-8adcd2b9541e | note | Method/Description - Inspection of Settlement Plate Placement
ced4007a-bb2a-5128-b5a9-450451a53d9a | note | Test frequency - Before placement of the Settlement Plate
178b4a6e-95c0-5bc1-81e9-47fb89dfe5bd | note | Contractor - W
996590a1-444e-5587-9c96-e3f1d93e821d | checkpoint | 3.4.2 - Ground surface finish of installed settlement plate
b0d87ca3-c6d6-56d1-b1d2-5c7d154e48e9 | note | Method/Description - Inspection After completion of the installation process of Settlement Plate
dff90545-1264-54d1-a485-97a9f651e52c | note | Test frequency - After completion of the installation process of Settlement Plate
01feb329-aa58-576d-895f-6fbb32cf4390 | note | Contractor - W
fa8f12dc-b4e2-5d9e-a40c-4bb87668536c | note | Designer - H
27aa79dd-fc84-583c-9052-82233ef9f598 | signoff | AUTHORITY HOLDPOINT
8645cf57-d8f3-5e03-94b8-e8748a7002f0 | section | 3.5.0 Surface Settlement Marker Installation
ad09b4cd-e367-5da9-8c2e-5104f78853cf | checkpoint | 3.5.1 - Ground surface finish of installed surface settlement marker
12c28ec4-7509-5eea-866f-55a4eb60490b | note | Method/Description - Inspection After completion of the installation process of Surface Settlement Marker
8e782d1b-2327-5607-91e6-ba940ddaefb2 | note | Test frequency - After completion of the installation process of Settlement Marker
19b40d84-cffa-5151-a230-a3b87eb72286 | note | Contractor - W
21828e3a-46e3-56a4-a453-c1ffb1ab7f8d | section | 3.6.0 Surface Monitoring Marker Installation
0c4673db-b658-5d7d-b3b2-34188b51b793 | checkpoint | 3.6.1 - Ground surface finish of installed surface monitoring marker
8a0d960c-a395-504f-aa6e-cfc85c03df45 | note | Method/Description - Inspection After completion of the installation process of Surface Monitoring Marker
f41722d4-3d83-5ab8-974c-c1198d6042a9 | note | Test frequency - After completion of the installation process of Surface Monitoring Marker
5d6ccca7-17d1-51ba-8cfa-2a511b156897 | note | Contractor - W
fdfda3ae-205e-5e92-a15d-4a91ed160ab1 | section | 3.7.0 Lateral Deformation Marker Installation
cf17dcae-cf84-5434-aa94-a2e3d7490e4b | checkpoint | 3.7.1 - Ground surface finish of installed lateral deformation marker
5f4684ae-85e6-5f75-b3f4-a64a75da9f3b | note | Method/Description - Inspection After completion of the installation process of Lateral Deformation Marker
8d7bc81c-b034-5de6-ab15-5913d1bd0520 | note | Test frequency - After completion of the installation process of Surface Monitoring Marker
c5184587-7eaf-5514-9aee-a96b95b725a4 | note | Contractor - W
e1c535fb-bc03-55cc-b8fe-48eaf58ee880 | section | 3.8.0 UAV Survey/Face Scan
08c06f83-0db1-5a7c-bd8e-44e9fb2b6d77 | checkpoint | 3.8.1 - Ground surveys using unmanned aerial vehicles (UAVs)
ff397604-66ba-5727-82c1-e50612b044cf | note | Method/Description - Survey
16c126cf-4cf4-5f99-92d3-2d754dba672c | note | Test frequency - 1. Prior to any ground disturbance;
fa761dd1-6a0a-5f2d-a356-7c89bbe5d2a5 | note | 2. Upon completion of vegetation and topsoil strip;
fe26bbcc-8f75-5746-86b0-8d78b232c25c | note | 3. Regular intervals as fill embankments are raised (maximum of 5m fill placed between surveys) and cuttings are formed (maximum 10m depth increments between surveys);
47523000-bb8a-5cd6-bc86-329d428d6862 | note | 4. Upon reaching final surcharge heights for preload embankments and final embankment heights where no surcharge is required, and full cut depths;
c408f7c8-88d9-5581-98df-2c4f1abb8d27 | note | 5. Monthly intervals during the earthworks operations and at the end/commencement of each earthworks season;
970944db-e1b8-5ff4-9efb-b53d40e2ac9a | note | 6. Following removal of surcharge and final embankment profiles have been formed;
cfe094c5-f654-503a-97bf-2f7a0a5c714a | note | 7. Immediately prior to pavement construction;
bd0c50c0-63a4-5997-a98b-239aec0cc083 | note | 8. At completion of pavement construction;
3c070420-743b-52ba-b14d-cbcebdcd7782 | note | 9. Practical Completion;
6a9fc6f2-38e4-561b-82a7-ba8ead8b497a | note | 10. Every 3 months during Defects Liability Period;
7fbbd909-0a83-527d-937a-81320481ebe6 | note | 11. End of Defects Liability Period.
9291600c-56f5-5442-9762-9598619a6b38 | note | ○ Face scans of rock cuttings shall be completed as each cutting is advanced in increments of 10m and at maximum three monthly intervals thereafter during the earthworks season and at commencement and end of each earthworks season. Scans shall have an accuracy of ±100mm and repeat surveys shall be able to compared to previous surveys to assess potential surface movements between surveys using 3D Reshaper software or similar.
449c42a6-1111-5837-a418-2724896acca6 | note | Contractor - W
d5c4d3ce-97ac-57d1-b4b4-e2b489db6c9b | section | 3.9.0 Extensometer Installation
cfa377e4-025c-5d5f-a708-27ce6b86eba6 | checkpoint | 3.9.1 - Extensometer location per construction drawings
72b433e7-4cbe-5e1b-89de-0c7eeadc0f3a | note | Method/Description - Inspection of extensometer Placement
4c53ae68-18d2-5be5-8527-5805a39dc404 | note | Test frequency - After Placement of extensometer
6c0a9d21-4865-552d-96f1-1577037db03b | note | Installer - I
e210a09b-d647-511f-b5d3-6e454a621574 | note | Contractor - W
247066ec-c6aa-5131-94ea-cb154365f94b | note | Designer - H
fa1965e4-2a0d-55fc-b838-f1d5bc952965 | signoff | AUTHORITY HOLDPOINT
f33d1ae5-634a-5043-8e52-ea21db14e244 | checkpoint | 3.9.2 - Borehole Drilling
e73b1582-6f35-5058-bdfd-72b66ef4d71c | note | Method/Description - Inspection of Borehole Installation
8a028854-8e69-5f3d-8b50-04970fdf686b | note | Test frequency - After Borehole drilling
d45c498c-9a80-5018-898d-55c6b2f860ed | note | Installer - I
559b6cf4-7830-50d5-8486-ad5ec590d965 | note | Contractor - W
5efc927b-06b4-51c6-bcf1-3246a04c3363 | checkpoint | 3.9.3 - Extensometer tubes
e1114823-735b-5dc5-89e5-b59d438ce1f8 | note | Method/Description - Inspection of Grouting Installation
0dc02987-80e2-585a-9e9f-c3585fba33e8 | note | Test frequency - After Grouting Installation
9884911d-7e85-5ec3-9242-12a86d880434 | note | Contractor - W
ad3beebc-2158-5e70-8864-27c4f63ba8c3 | checkpoint | 3.9.4 - Spider magnets
5197d379-87f2-5d41-a9ea-1ddd38391deb | note | Method/Description - Review & Approval regarding depth of based on the results of the core logging
6e17de07-c027-5506-ad0c-fc19c838fa42 | note | Test frequency - During Borehole drilling
85763d7a-c607-5ede-8e4e-3d7866579910 | note | Designer - H
fb321688-5c98-5bbf-8f99-a3a171ca9c18 | signoff | AUTHORITY HOLDPOINT
525688b5-6d03-5c8a-a34a-4ce579e88227 | checkpoint | 3.9.5 - Reading and recording settlement
21def668-4d44-52bb-b14e-d0331b2b4ed4 | note | Method/Description - Inspection after completion of the installation process
ce9f5d49-1213-550a-8a67-c970b89cbcbb | note | Test frequency - After completion of the installation process
72379078-f1bb-548b-b1ac-710d3c8335e1 | note | Contractor - W
aef4bfd1-8093-5b02-a33b-ba9f3178bffd | section | 3.10.0 Reflected Survey Marker Installation
fee252f1-4e34-5ab1-be35-d967ba83df74 | checkpoint | 3.10.1 - Reflective survey target marker installation
b97cdc96-bec8-5919-bc35-ff5dc190fb81 | note | Method/Description - Inspection of Reflective Survey Target Marker Placement
3688127d-ee25-582f-8596-32c2ab883506 | note | Test frequency - Before placement of the Reflective Survey Target Marker
c5fb0be3-84e7-5e2b-8adc-dabccb5da398 | note | Contractor - W
ab51fb9f-7c39-5bd9-9a67-dd80744b81a9 | checkpoint | 3.10.2 - Reflective survey target marker installation completion
97500cb2-4b45-5c75-bef2-05c3273cf05e | note | Method/Description - Inspection After completion of the installation of Reflective Survey Target Marker
8205f658-8159-548b-9e09-c28f697db238 | note | Test frequency - After completion of the installation process of Reflective Survey Target Market
c95eb16f-4a6d-57cf-ad36-9f798b2c3d2a | note | Contractor - W
9af1103d-c33a-5e98-8923-d5455d0652f0 | section | 4.0 Completion of Instrumentation Installation
6f86276b-1e36-5551-a071-15960db959ad | checkpoint | 4.01 - Vibrating Wire Piezometer completion of placement
91bae5e2-adff-5e01-8a18-a08ff63dba4f | note | Method/Description - Document Review submitted through Hold Point
d8f0ae87-7708-52c4-b3d5-e28da38ed040 | note | Test frequency - After Piezometer Completion of Placement
1f1925bb-697a-56c6-8f98-70f0e557ebcd | note | Designer - H
c7762ac1-9fd8-5924-9081-e0d50a4306a0 | signoff | AUTHORITY HOLDPOINT
93a9399f-f068-550b-a09e-950f26a4039d | checkpoint | 4.02 - Inclinometer Completion of Placement
c1e1cef4-b791-555c-8e55-9b79edace93a | note | Method/Description - Document Review submitted through Hold Point
b367d381-b385-5da6-8bb4-16537299825c | note | Test frequency - After Inclinometer Completion of Placement
1b373216-a562-5ee8-b9ca-231fe044321c | note | Designer - H
002d6da7-a6bf-5f35-8479-485c47bb93a3 | signoff | AUTHORITY HOLDPOINT
e1b83da4-a178-534e-a80f-d40068539458 | checkpoint | 4.03 - Profilometer Completion of Placement
722dc441-c4a1-52bf-8443-a52ad721351a | note | Method/Description - Document Review submitted through Hold Point in Aconex
de53ffa8-244d-5d30-9b11-3dda284f00dc | note | Test frequency - After Profilometer Completion of Placement
2c6dc184-f948-507a-abf6-b47dccf41918 | note | Designer - H
f76b4cba-bc37-52f5-b502-12b08a26635b | signoff | AUTHORITY HOLDPOINT
9afe4495-a514-5d07-a874-3f234ad713c4 | checkpoint | 4.04 - Instrument has been received and approved by the Designer
d3be3eb0-81e3-5b87-b470-fe7b9c733dce | note | Method/Description - Document Review submitted through Hold Point in Aconex
5b9b3803-1b96-51b6-9c19-33c8507be1f9 | note | Test frequency - After Completion of Instrumentation Installation
19e1a056-7e2b-5508-81e5-dc5bddf34a3c | note | Designer - H
0acb7dc4-164a-5967-af22-8fe797e16e3c | signoff | AUTHORITY HOLDPOINT
55980df0-2a76-5407-817a-dc6eacb6e740 | checkpoint | 4.05 - If an instrument is blocked, obstructed or damaged
bfcf9f5d-f544-5fea-a5e5-cd73fc10727d | note | Method/Description - Inspection and Document Review
d6dff28b-fac1-5fb7-aa97-c12a8371292a | note | Test frequency - After completion of the remedials work on the instrument
963535b4-5bef-5647-8f94-50fb96e14367 | note | Designer - H
15ace072-e162-5fe2-bd3d-e0303ad93d1c | signoff | AUTHORITY HOLDPOINT
d7bd260f-d560-5591-8343-1c9257b3441c | section | 5.0 Monitoring
81e6af42-2d12-5727-adc8-fd43afae8424 | checkpoint | 5.01 - Base Line Readings
b6f75633-e64a-5c5a-9077-e265a91b7a3d | note | Method/Description - Survey
edd211c2-4364-55e4-a3b5-e7bfe7eca4d2 | note | Test frequency - Per individual piece of equipment refer to ITPs for embankment/earthworks and cut slopes
799e7cca-1c0c-5637-8749-228bd57ec4b1 | note | Contractor - H
a136935f-33f9-59fd-b609-06e9bc6056b4 | note | Designer - H
d21a9e11-563f-5033-b18c-8431495d4449 | note | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
21123c72-aeba-5dde-9f77-016cb4e1467f | signoff | AUTHORITY HOLDPOINT
40c10db9-951b-5411-b1f8-17e3c1db6a88 | section | 6.0 Verification Testing
f9e43ea6-274c-538c-b93a-cbe7425c0516 | checkpoint | 6.01 - Cone Penetration Tests with Measurement of Porewater Pressure (Piezocone) on embankments constructed on soft ground.
25b83bab-2e63-58d2-8161-f74d2f3fad0b | note | Method/Description - Document Review
a526018d-a623-57d9-916c-77b4e4e84e3a | note | Test frequency - Following surcharge removal or as directed by the Geotechnical Designer
aed0e893-ae5a-5015-be33-fb306be96076 | note | Designer - H
f7cedd37-a9cb-5174-b18a-f0e0cb7926ad | note | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
110586ab-4c47-5749-8624-d8c8f2d77547 | signoff | AUTHORITY HOLDPOINT
a147d8f6-e10d-5f20-87e0-430eb54e3e3f | checkpoint | 6.02 - Geonor Shear Vane Test in Borehole
b5ba8aac-43bd-5d42-932b-787b8bca6b46 | note | Method/Description - Document Review
983d5752-c4d4-5df5-aae7-2aceeb77145c | note | Test frequency - Following surcharge removal or as directed by the Geotechnical Designer
cbf20790-1bc4-5707-a234-67dfa0e10846 | note | Designer - H
3edad595-afdc-5c62-aeac-a93461fb4435 | note | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
362924a7-c48b-5e69-8ebc-ad5a75d17a6d | signoff | AUTHORITY HOLDPOINT
3e0702ed-0e9a-4f5c-93d5-42bb4cf008f2 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
59dd49c2-595e-4d24-a16c-fb1471f15538 | checkpoint | ITP Close-Out by
c556cb97-27a2-54d1-ac22-33c5add19a2b | note | Site Engineer/Project Engineer
9085754f-7919-5f99-aa9b-8b51a6ef85c9 | note | Zone Manager Approval
172aecee-c4ff-5342-b113-6a7fea964577 | note | Construction Manager Approval
1a4a79be-3d44-55df-a6f3-39ee885349f4 | note | Quality Manager Approval
3aa16109-4f17-5b44-a99b-ce5b19258f75 | date | Date:
cfabef62-e9dc-48ed-a9f6-e5faec10f11c | signoff | SIGNATURE
2577f558-f88f-5fa8-b083-b8e49bad5cee | checklist | ITP-011 - Fill 15 | itp | ITP-011 - Fill 15
69ce9b50-1ebc-5d31-8f34-23a4d34fa275 | section | 1.1.0 Pre-construction Approvals
c6325e1f-98cf-5dd9-a024-c2741f8830c3 | checkpoint | 1.1.1 - Construction Environmental Management Plan
50034a9b-c7fd-5d4a-ac48-4a40acfd5153 | note | Method/Description - Document Review
ca266398-4518-5357-8549-a06a9b788e3f | note | Test frequency - Prior to work starting
f0e3afb8-6790-5be9-a0f8-80f3ec578b99 | note | Contractor - H
ba562c65-bc6c-522d-9f17-2f2b27639032 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CEMP
ee7771bc-2366-56f9-836d-696e37f5e599 | checkpoint | 1.1.2 - Construction Work Plan
07bf01a9-825c-5fdc-b175-9ae5c8ca892f | note | Method/Description - Document Review
9b7eeef0-c1e4-56e5-b431-7adfa97d42a0 | note | Test frequency - Prior to personal starting
35ee3d69-2c98-5c1e-85f0-9f0593f4aa04 | note | Contractor - H
ae769efa-75b8-536c-860e-dbb95892bf82 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
80997794-398e-58e2-88f5-b742e9843f56 | checkpoint | 1.1.3 - IANZ accredited testing organisation
dc14c63e-01e6-5479-9e93-4f506f8ac28d | note | Method/Description - Document Review
be91758d-b187-54a6-9a01-4dc6ce1f1c07 | note | Test frequency - Once prior to works commencing
4eb99b6d-d70c-571b-b090-cec6be83195e | note | Contractor - H
67fdb9b4-4c51-5187-b60f-def6158133b7 | note | Designer - H
4b926d1e-7dc3-59f3-a856-b730cdafc0c1 | note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
1b40a37a-e607-5a69-894d-892e8bd1f5d4 | signoff | AUTHORITY HOLDPOINT
1506fbf7-5b48-517d-a6d7-cb5c453622a3 | checkpoint | 1.1.4 - IFC's specification
2450ca51-e036-508c-b9f4-8d0a3dbd04a8 | note | Method/Description - Document Review
ecf481fe-aa10-5f6c-9eeb-33e0dc2a64a3 | note | Test frequency - Once prior to works commencing
20b4c479-3a6d-5812-9a25-7374d89f6fdb | note | Contractor - H
9f9cade3-9e8b-5b6d-834e-672f2279b41e | note | Designer - H
86591545-de2f-5cef-8092-31f351edb218 | note | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
2358ac4e-bff1-5d5e-8f51-59f40a42db53 | signoff | AUTHORITY HOLDPOINT
66467056-0c6d-5a0c-8857-462d47f00167 | checkpoint | 1.1.5 - IFC drawings
d8ddcaa6-3582-5415-81c3-661c617f6746 | note | Method/Description - Document Review
83b2c398-5712-59c6-a5db-35bfd54ccb56 | note | Test frequency - Once prior to works commencing
5c4b541e-c631-5927-992e-7794c26099b2 | note | Contractor - H
3bcfe335-1b32-5b01-a8c3-d3124621f671 | note | Designer - H
e7cf6945-0b86-53c6-a8bd-15cd5969fe82 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
9f8f9341-c120-5c71-b92d-67279bb7414d | signoff | AUTHORITY HOLDPOINT
316bbdcc-8b33-5a80-808c-5b370f7f4360 | checkpoint | 1.1.6 - Approved earthworks model
dbdd446d-910f-5404-aff5-101f91ddd9e3 | note | Method/Description - Document Review
a52bbb2b-cdd1-5db8-9599-2bb2aff2ebe5 | note | Test frequency - Every new Earthworks Model and prior to work commencing
3604447a-d645-5d16-85c1-4d0ce474b5bf | note | Contractor - H
da4ad63a-38af-5b42-8c77-10e66b0f0fb6 | note | Designer - H
6d2e6e99-3707-508d-a97d-0d75889b5c9a | note | Verifying Records Checklists, Test and Supplier Certificates - ?
cda43a17-cf1a-5b2c-ae43-dc8d2fdf0ccb | signoff | AUTHORITY HOLDPOINT
19d8b93b-c4a4-55e7-ad84-fcfed6a60769 | checkpoint | 1.1.7 - Approval of stockpile location
1b3a81d4-0e09-5121-9c26-788f157b3581 | note | Method/Description - Document Review & Approval
326eba61-a9dc-5712-b9ca-9966dc847b73 | note | Test frequency - Prior to works commencing
b25e1244-930e-50ab-bb58-0e00d83a8336 | note | Contractor - H
0fe42e9c-25ef-5976-a855-5eb2a06e11c0 | note | Designer - H
d6e67424-952f-5384-bec9-25ef44e9b841 | note | Verifying Records Checklists, Test and Supplier Certificates - ?
724843d0-fcb5-5464-bdfa-4148b5a2ce77 | signoff | AUTHORITY HOLDPOINT
40ac7040-23b3-5151-b100-bc666aea5ad7 | section | 1.2.0 Material Compliance
a1238f1d-a91f-504e-994d-e554accc72cb | checkpoint | 1.2.1 - Structural fill
5fc7058d-46da-5dfd-a86d-1732f318088c | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
cc0df67d-b45e-5269-b280-818b498dd30f | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
caf36ebc-9909-584e-aef0-edd566e89c93 | note | • Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8
cec78310-376b-52e9-b854-ce279b2cbb61 | note | Test frequency - 1 test per 20,000m³
06e6a241-3136-5004-8427-a080f041cd13 | note | Contractor - H
617c7773-2781-5469-bfc5-843c1ba862da | note | Designer - W
d698a9e7-51a5-5ed3-bdf9-c793b6b02760 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
57f696ae-0fa0-54e5-8594-35630edd6b1a | signoff | AUTHORITY HOLDPOINT
4375cfa0-b14d-59a0-a47d-b583f3b063a4 | checkpoint | 1.2.2 - Buttress Fill
6e842e6a-54ff-59d3-9470-fb4a5205080a | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
45ecceae-e84d-57d2-a88e-f8bdab0ad1ff | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
1f04baf1-07ca-5358-88c2-91c150c5d2bf | note | Test frequency - 1 test per 20,000m3
0a900ba6-1f79-5556-9fcd-ecd98196d97d | note | Contractor - H
f92a7750-3e4e-5d0a-a3a9-a900b540ce28 | note | Designer - W
670aa45d-4889-5e43-b84a-e1249e99e5d2 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
c0efaaf7-f4e4-5afb-b6b5-5becf2f21833 | checkpoint | 1.2.3 - GAP 65
9c740a6e-8cdb-52a6-9d62-8e429ce97fd9 | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.3
67480ea2-8248-598c-823e-7344fffeb339 | note | • NZS 4402 Supplement No 1:1998 - Test 3.8.1 Determination of the particle size distribution Standard method by wet sieving
be8cc692-0330-558a-b852-0ea7a4214757 | note | • Large shear box (min 3 normal stresses) - BS 1377 Part 7: 1990. Methods of tests for Soils for civil engineering purposes – Part 7 : Shear strength tests (total stress).Test 5 – Determination of shear strength by direct shear (large shear box apparatus)
e6bea317-9c5a-5276-8c06-2e25199693e4 | note | Test frequency - Determination of the dry density/water content - 3 tests per source.
c694db45-500d-57b6-90c3-0997b8a422df | note | • PSD - 3 no. tests per source + 1 test per 2,000m3.
75054765-b58d-5321-b86b-3576953a5afa | note | • Permeability, Large shear box (min 3 normal stresses) - 3 no. tests per source
bd06ccbb-640f-559d-9286-017191331ada | note | Contractor - H
9bb7105e-96e5-5b5b-b5a9-c3e8c81a4c45 | note | Designer - W
c5bcb335-c9c1-5f34-bdff-091d90a12925 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
91de1951-4552-50a8-8b6d-89dffc792541 | checkpoint | 1.2.4 - GAP 65
b95347ff-aa0e-5115-af84-f66859e6c3bd | note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
c1f243d8-d504-571f-8662-93d4b1b08273 | note | Test frequency - 3 no. tests per source and 1 test per 2000m3
1c4c2757-5579-5847-82e5-8f21a5255178 | note | Contractor - H
8ef58d5b-1336-52d3-91e5-f42d49851d85 | note | Designer - W
5609d593-aac0-5012-8424-f895ca3aa213 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
61091160-50f7-5108-8cbe-c665a30e8ac7 | checkpoint | 1.2.5 - Cement stabilised structural fill
23fe0fbd-c79a-5fd2-bfc0-a2888cef20ea | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
ef52621c-cc35-5389-9836-fc2ac990b949 | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
76bde9e1-5a97-5375-98cf-727ab48a46aa | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
a4fae4c5-76c9-5f65-bc55-8e3b5b2f4a2b | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
b9c041f6-1aa6-539d-87ac-4f9364055105 | note | • Atterberg limit - 1 test per source and 1 test per 500 m3
85a13705-1cdb-5924-9a3a-f225b9fabdd2 | note | • UCS - 3 no. tests per source at adopted cement ratio.
17d9408c-e7c0-5a2d-90b9-7d0912274a11 | note | Contractor - H
e93eefa6-9f30-5c6d-9395-ef2bea0b7640 | note | Designer - W
bf1b304c-f40d-58ad-a6cf-d83763cf48e7 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
2e35b49a-2d9d-59fa-b7b4-d467015e88c4 | checkpoint | 1.2.6 - MSE Fill
c924383a-bf1e-57a6-97ab-b7327c09ef88 | note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
4bf57aed-417b-5982-8772-317488d061c6 | note | Test frequency - 3 no. tests per source and 1 test per 2500m3
4a95af0c-5716-5bf3-8137-06135e0403f7 | note | Contractor - H
86686b7e-b0c1-5e3b-8575-9804afd8440f | note | Designer - W
b83b7c0a-9874-5bbc-89d6-b929b0828073 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
c4ea4217-0ca9-5320-ae9c-f4a7996a939b | checkpoint | 1.2.8 - Cement stabilised GAP 65
e8758f56-a0ce-5fd0-813e-4b7520f917a5 | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
7be8c2e0-eadc-5384-ad7d-c5109ece7686 | note | • NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving
29d3a139-27f9-5be9-9860-dfbf27d5f1c9 | note | • NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer
aeeba150-74c3-5372-8492-c67b72ecb26c | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
3312b536-d2c2-5662-91f2-640a460737e0 | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
9a133854-2b1a-5cf6-a81e-b33e01e4cdff | note | • PSD - 3 no. tests per source + 1 test per 2,000 m3
4a64f4f3-3f6e-5fc2-b3f9-39b5564623c6 | note | • UCS - 3 no. tests per source at adopted cement ratio.
3890c8ee-7f55-5734-bb14-8ac156315037 | note | Contractor - H
c3c19303-7fa6-5e2e-aab1-6e88c6ed3e80 | note | Designer - W
222c3b85-555a-5189-93d0-137c0f28e710 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
0aacd5c2-02bb-5e46-82b4-75d8e4af789c | checkpoint | 1.2.9 - Cement stabilised structural fill
ce1a64af-ba5d-5af2-9c4a-bd52d9c04c5d | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
d390698d-822c-582c-b0f0-2c1a57a3b314 | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
e42c1b44-e183-5f1d-b8ec-594f650831e0 | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
7312d13e-7a47-59fc-810b-63332e2a420a | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
3f5d2f30-e252-5ec0-b102-00e15489ebf4 | note | • Atterberg limit - 1 test per source and 1 test per 500 m3
9f298b74-ab69-52d8-9b49-094ec559f3fb | note | • UCS - 3 no. tests per source at adopted cement ratio.
11a054a6-eb72-57a0-ade8-885820346df2 | note | Contractor - H
89b7c534-a19b-5331-8ec4-61780cdf09ef | note | Designer - W
3a63962c-0f91-5111-9c75-5e5db315b837 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
2cb6f306-2e70-5654-8402-8b2ec9e52277 | section | 1.3.0 Geosynthetics, geogrid and basal reinforcement - Pre-construction
a0d1b4c5-5949-5558-8250-7684a084cf68 | checkpoint | 1.3.1 - Product name Name and address of producer/supplier Manufacturer’s compliance certificate
dfc6d86c-a7d0-549d-8103-ebfbc43d72b9 | note | Method/Description - Document Review
3f49e66f-27b3-5db3-b4c7-01ae780c9357 | note | Test frequency - Check each lot (1 roll)
3dcf9eaf-134d-5b8b-b37c-d452438c3c81 | note | Contractor - H
6a00fbbb-96b0-571a-844c-dc0fdbfc4520 | note | Designer - W
977b0cb2-fab5-597f-ad3d-fcb59fcf2fa1 | note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
b8261911-8ced-51ae-8ad1-71ec10996ee5 | checkpoint | 1.3.2 - Tensile strength (machine direction) - geogrid and basal reinforcement
6b312682-20dd-5521-a652-4a804adb6c19 | note | Method/Description - Document Review
27d5b2fa-0b8c-5a08-970c-9d355b1461ca | note | Test frequency - 1 test per production batch
90077b3b-9ade-5198-aea3-b92e7a44febe | note | Contractor - H
9fe05ba0-e3d1-5689-abd2-9f043b9dcff1 | note | Designer - W
5acde8d0-aa95-5250-bfab-031799620b49 | note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
b4649fe9-a20a-5953-8fd0-6c614ee5b97b | checkpoint | 1.3.3 - Visual inspection - separation geotextiles, basal reinforcement
7edba1c7-cfc6-5c26-9ac6-8a370dbd5f8f | note | Method/Description - To inspect geotextile and basal reinforement is the proper type and no tears, rips or other signs of deterioration.
70b3561c-9dae-5efe-ad2e-218ddbe437cb | note | Test frequency - Check each lot (1 roll)
dc30d6c0-16d2-52b2-a254-58e7f99e486e | note | Contractor - H
cff40156-97da-5a03-b246-2ecb3e6845b5 | note | Designer - W
b2445143-698f-575b-9370-ce13a1387c07 | note | Verifying Records Checklists, Test and Supplier Certificates - Approval checklist
1a6ab162-84a3-5713-bd08-b7d0fc7fd420 | checkpoint | 1.3.4 - Visual inspection - geogrids
a6fa02d3-5d52-5402-a62a-291db157f256 | note | Method/Description - To inspect geogrid is the proper type and no tears, rips or other signs of deterioration.
7af6b0af-0b4b-52e4-9c62-24c8b4e50d74 | note | Test frequency - Check each lot (1 roll)
f9a1cdca-dba7-50cf-9e52-bbd393bc9711 | note | Contractor - H
de95b5aa-14ff-5c6f-95ba-fd9685ca48ad | note | Designer - W
d8e9db36-8fb2-50b3-aea1-8439359b718f | note | Verifying Records Checklists, Test and Supplier Certificates - Approval checklist
d65f2e5c-a857-5839-a24b-993bea45ce2f | section | 1.4.0 Monitoring - Pre-construction
42702933-7cc6-5ba0-b870-39eda8f6d009 | checkpoint | 1.4.1 - Monitoring prior to preload
4e4ad618-ec23-5ca0-ab5e-a1237938ffd1 | note | Method/Description - Baseline readings
057ae6a7-fec6-5698-85ae-f7f142d42112 | note | Test frequency - Settlement marker, extensometer, profilometer, and lateral deformation markers - 1 month before construction start. 2 consistent readings (24 hrs apart) post installation and one immediately prior to filling Vibrating wire piezometer - 1 month
c5f36bfe-9cf2-546e-bad0-d56637147e4c | note | Contractor - H
1b6b515d-d125-5456-9c97-3c1e434b5a2c | note | Designer - H
096e062b-f92d-5bff-bb7c-915e2808986d | note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary - confirming baseline readings satisfactory
62a168bf-14f7-5bcb-ae11-291e4b8c17b8 | signoff | AUTHORITY HOLDPOINT
cf067a8d-e9b1-5966-8add-fb54234eef7d | section | 2.1.0 Pre-filling
58543979-2b9b-5921-8d5b-0c34906f420b | checkpoint | 2.1.1 - Set out extents of fill and check against design
1056ca91-1289-58de-922b-0e500e9fcfff | note | Method/Description - Survey/visual
7b79e7d6-a31a-5931-bd63-9a1dd80f8e9e | note | Test frequency - Prior to Commencement
50ac7331-e74c-5514-97e2-9cab71b1f8e2 | note | Contractor - W
438590e0-ed48-5b3d-add6-e2963b4df405 | checkpoint | 2.1.2 - Vegetation Clearance
e3e61131-c40d-5470-a93c-090e828e4830 | note | Method/Description - Survey/visual
40e89c54-9b20-5897-855a-227d098f02fc | note | Test frequency - Fill area foot print
610d68e9-9738-5b5c-920f-9ab0b99e6e3f | note | Contractor - H
40ee3f69-74ac-54fe-8a49-a9c419d5bec0 | note | Designer - W
5f2ced3b-2e57-58bb-b07b-88b49adfa8c7 | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet Designer site report (where advise given)
862245e6-f218-5a61-bb79-c5bfceec4f89 | checkpoint | 2.1.4 - Designer witness of in-situ subgrade prior to filling
0c7fa32b-93be-5b2c-86b8-e0c3a56c0203 | note | Method/Description - Visual inspection
4832ef5e-f47d-59e9-9a4c-bda04d23df25 | note | Test frequency - Prior to Filling
dc11d2b9-4407-54a9-88b9-33f592567cbb | note | Contractor - H
29e6c598-5b25-5aa2-beeb-530dd25eac36 | note | Designer - H
bf8b4fed-9c9b-52b3-b994-a42be9f71a1b | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
e1215e41-225a-5d6b-b773-fa60c65c633d | signoff | AUTHORITY HOLDPOINT
9544fc50-a083-526d-a563-9ec7a24959fb | checkpoint | 2.1.5 - General Undercuts
ac514d07-ddf0-592a-9153-4b5f546ab61d | note | Method/Description - Visual inspection
41dcbadf-ec3e-5ec3-84e6-400a3e26dc92 | note | Test frequency - Prior to Filling
a9e77516-a4c9-5340-aee7-d28fb19d4c46 | note | Contractor - I
7ac43eb5-b116-58fd-9178-36a0750aa2a8 | note | Designer - I
f0c579ef-ad83-53bc-97fc-53c6d8a96f31 | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
70202bbd-c12a-58c1-8344-9ef760ec6ead | checkpoint | 2.1.6 - Required undercuts for basal reinforcement installation
3480f777-a904-56eb-b9a4-d79f2b8c6219 | note | Method/Description - Visual inspection
06520e0f-6a06-5bd0-a4d5-4a8b37a31a13 | note | Test frequency - Prior to Filling
1f3264c8-20f1-5c43-ab5f-d35d7b96716e | note | Contractor - H
ab67a8df-28ab-5ae8-896b-013dd1bc9f9a | note | Designer - H
6f3e9b22-78ae-5763-b926-430f662340d3 | signoff | AUTHORITY HOLDPOINT
260c5884-acfb-5f8f-b8b0-bf35f1a7392a | checkpoint | 2.1.7 - Basal reinforcement installation
ee8adac9-fea8-542c-a789-b01a47493bca | note | Method/Description - Visual inspection of directional placement, panel length, laps, and damage
c662db2d-fab3-5b38-b749-9e849f6ea002 | note | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
84f5833c-b83f-58ea-bc82-75e82a408384 | note | Contractor - H
5067dfdf-d82a-54b2-8fc7-a37183507390 | note | Designer - H
f8c44445-6c82-55aa-96fa-0de241f02e15 | signoff | AUTHORITY HOLDPOINT
a6fb49d7-acf8-5f1b-ba57-15cc1e5a84d6 | checkpoint | 2.1.8 - Drainage blanket installation
bf44088c-6a88-5529-a4cd-fa2d06cccbba | note | Method/Description - Visual inspection
0a5f93b0-2ea9-5639-a053-77137316c762 | note | Test frequency - Prior to filling, and every 100m2 of geotextile installed.
c2db837e-4a44-5d64-9d6e-7e5e937c4872 | note | Contractor - H
f0c2daf9-4a2e-5221-a69f-8912915cd473 | note | Designer - H
fd0f6409-f3be-58b9-aaa7-79259a6aa1ac | signoff | AUTHORITY HOLDPOINT
72d9decb-4e4b-5ba1-9f0e-7853deac0d90 | checkpoint | 2.1.9 - Construction of wick drains
eed9ab96-9869-5901-9c98-73d791d28672 | note | Method/Description - Visual inspection and subcontractor record review
0dd722de-cdb6-58d0-b1f1-8c1fb2be2a69 | note | Test frequency - During wick drain construction
17596efd-2352-5432-9700-9e4d831de1d3 | note | Contractor - I
6cd7e87c-a2bd-5455-ae74-ad01f88c9c21 | note | Designer - W
7a4c5c42-e10c-5dfe-b933-747f38f45850 | note | Verifying Records Checklists, Test and Supplier Certificates - Wick drain check list
075a395e-5b9e-5fa4-914a-7b13d0564ca7 | checkpoint | 2.1.10 - Sub soil drainage
42ccfbf3-d7c8-5861-8695-87ef965970d0 | note | Method/Description - Inspection
3f6da756-e5f2-56f8-b4f6-cb3a297f7a5e | note | Test frequency - During subsoil construction
4e5a0339-543f-5332-92ca-06f701caa96a | note | Contractor - I
c42fb20e-057b-5948-a395-7a9c068ca1f4 | note | Designer - I
74c8065b-cd85-5891-a6fc-9f12d70d5128 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
3afa5f76-2a6d-5f28-9ab5-e2c4fe8297d6 | checkpoint | 2.1.11 - Monitoring Equipment
6b9bea36-81df-5467-b603-75cead2f7917 | note | Method/Description - Survey/ data logging
bfccd6c5-e006-5bd0-915b-9f1becba6486 | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
abf886e1-f802-519f-a7f1-802dca3eb53d | note | Contractor - W
0454222b-e3bc-5f84-823b-bacf51f4567f | note | Verifying Records Checklists, Test and Supplier Certificates - Drill logs
f5ed585a-3cba-525c-9dc6-89488bcc7c81 | section | 2.2.0 Fill Construction
ca8d15bd-63b2-5c11-9d8f-b2ab8edfad49 | checkpoint | 2.2.1 - Filling operations
1e4eee05-2b8b-5f7e-a4ad-75a8996d96ca | note | Method/Description - Visual inspection
0d9b7c2e-1f76-5e9b-9b34-987cbad8a792 | note | Test frequency - Daily
f5b59f25-1b02-5c93-abd6-bc4790a820d3 | note | Contractor - W
10a7a72d-399a-50e4-912a-938f130c7865 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
c6c48250-3625-5f48-8d72-509cfed59c1c | checkpoint | 2.2.2 - Filling operations
590f413c-bc5c-501f-9230-21d41c7b9ae8 | note | Method/Description - Survey/visual
f09d59de-6754-51dc-bec3-c047c0a6951d | note | Test frequency - Daily
1580519a-7ac8-5084-9aa6-a7d0bf1036bf | note | Contractor - W
23fa558f-48fd-518e-bad3-d13dc474fb25 | note | Verifying Records Checklists, Test and Supplier Certificates - test report
854030b8-6c68-56b3-b5d6-595a65916d36 | checkpoint | 2.2.3 - Insitu fill testing
ec20bb4c-a3d2-5065-a7fc-ccbb753ba82b | note | Method/Description - Plateau Test
a453c1a3-24d7-5eaf-8a06-5ac243dbeb4b | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone,
124fbdf9-52dc-5ff3-84c6-6fc5cf11502c | note | • Buttress Fill - 1 test per material type per earthworks zone
f0c0fca8-2726-598a-beed-31f8461f1af3 | note | • GAP65 - 1 test per material type per structure / location
d4efdf89-480c-5aa7-80a1-444e361aed7b | note | • Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
ee686f5a-7f8d-5631-bbf4-a4cc05909ece | note | Contractor - W
61833c91-188c-5c25-8c44-70fec08dc8a5 | note | Designer - W
f4b6f81b-bb5a-5bb0-850c-0cc72ba47c9d | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
67fa0f67-96ef-5f19-ad08-3d77ea125216 | checkpoint | 2.2.4 - Insitu fill testing
fe14da24-958a-5b46-9de0-6ea0dfc8194d | note | Method/Description - In situ moisture content and density
5b0cc25b-0198-57a4-96b8-f7aedf5e4bdc | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length (approx 1 per 3000 m3) ; 1 test per lift per 50m length for top 1m of fill to subgrade level
3b5133b0-010c-5881-a1e8-5c20acdf6578 | note | • Buttress fill - 1 test per 200m length, approx 1 per 6000 m3
31c10d01-6a27-5b09-ba92-7d533d7d96e2 | note | • GAP65 - 4 tests per lift per structure
b95fa105-1813-5254-82fa-76d19ad6a362 | note | • Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
5eb78135-4bbc-52f3-a53a-94582587602c | note | • Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
1da394e1-1f8b-57d8-9229-00c507273604 | note | Contractor - W
2d842370-226b-5726-93ec-9ad07c0c106c | note | Designer - R
052d651a-6597-5ca1-a7b2-12188636fab2 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
0900f54e-be40-59d0-8c13-6db2d40791b3 | checkpoint | 2.2.5 - Insitu fill testing
ffe420a6-fa5e-5bd3-b6a5-db05ea076886 | note | Method/Description - Undrained shear Strength
12f930a3-afd3-5cd4-a47a-aaf3eb346a33 | note | Test frequency - Structural fill - 1 test per layer per 1000m2
d25a3467-ec32-5c9d-a55e-383c0a71567c | note | • Buttress Fill - 1 Test per layer per 2000m2
1635b668-6837-5e3d-a324-fad5ee830c8b | note | • Cement Stabilised Structural Fill - 1 test per layer per 500m2
283ac3a3-2e88-5042-82a5-6988c1b4c8e9 | note | Contractor - W
ae593c0e-dadc-56ce-a786-a4cf8aa09216 | note | Designer - R
703e8fbb-92b2-557c-9f05-380b2439272a | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
cbc38db0-5d27-5cb8-a99b-eecad01c06aa | checkpoint | 2.2.6 - Pavement Subgrade Fill Testing
cc647bff-19fc-50e3-8464-a62cdaa5f4e2 | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
50ab74b6-3db2-5da6-be8c-0764f24d0f39 | note | Test frequency - Surcharged Fills - 1 test at subgrade formation level per 50m length, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth
a669c3db-1caf-5be6-9e9a-fcf790db4faa | note | Contractor - W
cc7eae38-0c01-5b0f-86f1-5127d4ebc492 | note | Designer - R
bc577fb3-7c22-5f3d-aa96-cb1fedcbbdad | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
284a15fc-5f1e-5461-802b-39846fca04f0 | checkpoint | 2.2.7 - Pavement Subgrade Fill Testing
b2390827-462b-5793-91ae-2865fccef62b | note | Method/Description - Scala Penetrometer Surcharged Fills
6fc16cd9-d17f-57f9-b8e8-b0591bcaa905 | note | Test frequency - 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width
16b66314-a0aa-57d3-a05d-894fe995c16f | note | Contractor - W
664b35cc-d550-5ee2-b9fe-db2b478a84e0 | note | Designer - R
65d32115-8f52-592a-88a8-b6ad84eec55e | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
90f82bbc-7c77-5080-9894-3fee24b9e688 | checkpoint | 2.2.8 - Pavement Subgrade Fill Testing
01e3215c-e556-534b-a474-d5fa358c39d1 | note | Method/Description - Benkelman beam and FWD Testing
453fb531-f452-5b5b-9aed-aa2e53ca6026 | note | Test frequency - Surcharged Fills - At subgrade formation level 10m interval in each wheel path
a572348a-90b7-5565-ab36-52514901a76c | note | • Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
3134ec51-bfe1-5848-aab8-c6d362e75a81 | note | Contractor - W
0f8e517d-537c-5544-a591-34539a8f0986 | note | Designer - R
79a00819-98d5-5246-ae99-7eb67a88926c | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
4efa10f0-7afe-53e1-b597-18591b6c7850 | checkpoint | 2.2.9 - Pavement Subgrade Fill Testing
24a5717e-2919-5200-998b-997057ae1e1a | note | Method/Description - Laboratory Soaked CBR
1e4936b9-f357-57ff-b0c0-d98c2efc11b2 | note | Test frequency - Surcharged Fills and Cut Fill Transitions - 1 Test per 5000m2 at subgrade formation level
faf65416-3d56-58f3-85c1-015bebae8f29 | note | Contractor - W
8c6a3b80-1ba7-5bc3-81e0-d7bf5fda7642 | note | Designer - R
06f4e76b-e9c6-50ed-a167-d8eae77752f0 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
83fe715c-0c21-59e5-8e43-2a4cad5f184b | checkpoint | 2.2.10 - Confirm testing requirements are meet for insitu fill
af89f5a8-465b-5698-adec-10be03ae82a0 | note | Method/Description - Summarise, interpret and review test records
865041c7-878d-543a-846a-bbbbf75a23d5 | note | Test frequency - Every test result
a1854082-b9a5-599f-8a19-6a14e0b975c2 | note | Contractor - H
45e89e15-d49c-5fc0-a970-04f92ecdbf1e | note | Designer - H
8d8677ca-8b07-5302-b8b4-773fb9064aaf | note | Verifying Records Checklists, Test and Supplier Certificates - Review of testing records
8388a423-c359-55bc-9eff-1b899a325e81 | signoff | AUTHORITY HOLDPOINT
4641fb01-25ca-50ad-9142-2fea76a7350e | checkpoint | 2.2.11 - Failed test result and remedial approval
978410f7-d492-5c3f-8469-f4a587881556 | note | Method/Description - Review and approval of remedial action
da02a4e1-161d-5232-9191-1a3866fed6a4 | note | Test frequency - Every failed test and prior to remedial works
33cf084f-b57d-5e9f-bae4-3d31aa60290c | note | Contractor - H
eb9c6464-4c79-5082-b888-caa806c04c9e | note | Designer - H
bf673edb-be0e-5d76-a7be-9092fea4c24e | signoff | AUTHORITY HOLDPOINT
7f89079d-cda4-55b2-ab50-1a8db2ace849 | checkpoint | 2.2.12 - Insitu Fill Testing
82d4cdc0-3ec4-590f-bc86-5f7ca1bf3219 | note | Method/Description - Undrained shear Strength
22c5d558-a834-51b9-8b4a-934507e56f7f | note | Test frequency - Structural fill - 1 test per layer per 1000m2
2e832840-edc7-5ff5-9a03-7ef3dc05c5a3 | note | • Buttress Fill - 1 Test per layer per 2000m2
eece1da6-06bd-53e9-b2c9-cbb2a26f5e7c | note | • Cement Stabilised Structural Fill - 1 test per layer per 500m2
e8ee7147-d185-53a8-a85a-441af5ae2501 | note | Contractor - W
1cdec2cd-06d6-5f86-8dbc-cbc21614f28f | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
abf3d6d2-8f49-501e-8763-a456ac66b5f2 | section | 2.3.0 Preload/Surcharge (for embankments requiring preload)
6deb424e-254c-50ae-892e-99dec8122407 | checkpoint | 2.3.1 - Visual inspection for rate of filling
10c4545e-de25-5a5c-a168-4f21293bd73f | note | Method/Description - Inspection of fill height, rate of filling of 200mm/day (1m per week)
4f07bd8e-166d-5735-a1d8-267d811adfb3 | note | Test frequency - To be monitored daily
7806a283-7d1f-5d25-bb18-147fa620e32f | note | Contractor - H
065fbfb0-056f-5dfa-a5f8-32eff8f25091 | note | Designer - W
00e58ff8-9766-5514-9579-9d193dae66b4 | checkpoint | 2.3.2 - After 1m of fill placement. Await approval from Designer before placing more fill.
f2efcc47-ad20-52d1-9262-78af7d76a26f | note | Method/Description - Review data and TARP levels before releasing HOLD.
818092fa-e6cf-50c9-beae-ce0f8b8ff080 | note | Test frequency - Before releasing hold periods and allowing filling to continue.
366a83f9-ed1d-59b6-a51d-d91de90b554d | note | Contractor - H
d1f0ba82-7efe-5dcb-b6fc-1fbdf8798d13 | note | Designer - H
970d389c-1bce-51c8-8bd4-a427b9b4d60e | note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary
1a38b1ec-504f-57af-b33c-55650cd60378 | signoff | AUTHORITY HOLDPOINT
ba21e5c0-002b-581c-a9a2-df988f0b76ae | checkpoint | 2.3.3 - Removal of preload/surcharge
426f1f25-f038-5105-ae0b-f9faff0a44e5 | note | Method/Description - Assessment of monitoring and instrumentation data
d822bd21-2701-5001-9dd5-d8f220626730 | note | Test frequency - After completion of proposed hold period
5e007f41-66e9-542d-aa89-517a5c49edca | note | Contractor - H
e6c88f6a-d0ac-54a6-8221-9f476f4bd4ac | note | Designer - H
876481c0-bb68-5bb8-8241-0b258305c146 | signoff | AUTHORITY HOLDPOINT
5d38b1b1-f66a-5279-a5d4-cfbcba80db16 | section | 2.4.0 Monitoring
21607b28-2d45-5c79-8c1e-c9d831eb80c9 | checkpoint | 2.4.1 - During earth filling/preloading/surcharging
0508c0c1-3b68-5298-ab26-971a6c8cdd4d | note | Method/Description - Monitoring during earth filling/preloading/surcharging
ac6e85aa-d9b7-56a1-b2d4-9ed493d69c5e | note | Test frequency - Plate settlement marker, extensometer, profilometer, water standpipe, and lateral deformation marker- twice weekly Vibrating wire piezometer - hourly reading via data logger, twice weekly download
7b43fb96-5a3d-5665-861f-a1c7fd890290 | note | Contractor - W
ea56ba06-57cd-5c61-9b21-b229ce4daedf | checkpoint | 2.4.2 - During preload or surcharge hold period
ec8a779d-8d2d-594b-907c-c8f6dd8e0c8a | note | Method/Description - Monitoring during preloading or surcharge hold period
d60d1926-e190-5341-9c8b-a189abfec7ad | note | Test frequency - Plate settlement marker, extensometer and profilometer, and lateral deformation marker - twice weekly for the first month then weekly. Vibrating wire piezometer - hourly reading via data logger, twice weekly download
678f212b-8a42-5868-a84c-12b6fbed5944 | note | Contractor - W
0cf7ff11-e900-53fd-bf72-eb63a2e335fb | checkpoint | 2.4.3 - At surcharge removal or hold period release
1c573b88-3078-5933-91db-1c442ee4743d | note | Method/Description - Monitoring at surcharge removal or hold period release
4c9e8f91-f39a-572f-a85a-6505d660fd59 | note | Test frequency - Plate settlement marker, extensometer and profilometer, lateral deformation marker, and vibrating wire piezometer - one reading 24 hours prior and one reading 24 hours following.
7a325fb4-0492-5d84-bdd5-f0cbfe83eff1 | note | Contractor - W
28f0a228-5fb7-5aaf-bb29-794b3586bca9 | section | 2.5.0 Monitoring reports
8b606181-c983-5bca-88dc-b467817ced37 | checkpoint | 2.5.1 - Preliminary inspection/monitoring report
b08d460d-bc6d-5fba-b22b-ad6393e8bc26 | note | Method/Description - Summary of site inspection / observation / measurement
16ce8cc1-eecb-5edc-ae6b-8e98181bffa8 | note | Test frequency - Within one working day of site inspection/observation/measurement
2967dff5-eddc-54d8-926c-341b575369c9 | note | Contractor - W
7f047d64-3aed-5f16-821e-f32443e70d74 | checkpoint | 2.5.2 - Inspection/ monitoring report
9f48fe2d-8360-5dda-a43f-e4871c95e452 | note | Report - Full and certified results
3dfc2134-58ee-5b80-88dd-5c8590d4f4a6 | note | Frequency/timing - Within five working days of reading the particular instrument
4e48e42a-eaec-50aa-90db-eb341fc3afc4 | note | Owner - Construction Team and Geotechnical Technician
8b2b65f7-137a-56db-b113-5b69bccfff7b | note | Distribution - Geotechnical Engineer, Geotechnical Lead
c7e4d0ae-e975-5d2e-b7f3-b9458e127e4c | checkpoint | 2.5.3 - Pre surcharge removal report
ff8beb86-d12f-5560-8246-a1c80f7c0678 | note | Report - Comparison between monitored results and baseline design predictions in both table and graphical format. Provide approval to remove surcharge.
a7d4b419-c260-5cf8-96f5-a4e0b22aa619 | note | Frequency/timing - Prior to surcharge removal at each fill
e60d8ccf-98e9-5478-985a-87c124c23c05 | note | Owner - Geotechnical Engineer (with Geotechnical Lead approval)
6a7e8fcd-a899-5703-8f66-c8f396c9dd6e | note | Distribution - Design Manager, Construction Manager
d5545795-84a2-5564-99ac-44165c0761fb | section | 3.0 Post Construction
c421ac5b-2341-54ac-9eef-7f76b03d37ee | checkpoint | 3.2 - Survey As-builts
5da60d60-bdd0-5bfe-b0e7-868735364dd0 | note | Test frequency - During construction and at end
2b08a453-1ed5-568f-9545-ce3745e7ef82 | note | Contractor - H
cff27b27-0d6d-53c6-8a51-7394f8cc638a | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
f942a45e-241e-5b37-8e44-9028309ca493 | checkpoint | 3.3 - As-builts
8d12136b-99b7-56a6-b8e8-423c4f932c01 | note | Method/Description - Mark up of construction drawings to reflect completed works
b5546a51-57d1-5cf1-9ae4-55734aedefc3 | note | Test frequency - End of Construction or after completion of preload/surcharge works
79a814d3-c269-50a3-8459-acaec7673abd | note | Contractor - H
3dd1ce46-19e3-55b4-9cd6-a7d70d14373c | note | Designer - H
4110ec92-8b1c-5466-a377-9bccbb7254f0 | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
a7e79338-2b18-506b-bce6-2cb742cbfcd9 | signoff | AUTHORITY HOLDPOINT
8919eff8-fed3-572c-bcf7-d24e7712e7ba | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
45524c2d-1de8-5e60-b52d-1f4484181dd2 | checkpoint | ITP Close-Out by
37d3795c-51da-5d7f-ad97-0fb503cf9c4f | note | Site Engineer/Project Engineer
7726aa8f-f137-5131-9ccb-a0d7cb3915d0 | note | Zone Manager Approval
9ee3c4da-5bab-5d55-ba41-2d8efd8d318b | note | Construction Manager Approval
c4b083ec-831a-54d2-ad43-5c7405c973ff | note | Quality Manager Approval
8093829e-d2ee-5a87-9383-b08bc5ebef17 | date | Date:
1dc2c9d0-048a-5501-9488-936d3248a797 | signoff | SIGNATURE
8d601d1c-06a2-5f2f-bba2-8c4ea77dd9f2 | checklist | ITP-013 - Fill 13 Rev 2 | itp | ITP-013 - Fill 13 Rev 2
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
c9e7969a-5007-57ec-ba14-7e88241a4737 | checkpoint | 1.01 - CWP
1fd7bc15-7b75-56ee-90ea-64d2ed7cd0fa | note | Method/Description - Document Review
2d6fe952-cf71-5bfc-9670-82288734cf09 | note | Test frequency - Prior to personal starting
edeb92b5-8427-55c7-a8c3-c6d9907e3017 | note | Contractor - H
3d72a513-8b7c-5811-9207-becb8381f6b0 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
5c6d3d2d-8b90-5b45-ac77-8cb3e4b937f4 | checkpoint | 1.02 - Design
8c4b0047-156c-586f-8f33-0259491ef1fb | note | Method/Description - Document Review
5d603b27-a348-586b-9d5d-4a9e16c405df | note | Test frequency - Prior to starting
58328657-106f-576e-bef9-66260f63f3bb | note | Contractor - H
94770155-8c54-523d-86d3-f5001fe94dac | note | Designer - H
230170c5-4b0d-5a1c-831d-aee8dcc0214b | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
7bd1fe4b-029d-5a22-999a-91130e63165b | signoff | AUTHORITY HOLDPOINT
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
c5860170-7555-5902-b6a0-5e5af09b61c9 | checkpoint | 2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural fill Material
843a877e-afab-5723-b797-d1e3e4a6d016 | note | Method/Description - NZS 4402:1986, Test 4.1.2
1ef9ada4-cbd5-5c9f-8615-b75fcad5a5a7 | note | Contractor - H
5e07418b-5d1e-525a-a70f-5f83018efce4 | note | Designer - R
15750547-c9ba-5ba1-9d88-1a2406902a8e | note | Lab - I
79172de2-0ca6-53ba-a825-f50e292e216d | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
235d1d5d-9af2-5bc5-ae7f-3fd0f28baa68 | checkpoint | 2.02 - Atterberg limits test for Structural fill Material
72f577ab-2a72-5a15-ad9a-e191a2caf005 | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
de4a0cb6-c889-55ba-8927-2ac74ed52b77 | note | Test frequency - 1 test per 20,000m3
68c11a0c-177b-5be6-93bf-517e2dfc875e | note | Contractor - H
961cda57-bca9-5b4a-955e-9a7dbb6bed30 | note | Designer - H
7a1bc3f8-bd1e-5d53-9c31-69881a980b0e | note | Lab - I
4bc29786-16d7-58af-bf4a-a7ad9a0c980c | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
293db33c-cb61-566d-bafc-5f8ae2ab4a45 | signoff | AUTHORITY HOLDPOINT
7f582d98-61ec-5278-8c11-9dc43d59f9f2 | checkpoint | 2.03 - Determination of the dry density/water content relationship (Heavy Compaction) for Buttress Fill Material
77274685-363e-5166-8b0d-d0c591def09e | note | Method/Description - NZS 4402:1986, Test 4.1.2
7752ce6a-848f-5a2b-a67a-7bafbb4ea3cc | note | Test frequency - 1 test per 20,000m3
6528791e-e046-5199-961c-637065c8e122 | note | Contractor - H
ba85572a-b910-5b85-a31c-3d45d151896b | note | Designer - R
fd085827-22c6-5c13-8b09-7169179cdc50 | note | Lab - I
c04d6f18-c424-5035-b42f-9e3927ce7a25 | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
7d6904fa-05eb-5017-88ff-f9f456e0acf7 | checkpoint | 2.04 - Atterberg limits test for Buttress Fill Material
8a95d50b-0ed7-5eb7-ac6b-cb116f08a00c | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
d40d8914-fc9f-5087-b619-570794d09068 | note | Test frequency - 1 test per 20,000m3
d0e7a1bf-18ae-5d3c-9ddc-11a18a26a493 | note | Contractor - H
86321d19-6dbb-5254-a501-5d77605be0e4 | note | Designer - H
e465448c-730b-51f5-ae47-fb85cf4cf9c3 | note | Lab - I
d2039d21-6adb-51fe-b0b6-42b6ffe81ea3 | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
4102e8ea-397b-58f8-b887-3bfbfdb96db5 | signoff | AUTHORITY HOLDPOINT
eaa4bde7-3333-5990-8dc2-4ced4d650c06 | checkpoint | 2.05 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material
59c8614f-2e45-5e4f-9743-8a85113f31d2 | note | Method/Description - NZS 4402:1986, Test 4.1.2
4c5d01f7-83ce-5d1e-a077-be848a7a3331 | note | Test frequency - Source approval 3 no. tests
89b60b08-8f3e-54ca-9ef8-dfb5b94e8796 | note | Contractor - H
e9e855b8-09c3-54ef-a955-eaf22a116a54 | note | Designer - R
fd0f7e41-5f28-5608-ab38-013121f9a32c | note | Lab - I
5680fc2a-f6a3-5777-ab0d-2e4c09368ab6 | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
3cdaa73e-31f8-5bf7-b4d2-bda5d46ff56a | checkpoint | 2.06 - Particle size distribution (PSD) Test for GAP 65 material
c58ec3c9-7664-5157-bca8-635f273b82ed | note | Method/Description - NZS 4402:1986, Test 2.8
cf0895ad-19e5-5b0e-b9d8-091871b6f1b5 | note | Test frequency - Source approval 3 no. tests then every 2000m3.
1abed39a-ae15-58af-970a-6dbfe703977a | note | Contractor - H
269fd288-f6d2-57f6-82de-75a839740e51 | note | Designer - H
de9dfa1a-7598-5996-a7af-4af5f530f547 | note | Lab - I
002b2aff-3acf-56b7-a722-7313097c1c9c | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
e451af1e-f752-5a54-a441-a4e522577541 | signoff | AUTHORITY HOLDPOINT
4c70cee2-b353-538d-9f04-883677264fe7 | checkpoint | 2.07 - Permeability test for GAP 65 material
7dc369cc-95bb-57ae-916d-21dc44695ba0 | note | Method/Description - ASTM D5084 - 16a
d1a1acf0-6d24-5080-bea1-1c701a025846 | note | Test frequency - Source approval 3 no. tests
94a91b89-d0a8-5a67-a9f3-b94e543b9ed3 | note | Contractor - H
b903f8b7-4152-5c05-a0a5-a4d33407e4a2 | note | Designer - H
7ab9cec1-9ef3-5aa9-b1c6-78aec72effc7 | note | Lab - I
b81b7762-fb5d-52d7-9768-8556a5d26523 | note | Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report
6732cb05-6996-515f-bdee-b84ec622ba5a | signoff | AUTHORITY HOLDPOINT
39b08672-8e77-55f3-b312-9ca6941ef427 | checkpoint | 2.08 - Large Shear Box test for GAP 65 material (Minimum 3 normal stresses)
c7dd4807-fd23-5a31-8f65-bf05b38287ff | note | Method/Description - BS 1377 Part 7:1990 Test 5 Determaination of shear strength by direct shear
64d05026-d66a-5dab-a65c-e3d8a405ddfb | note | Test frequency - Source approval 3 no. tests
dd13388b-8d66-5cc1-9dfa-f06963b57cc2 | note | Contractor - H
4337f88f-dca1-5467-bd54-55c5b1554046 | note | Designer - H
788774d5-ab12-5488-b468-77e7e0765170 | note | Lab - I
1e1555b5-06a7-5c07-b84b-a6f929879d60 | note | Verifying Records Checklists, Test and Supplier Certificates - Direct Shear Strength Test Report
b17bc04f-f801-5254-b66f-20b0b5af172a | signoff | AUTHORITY HOLDPOINT
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
f80e3859-9837-5795-b26c-edce867f3449 | checkpoint | 3.01 - Set out extents of fill and check against design
54470988-20a7-588b-9eaa-7de92c883ade | note | Method/Description - Survey/visual
dbbcf320-807a-50e3-a052-c5f4f8daaca6 | note | Test frequency - Prior to Commencement
a3ca4369-038a-5267-ae01-95a64d991327 | note | Contractor - W
9a2366ea-dde1-5a1f-aa20-31976fcfcac4 | checkpoint | 3.02 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
4689b6f4-b066-5f1b-8240-8fcc4de99da1 | note | Method/Description - Survey/visual
997ac537-43b3-5192-9017-0bf3e3dcb597 | note | Test frequency - Prior to Commencement
d9ac4fbc-7600-56df-85a5-8ea200705489 | note | Contractor - W
ad7cde9a-ab42-5a9a-a9cd-4dd8a4d67d81 | checkpoint | 3.03 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots. Except for Fill 12 and 13 where the fill height is >=5m.
b4fb3a68-71ef-58da-8097-40b7a89c112a | note | Method/Description - Survey/visual
8970b38d-8b8a-5e49-9c38-d63fc8472797 | note | Test frequency - Immediately prior to earthworks beginning in all Fill areas except Fill 12 & 13
f6a103a5-5e83-54ad-a66a-0eff52520bbf | note | Contractor - H
b87f98d4-d11c-551d-81c7-8f4f29f9fedf | note | Designer - H
21e996d7-b1c6-5e55-bfcc-f4f44de77c3c | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
7c1023a7-79db-5bcd-a3bb-3fd56c97e2da | signoff | AUTHORITY HOLDPOINT
968214fd-11f9-5702-8296-7a714958f524 | checkpoint | 3.04 - Designer witness of in-situ subgrade prior to filling
ba2f9358-a9a9-5881-bc01-18f984aee4f3 | note | Method/Description - Inspection
11f42312-c5e8-5541-9374-4f1594c9a91e | note | Test frequency - Prior to Filling
8a0edce7-145a-5525-b5b4-f396d248a2e9 | note | Contractor - H
36da4f01-26aa-5525-99f1-2d9554b96007 | note | Designer - H
62478400-b8e3-59d6-a6a1-8dcf7c77e368 | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
0df5fe88-5f22-57d6-b8f0-47988d704f9b | signoff | AUTHORITY HOLDPOINT
9337de40-bb4e-5c4d-869b-d8f3bcf1a9cc | checkpoint | 3.05 - Undercuts
69ecde8d-3869-5cf5-ae08-76c8bd5d180a | note | Method/Description - Visual inspection
438a220f-e72c-56fb-9404-7451932cbae9 | note | Test frequency - 100% of works area
bc6f60ed-4f21-5290-8116-2a8222b4d19d | note | Contractor - H
8d209e60-b20b-5233-9b84-a05bf17c9165 | note | Designer - H
34a39f77-c01f-567f-94a3-2f5cb3545c04 | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
b0f007b2-da0e-5103-a4d5-29026850c2cf | signoff | AUTHORITY HOLDPOINT
580053e5-baa8-5405-9489-549ebcfb830a | checkpoint | 3.06 - When required Undercuts (cut-to-fill operations)
1a089570-6390-58b5-8b70-7e61af11ec2d | note | Method/Description - Visual inspection
1b9050a5-547b-527d-9c0b-c94f51eff89c | note | Test frequency - Prior to Filling
9e02960e-ab55-55c1-9b30-b7fca11a2b74 | note | Contractor - H
eb43c112-b2d0-56f7-882d-36705c85ffc3 | note | Designer - H
dbc35f7b-b8a8-52b7-a189-44533021e349 | note | Lab - I
6c418ec5-1ac1-5285-95a1-488379d4d2d2 | signoff | AUTHORITY HOLDPOINT
2552f911-8442-52c0-9af0-728f86ec61c8 | checkpoint | 3.07 - Sub soil Drainage
1ef14143-ffb9-517a-8f56-4a92d767339c | note | Method/Description - Inspection
de174a21-52f0-5099-bc2a-2fce93f54897 | note | Test frequency - During subsoil construction
988e2157-806d-5f8a-b89e-c6251768791b | note | Contractor - I
9a75421e-9f90-5e9f-93ee-665134a87991 | note | Designer - I
5e4495f7-1404-5969-92b4-0f14e57f6446 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
98241a54-b8c7-5bd4-959e-35df3ae73c33 | checkpoint | 3.08 - Monitoring Equipment
adbb1f75-98dc-556c-a631-3bc5b41ba1e0 | note | Method/Description - Survey/ data logging
66e1ae20-c616-5dc4-9692-bfd386ade1d1 | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
17d7b1e3-8e17-59c3-b4c2-f7bfadb16577 | note | Contractor - W
57217e4a-375b-5ffc-9541-bfc283c15f5a | note | Designer - R
6e784698-1cef-5ede-821d-0ea3d92bd445 | note | Verifying Records Checklists, Test and Supplier Certificates - Drill logs, borehole logs and monitoring instrumentation asbuilts.
ec83abcf-a19b-5853-bcb4-61fa99665448 | checkpoint | 3.09 - Filling operations
ee8cacb4-bc0a-5ead-b3e9-8dd2e866d9f6 | note | Method/Description - Visual inspection
310c020a-61b0-587d-a195-8b4d2bc41a10 | note | Test frequency - Daily
10983cb4-a0f8-543a-84d5-dfe3867faf88 | note | Contractor - H
a587fd4b-1255-5608-80ce-994f8219d2a4 | note | Verifying Records Checklists, Test and Supplier Certificates - checksheet
b1bff344-bc71-52de-be11-9a49585bc454 | checkpoint | 3.10 - Filling operations
69a46851-b372-5748-8d21-a101d637e99b | note | Method/Description - Survey/visual
8d5d5d55-7dbc-5e0a-b42b-4505a96aae12 | note | Test frequency - Daily
c350c99f-eccb-585b-82ac-03e070b715f7 | note | Contractor - H
7364e9ca-6681-5b8c-be6d-f877ddd2313d | note | Verifying Records Checklists, Test and Supplier Certificates - checksheet/ Survey Report
fde1ce1d-6645-5ebc-ba18-97117995efc0 | checkpoint | 3.11 - insitu fill testing-Plateau Test
600dd621-0d81-50d0-80c4-9dc0f518b981 | note | Method/Description - Plateau Test
0c1794d4-660b-55ea-acae-9466ec554854 | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone, except where outlined in RFI0057
09464a21-4611-56a8-a5fe-3e0edf4ffdaa | note | ○ Buttress Fill - 1 test per material type per earthworks zone
6a52ccdc-6010-5574-b132-a0d049b97e2d | note | ○ GAP65 - 1 test per material type per structure / location
bf649d32-6efc-510e-a4e4-7ac5a51a475c | note | ○ Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
ab9c7014-a1ba-5128-ac98-b04a6a10e016 | note | Contractor - W
9845a94d-a7ac-57ea-b6ec-a955ba36eed0 | note | Designer - R
dd83c3d4-fd48-537b-b1fa-abfd1bf94a9c | note | Lab - I
b7a0974c-d85d-5dbc-be75-46e04d7fa2f4 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
59fa6d4f-9210-514c-8b0f-d81a5b525263 | checkpoint | 3.12 - insitu fill testing-In situ moisture content and density
a0afe7b1-fee4-5fa3-9c71-8fbf8f5a5acf | note | Method/Description - In situ moisture content and density
af0fabf9-9e6b-5b60-adc5-e80a21430127 | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057
6c4d0280-0c7d-5097-98a7-f68560fc8028 | note | ○ Buttress fill - 1 test per 200m length Average
fbe8a438-4bda-5e3c-9d73-322b30940467 | note | ○ GAP65 - 4 tests per lift per structure
f28bd76e-62a3-5f63-9305-592f4b3f88d1 | note | ○ Subsoil Drainage Back fill - 1 test per 500m3 ,
9dba6b2e-7d63-58a8-ac07-edade3b7c580 | note | ○ Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
c225eafe-d341-5a94-9124-1ca33e130548 | note | ○ Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
0ceafaf5-dffb-5f33-ae88-522e879fb571 | note | Contractor - W
a403cb72-3a42-5cf3-ad38-936d5a074e5c | note | Designer - R
843c14af-e1da-5815-ab95-509aeb970ca2 | note | Lab - I
786578df-e825-5f5a-9a37-4f5fbd88e254 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
de9398e8-a388-53dc-a93f-ca29f461df80 | checkpoint | 3.13 - insitu fill testing- Undrained shear Strength
5c909215-a304-562f-ba2e-1b17343aed8e | note | Method/Description - Undrained shear Strength
02bc81e6-ca2b-5dc5-a474-4c20bd89a2c7 | note | Test frequency - Structural fill - 1 test per layer per 1000m2
c69f231d-1c8d-5151-846b-45fe51c69acf | note | ○ Buttress Fill - 1 Test per layer per 2000m2
49638fac-20ae-5cd6-a1f4-ceed719c72c3 | note | ○ Cement Stabilised Structural Fill - 1 test per layer per 500m2
75a7bf48-2394-5764-bda7-b7e8a5b794e6 | note | Contractor - W
c81227cd-0bca-59ab-aa02-b5a01e9f1978 | note | Designer - R
bc66198b-6847-5e0f-9023-3cafec664952 | note | Lab - I
bfbd1086-6106-58ae-a278-b5dce3a27894 | note | Verifying Records Checklists, Test and Supplier Certificates - test report
94db9489-fa95-59c4-81f4-1b1869b18e9b | checkpoint | 3.14 - In-situ moisture content and density (and/ or air voids) testing of compacted for fill material Subgrade
f555f46b-d1e3-5003-8844-e622c6d88ac5 | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
b9934e02-df02-58e0-87fd-ee458ddd54ac | note | Test frequency - Fill 12 & 13 - 1 test per 0.5m lift per 50m length for 1.0m subgrade depth
fd34ab6a-c392-52d6-9c5c-0fed575b1764 | note | Contractor - W
d86a7167-2b5a-5754-bb5f-f0e4f1a196b9 | note | Designer - R
f70c4512-c156-5f81-8234-2b77eed4595c | note | Lab - I
11325940-a36c-5b2e-b0af-8a8f27652ba0 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
c5bdb7ee-403e-5550-9d7d-933aa522812d | checkpoint | 3.15 - Carry out deflection testing (either Benkelman Beam or FWD) at the subgrade
c9fb14e6-4cd2-5dc0-af5c-95b191f08475 | note | Method/Description - Benkelman beam or FWD Testing
c428f2d7-9aa5-5956-98a3-072d60654b87 | note | Test frequency - 10m interval in each wheel path at the following levels: 1) 1.0m below Subgrade Formation Level 2) 0.5m below Subgrade Formation Level 3) At Subgrade Formation Level
ec4011ac-576e-544f-b4aa-606496abe07b | note | Contractor - W
d2973614-4cc8-59bc-8d68-4022b26ad1d4 | note | Designer - R
8799388d-3b99-53dd-9b44-0bc3daefce40 | note | Lab - I
d2f8f714-14cc-55e1-ae0b-bee7ddb3740c | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
a22abca3-0365-576a-95d5-c65bbd5e33bc | checkpoint | 3.16 - Laboratory Soaked CBR testing for Subgrade Fill
3e147788-ed35-54be-8ec5-a539d24bf29e | note | Method/Description - Laboratory Soaked CBR
0fc8e469-f22c-5704-89f9-d7fe018fb000 | note | Test frequency - Test per 5000m2 at subgrade formation level
8931dde4-2398-509e-9f8e-52ed93d5f832 | note | Contractor - W
0fb58b69-8f60-5619-bacf-d43c590a3e70 | note | Designer - R
6edd5fe1-939d-536b-bc73-212a41358941 | note | Lab - I
37689b01-0ff3-596d-a36a-925c3feb4deb | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
de153151-2496-515f-a86e-a71e4ea85abf | checkpoint | 4.01 - Monitoring Data
a7db3a4b-38db-57a6-b6e3-59634dff1edc | note | Method/Description - Data Recordings
2a085e1a-02b9-5208-940b-25fa6a85b2e1 | note | Test frequency - During construction and at end
3167efb4-0f87-5712-9e42-e14a688fc186 | note | Contractor - H
c842e8aa-996e-5622-a3a8-8af7e1d2ec92 | note | Verifying Records Checklists, Test and Supplier Certificates - monitoring Data tables
96b27424-f2a1-51a5-ba79-d8a2e76ef901 | checkpoint | 4.02 - Survey As-builts
36fe3d22-feb1-5dc2-9164-8b5f09094e1d | note | Method/Description - Survey As-built
52dd3e4e-8331-5648-bad5-815d78477912 | note | Test frequency - During construction and at end
5193b0a9-ec26-5a50-b6c1-11b49445bce8 | note | Contractor - H
1674725e-8610-5f4e-9cb6-85c094bf0c22 | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
5c0732e6-58ca-5568-815f-7eb40f0c0149 | checkpoint | 4.03 - As-builts
2454005a-a3a1-5a1e-8746-49dd0e0d6520 | note | Method/Description - Red Pen Mark up
96a442d1-51b2-58fb-8c6a-9faa90e5fc92 | note | Test frequency - End of Construction
464ca93d-6b25-544b-a8d5-12229c34574b | note | Contractor - H
e733f8c7-53c6-5be1-a3de-610e2867dd0c | note | Designer - H
c8c4f16c-a75c-5270-82f0-708815469c7c | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
da8801c3-a745-57ae-8ee9-97e0c79c7f28 | signoff | AUTHORITY HOLDPOINT
5fba6545-f385-42a9-9359-834e87cfda72 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
d52d278d-3c9e-445a-840d-88559f671b8d | checkpoint | ITP Close-Out by
302b94ed-ea39-52df-b40d-2a66e9c1005b | note | Site Engineer/Project Engineer
97da0f09-e6b4-53d6-8df8-0650c92ee12d | note | Zone Manager Approval
9069c016-6527-5a42-83e1-9b3502d34ba4 | note | Construction Manager Approval
9636a2bd-9785-5b76-a827-7f6b0c8c3601 | note | Quality Manager Approval
5f046336-c22f-553d-a603-5633d81398ec | date | Date:
991c0350-4049-4b7e-b672-1d020fcc578d | signoff | SIGNATURE
c709a69b-9953-530a-9bce-a5f0677674ac | checklist | ITP-014 - Fill 14 Rev 3 | itp | ITP-014 - Fill 14 Rev 3
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
c9e7969a-5007-57ec-ba14-7e88241a4737 | checkpoint | 1.01 - CWP
e089dd61-1536-5853-b386-da5ac012a822 | note | Method/Description - Document Review
39acd8e3-3204-52a1-8063-8a84de727505 | note | Test frequency - Prior to personal starting
fb74a4ec-b970-5a82-9438-0371ff2c4f60 | note | Contractor - H
24e19b5d-b714-51a0-871e-2fc4077a520b | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
2ece2dea-0ece-5f8b-808c-1cdc710ec1da | checkpoint | 1.03 - IFC's specification
4257e64a-85d4-58d9-ac5c-ff666a5cfb32 | note | Method/Description - Document Review
5230702f-d278-5658-a1d3-b49fa06541f8 | note | Test frequency - Prior to works commencing
7f1cfa8a-1324-5bbe-8e81-b61f3faa9861 | note | Contractor - H
29646630-3fb9-533d-b171-9e4cf8f44811 | note | Designer - H
a31745d4-ff53-5865-bb8f-f5113a7501f3 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Technical Specifications
4f53a227-7472-56ba-a5a6-4c3ac8e4c227 | signoff | AUTHORITY HOLDPOINT
9f3782d6-fcad-57e8-9f89-25cbd7e66940 | checkpoint | 1.04 - IFC drawings
306054e1-5f7e-5a9e-9293-a2d5c4f460ea | note | Method/Description - Document Review
9fef44a4-1c56-50e4-bd9c-758c6a3e91de | note | Test frequency - Prior to works commencing
ede6e919-9c31-590b-a63f-de014264a326 | note | Contractor - H
17e771b9-78be-537c-9d0f-a2ce791868cf | note | Designer - H
815c58e5-413d-52ba-841c-7c25c85b51cc | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings upload into InEight
0a00808e-11fa-5083-96cc-194ed9762c58 | signoff | AUTHORITY HOLDPOINT
2b364d5c-7aaf-5e79-9c71-67ea904b450c | checkpoint | 1.05 - Approved earthworks model
01ed7ab8-e726-5289-baf1-a02abb6ed932 | note | Method/Description - Document Review
14c5379d-7ee1-5304-9c5b-3f018a80d31d | note | Test frequency - Every new Earthworks Model and prior to work commencing
dbbf0570-b9dd-5c71-832a-19a7885904a3 | note | Contractor - H
36c8e97f-e357-50b5-b7a8-7c1a3cc5021a | note | Designer - H
20908a2c-eb88-5181-b450-52efe7c43b5a | note | Verifying Records Checklists, Test and Supplier Certificates - Earthworks model approval
18282456-db58-50bf-8234-42a16bd82c94 | signoff | AUTHORITY HOLDPOINT
22242bb5-b1b0-57c3-a337-bc595452c87a | checkpoint | 1.06 - Approval of stockpile location
9b76d029-9a17-5010-a234-f64302f8b71f | note | Method/Description - Document Review & Approval
197af4fe-a59b-500d-8df5-16c49792cc02 | note | Test frequency - Prior to works commencing
ca87598a-5c60-504a-b9b2-2a1df578b983 | note | Contractor - H
cd0c588b-b973-51b0-a4b7-2e2e82094b69 | note | Designer - H
170dea46-b59b-5c8f-8531-5e621947838d | note | Verifying Records Checklists, Test and Supplier Certificates - RFI of Approval of stockpile location
9a3784fe-c98b-59e5-ad98-a9d610e27a03 | signoff | AUTHORITY HOLDPOINT
2537b5b9-ef32-5d24-abfd-bb685d8c11d2 | checkpoint | 1.07 - Installation of prefabricated vertical drains sequence and method
85400be2-a428-5805-98bc-800258186bf2 | note | Method/Description - Document Review & Approval
8c3e6ade-519a-5f6a-a625-19f8909ed9ab | note | Test frequency - At least 4 weeks prior to commencement of PVD installation
847212ec-70ca-50f2-9431-e056b4149ae6 | note | Contractor - H
4aae23c8-b4ce-5f8a-bfcf-369ed9d8b142 | note | Designer - H
1dc449ba-d1b8-5c9f-82b2-fd308a2413d4 | note | Verifying Records Checklists, Test and Supplier Certificates - CWP approval
3621c2c1-0db5-59f4-abc7-6d4c33e56398 | signoff | AUTHORITY HOLDPOINT
99926cbc-6ec1-5891-b497-60c63a32941e | checkpoint | 1.08 - PVD sample
0eee56b4-55ac-5546-b040-654ba8683847 | note | Method/Description - Approval
80081bcd-1079-5c4a-8387-329e87e5628a | note | Test frequency - At least 4 weeks prior to commencement of PVD installation
c611e8e2-079a-55d5-988e-8cd0d0803aa6 | note | Contractor - H
a7cf3122-eea5-5164-aabe-66226997eb8a | note | Designer - H
638c7a7f-872e-50ac-a2d3-e8032f4695e4 | note | Verifying Records Checklists, Test and Supplier Certificates - PVD sample approval
c2a99c60-870e-5745-90e0-715c34c28d01 | signoff | AUTHORITY HOLDPOINT
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
87e4a759-a171-5594-aff6-7de9dd71dd3b | checkpoint | 2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural Fill Material
fe3d3893-9b75-5b64-a04e-1d86acb4c29b | note | Method/Description - NZS 4402:1986, Test 4.1.2
3495b883-135d-5188-a0d3-d10d9d52de1d | note | Test frequency - 1 Per 20,000m3 (Structural Fill)
67342cb9-e379-5628-a679-ce5a8db057c2 | note | Contractor - H
a28c4d46-5800-5e2f-874f-026ddf166bf7 | note | Designer - R
43f46eb8-2a53-5e14-bb91-3c6e4f968bc8 | note | Lab - I
08e9d96a-e0bb-5542-8746-18d30c8a2f2d | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
dba88c58-c275-5120-89c2-82a26527a522 | checkpoint | 2.02 - Atterberg limits test for Structural Fill Material
8efac5e3-3f65-5738-b1ef-ec1292709d9b | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
69535725-4c0e-5f33-8524-84264d367b24 | note | Test frequency - 2 Per 20,000m3 (Structural Fill)
a7c3cdf6-e207-5b7c-94c0-021fa86c896c | note | Contractor - H
589c06d6-31ed-5107-8627-2f07da1e5e18 | note | Designer - R
5a220030-7b33-59f4-a579-fbbdf4a7dcc2 | note | Lab - I
0ffef775-f465-53b4-a18c-cb1c8b8f6766 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
7f582d98-61ec-5278-8c11-9dc43d59f9f2 | checkpoint | 2.03 - Determination of the dry density/water content relationship (Heavy Compaction) for Buttress Fill Material
69d19818-b469-529b-9ef7-aff4c821fe86 | note | Method/Description - NZS 4402:1986, Test 4.1.2
b785a442-961b-5b94-8af8-151734794fbd | note | Test frequency - 1 test per 20,000m3
9dc921ba-1c25-579d-91bb-dc10a63c0afb | note | Contractor - H
8c71261a-99b2-5147-b6ef-5ae27e292320 | note | Designer - R
84d35f5f-7d9c-5a6e-8f30-54288b08faf8 | note | Lab - I
7a182bf3-cccc-5a7c-8f91-8121237d9a3c | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
7d6904fa-05eb-5017-88ff-f9f456e0acf7 | checkpoint | 2.04 - Atterberg limits test for Buttress Fill Material
c59817c9-50be-57fa-8a32-5c7c76032d5e | note | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
76ac39ed-9b7a-59a0-b5ac-3bb48e1f216e | note | Test frequency - 1 test per 20,000m3
6933c107-6455-5372-9895-8562ca47e33a | note | Contractor - H
75fb34ac-acdf-5390-bec7-ea6b8ccb8b3e | note | Designer - H
b84d75df-09d6-5625-82b4-5dcc25d460ea | note | Lab - I
bf3fd3b6-0a3a-54e8-82d2-93b93a3b84bb | note | Verifying Records Checklists, Test and Supplier Certificates - Atterberg limits Test Report
4102e8ea-397b-58f8-b887-3bfbfdb96db5 | signoff | AUTHORITY HOLDPOINT
59192456-18db-534d-a45f-0de0f4d8c208 | checkpoint | 2.05 - Drainage blanket
5f61ab54-103f-57e4-b3d5-36ed0ad1c60e | note | Method/Description - Designer Approval
05a674f2-7e45-5ea9-bc15-ba0ac76a05cf | note | Test frequency - Once Prior to commence
decef77c-f13e-5384-af72-010f0e562add | note | Contractor - H
550c5d7f-12c3-57f0-8220-b741f2afe396 | note | Designer - R
eed25f06-ee66-51fe-8fcd-4c2230e42877 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
2bbc62c6-7f4c-5520-a7bf-5ca8c652de60 | checkpoint | 2.06 - 40/20 drainage material
2aad36c5-3178-5d0c-b563-cea580cd6ca9 | note | Method/Description - Designer Approval
1bb11428-cc48-5cb8-9500-5416e5d302a9 | note | Test frequency - Once Prior to commence
70f7244d-d97b-57fa-ba1f-11ca991144e6 | note | Contractor - H
93dcab24-a726-5715-a574-d685ab37c873 | note | Designer - R
69f55381-5238-5045-8214-2b52b33454b8 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
2be97d0d-c1cd-5aa7-9f9b-03438414ca03 | checkpoint | 2.07 - High Strength Geo Cloth
cc42d98a-b6e1-545c-a3e8-a8f0711fb4d7 | note | Method/Description - Designer Approval
ba53d346-cff1-5f5f-9c68-4435402ee6e1 | note | Test frequency - Once Prior to commence
1811fe65-9427-59db-889b-58dc829be190 | note | Contractor - H
d39fbbec-30d7-5c3f-8345-7aca5985147a | note | Designer - R
de6d87a0-7015-588a-ae4a-9848e89f27f4 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
ec372996-43c5-5d37-9bc0-cb10dc3056bb | checkpoint | 2.08 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material
4fe0414f-4239-55ef-a22c-522af0dbe57a | note | Method/Description - NZS 4402:1986, Test 4.1.2
9af2b779-18d4-5639-b763-35fc911342e9 | note | Test frequency - Source approval 3 no. tests
84bc0c4c-e53d-5bdd-8ea2-8e0f713d599f | note | Contractor - H
be7c19d5-d59b-577a-b17e-1340b30702ae | note | Designer - R
92b1ceab-f0f3-5745-9dd7-568ee317fc8f | note | Lab - I
ed72e9b7-06b2-5fef-8081-5fd20bbf7445 | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
0f759934-0789-54d7-9c36-6a2edac76518 | checkpoint | 2.09 - Particle size distribution (PSD) Test for GAP 65 material
6df844d5-c6e5-5b50-bc97-f066190d8d5f | note | Method/Description - NZS 4402:1986, Test 2.8
2024b29f-6e6e-5046-a5b1-d068b202c155 | note | Test frequency - Source approval 3 no. tests then every 2000m3.
81dd4ea6-c9f3-535b-b8a4-e25de9ca5bc7 | note | Contractor - H
da3423e1-4912-559a-a70a-22c67be079e6 | note | Designer - H
34e401da-14b0-5355-909b-1fab55def249 | note | Lab - I
ffc35911-fefb-5f3c-81d9-9f1138519e2a | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
baf13600-ce53-5081-88e5-3bc7baab8e2a | signoff | AUTHORITY HOLDPOINT
3e546cf3-278e-5436-baac-044b4774e9f4 | checkpoint | 2.10 - Permeability test for GAP 65 material
abb288ed-94c4-565a-bcbe-80a7a9498f05 | note | Method/Description - ASTM D5084 - 16a
667c33d2-16ea-59ad-b248-0140ab162dae | note | Test frequency - Source approval 3 no. tests
8a353e9d-0b0c-5277-bc4c-19a6ae765ccd | note | Contractor - H
3461238d-3066-5158-86e0-f70bf1338b73 | note | Designer - H
e5afa4ec-f602-5c85-b1f6-4e9dc54888f5 | note | Lab - I
ccbdcac9-77d7-502c-b0c6-8af78eb7f154 | note | Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report
d3316e7a-c92d-5b11-8447-5e9953776b06 | signoff | AUTHORITY HOLDPOINT
04861871-f557-55ff-945e-3dbf04afeb11 | checkpoint | 2.11 - Material approval of prefabricated vertical drains (PVD). The PVDs shall consist of a continuous plastic drainage core wrapped in a non-woven geotextile material. The geotextile wrap shall be tight around the core and shall be securely seamed in a manner that will not introduce any new materials nor present an obstruction that will impede flow in the channels of the core. PVDs shall be produced by a manufacturer with an in-place quality control program which is monitored by an independent third party testing organization.
3e8c1bb0-c1ab-5fb5-89b8-3ef7172e6251 | note | Method/Description - Document Review & Approval
fd487ad6-02d2-5418-bd50-438713622a49 | note | Test frequency - At least 4 weeks prior to commencement of PVD installation
22746887-54ff-51c8-82f9-880c730c907a | note | Contractor - H
e094b828-fa6e-514d-9556-53061f6e13e2 | note | Designer - H
983be9dc-0e75-51d3-9080-11838c3f6709 | note | Verifying Records Checklists, Test and Supplier Certificates - Material approval, Material test certificates
c935d4d0-d83b-5bbd-b38c-5401b4380a3d | signoff | AUTHORITY HOLDPOINT
fc911546-64a8-5d88-ae94-4fae53597f0e | checkpoint | 2.12 - Delivery of prefabricated vertical drains (PVD)
c4d0f25b-c01c-55f0-ac5d-da60e709be1c | note | Method/Description - Inspection
e91f0f77-e1e1-5a3e-b754-e0fd3b4c509c | note | Test frequency - Each delivery
37198f97-9691-5687-98f1-5de475b20e13 | note | Contractor - H
d3b190cb-bdc8-58a7-94dc-e8757bfd86a6 | note | Designer - R
def2bcb4-5b54-58c2-bd1e-b67895b50ca0 | note | Verifying Records Checklists, Test and Supplier Certificates - Product name and identification
69194214-b8dd-5492-a6fd-adf96ae38b13 | note | ○ Date of manufacture
39120593-16c7-526d-a9c0-756e3d8a250e | note | ○ Lot or control numbers
b68aedef-2480-53fc-a83c-ba6abb04e1da | note | ○ Name and address of producer/supplier
210d1a1d-b0d4-511c-9de2-9ca121ad46ab | note | ○ Manufacturer’s certificate
202807af-e5b8-5897-89f7-974afbafb89a | note | ○ Material Delivery Inspection Checklist
5bae7e84-ac3b-5717-9535-7891b3c7f2cd | checkpoint | 2.13 - Visual inspection - separation geotextiles, basal reinforcement
1bd88497-d9fb-5902-84bb-cfdc5803aee2 | note | Method/Description - To inspect geotextile and basal reinforcement is the proper type and no tears, rips or other signs of deterioration.
71eb19da-0af6-507b-98b1-2e074189508e | note | Test frequency - Check each lot (1 roll)
d2cc6a8e-ea17-5dd1-81ee-362bb5e76a6d | note | Contractor - H
e39e4363-a496-551a-9b40-bb8b6c8098b8 | note | Designer - H
3ab53a30-a262-5f5d-99ad-0793e7430328 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Delivery Inspection Checklist
923b4ad2-6347-52b4-9a87-39abd41d4ab5 | signoff | AUTHORITY HOLDPOINT
5e281401-04a5-5da3-9c97-babb1878e04f | section | 3.1 Pre-filling
a0be629f-1173-51fe-9ab9-b2a0883eff9f | checkpoint | 3.1.1 - The installation trail of prefabricated vertical drains (PVD) shall be conducted.
97f9bb0b-efa0-5e7e-9a39-524fca722d8e | note | Method/Description - Inspection
e775fc77-3d94-5aba-bd13-e6f88a90f925 | note | Test frequency - Prior to Commencement
1661fe29-029e-5561-bc4e-c6cbcc706096 | note | Contractor - H
e6cebe15-0755-5252-bb65-539748cf44ec | note | Designer - H
6dcf5206-64ff-5c45-bdad-5893da52433e | note | Verifying Records Checklists, Test and Supplier Certificates - PVD installation trial approval
4583b9b3-9a94-5b83-92bb-e7c9dd295b20 | signoff | AUTHORITY HOLDPOINT
7a90184b-07d5-5c5f-b671-f24dcf7278bd | checkpoint | 3.1.2 - Set out extents of fill and check against design
25cac1dc-aace-5742-9749-f1f60709f72b | note | Method/Description - Survey/visual
325250a9-1fea-53ba-a6fd-3f9cc2992dcb | note | Test frequency - Prior to Commencement
3e4fec7a-f0c0-5fef-84b4-d44b36b4a27c | note | Contractor - W
c69a12d2-db03-5683-9bc5-9bc4c008074f | note | Verifying Records Checklists, Test and Supplier Certificates -
9e649971-9af1-521c-a700-25d43fd4fb7b | checkpoint | 3.1.3 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
361d3fcd-5761-5969-b127-8f78ac70eec6 | note | Method/Description - Survey/visual
32a28ac9-03ff-5114-a365-62d5b468379f | note | Test frequency - Prior to Commencement
94fb3fe3-284e-5f1f-b1b3-c7a605682912 | note | Contractor - W
19deee23-2985-533c-91d5-1b2ba15f919a | note | Verifying Records Checklists, Test and Supplier Certificates -
13dc5be4-94d2-511e-a55c-2702ed0bc666 | checkpoint | 3.1.4 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots.
1a348236-b66a-5bd4-8e38-49fb771503d0 | note | Method/Description - Survey/visual
dd07b0db-1b64-5554-996c-13f88aeb70ce | note | Test frequency - Immediately prior to earthworks beginning in all Fill areas
4cefef70-d70b-5f2f-bd0a-9dd8aaf9a7af | note | Contractor - H
434a115a-1bb4-50fa-b482-55f18e55ab9e | note | Designer - H
2300c56a-cfa5-5688-8427-01c065d552f5 | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Lead
0bc83e3c-9a19-567e-a14e-3d6f50758ccb | signoff | AUTHORITY HOLDPOINT
6ce4d2ed-7aa3-5882-8119-6497837811cf | checkpoint | 3.1.5 - Designer witness of in-situ subgrade prior to filling
bd8a8c5f-6389-5d13-8c98-1be5295a12aa | note | Method/Description - Inspection
33e3c142-ebd8-576e-b307-69c7f771e120 | note | Test frequency - 100% subgrade inspection
79406ac8-c103-5021-a391-bcd811ea7178 | note | Contractor - H
9706c16a-b806-557f-b718-5a5485afc829 | note | Designer - H
1c2b0ef5-892e-57c8-bcdd-b0cb4f179983 | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
c85636d8-ee47-5f5d-aa04-2dccf0e1f457 | signoff | AUTHORITY HOLDPOINT
4ecc1ee3-2a49-5afc-a40c-07d92b0a4ed7 | checkpoint | 3.1.6 - Undercuts Inspection
1c92114b-c3a2-5ff5-bf14-380ce17efb4e | note | Method/Description - Visual inspection
8cc3f98a-7992-5c34-a970-aa9b90fd9d6c | note | Test frequency - 100% of works area
9d38d27f-ca7d-590b-8db5-af470db6d917 | note | Contractor - H
80624815-64ab-54b6-b308-94b8f8f55539 | note | Designer - H
dba31996-79a8-5d7d-bd7e-c377ccdaa919 | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
f808adb6-6125-5e71-9e93-48433c8bc59c | signoff | AUTHORITY HOLDPOINT
73d8c9e7-24ce-5e7f-92e4-23a6367f1273 | checkpoint | 3.1.7 - When required Undercuts (cut-to-fill operations)
573f101f-9c92-5dd6-9ac1-23ee73f3074d | note | Method/Description - Visual inspection
ebc841ad-eda4-51ef-9e98-314cc1ecac4e | note | Test frequency - Prior to Filling
631ebf2c-da87-5e05-bb1c-8398efa8f066 | note | Contractor - H
d751f6fa-d6dc-5441-b9f7-98fd09470c69 | note | Designer - H
816cda5f-7d1d-5433-ac80-6adf6a0a143f | note | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
0ccf7b12-05d9-572b-bd39-940f8b7cfdd4 | signoff | AUTHORITY HOLDPOINT
09e7fec1-6933-59de-a369-1f7a85ae21ed | checkpoint | 3.1.8 - Piles
9e292be0-218c-5ad6-83fc-39a460da28ec | note | Method/Description - Inspection
89558d2d-a6af-598b-afac-4fd569abfea0 | note | Test frequency - Ongoing
bb1043b4-a984-5987-9ffb-3b2344f37241 | note | Contractor - W
812ce363-a49f-5498-88ac-1455a3fd3dfa | note | Designer - R
f4e19a1d-9781-59ef-990b-14e71c021e0b | note | Verifying Records Checklists, Test and Supplier Certificates - Separate Signed ITP
f74ac11f-07d4-5d61-b2b6-1f3605ba091f | checkpoint | 3.1.9 - Installation of prefabricated vertical drains (PVD). PVDs shall be installed after the sand blanket is placed and before the installation of high strength geotextile (basal reinforcement) and the embankment fill. The proposed locations of the PVDs shall be marked out in accordance with the Drawings.
02772269-8cd9-5812-8490-49c9fb5ea26c | note | Method/Description - Inspection
fcaa78c8-eaec-5af0-8068-8694c820285b | note | Test frequency - Each installation of vertical drains
064360f2-54db-57e9-a4aa-8667c2c68884 | note | Contractor - I
920d3cd9-9abb-5771-bb1d-9879caee64c9 | note | Designer - I
a828426c-18b1-5d81-bc8e-0ef079211b3a | note | Verifying Records Checklists, Test and Supplier Certificates - Vertical drains Installation Checklist
b68c3d84-fdf7-5dc9-ae36-584c3d39c078 | checkpoint | 3.1.10 - Basal reinforcement installation
22501e99-b98a-533e-bab5-2dec0e3e01c4 | note | Method/Description - Visual inspection of directional placement, panel length, laps, and damage
b9f3449b-b28c-52de-9d81-d6feb598e690 | note | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
78056acd-72a3-5086-ad48-99da7b326ea6 | note | Contractor - H
5fd9e1e3-4c81-584e-a6df-82f98dacffa5 | note | Designer - H
8d7c27b1-582a-5788-9d77-b4341a49eb13 | note | Verifying Records Checklists, Test and Supplier Certificates -
a8ae9692-286d-5a9f-821f-49ec3f5ee728 | signoff | AUTHORITY HOLDPOINT
59974322-04de-5fb1-b8d7-b34fb24f1d97 | checkpoint | 3.1.11 - Drainage blanket installation
e66d49e0-6a2c-5dba-86c0-571245b0190e | note | Method/Description - Visual inspection
468681a3-e2b8-5559-9dcc-66c5968da39a | note | Test frequency - Prior to filling, and every 100m2 of geotextile installed.
3101edb3-e15e-5a0e-a8cf-2ef9b2b70ee0 | note | Contractor - H
29893417-818a-5baa-ac98-58662688a3fa | note | Designer - H
32daacef-533c-5bd3-9312-0d9c1ac5f204 | note | Verifying Records Checklists, Test and Supplier Certificates -
0a812758-ce1c-538e-b6d2-f3b509a75dac | signoff | AUTHORITY HOLDPOINT
bd0a5581-4083-5ad9-8f5b-b9056c8ce441 | checkpoint | 3.1.12 - Monitoring Instrumentation
e2a4e63a-4b09-5aad-aed8-1a1637c9a195 | note | Method/Description - Survey/ data logging
beb620e3-0d13-5345-aa39-e51abca915bd | note | Test frequency - Ongoing
7414e67b-d4c9-5f2c-b4d3-7c1f33df2da0 | note | Contractor - W
a5ad977e-4b9c-5ca9-bdc7-db37e3b8fd20 | note | Designer - R
07952f33-9b11-5337-b4e0-37461539d0f9 | note | Verifying Records Checklists, Test and Supplier Certificates - Separate Signed ITP
bc82b27d-c623-5763-9232-402697bf42e7 | section | 3.2 Fill construction
31b259f4-1f5e-5533-b5e3-2f59ba32f674 | checkpoint | 3.2.1 - Filling for the first 5m of Fill
0d8da633-65bb-599a-b6c0-b002435afb62 | note | Method/Description - Visual inspection
58eb5e2e-840a-56ce-a71b-42f823542139 | note | Test frequency - Daily
ede1dd0c-957e-5d6e-97ee-f9f01f364642 | note | Contractor - H
9d95cad0-2ece-5f3c-b427-9aa1b730f5ce | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built Survey Report/ UAV Scan
8d43a5c4-1765-58e7-a9be-1df34fb87b06 | checkpoint | 3.2.2 - Hold filling operations for a period of two months
ff990dcf-077e-5fb4-ac6f-76f0372a01fa | note | Method/Description - Monitoring data records
1b93eb8f-b083-5cdf-bd41-030dfd2360cf | note | Test frequency - Daily
6f94c824-74cd-5099-8ca0-cdefa294f20b | note | Contractor - H
dea990f0-55b6-5065-9874-9039d72c47df | note | Designer - H
1e53fcf8-4ab0-5c2a-8d99-45583015dbd8 | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring data records
b26d161a-0843-59db-9c4b-064bc1688e02 | signoff | AUTHORITY HOLDPOINT
ee6b74a9-8126-59a4-a310-681284b3a4b1 | checkpoint | 3.2.3 - Filling for an additional 3 meters of fill
f47258d0-78fa-511d-b328-fd7ef96471bb | note | Method/Description - Visual inspection
58d948d6-aac7-580e-b62d-e6ebe4e1c09d | note | Test frequency - Daily
822753bd-6896-5ce6-a38e-0fcb7d5631e9 | note | Contractor - H
0e4c94f1-5dce-5069-90ca-b92ed54bf024 | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built Survey Report/ UAV Scan
1f561203-acfd-5e97-92cd-5ce1d1747ea5 | checkpoint | 3.2.4 - Hold filling operations for a period of three months
04824692-cc05-5760-b0a3-693cf0409c82 | note | Method/Description - Monitoring data records
db7409ff-c9a6-52ab-8d1b-8ce9d6978a1d | note | Test frequency - Daily
8561b152-b8c4-559b-8bd8-dc8ace1f0fc7 | note | Contractor - H
f2ad873d-5fd2-5c4b-b875-c634abbf80e4 | note | Designer - H
8a6094c6-873f-5555-a91d-f47ba3e9a58a | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring data records
b45306f2-e403-528d-8ef4-467afac9bfbd | signoff | AUTHORITY HOLDPOINT
376012fe-7ca7-5bbf-af8e-beccda279d8d | checkpoint | 3.2.5 - Final Filling for an additional 2 meters of fill including Surcharge Fill
69398610-29e8-5c92-8de5-bde733cdb156 | note | Method/Description - Visual inspection
020f6e60-4440-52c3-b5e8-525cfc89b29c | note | Test frequency - Daily
176b4040-9ae7-5ddc-8655-5de7f6ca00c0 | note | Contractor - H
5ae21137-54ab-52b4-aa3f-840bea887af6 | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built Survey Report
767693db-72ab-53b5-9b9e-ced44ef9f30b | checkpoint | 3.2.6 - Final Hold filling operations for a period of four months
862c82aa-1a38-5347-b2ef-3f791e980955 | note | Method/Description - Monitoring data records
d1668086-a894-54a9-b0e1-4d43d901b390 | note | Test frequency - Daily
1686beaa-8244-585a-b36a-e0a6b01aa41e | note | Contractor - H
8549cc54-f46d-56a2-b705-1a6147684e94 | note | Designer - H
c17292ab-b695-5113-813b-c97e05422961 | note | Client -
7fcadc5a-fef6-5563-808f-a8647675971f | note | Lab -
f6766ae8-4f13-52b8-a638-857f0397d4ba | note | Verifying Records Checklists, Test and Supplier Certificates - Monitoring data records
2d25fcc2-c6f0-5526-a537-6a93a8a6699f | signoff | AUTHORITY HOLDPOINT
5b9ecbef-becc-57f4-acc6-85aa6d2bd516 | checkpoint | 3.2.7 - insitu fill testing-Plateau Test
5da6f556-2b73-50e1-bbd5-30e65df10b9b | note | Method/Description - Plateau Test
9d1bac17-f531-5f5b-87f5-9f5a33f37f83 | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone, except where outlined in RFI0057
143c8588-d415-50f4-842a-02dff6a89558 | note | ○ Buttress Fill - 1 test per material type per earthworks zone
d374a113-127a-5bf0-94d5-8b416648db1c | note | ○ GAP65 - 1 test per material type per structure / location
f4597b70-a6fa-5bdf-9da1-a9f4d5d1129a | note | ○ Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
1019ede0-0998-5406-8262-35faacc96467 | note | Contractor - W
fbf4a85d-fe76-5e66-86e2-040c2053e20b | note | Designer - R
bd103c5e-e991-50c1-981d-299167afa610 | note | Lab - I
932fb583-e789-5b0b-8566-ea6ca830b9e7 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
2e37b9a8-e773-59ae-8196-129b03d9f68d | checkpoint | 3.2.8 - insitu fill testing-In situ moisture content and density
4757a938-eaae-5414-8685-7ed14d10f674 | note | Method/Description - In situ moisture content and density
735c12a9-348f-582b-8cb7-d0f9f5bfc459 | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057
f9122816-534a-5f15-98a7-ad69907716b0 | note | ○ Buttress fill - 1 test per 200m length Average
621e3aac-6cb7-5b99-832e-afecdbc458b7 | note | ○ GAP65 - 4 tests per lift per structure
5829263a-2c06-5d42-9917-415a11925fda | note | ○ Subsoil Drainage Back fill - 1 test per 500m3 ,
8db3ccf8-81ce-5f4a-bf7a-cd987eb4f351 | note | ○ Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
86921369-b0d5-5580-9e9e-82822fb49a15 | note | ○ Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
d6ce2114-715e-5cb1-ab28-8b01249fb48f | note | Contractor - W
7ae1c2ff-d590-51ae-847a-0ad3f5ff9491 | note | Designer - R
5c3759fc-2d05-51b8-8177-ac26a69e4443 | note | Lab - I
5839c8a0-bb81-5456-957e-29a6b63a0212 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
ace427e5-e933-513e-935a-95afac1d2338 | checkpoint | 3.2.9 - insitu fill testing- Undrained shear Strength
dff28731-61c2-5064-8f68-f3eb355612e8 | note | Method/Description - Undrained shear Strength
e6bf610a-1d79-5f6d-ae6e-15574c4e11f5 | note | Test frequency - Structural fill - 1 test per layer per 1000m2
d7745797-de3b-5865-a17a-f086a183bd7a | note | ○ Buttress Fill - 1 Test per layer per 2000m2
8756d214-03dd-5cb6-b42b-e1fdc132f665 | note | ○ Cement Stabilised Structural Fill - 1 test per layer per 500m2
35d8e6a5-29a4-5c82-91b6-c3952259e969 | note | Contractor - W
8c1d7de0-8116-570d-8013-48994ef22edf | note | Designer - R
1eae4b03-88fd-56c0-bec9-39ef0702de61 | note | Lab - I
604095c1-89f3-5cbf-8255-c0b1f029484b | note | Verifying Records Checklists, Test and Supplier Certificates - test report
da7b21ab-0528-54fa-9340-ad21a32239cd | checkpoint | 3.2.10 - Scala Penetrometer Surcharged Fills
e05908ed-a6a2-5453-9b89-40477ff4dd2f | note | Method/Description - Scala Penetrometer Surcharged Fills
94525aa7-d10f-5f29-b4a3-af17478b829d | note | Test frequency - 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width
e69088d7-0f1a-593a-a283-770cc93dd46a | note | Contractor - W
463977ce-9d88-5e15-9f7a-6b503726d719 | note | Designer - R
6386da48-9d55-5cb9-9781-11b003f25189 | note | Lab - I
19196334-1836-563c-978f-b1cb4bb96e63 | note | Verifying Records Checklists, Test and Supplier Certificates - Scala Test results
6d4f8286-3a61-52b2-8a8c-3abbd62e397c | checkpoint | 3.2.11 - In-situ moisture content and density (and/ or air voids) testing of compacted for fill material Subgrade
56c08283-c410-541f-9c44-c459d79dcab4 | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
264badb8-ef71-5f06-a036-5c5dff8b461b | note | Test frequency - Surcharged Fills - 1 test at subgrade formation level per 50m length, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth
40c88e3c-deea-5172-9ca0-f4d3628ebd2e | note | Contractor - W
2a2b76a3-769a-551f-80c0-4baf1193e5e4 | note | Designer - R
f13c481c-11f0-5c81-ba5e-1c25fbd3339c | note | Lab - I
6462e5d1-8eca-5bc3-b2cb-06047e886094 | note | Verifying Records Checklists, Test and Supplier Certificates - NDM Test results
5b1f49b3-9e4e-5b76-9e2f-dedf87192530 | checkpoint | 3.2.12 - Carry out deflection testing (either Benkelman Beam or FWD) at the subgrade
c3358d7c-6703-5cf6-a98a-17c9d90a12a2 | note | Method/Description - Benkelman beam or FWD Testing
58e41b4d-1a04-59c2-8809-145636bef2ef | note | Test frequency - Surcharged Fills - At subgrade formation level 10m interval in each wheel path
c9ba7cba-efa2-5776-840b-87162fbd35fc | note | ○ Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
c4a55b13-321e-55a3-8c5e-abc09fda2668 | note | Contractor - W
ae5dd6f0-c5e1-5b48-8b46-09fccaf29ad4 | note | Designer - R
e59923a3-52e7-5266-9f26-c789904a89b3 | note | Lab - I
6fc46bdd-75a5-5dbd-922b-eac2b9a2c212 | note | Verifying Records Checklists, Test and Supplier Certificates - Benkelman Beam or FWD Test results
d69b8e82-7d61-51b5-bced-fb9292b831a4 | checkpoint | 3.2.13 - Laboratory Soaked CBR testing for Subgrade Fill
a33a086a-b43d-5576-8a6c-fec5c0625cc3 | note | Method/Description - Laboratory Soaked CBR
90cdda2e-ec09-585c-bffb-7f66bb251752 | note | Test frequency - Test per 5000m2 at subgrade formation level
5ea9c724-0330-5d31-9ce5-4c2ed445b328 | note | Contractor - W
a5cb8197-8160-5f63-b507-f0e551cae65f | note | Designer - R
4c5d424d-af18-5fea-a344-0c93e5b9f9f8 | note | Lab - I
b5620a46-bbb5-52d8-9574-12fe8816d7b8 | note | Verifying Records Checklists, Test and Supplier Certificates - Laboratory Soaked CBR Test results
4b33bf1d-7881-585c-a735-59ea25071c30 | section | 3.3 Preload/Surcharge (for embankments requiring preload)
08879fb5-734d-5d38-8eca-2d9ec42e4ea3 | checkpoint | 3.3.1 - Visual inspection for rate of filling
d0c0ae33-8412-555e-9032-21ac11f44f70 | note | Method/Description - Inspection of fill height, rate of filling as per IFC drawing
e6601ca4-5451-5cee-82e6-f490203bf319 | note | Test frequency - To be monitored daily
a862c07e-630b-5f90-a857-9a353fae23a4 | note | Contractor - H
e9b626ee-a331-5c65-8a2f-14c19d302f7b | note | Designer - W
6f179601-d8e6-50dd-ad7f-e2fa1af25cea | note | Verifying Records Checklists, Test and Supplier Certificates - PVD installation trial approval
d4d13462-7f39-5834-86e3-fe9a67175dcb | checkpoint | 3.3.2 - After 1m of fill placement. Await approval from Designer before placing more fill.
515cccf7-1e70-59e1-9249-da8fa8c5cdb4 | note | Method/Description - Review data and TARP levels before releasing HOLD.
2e20b8cb-ebdc-5f77-b2c4-d1c2bf71bee4 | note | Test frequency - Before releasing hold periods and allowing filling to continue.
482f9687-fb94-54cf-b6b4-ad30e220d638 | note | Contractor - H
6c2d1ff7-ac63-5b30-b9ef-de35b714c2ac | note | Designer - H
8bf46582-ed46-51b9-946b-e53e5594b2cb | note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary
97e2ef9c-0164-5e7c-9f8f-956ec7577d27 | signoff | AUTHORITY HOLDPOINT
1dab5a43-11c0-5e47-834a-8e3feb54140b | checkpoint | 3.3.3 - Removal of preload/surcharge
ea4b15c0-efed-5f67-8519-744384396c88 | note | Method/Description - Assessment of monitoring and instrumentation data
dbb0e9b3-691a-5d67-8b04-4241de5d218c | note | Test frequency - After completion of proposed hold period
c7864cc0-aa09-5477-843f-76d88b94edcd | note | Contractor - H
37faecad-eedd-5cec-a6b7-a013fe0132c5 | note | Designer - H
c89e584d-a485-556d-8cdf-bc5b018732f5 | signoff | AUTHORITY HOLDPOINT
50613bbc-0d57-5a9b-a41f-02ba7c3cdaf6 | checkpoint | 3.3.4 - Removal of preload/surcharge
4eb297f2-dc9d-5243-a546-c486f39d9cd4 | note | Method/Description - Preparation of preload/surcharge report
b61877c4-0e06-5f82-9648-5ca68bf1365b | note | Test frequency - Every four weeks during earthworks operations and at the end and commencement of each earthworks season
568b9b19-1b2e-5b63-9ff8-0dcf33f0b480 | note | Contractor - H
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
1690449e-011a-5466-a2d4-63d66de79f44 | checkpoint | 4.01 - Survey As-builts
bf837071-8cc8-5087-9646-2dbc40ef0ded | note | Method/Description - Survey As-built
0d929048-55ad-5c35-8f41-9672d7a8f8a6 | note | Test frequency - During construction and at end
b2c54a07-50df-5579-a2ba-adc2e5d6607a | note | Contractor - H
e8d323a0-316f-5aee-93e3-d5d5dc09c8d4 | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
22f76ff2-277f-5a2a-af01-429bdf354ccb | checkpoint | 4.02 - As-builts
3ac2dfb5-287b-5f27-b4c9-eb83b0e5cefb | note | Method/Description - Red Pen Mark up
455cc87c-caff-5553-bf2e-1139f217140f | note | Test frequency - End of Construction
4ee424f2-1474-5156-805a-5d55c63db3b0 | note | Contractor - H
61e0557c-a0f3-5912-8d84-2f92df4e9a3b | note | Designer - H
5b58b048-cfcc-57af-806d-685881d658b1 | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
ea139fba-e7b4-5b09-9f31-d443d7a08cac | signoff | AUTHORITY HOLDPOINT
23324d68-6945-49ec-86a5-28f8553236c5 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
2d121df2-8d34-42cd-b802-fc3f2faaa369 | checkpoint | ITP Close-Out by
5c40cb5b-0020-597c-be39-a1836b21fd67 | note | Site Engineer/Project Engineer
1dd2da1e-51c7-5ada-b9d7-775e35072691 | note | Zone Manager Approval
bfce312f-7cf1-52c0-aefb-ebf427269aed | note | Construction Manager Approval
b2950af8-bc4d-50ba-8e52-3001cb0fcdfc | note | Quality Manager Approval
3c77f6d5-f9a0-591b-b892-364a89e1215e | date | Date:
b92eb4fc-9cab-4c1e-9f1b-350c25fefd7a | signoff | SIGNATURE
473dd80f-78b7-5498-b2e4-8e5070fcfcf0 | checklist | ITP-017 - Concrete Culvert 17 | itp | ITP-012 - Concrete Culvert
42f478fc-2189-5924-ba07-4baaf8f6299c | section | 1.1.0 Pre-construction approvals
c6325e1f-98cf-5dd9-a024-c2741f8830c3 | checkpoint | 1.1.1 - Construction Environmental Management Plan
9228b49e-5aee-50d3-942b-513a1e401c62 | note | Method/Description - Document Review
5377f383-17ff-587f-8f81-1473fcf043e6 | note | Test frequency - Prior to work starting
ec45cb7e-6dfa-5859-baa1-f3d73975ea0a | note | Contractor - H
75e814f9-98ac-5a60-b5b6-2b847c137ed4 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed CEMP
ee7771bc-2366-56f9-836d-696e37f5e599 | checkpoint | 1.1.2 - Construction Work Plan
87ecf765-4293-5159-912e-f58d4aa9e29c | note | Method/Description - Document Review
43582105-9874-562e-a056-f5fef5f7bebe | note | Test frequency - Prior to work starting
577042e6-c79f-572f-a20c-2060ec37af0f | note | Contractor - H
5c2d71bc-4f66-5599-8f1f-c89960790661 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
80997794-398e-58e2-88f5-b742e9843f56 | checkpoint | 1.1.3 - IANZ accredited testing organisation
d73622e4-339e-57f0-8976-0951e2f36dba | note | Method/Description - Document Review
0cfa570d-3e93-5252-968e-96862152a449 | note | Test frequency - Once prior to works commencing
b5ef69a8-7b63-5c04-a0db-11432dc931b5 | note | Contractor - H
57277e7f-aec3-5eaa-ba65-bfc85d2bf0ee | note | Designer - H
49551789-7e21-5026-b6bf-2296c8af16ad | note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
1b40a37a-e607-5a69-894d-892e8bd1f5d4 | signoff | AUTHORITY HOLDPOINT
1506fbf7-5b48-517d-a6d7-cb5c453622a3 | checkpoint | 1.1.4 - IFC's specification
a2b1b20e-abef-5ee8-bf13-ba4a3c21c1ad | note | Method/Description - Document Review
f5842c77-6e5a-5e98-aeec-edf052fa72a2 | note | Test frequency - Once prior to works commencing
a7b08a26-79f9-585e-9f62-84ec09d1c8c0 | note | Contractor - H
da4d491c-8d62-5680-9df1-96017b9bf004 | note | Designer - H
fb143926-042d-58fc-8ca4-eec66f248683 | note | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
2358ac4e-bff1-5d5e-8f51-59f40a42db53 | signoff | AUTHORITY HOLDPOINT
66467056-0c6d-5a0c-8857-462d47f00167 | checkpoint | 1.1.5 - IFC drawings
d02bfaf1-7299-5414-b0e0-98744319620b | note | Method/Description - Document Review
fec2408c-f0cd-5a7f-a5b7-0b1e81716e06 | note | Test frequency - Once prior to works commencing
f9724dbf-bbef-5a78-a688-caa65e6b1b06 | note | Contractor - H
f09a0e65-2f7a-594b-aee0-d5908c89cdd7 | note | Designer - H
25fe20b3-1c16-5164-820f-b435da814784 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
9f8f9341-c120-5c71-b92d-67279bb7414d | signoff | AUTHORITY HOLDPOINT
edd8ec75-09d1-5a78-addc-e4f573ae83d2 | checkpoint | 1.1.6 - Approved Drainage Strings
859362a7-67dc-5889-b3ca-caf93ee2434c | note | Method/Description - Document Review
50b400a9-6b28-55ac-bcf7-162f72351b1f | note | Test frequency - Every new Drainage Line and prior to work commencing
7219ff0f-4965-5490-b4b6-c12ceb794f6a | note | Contractor - H
86b0c31e-7352-5b3d-9ad9-97b67ae08f6c | note | Designer - H
49771ed7-1726-5648-b0a6-189e97078026 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Cover Form
19cdabf6-b42a-519e-a7e2-a761366ff32b | signoff | AUTHORITY HOLDPOINT
19d8b93b-c4a4-55e7-ad84-fcfed6a60769 | checkpoint | 1.1.7 - Approval of stockpile location
642f99c1-08c7-506b-8db2-2883f207768e | note | Method/Description - Document Review & Approval
d546ad01-1270-5ac6-a636-f549e73d0c2b | note | Test frequency - Prior to works commencing
37a316ed-bb20-5d4e-a168-6bf6c2b76503 | note | Contractor - H
78dd2113-9c68-5c3b-8803-a60c3627460d | note | Designer - H
724843d0-fcb5-5464-bdfa-4148b5a2ce77 | signoff | AUTHORITY HOLDPOINT
0f3f7c86-5e36-5d1b-a6d0-ea9aff9da0d5 | section | 1.2.0 Material compliance
443b6e21-aa0b-567e-950b-550682a95cfd | checkpoint | 1.2.1 - Materials Approval- pipes and fittings
52bd9155-494f-50d7-9d15-f147933cb9e2 | note | Method/Description - Material Submittal to DSR review
8f9fee52-df73-5037-ae6e-15486c792166 | note | Test frequency - Prior to works commencing
0bbd4002-a9a9-5e67-95ad-5336d271823e | note | Contractor - H
d45cc9dd-3a9c-5658-8ee3-f4f279645b18 | note | Designer - H
b3a4b655-16ee-5511-9857-d63a707641ea | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
b9e28ee0-e9b6-54f8-88e5-0f6824bf8ebf | signoff | AUTHORITY HOLDPOINT
d649f4df-50ca-567d-ac0c-c0bf2ef2e678 | checkpoint | 1.2.2 - Materials Delivery- pipes and fittings
cc85ecff-a0a9-5dff-9f0d-62f3ed39471f | note | Method/Description - Inspection the new Delivery and review the Dockets and test certificates
fb6948fc-a24a-5291-ba8d-40f8b19a9977 | note | Test frequency - Each delivery to site
36a9fc4a-073f-5fb2-b911-50585553b5ad | note | Contractor - H
16b99f2f-7550-5378-9ea1-c0e18cdd3938 | note | Designer - R
a8b26609-a72c-5441-8fea-d0a3727e055e | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Material Delivered Check Sheet, Dockets, Compliance Certificates
8df98f21-357b-50f4-b628-ffecf6bef8cf | checkpoint | 1.2.3 - Materials Approval – pre-cast Concrete Manhole units and wingwalls
6127b00d-50de-50be-92d7-9842234e7627 | note | Method/Description - Specification compliance – manufacturer’s certificate to TNZ F/3 for pipe and pre-cast units
21e84d09-0dd6-5311-b066-688534eeca4b | note | Test frequency - Prior to works commencing
97cbce36-4cb4-5ede-8b72-da68dbed02b2 | note | Contractor - H
cc179de9-a7a0-51e4-9176-705d7e1bf48a | note | Designer - H
a002bb78-6be2-584f-bf16-fab19d6b0b3b | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval
68311dce-be0f-55fb-8cea-aa77e7038764 | signoff | AUTHORITY HOLDPOINT
72197132-d628-531d-a8ac-e88cc2697f78 | checkpoint | 1.2.4 - Materials Delivery – pre-cast Concrete Manhole units and wingwalls
86342b20-ceb0-5782-9c67-c639fa47c4a5 | note | Method/Description - Inspection the new Delivery and review the Dockets and test certificates
be977e92-5547-5fe0-9598-a70a11a6f493 | note | Test frequency - Each delivery to site
9bbea42a-4985-5447-908b-4be23dfb7261 | note | Contractor - H
ff97a6ad-39fc-54d3-aabe-d8225f1a9a24 | note | Designer - R
de9a1911-a267-57cb-91b1-39f1b813891e | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Material Delivered Check Sheet, Dockets, Compliance Certificates
d933df28-57d4-5f26-8b56-38e7b14127ea | checkpoint | 1.2.5 - Materials Delivery – Lids and Grates for Manholes
65f1536e-47d5-5d9f-8ba7-43e351273f6e | note | Method/Description - Inspection the new Delivery and review the Dockets and test certificates
2cd7c8dd-710e-5143-9509-543b9368f5c6 | note | Test frequency - Each delivery to site
1dcc800b-9f9b-54b4-8b5d-162fe72c0b8f | note | Contractor - H
6a1f3567-b35c-5172-9d6e-8edf6b5b96b6 | note | Designer - R
8cd22a33-3a32-512c-bf5b-3748f591d44a | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Material Delivered Check Sheet, Dockets, Compliance Certificates
c102f7f6-fafc-59a4-a0c4-745a3ed2343f | checkpoint | 1.2.6 - Materials Approval – Weathering Index for Bedding, Haunch Material AP20 aggregate
83436569-fa71-5144-aa61-2d89e282a663 | note | Method/Description - Weathering Index test
7bc3ed3a-3ca9-5c2d-8836-200c464ab9a1 | note | Test frequency - Two tests per source 4 weeks before use in the works
8582ab00-843f-5371-aa75-07b417e65dd8 | note | Contractor - H
4203cd20-24ce-53a7-8d67-07d728e562cf | note | Designer - R
efc084eb-7a7a-5c1d-b8bd-15648d90c3a1 | note | Lab - I
70aaf10c-a346-5aab-bc91-41112d8f53c5 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Weathering quality index Test Report
a1055b37-8269-5d94-b655-b34fcc7ef548 | checkpoint | 1.2.7 - Materials Approval – Crushing Resistance for Bedding, Haunch Material AP20 aggregate
25d5cdf5-53b6-5069-84f3-df1fea371e38 | note | Method/Description - Crushing Resistance test
8b0e5de7-e311-520a-bdcd-31fa19e427c1 | note | Test frequency - Two tests per source 4 weeks before use in the works
339a17bb-ac56-58dd-a213-d1b3beff7630 | note | Contractor - H
ef21b36e-4f63-56e5-bfe9-ffc1742911d7 | note | Designer - R
ea842e33-c074-55d0-a5a1-08194f2d3d06 | note | Lab - I
0cae91a1-d7d5-57a7-8c8a-56833eb9a809 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Crushing Resistance test Report
09570336-dcb7-5dfa-8e99-926fb9353471 | checkpoint | 1.2.8 - Materials Delivery – Grading for Bedding, Haunch Material AP20 aggregate
bc5f7429-197c-5f43-806c-a083bff36ec1 | note | Method/Description - Grading Testing Inspection the new Delivery and review the Dockets and test certificates
b5443b02-cb36-54f0-9d3f-a5b2b509e24f | note | Test frequency - 2 per 400m3, 3 per 400-1500m3, 4 per 1500-4000m3 and for over 4000m3, 1 additional test per 1000 m3
58ec9069-dae4-53b2-8ce5-75fd90b44de2 | note | Contractor - H
c5407b9f-e654-5447-9d66-8661bac1269a | note | Designer - R
e04ed7d5-504d-50fd-85d2-6fe379953ae2 | note | Lab - I
4a5e922c-0e9d-582b-bb3b-85672a1431bc | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
29595088-b6b1-562b-ba05-8e5c81115476 | checkpoint | 1.2.9 - Materials Approval – Maximum Dry Density for Bedding, Haunching AP20 Aggregate
cd4baa4b-91f6-5c0a-ace9-cd6ee27b175b | note | Method/Description - Standard MDD Test
a6a8d166-d53c-573f-881f-05defcc1407c | note | Test frequency - 3 no. tests per source with minimum 5 points
86b62a4d-06ff-5f12-ba8b-67ba02bd1470 | note | Contractor - H
0c0daa9c-346a-540f-8493-22ce36bc0266 | note | Designer - R
078c2dc3-2c7c-51db-a567-9c6a6ae74c88 | note | Lab - I
344073d1-f3ef-5f45-a097-fe1bba1fef63 | note | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
a4a34272-dcbb-5ca8-981a-f6f4b5f77a71 | checkpoint | 1.2.10 - Materials - Structural Fill for Overlay Zones (AP65)
8fedcc53-0875-509b-8b60-6a5c450f37ab | note | Method/Description - As Per MMA-CON-CMA-ITP-31067
f8e2b0f3-9dc2-55d4-a121-8319ba8be70e | note | Test frequency - As Per MMA-CON-CMA-ITP-31067
7d87816f-8a30-5fc6-b191-8cfe4b067382 | note | Contractor - H
4c70234c-da14-5be1-9585-3a68fe8d4284 | note | Designer - R
04c98a3e-da02-5b42-85c7-7a839f249836 | note | Lab - I
530fc226-ce63-512c-97b3-7742c4f04065 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Reports
247cc866-0cc8-5c20-b2db-7dd140dcb2aa | checkpoint | 1.2.11 - Material Approval – Rip Rap
f29bbd4a-58c3-518b-bfa2-dd9bb2369659 | note | Method/Description - Test
579e6197-b2f2-51a9-9cb6-349506b7c731 | note | Test frequency - Prior to works commencing
650c2dc0-f9a1-5372-894f-2f502109c62f | note | Contractor - H
ec637ec8-7e7c-56b7-a74a-8fb29f7243b7 | note | Designer - R
cf22aa9f-e7dd-56ac-ae42-3228ffeae010 | note | Lab - I
5b87d090-3971-51fa-b9e4-8d9550c84264 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
fec6d0a7-b238-5554-adc0-de639dedb1e1 | checkpoint | 1.2.12 - Materials Delivery – Weathering Index of a Coarse Aggregate for Rip Rap
76d76450-aa41-57a2-b65a-f7469001594c | note | Method/Description - Weathering Index test
5dd95292-dc1f-5a31-8582-e3dc1b982f05 | note | Test frequency - One test per 1000 m3
2299bdab-318f-599f-beb9-fab2b24ab1d5 | note | Contractor - H
c29c1dd3-e6f5-5924-a8ba-2fb0916a57fb | note | Designer - R
084e7d2d-a7dd-5dde-8c31-521cde127c0c | note | Lab - I
f1ef77e9-68e0-5c4d-b0a6-bebefce552d3 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Weathering quality index Test Report
3d9f5821-60a3-55a1-bb3e-009b80fede04 | checkpoint | 1.2.13 - Materials Approval – Crushing Resistance of Coarse Aggregate for Rip Rap
ace74ae8-bb30-53f5-9cba-38fc3b840177 | note | Method/Description - Crushing Resistance test
e9c655c2-b83d-50d2-abd6-988cecfd500b | note | Test frequency - One test per 1000 m3
09add22f-c38c-5c33-9d65-33561b80bb8b | note | Contractor - H
12b6174a-ab9a-5ac6-9414-4752329ddf76 | note | Designer - R
77130f70-ebb3-59c4-9470-ebc25bde8cf0 | note | Lab - I
56c5d09e-4671-54e3-ab99-ec26663198ae | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Crushing Resistance test Report
0082900f-30ff-51d3-95ef-8525bf4e965a | checkpoint | 1.2.14 - Materials Approval – Solid Density of Aggregate for Rip Rap
16241c37-b56e-5992-aa1b-aacff7797c63 | note | Method/Description - Solid Density of Aggregate test
b3fe0262-8281-51bb-bd7a-2eb3aa0706f3 | note | Test frequency - One test per 1000 m3
35389f48-0b1f-5623-aa22-cb338b069eb3 | note | Contractor - H
6b4b9f0f-ccf2-5407-b7a7-bc629d4eb14e | note | Designer - R
ce520bfb-c4bb-56db-ac5e-b62d82e4c5a7 | note | Lab - I
04712e61-9d90-5cf9-81ad-dea279d7b4f7 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Solid Density of Aggregate test Report
813623a3-2317-5d0f-a077-165b4116cd86 | checkpoint | 1.2.15 - Materials Delivery – Grading for Rip Rap
418d53d7-b473-5e55-9394-69829ce1f519 | note | Method/Description - Grading Testing
ad12a285-38e9-5200-875f-2de03a60615c | note | Test frequency - 1 per 500 m3
324efc51-a05f-5244-9a3a-89ff808d6bdb | note | Contractor - H
5a691c0b-f3a1-542f-9d48-0b8b9f0e2bb1 | note | Designer - R
93cf2d6e-d631-5297-be5b-7cccebca74df | note | Lab - I
ab37d86c-5690-5391-b799-11d45f798d9e | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
dc933034-c57b-5974-b3cc-48feddca0a77 | checkpoint | 1.2.16 - Materials Approval –Point Load Strength for Rip Rap
a60cabeb-6df7-5495-84a9-1dc7d01b2c3d | note | Method/Description - Point Load Strength test
78605a8d-9ff1-5c4a-bbf1-0edfd45b279d | note | Test frequency - One test per 1000 m3
3a2784c2-123b-5657-aad3-25765a771a21 | note | Contractor - H
bdfc2831-7f77-5018-adc1-7bc743b52b93 | note | Designer - R
f5ce3993-0879-5921-af5a-678877962c29 | note | Lab - I
603d2c75-6a46-5f90-8006-4e818479e54e | note | Verifying Records Checklists, Test and Supplier Certificates - Material Approval, Point Load Strength test Report
f61568cf-b9cd-5480-a399-bfbd3ffd0102 | checkpoint | 1.2.17 - Materials Delivery – UCS Rock for Rip Rap
a0050bb9-62a2-5f6e-bcf5-ef037ba1c3d1 | note | Method/Description - UCS Rock Test
c05cef0c-ff14-55de-96a3-417ee73d3832 | note | Test frequency - One test per 1000 m3
748ed59f-a8cb-531a-a778-4854e6f862be | note | Contractor - H
e35fa1c1-981f-5fe1-82e9-0828acba424f | note | Designer - R
fbf26c5a-2355-5b59-8623-32c70741ba18 | note | Lab - I
2d562601-9907-5560-afa8-bb69b85a94c6 | note | Verifying Records Checklists, Test and Supplier Certificates - UCS Rock Test Report
7776722d-c74f-534d-951e-10aa78343830 | section | 1.3.0 Geosynthetics
6368f7e9-4970-524b-b51b-a635a5605c3a | checkpoint | 1.3.1 - Designer Visual inspection of the bottom of the excavation
0db1dd08-cf25-5a83-98fb-b78beabf6e34 | note | Method/Description - Inspection
a4c984cd-ae01-5139-99e9-e5b98c37dd16 | note | Test frequency - Check each lot
268892fb-2c5d-5ce1-ad2d-f8e82d79373f | note | Contractor - H
88b4001b-385e-57ac-9181-fece7ee10919 | note | Designer - H
3b6dabf8-b6a7-5b7e-a02f-ab02d1ccc8ae | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checklist, Daily Site Inspection
9a1164c3-6044-542f-a8bc-55217fddbd10 | signoff | AUTHORITY HOLDPOINT
3560fee5-63bd-5a8b-ac1e-3377036c2e19 | checkpoint | 1.3.2 - Geotextiles
2ff86310-02b0-5683-be3b-65387d1ae0e0 | note | Method/Description - Inspection
85c3a159-0f78-536a-971c-759c0364cb62 | note | Test frequency - Ongoing
0c3c90a2-c72c-5b90-a571-de290875c9ae | note | Contractor - H
6261776d-24d8-543f-a2b8-6d3a56fd1e4d | note | Designer - W
ad6c9d91-dcfe-5123-9922-d9c2d3e1687e | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checklist, Manufactures Certificate
4c0dc328-3b88-5f08-b329-45e2cf194f3a | section | 2.1.0 Trench Excavation
f986fadd-ceae-50ae-8ad8-b02d3b3a73e8 | checkpoint | 2.1.1 - Trench Subgrade
847e7178-d71f-5f9a-8147-da80203f137c | note | Method/Description - Testing trench foundation material to assess is undercut is required. Scala penetrometer test as per NZS4402.6.5.2:1988 for non-cohesive materials. Table 18
45a647cb-092a-5069-a13c-23fbaee0f119 | note | ○ The CBR value of the subgrade soils shall also be measured using the in-situ CBR test in accordance with NZS4402 Test 6.1.3.
70b28c97-0316-5492-9fda-120649e4d15d | note | Test frequency - 2 nos. Dynamic Cone Penetrometer tests / 5m of trench, 1 per ancillary structure
f9b21d77-9275-5be5-bc34-7bbdfc68b456 | note | Contractor - H
72bc675b-d854-517d-8eb5-e36777048a7d | note | Designer - W
5c45e531-83d5-53a4-ab3e-51126cdad3e0 | note | Verifying Records Checklists, Test and Supplier Certificates - Dynamic Cone Penetrometer Test Report
eb50ab69-1329-59cf-a234-f44f19866d30 | checkpoint | 2.1.2 - Trench Benching
ea4b4f01-db21-5042-aa47-a6bffcb6519a | note | Method/Description - 1.5m benches to be constructed starting from rock face
e3e0e14b-b1f3-5841-838e-ff78e88bb891 | note | Test frequency - Daily
85cc4c53-0690-5d9f-8dda-8c730a8a3309 | note | Contractor - H
6945ba66-2aef-5448-b240-0f6c8238fe9d | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check List
50816fdf-3a18-5603-b151-5a929acd38e6 | section | 2.2.0 Pipe Bedding and Construction
105a0377-f680-585a-8f43-0393b04334fd | checkpoint | 2.2.1 - Construction of embedment side zones using AP20
3a7ba378-3987-5b74-8f07-b83588c52669 | note | Method/Description - Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991;
33deb3de-4a1a-5a03-8e66-8127f4ea16af | note | Test frequency - Two test “sets” per layer, 10m evenly spaced intervals on combined lifts upto 300mm lift
919547bb-70d0-5ccf-b4dd-321aeb76e91c | note | Contractor - W
0b9d354a-383a-59b4-bd63-18093e708e72 | note | Designer - W
d1570523-4240-5e8c-8472-5d3a389c01d6 | note | Lab - I
ba0ecf47-244f-5440-b923-0f52e5fd3c52 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
75f1d9d2-90be-5906-b1d5-437f0bb9dfd3 | checkpoint | 2.2.2 - Construction of Overlay Zone
69b3b9a8-f078-5dbb-9f5e-9c813035422f | note | Method/Description - Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991; Undrained shear Strength
9e012799-ff14-5a55-aefa-01c479d91ba7 | note | Test frequency - 1no NDM and 1no Shear Vane Test per 20m max canters at 300mm lifts
a1c7c260-c6b0-5a2c-9435-7ca233679ef8 | note | Contractor - W
943df5af-0820-5d7d-9e21-bdb41665cadb | note | Designer - W
37d8da41-ddd1-5515-888a-c20a8228259f | note | Lab - I
fe7b455b-e6bb-5d65-a5ed-1aa67681411c | note | Verifying Records Checklists, Test and Supplier Certificates - NDM Test Report
da31c029-6072-53a1-a4b7-22c4aa43839b | checkpoint | 2.2.3 - Construction of pipe
5495e333-1841-5d58-a491-9d43276c9772 | note | Method/Description - Visual test prior to backfill above the side zones – line and level, correct installation, and joints are all sealed.
2c330310-90ff-58e2-966d-39f47fe9b707 | note | Test frequency - Review every 10m and witness every 25m
63264f0b-8b4c-562c-8ba5-74f0d41f691f | note | Contractor - W
150709ef-07d4-5761-94ab-46be48debe81 | note | Designer - W
2cb52ef5-085e-528a-ab3b-fd0f482a608d | note | Lab - I
a9ac0eb5-2063-5928-815d-ac0a351654aa | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
f5fa687b-8e4f-5725-9c87-97b706549725 | checkpoint | 2.2.4 - Construction of Wingwalls
63e31e78-1cb6-5685-a317-de149d6ba04a | note | Method/Description - Wingwalls shall be constructed on a compacted, 150 mm layer of AP65 granular material. Jointing between the connecting pipe and the back of the wingwall shall be completed using mass concrete.
23794daf-fd71-5587-ae40-508d5f86f8fb | note | ○ Visual inspection of joints between pipe and wingwall
b3f0c1c6-cede-5fe4-8db2-a2f7618ad84f | note | Test frequency - Each Wingwall
a64fac22-c168-52a8-8e9c-17a8ca99a408 | note | Contractor - W
95dcca66-7830-5bcc-8e0b-c1fa1340f6df | note | Designer - W
a7c398a7-c4e2-55e8-89f5-9fbbcb7152a9 | note | Lab - I
e71736b2-6383-5e48-8937-ae2a8056a9bf | note | Verifying Records Checklists, Test and Supplier Certificates - Test report, Onsite Check sheet
a50d0e9f-e834-599b-8523-b84375fdd90f | checkpoint | 2.2.5 - Construction of Antiseep Collars
4c99c008-fdb2-5621-8d69-e78e5f9ee706 | note | Method/Description - Antiseep collars to be embedded 200mm horizontally into side of trench and 400mm below base of trench. To be located every second pipe joint. The collars shall be constructed using 25 MPa concrete.
85ddf569-907e-56ec-8b62-49a94a82b8c8 | note | Test frequency - Each Anti Seep Collar
60bb4a34-1198-5817-a955-75899b32e8f7 | note | Contractor - W
dc501a93-a067-500b-b7b2-b712ae7708fd | note | Designer - H
6e4341db-cdb0-5dfb-b7ec-d0d4d9996949 | note | Verifying Records Checklists, Test and Supplier Certificates - DSR Inspection (Pre-Pour), Pre-Pour Check sheet, Concrete Dockets, Concrete Test results
6cde02ed-5070-566a-b966-0872f46a6950 | signoff | AUTHORITY HOLDPOINT
582cd8b8-8363-549d-9259-a765ac8c6e8b | checkpoint | 2.2.6 - Construction of Cut Off Toes
427d8625-88da-5823-8de8-4f5aadec412b | note | Method/Description - Cut off Toe to be embedded 1m (or note 4) from top of wingwall base, to be constructed as per IFC Drawings
ca58d884-f8f0-5b9d-9796-e3ee82da142a | note | Test frequency - Cut Off Toe
1d881238-7e12-5496-aa65-5a99f5277924 | note | Contractor - W
d1641998-47dd-5bb3-9217-e0d77c23c526 | note | Designer - H
a122cb44-bda1-5576-86aa-cd11a610b441 | note | Verifying Records Checklists, Test and Supplier Certificates - Pre-Pour Check sheet, Detail Sheets
d14e1df5-6882-5afd-a62c-c939f4ca19f3 | signoff | AUTHORITY HOLDPOINT
594c0178-f298-52f4-9f5b-7c9b1e5b64e5 | checkpoint | 2.2.7 - Construction of Inlet/Outlet Channels
45ed5101-68a7-5e22-a22f-f5825168438d | note | Method/Description - DSR to inspect geotextiles before rip - rap is laid. Max drop heights to be adhered to when placing rip-rap
5afe2323-d6f6-5caf-b559-8b73dba33b0e | note | Test frequency - Each Channels
c0b813fb-a9aa-5f37-aae5-84685b21bd6e | note | Contractor - W
1e47230d-026c-5f7d-9395-bc17239f19f5 | note | Designer - W
3086fc60-1d3c-57a8-a396-5bfc16171ca0 | note | Verifying Records Checklists, Test and Supplier Certificates - Geotextile Installation Check Sheet
c512f035-a60f-5265-aa88-74075cc49bc6 | checkpoint | 2.2.8 - Fish Passage
a09e9033-37fe-59f4-805b-6df53e475682 | note | Method/Description - 25% embedment depth with meandering low flow path from void filled riprap. Spat ropes for CU-17
5661c784-7c55-55e6-963d-25c98bc02011 | note | Test frequency - Review every 10m and witness every 25m
3abb2b58-3dab-5492-85a0-92faafcb0ecc | note | Contractor - W
58acd012-3564-52bb-8c5f-829e197eeb19 | note | Designer - W
b3639ecc-1436-532c-98be-e037658ce66b | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check sheet
37038c88-37a8-5007-ba3d-45bc5b4228f4 | checkpoint | 2.2.9 - Construction of Safety Rail
3e635c4d-68d4-5c4e-ad17-6fdfcc89400f | note | Method/Description - Constructed as per IFC Drawings
eeccdb52-2237-5e3e-a86f-4cd66649a4c6 | note | Test frequency - Each Fence
4cd7c820-cb60-52e5-ba17-3960a61db922 | note | Contractor - W
f527a4c2-cae9-57f6-a5a6-84009edc69f3 | note | Designer - W
94535d2b-004f-5af0-8369-14420763c9a4 | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check sheet
d5545795-84a2-5564-99ac-44165c0761fb | section | 3.0 Post Construction
be98c092-01d5-5b90-971c-8c4da0244e2b | checkpoint | 3.1 - Survey/as-builts
40494747-1472-5bb5-97a8-aec6c59a584d | note | Method/Description - As built survey of coordinates and invert levels, structures, and pipe ends
d0bc6e8a-5d57-5205-96ec-3b694ce97faf | note | Test frequency - Every 100m
b7b8a638-6e8e-54a2-a65d-1745e26dfbf9 | note | Contractor - H
dce60108-fd2f-58a4-a4b9-29f1c2f24a17 | note | Designer - R
56259f04-79c5-52f0-aeac-f4d4376e7aa7 | note | Verifying Records Checklists, Test and Supplier Certificates - Survey As-built Data
cbc3445c-ac90-550f-9e82-af6420eeb789 | checkpoint | 3.2 - Post Construction CCTV inspection
95f0d49c-e324-5e35-baf4-fa86f7683f68 | note | Method/Description - Check conformance with the specification and assess the asset condition post construction
643a8dbb-4725-5eca-8ad5-5559c1234b0a | note | Test frequency - For all pipelines > 225 mm Diameter
45a53d30-beb9-5f86-9463-33c05271ac0e | note | ○ At completion of trench backfill of minimum 5 m fill prior to final surfacing
9fa72698-7372-5ff0-bf78-8761ee087785 | note | Contractor - H
ad14c004-5c03-5329-98e8-cd1f97967c30 | note | Designer - R
6b831f80-8582-55ad-b922-6aa4926f093e | note | Verifying Records Checklists, Test and Supplier Certificates - CCTV log Report as per the standard
8919eff8-fed3-572c-bcf7-d24e7712e7ba | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
45524c2d-1de8-5e60-b52d-1f4484181dd2 | checkpoint | ITP Close-Out by
a57f4b42-7ec8-5415-9f65-ce1d2e335413 | note | Site Engineer/Project Engineer
ff8f41d9-1fe9-5988-adb9-7e759afebebf | note | Zone Manager Approval
b1b07624-6b73-5228-a07f-2293c17788af | note | Construction Manager Approval
0e4133ec-0e60-5fd8-b55d-a9be9b10ab3d | note | Quality Manager Approval
5750c7ec-09a8-5539-9a20-022691aefd0c | date | Date:
1dc2c9d0-048a-5501-9488-936d3248a797 | signoff | SIGNATURE
f4190f6d-6e2a-58ff-8a0d-fab406bb7a0c | checklist | SYS - Access Track and Stream Diversion Subsoil ITP | itp | Access Track and Stream Diversion Subsoil ITP
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
840d7178-b03e-537c-b111-82e872a14b9c | checkpoint | 1.01 - Confirm Method Statement Signed off
411bd5c4-b550-5426-8642-6e9d38cedd5a | note | Method/Description - Document Review
f6ff0115-1f4c-5d65-84e0-4a72c28bf9ca | note | Test frequency - Prior to Work, Once
b9764723-8ab4-5c67-9161-c65c2a44bca2 | note | Contractor - H
a3fc211d-6b84-5b39-a13a-b983ebbf904c | note | Designer - H
7e6343fc-ee4e-526f-9ad7-299d1c34eb9b | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Copy of Method Statement
42bc0245-639c-57f9-9f09-8f12305c24ce | signoff | AUTHORITY HOLDPOINT
5c8b235a-89c6-5bc2-95c3-af3747fcf89a | checkpoint | 1.02 - Confirm Compliance against Resource Consent & Management Plans
420fd7b7-423b-5959-993b-c73d42531c56 | note | Method/Description - Document Review
c0e5bc45-3814-5ff4-8b3b-a565b622cff6 | note | Test frequency - Prior to Work, Once
8bc82449-2207-5d7a-96f3-793f9ca06ac7 | note | Contractor - H
ee6e2cd8-d98a-5e50-8c59-1804da061700 | note | Designer - H
d9d381ec-bfa8-5bee-899c-969666ee4ecb | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Management Plans, Approved SCWMP and Approved CWP
80f44c70-59d0-5d07-bf6f-65b719d78da8 | signoff | AUTHORITY HOLDPOINT
a7abe052-25a4-5b64-9ac8-d2d5e962d5e3 | checkpoint | 1.03 - Confirm IFC Design is in place
5cbb18ad-918d-5405-baf8-81fe5da2b49a | note | Method/Description - Document Review
44f5de07-bec1-5e35-9c1d-3dbfd9464002 | note | Test frequency - Prior to Work, Once
3e53d722-fa25-56af-a398-678a5682fc0e | note | Designer - H
52e4814e-6fe0-54f8-8f1f-0538178473a1 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings Issued
124b501d-73e4-53df-a8f5-6b9175b379e6 | signoff | AUTHORITY HOLDPOINT
3e4ca7a6-fdcd-5bc0-9f74-9e85ab2206e0 | checkpoint | 1.04 - Complete Permit To Dig
6c102f09-b37e-5afb-9f26-f77c2b9aaf0b | note | Method/Description - Document Production
7fa5eb99-b91d-5ad4-a556-531062f8850e | note | Test frequency - All Excavation works
e699e163-c0cf-5681-8f18-b79553cb4f80 | note | Contractor - H
22edda1f-88cd-53b8-aea5-1fcfe52e7623 | note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Dig Form
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
e86f10e9-8b19-553f-804e-38c741e160bf | checkpoint | 2.01 - Order Subsoil Pipes
af305bec-6dca-5765-b4f2-db988afa71b5 | note | Method/Description - Ensure Pipes are ordered as per drawing
58b89afa-b730-5c29-8e64-326ba59444aa | note | Test frequency - All Subsoils
aaf13ecc-db2a-5c90-b8f9-81bdf5689aee | note | Contractor - R, I
4c61e2ae-16c6-515a-ae67-2009a7fad8cd | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Material Complaince Certifcate/Data Sheets, Material Delivery Inspection Checksheet
c73d4d38-f592-5050-beca-bb24f088b3c2 | checkpoint | 2.02 - Order Geotextile Material
89d6f497-7bfc-594c-8eb7-f5bf197f03de | note | Method/Description - Document Review
ed503d8c-d3ee-56a7-95a4-7d45becbd6f0 | note | Test frequency - All Geotextiles
6dab2856-732b-5149-bb06-32b809f5eebd | note | Contractor - R, I
f6b1b5ff-c92c-5653-ab33-115f67ed0fb4 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Complaince Certifcate/Data Sheets, Delivery Dockets
ab193b17-ff99-5108-8392-edbe34f38cb4 | checkpoint | 2.03 - Order Subsoil Drainage Backfill Material
622bff40-4a90-54e1-ac66-8edb6738428f | note | Method/Description - Laboratory Testing
c03b408a-b9c9-5dde-a71e-959b63c50f10 | note | Test frequency - All Material
6e3b59f8-2e8a-5963-b6e3-3d0ed4beccf3 | note | Contractor - R
fffe0c0f-4766-5f30-bcb7-3d94a3257e7b | note | Designer - H
06f57223-d4a2-5114-841e-5138808b0dbf | note | Lab - R
31c62d6a-1468-5b2c-a597-e96682946414 | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Results, Permeability Test Results, Crushing Resistance Test, RFI - Confirmation of Material acceptance from Designers
a40a5658-bcec-5b25-9610-992d44c8435f | signoff | AUTHORITY HOLDPOINT
a60c08ec-043a-5ac7-968a-e6a03c1faea3 | checkpoint | 2.04 - Order FarmBoss Pipes (Temporary Drainage)
30bbcc20-5408-5d2e-bbb9-6a5cc69851f3 | note | Method/Description - Document Review, Material Delivery Inspection
097d041c-1f47-517b-ba4d-56ce9da6c904 | note | Test frequency - All Pipe
54e4c6d4-86dc-5dc4-8573-38697687ca70 | note | Contractor - R, I
b2774fba-4484-5c97-9af9-b270674f6e74 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Docket, Material Delivery Inspection Checksheet
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
3e503167-dfec-5627-8b25-d5091f7b1f38 | checkpoint | 3.01 - Clearing and Stripping of Area
54a0b372-b788-5f8c-8fd7-89a9b8adf917 | note | Note: Fill 12 and 13 are exempt from Organic Waste Clearing and Stripping when >5m from finished ground level
7eba61e1-a678-5b88-9a49-d2db0087350f | note | Method/Description - Removal of Organic Material
bdb87169-5d7d-5d33-8552-99ef9253825d | note | Test frequency - All areas. Subsoil Checklist completed for every independent section and minimum 100m length.
8d14f524-c053-58df-8c51-56f43d393668 | note | Contractor - I
cce81a3b-409a-51fc-9e95-83e31b1880d2 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
d731f851-5a53-5724-9682-975128810a16 | checkpoint | 3.02 - Inspection and Confirmation of Foundation Subbase (Designer shall be notified 24 hours prior)
f3036a5d-b13c-5a63-88a3-3ad0e220544f | note | Note: Fill 12 and 13 are exempt from Organic Waste Clearing and Stripping when >5m from finished ground level
73ba8bc8-6bab-599d-880a-2e0ac03881d2 | note | Method/Description - Visual
c5c8c29f-0e83-5d1a-bd36-890b925bcb8a | note | Test frequency - All new areas opened. Subsoil Checklist completed for every independent section and minimum 100m length.
12b260a7-1688-5966-a01b-82021a9ef5d8 | note | Contractor - I
908813d1-8520-5971-8f63-9195c1247d12 | note | Verifying Records Checklists, Test and Supplier Certificates - Designer Site Report Issued, Visual inspection
3ffb03be-3168-5ad5-a602-7618f3bca33c | checkpoint | 3.02 - Formation Level Inspection
f3036a5d-b13c-5a63-88a3-3ad0e220544f | note | Method/Description - Visual
73ba8bc8-6bab-599d-880a-2e0ac03881d2 | note | Test frequency - At formation level before installing the geotextile. First section of pipe and then once every 50 m of pipe laid.
c5c8c29f-0e83-5d1a-bd36-890b925bcb8a | note | Contractor - H
12b260a7-1688-5966-a01b-82021a9ef5d8 | note | Designer - H
908813d1-8520-5971-8f63-9195c1247d12 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
264dba25-731d-5ed7-a78b-a7a629fa9437 | signoff | AUTHORITY HOLDPOINT
a6f1c758-656b-5240-862b-c139a4e5de79 | checkpoint | 3.03 - Lay Geotextile (BIDIM A29)
b0109de6-b404-5c76-83d0-ee683c2dfc73 | note | Method/Description - Inspection
8a80bde1-54b6-543b-b6c2-cda6cba54adf | note | Test frequency - All BIDIM. Subsoil Checklist completed for every independent section and minimum 100m length.
24ab384e-d96a-5aee-8fd9-df1dbc3afed3 | note | Contractor - H
ebdc72b7-9bbb-5a3d-a0bd-4a4bcb2818a5 | note | Designer - R
21353ae2-3c95-5f46-a40e-3f9a08d0b24a | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
64925617-a85a-5a43-bba0-7650792c7468 | checkpoint | 3.04 - Install Bedding Material for Subsoil
b1b5b860-f0e8-59d4-8346-be74e228a313 | note | Method/Description - Inspection
1932a309-a32e-55fc-93d9-935909f265bb | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
b5aa431b-d802-58d1-9bbb-f308f7575c4f | note | Contractor - I
9d45cff1-e3db-556c-af76-eccfe60a67a3 | note | Designer - R
a401c1cf-1d25-578f-a88d-dddeb91d97c4 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
48dfe27e-ff7a-521b-bae5-f5f55a05dd96 | checkpoint | 3.05 - Install Main Gully Subsoil
d93d3077-04f3-546b-b3be-ac4b4e79bcd9 | note | Method/Description - Inspection
674c2c76-db0e-5354-9d19-d1bba290b267 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
70ae588f-5643-5ac0-b22f-66abfa02029d | note | Contractor - I
6726ff69-0b15-5532-9c98-d9bc9e2801b3 | note | Designer - I
def36970-6afd-5238-9837-484c1143cf7b | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
90d6e7a1-cbd8-5795-bbe8-f63561ce30fc | checkpoint | 3.06 - Install 450mm FarmBoss (temporary Additional Drainage)
8b8f3e16-dd01-5675-92a4-435fab8755d0 | note | Method/Description - Inspection
8fbebcb2-31f7-5f10-b82e-ddee47f53f77 | note | Test frequency - All FarmBoss. Subsoil Checklist completed for every independent section and minimum 100m length.
6dfe1a21-1962-5a75-b326-ae092497b44c | note | Contractor - I
aed160f8-f5ac-58c1-a9fd-a2328f4a380a | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
4a8e29a9-6a51-5d0b-a0ba-a0530485b2f3 | checkpoint | 3.07 - Install Backfill Material
b4e7f7da-0ff1-5759-9d07-6a0864cfeec3 | note | Method/Description - Inspection
4b40a2a4-a5b6-5991-bf26-b9638cf60226 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
95d1b2f7-f730-57c0-9193-1e90daff09ff | note | Contractor - I
a058d4fd-902f-543e-a36c-8526c32e317e | note | Designer - R
41c9c328-47f6-593f-8583-164ac40798a2 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
c04adb27-0b59-522b-aa33-a966e3353cf0 | checkpoint | 3.08 - Install Vertical Subsoils and Connections
70d540f5-3674-5eb4-9939-8a266b433505 | note | Method/Description - Inspection
3025783b-2ad7-52b3-b7d8-46663eff93c3 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
593fd4d7-8d4c-5b1a-854f-d31948c4321e | note | Contractor - I
b0b52af5-2717-5265-adcb-6f49bfc656a4 | note | Designer - R
026816eb-1786-5f1e-961b-799c1ca2c9aa | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
a91430d2-3995-5e25-9013-6a3786f37df3 | checkpoint | 3.09 - Install Additional Vertical Subsoils
f73c7e64-4c1d-577d-8897-de04a5088be1 | note | Method/Description - Inspection
b698bbae-bbee-51e0-a8d4-9e6765faddd9 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
4bbb6a7d-4a4e-55e4-a0cd-1800f317b7d1 | note | Contractor - I
e6260eb6-b8f2-5558-8c53-26626c1ca0a2 | note | Designer - R
da5d75ec-f13e-5505-ba75-0d4508d09075 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs, As built, Formal correspondence
e938a91e-74a1-5e8d-a2f9-7fc1fe37cb86 | checkpoint | 3.10 - Wrap Geotextile
b951fc49-e9bb-5569-a949-395e600ee30a | note | Method/Description - Inspection
1c01c10c-9fa7-58ab-8b6b-3fb8505c1baa | note | Test frequency - All Geotextiles. Subsoil Checklist completed for every independent section and minimum 100m length.
8a4e6575-67ed-5e13-9a2a-850167260611 | note | Contractor - I
e073d395-68ca-51a8-8020-9c1788f97bb9 | note | Designer - R
f54484f6-89d0-5be0-90bd-3c34df2a0802 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
fae5e183-4e7a-5bc3-a094-f921f788ef4c | checkpoint | 3.11 - Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top
14bcfb28-8ee2-59d4-98f6-b3db43730e62 | note | Method/Description - Inspection
1860d7b7-3a54-5c3c-85ba-ecb2572989b9 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
dfea8ab4-fa9e-50fa-b290-3ce40295a690 | note | Contractor - I
d31434ef-14ff-5ac1-8c82-8d3cddfb7331 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
f761d223-9345-5a5d-b40f-3a06946049ac | checkpoint | 3.12 - Construct Outlet structures
5339cc5e-3443-5fec-bdd4-21e0f10d5a58 | note | Method/Description - Inspection
668a31e4-9a76-5145-8e78-0956646d97a8 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
78b9c36b-690c-5484-b0a6-77e3f0dc8fcc | note | Contractor - I
d6830253-1bb1-55e1-9676-884360d4f7bc | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
d2ef6b17-bd1e-5c35-a60f-ec686fb1ab1f | checkpoint | 4.01 - Completion of works
f02a4548-7e0b-51e6-a9f6-074e47f3d4c0 | note | Method/Description - Inspection
5cd33b37-6710-54c6-ad63-77e8e0294792 | note | Test frequency - All Subsoils
a0972601-b0f8-5893-800a-3405c5695e7f | note | Contractor - I
a7e369d4-7517-5cb4-953c-c8ee47bd25ca | note | Designer - R
3d4b2ee6-962e-5c38-9871-4f195c3114c3 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
5b8df720-9ca7-5ae8-a81d-997056d6c93b | checkpoint | 4.02 - Provide Maintenance and Inspection Report/As Built
cb221f93-58c1-52bc-8de9-adf7abe7dea6 | note | Method/Description - Maintenance and Inspection Report Completed
d7776e28-748f-5c55-bf04-2ececb274d93 | note | Test frequency - All Subsoils
d00a9801-7a1c-5d96-9a3b-1d01d832ceaf | note | Contractor - I
92feb325-2ac3-5e68-a22c-4ee3742ece37 | note | Designer - R
5ef0b631-7bc9-56bc-b929-46845b742467 | note | Verifying Records Checklists, Test and Supplier Certificates - As Built Plan, Redline markup
f4428f7c-2764-46ca-8aea-4bd572177e50 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
5cc48b5a-4014-4540-9412-6eefabfe836a | checkpoint | ITP Close-Out by
a3b0a5a6-cc87-5263-bc5d-1d21ace5d4c3 | note | Site Engineer/Project Engineer
7b1e67ad-da65-5b6a-957b-c4179921b688 | note | Zone Manager Approval
9c1b948d-ff21-52d2-86ed-bfb55a2768d3 | note | Construction Manager Approval
e88c638a-0e23-5927-ae96-6c8ee89be69f | note | Quality Manager Approval
b614d225-e8af-53cf-ac37-d30643ca0ef9 | date | Date:
d3b1b717-ec33-471e-94cc-290070083d3a | signoff | SIGNATURE
48168aec-e573-5ba9-a05d-fc6b6866d9eb | checklist | SYS - ITP - 009 - Geotechnical Equipment Installation Cut 15, Fill 15 & 16. |  | ITP - 009 - Geotechnical Equipment Installation Cut 15, Fill 15 & 16.
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
5db01920-7d30-5f29-9615-65837ccd9caa | checkpoint | 1.01 - Construction Environmental Management Plan
c1781c39-6cac-5686-bf54-d6edb8e4135b | note | Method/Description - Document Review
d179a05e-3643-5bc1-a50d-a3081f64eb5d | note | Test frequency - Prior to personnel starting
09cac770-3cd8-52a3-8bc5-2e8a80f8cafc | note | Contractor - H
c9edf3ba-d9d5-5c74-81bb-44dd40ee758e | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
1735e9e8-adfb-572c-9a8c-6517471a2e66 | checkpoint | 1.02 - Construction Work Plan
4e0b4904-362c-544d-a719-519af9756510 | note | Method/Description - Document Review
68d92397-5cc2-5989-980a-c1b77fa042d9 | note | Test frequency - Prior to work starting
996f184d-097a-5a25-b169-b2d8603b4679 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
2ece2dea-0ece-5f8b-808c-1cdc710ec1da | checkpoint | 1.03 - IFC's specification
75236a7c-b6a6-5779-acfd-5a519a419c98 | note | Method/Description - Document Review
d571d8ab-9eda-5b36-ab0d-87d643deb4cc | note | Test frequency - Once prior to works commencing
67804dd6-5d72-5463-9386-41204f75d563 | note | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
9f3782d6-fcad-57e8-9f89-25cbd7e66940 | checkpoint | 1.04 - IFC drawings
570dcf66-8dcf-5ff0-a2ab-37d011c8b838 | note | Method/Description - Document Review
4f6d9c99-2ee3-5e87-ae50-79704bd5e962 | note | Test frequency - Once prior to works commencing
f3b9d3d1-e7e4-5dc6-af7f-93e427e7c2fd | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
88046553-aa6f-52f9-90e3-e891d6407ce1 | checkpoint | 1.05 - Approved setout locations of instrumentations
1206e3f9-55f0-5149-b537-d0cb066f8a02 | note | Method/Description - Designer Confirmation
234615fe-858e-5b91-84b6-936b7919e60b | note | Test frequency - Once for every fill site prior to work commencing
4da0b8e2-90de-5038-a64d-46d5bab7e7ca | note | Designer - H
087d1f16-fa33-5b3f-871f-0bc2341b77e6 | note | Verifying Records Checklists, Test and Supplier Certificates - Written Confirmation from Designeer
b44d7639-8d9c-55a4-9c83-b431678d98d6 | signoff | AUTHORITY HOLDPOINT
44a0d20e-8a4a-5ae0-aa01-d566f7bbd0e5 | checkpoint | 1.06 - Method Statements Approval
58043e0d-7a7c-5d6b-b0cb-2a5cb8308248 | note | Method/Description - Document Review
28484890-c6bd-57aa-a072-f138cd85aad8 | note | Test frequency - Prior to installation of instrumentation
84f1f6ba-afbe-56d4-b668-c6badf80a7ab | note | Designer - H
0d9b24a0-379f-5029-8b3b-a9dce4fb710d | note | Verifying Records Checklists, Test and Supplier Certificates - Method Statement
80c5463d-a41f-583d-8d84-d1acff384202 | signoff | AUTHORITY HOLDPOINT
bb35f236-5d4b-5379-8828-26d0db8da5a0 | checkpoint | 1.07 - Calibration of Read Out Equipment
5ce63ece-0744-5b28-8663-673fa4ec1110 | note | Method/Description - Document Review
15a52ad9-a3d0-55a7-9e72-8b6f88f00fbb | note | Test frequency - Prior to starting
90e5d4a7-3752-58ea-ba82-fda72e3a8599 | note | Contractor - H
1d0cd476-aa76-5660-b4ca-c6e7df0b0dff | note | Verifying Records Checklists, Test and Supplier Certificates - Calibration Certificate
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
887763dd-cf3b-5bf4-9f81-61012322a83a | checkpoint | 2.01 - Vibrating Wire Piezometer manufacturer specification
8508f579-26f6-5f9b-ab9d-ed5b0788bdab | note | Method/Description - Document Review
e2832465-6268-5839-a4ec-ae1f5f07a2e1 | note | Test frequency - Once
247fa4c5-f5b6-5c18-ae09-0393c9d95ff6 | note | Designer - H
83268092-d390-516d-9f97-e3d207dddff9 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
cb1e758b-2883-5843-9bf8-4649283796cb | signoff | AUTHORITY HOLDPOINT
c532d2b6-ed2c-54fe-aaff-6f5cf869c385 | checkpoint | 2.02 - Vibrating Wire Piezometer calibration
b7f5e511-5b4c-523e-98f3-9186391fa4a1 | note | Method/Description - Document review of manufacturer's calibration certificate of piezometer
fd59376a-761f-529a-b44c-0563362362cc | note | Test frequency - Delivery and acceptance of piezometer material; prior to installation
a55a6cf7-0e6a-5223-b682-9188a30e3f05 | note | Designer - H
9197808e-38e8-56aa-b5d1-141467cac314 | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
b15780a9-f82e-5493-ac0b-a891f5cbda1a | signoff | AUTHORITY HOLDPOINT
769dda50-5983-571f-b49a-508273809562 | checkpoint | 2.03 - Extensometer manufacturer specification
9bd24c8f-a7ad-56b6-aa41-95a90caf0ae4 | note | Method/Description - Document Review
7adb8326-68d5-5a2e-905f-7abd3abe33fa | note | Test frequency - Once
7b10df48-62e5-5e4c-b46a-9ee89ab0f16a | note | Designer - H
7aecb46d-b871-5133-ba74-0800c6d852fb | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
5646f79f-aaba-51a4-9dcc-c9ea3c293cc3 | signoff | AUTHORITY HOLDPOINT
8ad36448-96f8-5d2e-b971-9049b199376b | checkpoint | 2.04 - Inclinometer manufacturer specification
61c5fa70-bf23-5469-ac68-32ed9196b1df | note | Method/Description - Document Review
a8c594f8-15a5-5f7f-ab2a-0b605b319f00 | note | Test frequency - Once
4f4b3d8a-936d-55c9-b24f-1c47c5d15527 | note | Designer - H
e0a9a8b1-3235-57bb-9522-feee8457c568 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
d2fe9598-c4b4-57c4-bb29-979b45342e00 | signoff | AUTHORITY HOLDPOINT
9fcfa480-540e-56b2-bad2-0a68740152ad | checkpoint | 2.05 - Inclinometer casing material
8d049a49-da62-5946-8522-3ef97ebf2e26 | note | Method/Description - Inspection of Inclinometer Casing Materials
197696da-5ff4-5fc2-a53c-3efe9fd19852 | note | Test frequency - After Delivery and acceptance of Inclinometer Casing Materials; Prior to Installation.
b541f439-cf8c-5c76-ab19-e156a625e233 | note | Contractor - I - Installer Engineer W - Site Engineer
51a32b4f-53df-507b-882e-d3af5dfe1dd6 | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
66bb8975-da17-572c-adb0-6d0713c4ca29 | checkpoint | 2.06 - Inclinometer grouting materials
786b931c-3c88-5ecd-a3fd-19727c3c31c7 | note | Method/Description - Review & approval of approved grout mix
f1b8de27-97da-5ca9-883d-dddb212c54c2 | note | Test frequency - Prior to Equipment Installation
1cb33d54-ad44-5e27-a7db-8487d8dd5b73 | note | Designer - H
fb59121f-6951-5c4f-99d6-54eff3ec4557 | signoff | AUTHORITY HOLDPOINT
aef98b18-565f-5f1b-bd7b-fa8585342fc2 | checkpoint | 2.07 - Inclinometer materials
e2fd1a81-73c7-565d-b853-c3111cd40f20 | note | Method/Description - Inspection of Inclinometer Measuring Equipment
0a2a2ef6-b16b-542c-94d1-90837bbb9950 | note | Test frequency - After Delivery and acceptance of Inclinometer Measuring Equipment; Prior to Installation.
273c8ca0-7b83-5e92-af35-22612739ccea | note | Contractor - I - Installer Engineer W - Site Engineer
37aeb6fe-099d-5cd6-bc9d-f1f22fc60d4d | checkpoint | 2.08 - Rod and Plate Settlement Markers
f1767a56-98cd-5161-b485-5858026a6851 | note | Method/Description - Inspection of Settlement Plate Materials
726e8b24-7574-53c7-9215-d1d151994374 | note | Test frequency - After Delivery and acceptance of Settlement Plate Materials; Prior to Installation.
3cf9b493-b1e0-5d9d-a648-c37d96e8394f | note | Contractor - I
5a063c6f-4079-5503-8288-efc6fa7dd4e9 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
c17d86d9-8948-59d6-8cbb-73c7541fdc5a | checkpoint | 2.09 - Surface settlement marker material
31e46699-57c0-56a7-8109-4cccd4ab8ee3 | note | Method/Description - Inspection of Surface Settlement Marker Materials
2c9b7967-160f-536e-a28b-4bd1712851fa | note | Test frequency - After Delivery and acceptance of Settlement Marker Materials; Prior to Installation.
abeb4c4b-eee1-5237-9714-a27ffa8bd5b5 | note | Contractor - W - Site Engineer
3dd86950-26c3-5903-81ca-bee2ccddc4f3 | checkpoint | 2.1 - Surface monitoring marker material
c4008508-cc50-5c19-be8f-4018488f2557 | note | Method/Description - Inspection of Surface Monitoring Marker Materials
d86f0420-126e-5a8d-88ff-7c3066693792 | note | Test frequency - After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation.
13ad65bb-3c90-5749-ade3-e6a0e787ead1 | note | Contractor - W - Site Engineer
90de7fdc-f9e0-5b70-b111-31b226c72498 | checkpoint | 2.11 - Lateral deformation marker material
a7981613-659f-5d55-981d-5d3e613e1e42 | note | Method/Description - Inspection of Lateral Deformation Marker Materials
657d885f-23ab-5574-b5d9-a08ea4deb6ad | note | Test frequency - After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation.
2a2be6e3-afff-5414-b3ad-fa7767e0a6f8 | note | Contractor - W - Site Engineer
5c0d8b58-428d-5557-8e39-979c18fbb503 | checkpoint | 2.12 - Profilometer material
70f4ec1f-91f0-564f-81eb-d3a72d163771 | note | Method/Description - Inspection of Profilometer Tubing & Backfill Materials
ec702f18-1775-5b9c-b45f-6b30324f79c6 | note | Test frequency - After Delivery and acceptance of Profilometer Tubing & Backfill Materials; Prior to Installation.
3d08e78a-3bd5-5c7d-b526-4aae589252f8 | note | Contractor - I - Installer Engineer W - Site Engineer
a3b00f9c-02d3-5924-b8b9-bb65e7b7e852 | note | Verifying Records Checklists, Test and Supplier Certificates - Material Certificate
971af1b5-8ff8-59fb-a547-1d7e319a9029 | section | 3.1.0 Vibrating Wire Piezometer Installation
24a176b0-5ce0-5bce-8a87-8bba38e87836 | checkpoint | 3.1.1 - Piezometer location per construction drawings
97f06828-2caf-5cd7-a4a3-409b96e73e83 | note | Method/Description - Inspection of borehole location
08542b2f-5be8-5165-a9f4-80124dd5228e | note | Test frequency - Before borehole drilling
e01a595e-dee2-5b3e-bdfb-c83057676e35 | note | Contractor - I - Installer Engineer W - Site Engineer
a05cd3a9-7117-5e95-b9e4-6461d8302100 | checkpoint | 3.1.2 - Borehole Drilling
997af7b4-aab4-5825-8684-2a5aaf387751 | note | Method/Description - Inspection of borehole
ab4b7269-2c4e-58b5-982e-0a1a4ee68169 | note | Test frequency - After borehole drilling
0b79cad7-6874-5b1c-8c45-1a37607add57 | note | Contractor - I - Installer Engineer W - Site Engineer
fcfd834b-52e9-5fad-abc1-0c9deb9f9a2d | note | Designer - W
234d71aa-d17a-5f15-a34b-1776293e0e26 | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
98900df6-8cc0-5705-a178-3e091b102f2e | checkpoint | 3.1.3 - Depth of piezometers
19339646-ac6e-5c9f-af2f-bbf5f09561d2 | note | Method/Description - Review & approval of depths of piezometer based on the results of the core logging
91b842e6-26dd-5935-824a-00c2399679f5 | note | Test frequency - After borehole drilling
5297a916-5715-5bd6-907b-5319098e1934 | note | Designer - H
8bd1f80c-5f69-5ed7-b9ef-d8e1feff3888 | signoff | AUTHORITY HOLDPOINT
0770b2f1-d660-5e90-86d1-f8d27d74a52c | checkpoint | 3.1.4 - Core materials
9554b4d3-c4ea-5dea-9d2c-0cd07e9bc21b | note | Method/Description - Inspection of all retaining cores
d3f129c9-1e47-59bc-83dd-9a69cd3fa3e9 | note | Test frequency - After borehole installation
bcfba8db-e93c-527c-bdfc-62d56597a233 | note | Contractor - I - Installer Engineer W - Site Engineer
b3cbb2b2-caa6-54e8-97be-562e08e8f2f4 | checkpoint | 3.1.5 - Heavy duty connecting cable placement
ee72f1d2-f712-5ae6-8c68-294c2596e4a2 | note | Method/Description - Inspection of completed heavy duty connecting cable placement
bc9713f9-36ab-56f9-be37-524735907d41 | note | Test frequency - After placement of heavy duty connecting cable
2729dba7-b3fd-5cbd-af0e-2f6e4c777e68 | note | Contractor - I - Installer Engineer W - Site Engineer
24654022-1160-5def-8779-eb7e0e827502 | checkpoint | 3.1.6 - Splicing of heavy duty connecting cable
0ee7fefa-c864-5e69-9cd5-30013489f77d | note | Method/Description - Review & approval regarding acceptance of cable splicing
e919a43b-93c1-52ae-9cff-a7a28a9573e4 | note | Test frequency - Prior to splicing of heavy duty connecting cable
edd93939-dc7a-56eb-86d7-51940cf19269 | note | Designer - H
d4911b86-e703-5d53-8d0f-540adbea9fe9 | signoff | AUTHORITY HOLDPOINT
60e399e9-99cd-5bb0-8962-74d694d85445 | checkpoint | 3.1.7 - Readout unit/data logger placement
1b610c73-588c-5083-bec8-876c667ca86f | note | Method/Description - Inspection of completed readout unit/data logger placement
6fefb079-9f32-574c-8ef1-8943af052b27 | note | Test frequency - After placement of readout unit/data logger
2db1dc4a-eea4-51fe-a4d3-f66abcd9afd6 | note | Contractor - I - Installer Engineer W - Site Engineer
3e097bf9-1805-5301-85dc-12801b742648 | checkpoint | 3.1.8 - Ground surface finish of installed piezometer
6cbe5381-8918-5cd6-b52e-6485a9b4c197 | note | Method/Description - Inspection After completion of the installation process of Piezometer
5f058a59-0929-5775-a961-872daac29d9e | note | Test frequency - After completion of the installation process of Piezometer
27761d93-7b50-52d9-a0b2-3bc85df1f09c | note | Contractor - I - Installer Engineer W - Site Engineer
e6b0e5c1-8bd5-57f3-a59f-bbf68736cab1 | checkpoint | 3.1.9 - Ground surface finish of installed connecting cables
4a8e6ed2-a4ed-55bf-9b16-50d3b59d7487 | note | Method/Description - Inspection After completion of the installation process of Piezometer
dcb90d5c-7062-5b1d-a38c-53435a0c5e18 | note | Test frequency - After completion of the installation process of Piezometer
b7afbdc8-5937-55d5-a73c-b756f25bfcdf | note | Contractor - I - Installer Engineer W - Site Engineer
317758d8-ba30-5957-9ef7-e14079ebd6d5 | note | Verifying Records Checklists, Test and Supplier Certificates - Bore Logs
38532a6b-2739-5a67-9019-173101a0c2c7 | section | 3.2.0 Inclinometer Installation
17c32914-90e0-5a94-90ee-2f89cc1912fa | checkpoint | 3.2.1 - Inclinometer location per construction drawings
266d8360-3ba0-58e9-b0a7-a8db93ae308e | note | Method/Description - Inspection of Inclinometer Placement
ad89ab14-1762-543c-a9b7-a9706711ee0e | note | Test frequency - After Placement of Inclinometer
a68a3803-ebe6-5f40-aac2-735cdeb2d727 | note | Contractor - I - Installer Engineer W - Site Engineer
8cd09675-fef7-51a4-8847-2123720ee558 | note | Designer - H
aee9c164-bf68-5320-84f1-322d6eec1d24 | signoff | AUTHORITY HOLDPOINT
60c35340-4236-532b-ac97-b34580edfc45 | checkpoint | 3.2.2 - Borehole drilling
ef57b910-6bac-547d-99bb-3d8ac65bb105 | note | Method/Description - Inspection of Borehole Installation
678a720e-e033-5fcb-a395-32f93a26ff9a | note | Test frequency - After Borehole drilling
94641131-d845-599b-9f75-11074bbc3bc0 | note | Contractor - I - Installer Engineer W - Site Engineer
3c1064aa-7e3f-5bb9-98f1-8a341672363b | checkpoint | 3.2.3 - Depth of inclinometer
ea8324a4-cc97-5fcc-a8c6-96470d2fd7c6 | note | Method/Description - Review & Approval regarding depth of Inclinometer based on the results of the core logging
8aa05df7-b4b3-5cbf-b59b-4a670c41f60f | note | Test frequency - During Borehole drilling
ee8f1b46-f208-5c94-930f-9ff75aec8109 | note | Designer - H
192b06f4-6036-58a8-818d-a1d5ee91b978 | signoff | AUTHORITY HOLDPOINT
b32ccf54-24a0-5a46-814f-9839a82629da | checkpoint | 3.2.4 - Core materials
6f6c3361-01a9-5af3-b8c5-1f77923dba36 | note | Method/Description - Inspection of all retained cores
0d720a3c-ce38-5bcd-b087-ce24a5292585 | note | Test frequency - After Borehole drilling
ee833ebd-1609-5ba5-bcca-8fdb572fa472 | note | Contractor - I - Installer Engineer W - Site Engineer
ac3bdbda-290f-556a-a150-4ffc806d2714 | checkpoint | 3.2.5 - Grouting installation
c0addd41-8376-5dd4-8ed4-305fb1b1402d | note | Method/Description - Inspection of Grouting Installation
e5fd02fa-8c25-5462-ba69-1e7931a3b790 | note | Test frequency - After Grouting Installation
33a90bd8-e353-5005-946a-51d06a4ddc15 | note | Contractor - I - Installer Engineer W - Site Engineer
520e0250-aff0-5d36-801d-200c9817e38d | checkpoint | 3.2.6 - Ground surface finish of installed inclinometer
98208c70-480a-5133-be0f-a1a21a5ffefa | note | Method/Description - Inspection After completion of the installation process of Inclinometer
8f5b2dff-6126-5aed-b9d7-b97245f67267 | note | Test frequency - After completion of the installation process of Inclinometer
e46e9ffe-71a6-5e3d-9764-848f1e8e4ab5 | note | Contractor - I - Installer Engineer W - Site Engineer
c4813869-485d-5bf3-8b0e-1dd22985442a | section | 3.3.0 Profilometer Installation
9b71cf4e-694a-56ae-b79e-748c235dd558 | checkpoint | 3.3.1 - Profilometer tubing levels and location per construction drawings
9e0f73d3-b9d3-5e14-82c0-eed9dfc2b27a | note | Method/Description - Inspection of profilometer tubing Placement
9e1c7723-acb4-5fca-9191-35f7196ecf53 | note | Test frequency - After placement of the profilometer tubing
7f3be2e5-d344-5eca-b438-40b7d865db39 | note | Contractor - I - Installer Engineer W - Site Engineer
68bdb094-09bf-5488-ab94-1442a59c4090 | checkpoint | 3.3.2 - Profilometer installation
fef720e7-04ca-50fd-9d16-b8c1a341e50f | note | Method/Description - Inspection of profilometer tubing Placement
c6419f97-c873-565c-8a1b-7dc6efa71f46 | note | Test frequency - After placement of the profilometer tubing
6b2766be-0847-58cb-9cd6-95df8f7d30bf | note | Contractor - I - Installer Engineer W - Site Engineer
0ed39647-7669-5112-83ca-adeb671a24a3 | checkpoint | 3.3.3 - Ground surface finish of installed profilometer
727a19eb-7b56-597b-bb6f-a7ed93a2f355 | note | Method/Description - Inspection after completion of the installation process of profilometer
594d1ea3-ddb0-515c-b99d-e41c2aea2530 | note | Test frequency - After completion of the installation process of profilometer
f8dfe5e3-e0e9-5bfc-ac43-ed37c8b588e7 | note | Contractor - I - Installer Engineer W - Site Engineer
8368603d-fcb7-5a19-96b9-661961066151 | section | 3.4.0 Rod and Plate Settlement Plate Installation
c4062047-40d7-596d-8c02-abbf2b1562ff | checkpoint | 3.4.1 - Settlement plate installation
8f2adc4a-81f7-5727-aa98-8adcd2b9541e | note | Method/Description - Inspection of Settlement Plate Placement
ced4007a-bb2a-5128-b5a9-450451a53d9a | note | Test frequency - Before placement of the Settlement Plate
178b4a6e-95c0-5bc1-81e9-47fb89dfe5bd | note | Contractor - W - Site Engineer
996590a1-444e-5587-9c96-e3f1d93e821d | checkpoint | 3.4.2 - Ground surface finish of installed settlement plate
b0d87ca3-c6d6-56d1-b1d2-5c7d154e48e9 | note | Method/Description - Inspection After completion of the installation process of Settlement Plate
dff90545-1264-54d1-a485-97a9f651e52c | note | Test frequency - After completion of the installation process of Settlement Plate
01feb329-aa58-576d-895f-6fbb32cf4390 | note | Contractor - W - Site Engineer
fa8f12dc-b4e2-5d9e-a40c-4bb87668536c | note | Designer - H
27aa79dd-fc84-583c-9052-82233ef9f598 | signoff | AUTHORITY HOLDPOINT
8645cf57-d8f3-5e03-94b8-e8748a7002f0 | section | 3.5.0 Surface Settlement Marker Installation
ad09b4cd-e367-5da9-8c2e-5104f78853cf | checkpoint | 3.5.1 - Ground surface finish of installed surface settlement marker
12c28ec4-7509-5eea-866f-55a4eb60490b | note | Method/Description - Inspection After completion of the installation process of Surface Settlement Marker
8e782d1b-2327-5607-91e6-ba940ddaefb2 | note | Test frequency - After completion of the installation process of Settlement Marker
19b40d84-cffa-5151-a230-a3b87eb72286 | note | Contractor - W - Site Engineer
21828e3a-46e3-56a4-a453-c1ffb1ab7f8d | section | 3.6.0 Surface Monitoring Marker Installation
0c4673db-b658-5d7d-b3b2-34188b51b793 | checkpoint | 3.6.1 - Ground surface finish of installed surface monitoring marker
8a0d960c-a395-504f-aa6e-cfc85c03df45 | note | Method/Description - Inspection After completion of the installation process of Surface Monitoring Marker
f41722d4-3d83-5ab8-974c-c1198d6042a9 | note | Test frequency - After completion of the installation process of Surface Monitoring Marker
5d6ccca7-17d1-51ba-8cfa-2a511b156897 | note | Contractor - W - Site Engineer
fdfda3ae-205e-5e92-a15d-4a91ed160ab1 | section | 3.7.0 Lateral Deformation Marker Installation
cf17dcae-cf84-5434-aa94-a2e3d7490e4b | checkpoint | 3.7.1 - Ground surface finish of installed lateral deformation marker
5f4684ae-85e6-5f75-b3f4-a64a75da9f3b | note | Method/Description - Inspection After completion of the installation process of Lateral Deformation Marker
8d7bc81c-b034-5de6-ab15-5913d1bd0520 | note | Test frequency - After completion of the installation process of Surface Monitoring Marker
c5184587-7eaf-5514-9aee-a96b95b725a4 | note | Contractor - W - Site Engineer
e1c535fb-bc03-55cc-b8fe-48eaf58ee880 | section | 3.8.0 UAV Survey/Face Scan
08c06f83-0db1-5a7c-bd8e-44e9fb2b6d77 | checkpoint | 3.8.1 - Ground surveys using unmanned aerial vehicles (UAVs)
ff397604-66ba-5727-82c1-e50612b044cf | note | Method/Description - Survey
16c126cf-4cf4-5f99-92d3-2d754dba672c | note | Test frequency - 1. Prior to any ground disturbance; 2. Upon completion of vegetation and topsoil strip; 3. Regular intervals as fill embankments are raised (maximum of 5m fill placed between surveys) and cuttings are formed (maximum 10m depth increments between surveys); 4. Upon reaching final surcharge heights for preload embankments and final embankment heights where no surcharge is required, and full cut depths; 5. Monthly intervals during the earthworks operations and at the end/commencement of each earthworks season; 6. Following removal of surcharge and final embankment profiles have been formed; 7. Immediately prior to pavement construction; 8. At completion of pavement construction; 9. Practical Completion; 10. Every 3 months during Defects Liability Period; 11. End of Defects Liability Period. Face scans of rock cuttings shall be completed as each cutting is advanced in increments of 10m and at maximum three monthly intervals thereafter during the earthworks season and at commencement and end of each earthworks season. Scans shall have an accuracy of ±100mm and repeat surveys shall be able to compared to previous surveys to assess potential surface movements between surveys using 3D Reshaper software or similar.
fa761dd1-6a0a-5f2d-a356-7c89bbe5d2a5 | note | Contractor - W - Site Engineer
d5c4d3ce-97ac-57d1-b4b4-e2b489db6c9b | section | 3.9.0 Extensometer Installation
cfa377e4-025c-5d5f-a708-27ce6b86eba6 | checkpoint | 3.9.1 - Extensometer location per construction drawings
72b433e7-4cbe-5e1b-89de-0c7eeadc0f3a | note | Method/Description - Inspection of extensometer Placement
4c53ae68-18d2-5be5-8527-5805a39dc404 | note | Test frequency - After Placement of extensometer
6c0a9d21-4865-552d-96f1-1577037db03b | note | Contractor - I - Installer Engineer W - Site Engineer
e210a09b-d647-511f-b5d3-6e454a621574 | note | Designer - H
fa1965e4-2a0d-55fc-b838-f1d5bc952965 | signoff | AUTHORITY HOLDPOINT
f33d1ae5-634a-5043-8e52-ea21db14e244 | checkpoint | 3.9.2 - Borehole Drilling
e73b1582-6f35-5058-bdfd-72b66ef4d71c | note | Method/Description - Inspection of Borehole Installation
8a028854-8e69-5f3d-8b50-04970fdf686b | note | Test frequency - After Borehole drilling
d45c498c-9a80-5018-898d-55c6b2f860ed | note | Contractor - I - Installer Engineer W - Site Engineer
5efc927b-06b4-51c6-bcf1-3246a04c3363 | checkpoint | 3.9.3 - Extensometer tubes
e1114823-735b-5dc5-89e5-b59d438ce1f8 | note | Method/Description - Inspection of Grouting Installation
0dc02987-80e2-585a-9e9f-c3585fba33e8 | note | Test frequency - After Grouting Installation
9884911d-7e85-5ec3-9242-12a86d880434 | note | Contractor - W - Site Engineer
ad3beebc-2158-5e70-8864-27c4f63ba8c3 | checkpoint | 3.9.4 - Spider magnets
5197d379-87f2-5d41-a9ea-1ddd38391deb | note | Method/Description - Review & Approval regarding depth of based on the results of the core logging
6e17de07-c027-5506-ad0c-fc19c838fa42 | note | Test frequency - During Borehole drilling
85763d7a-c607-5ede-8e4e-3d7866579910 | note | Designer - H
fb321688-5c98-5bbf-8f99-a3a171ca9c18 | signoff | AUTHORITY HOLDPOINT
525688b5-6d03-5c8a-a34a-4ce579e88227 | checkpoint | 3.9.5 - Reading and recording settlement
21def668-4d44-52bb-b14e-d0331b2b4ed4 | note | Method/Description - Inspection after completion of the installation process
ce9f5d49-1213-550a-8a67-c970b89cbcbb | note | Test frequency - After completion of the installation process
72379078-f1bb-548b-b1ac-710d3c8335e1 | note | Contractor - W - Site Engineer
aef4bfd1-8093-5b02-a33b-ba9f3178bffd | section | 3.10.0 Reflected Survey Marker Installation
fee252f1-4e34-5ab1-be35-d967ba83df74 | checkpoint | 3.10.1 - Reflective survey target marker installation
b97cdc96-bec8-5919-bc35-ff5dc190fb81 | note | Method/Description - Inspection of Reflective Survey Target Marker Placement
3688127d-ee25-582f-8596-32c2ab883506 | note | Test frequency - Before placement of the Reflective Survey Target Marker
c5fb0be3-84e7-5e2b-8adc-dabccb5da398 | note | Contractor - W - Site Engineer
0ac6ddd3-5200-566b-8cb8-a99d38d28593 | checkpoint | 3.6.1 - Reflective survey target marker installation completion
97500cb2-4b45-5c75-bef2-05c3273cf05e | note | Method/Description - Inspection After completion of the installationof Reflective Survey Target Marker
8205f658-8159-548b-9e09-c28f697db238 | note | Test frequency - After completion of the installation process of Reflective Survey Target Market
c95eb16f-4a6d-57cf-ad36-9f798b2c3d2a | note | Contractor - W - Site Engineer
9af1103d-c33a-5e98-8923-d5455d0652f0 | section | 4.0 Completion of Instrumentation Installation
6f86276b-1e36-5551-a071-15960db959ad | checkpoint | 4.01 - Vibrating Wire Piezometer completion of placement
91bae5e2-adff-5e01-8a18-a08ff63dba4f | note | Method/Description - Document Review submitted through Hold Point
d8f0ae87-7708-52c4-b3d5-e28da38ed040 | note | Test frequency - After Piezometer Completion of Placement
1f1925bb-697a-56c6-8f98-70f0e557ebcd | note | Designer - H
c7762ac1-9fd8-5924-9081-e0d50a4306a0 | signoff | AUTHORITY HOLDPOINT
93a9399f-f068-550b-a09e-950f26a4039d | checkpoint | 4.02 - Inclinometer Completion of Placement
c1e1cef4-b791-555c-8e55-9b79edace93a | note | Method/Description - Document Review submitted through Hold Point
b367d381-b385-5da6-8bb4-16537299825c | note | Test frequency - After Inclinometer Completion of Placement
1b373216-a562-5ee8-b9ca-231fe044321c | note | Designer - H
002d6da7-a6bf-5f35-8479-485c47bb93a3 | signoff | AUTHORITY HOLDPOINT
e1b83da4-a178-534e-a80f-d40068539458 | checkpoint | 4.03 - Profilometer Completion of Placement
722dc441-c4a1-52bf-8443-a52ad721351a | note | Method/Description - Document Review submitted through Hold Point in Aconex
de53ffa8-244d-5d30-9b11-3dda284f00dc | note | Test frequency - After Profilometer Completion of Placement
2c6dc184-f948-507a-abf6-b47dccf41918 | note | Designer - H
f76b4cba-bc37-52f5-b502-12b08a26635b | signoff | AUTHORITY HOLDPOINT
9afe4495-a514-5d07-a874-3f234ad713c4 | checkpoint | 4.04 - Instrument has been received and approved by the Designer
d3be3eb0-81e3-5b87-b470-fe7b9c733dce | note | Method/Description - Document Review submitted through Hold Point in Aconex
5b9b3803-1b96-51b6-9c19-33c8507be1f9 | note | Test frequency - After Completion of Instrumentation Installation
19e1a056-7e2b-5508-81e5-dc5bddf34a3c | note | Designer - H
0acb7dc4-164a-5967-af22-8fe797e16e3c | signoff | AUTHORITY HOLDPOINT
55980df0-2a76-5407-817a-dc6eacb6e740 | checkpoint | 4.05 - If an instrument is blocked, obstructed or damaged
bfcf9f5d-f544-5fea-a5e5-cd73fc10727d | note | Method/Description - Inspection and Document Review
d6dff28b-fac1-5fb7-aa97-c12a8371292a | note | Test frequency - After completion of the remedials work on the instrument
963535b4-5bef-5647-8f94-50fb96e14367 | note | Designer - H
15ace072-e162-5fe2-bd3d-e0303ad93d1c | signoff | AUTHORITY HOLDPOINT
d7bd260f-d560-5591-8343-1c9257b3441c | section | 5.0 Monitoring
81e6af42-2d12-5727-adc8-fd43afae8424 | checkpoint | 5.01 - Base Line Readings
b6f75633-e64a-5c5a-9077-e265a91b7a3d | note | Method/Description - Survey
edd211c2-4364-55e4-a3b5-e7bfe7eca4d2 | note | Test frequency - Per individual piece of equipment refer to ITPs for embankment/earthworks and cut slopes
799e7cca-1c0c-5637-8749-228bd57ec4b1 | note | Contractor - H
a136935f-33f9-59fd-b609-06e9bc6056b4 | note | Designer - H
d21a9e11-563f-5033-b18c-8431495d4449 | note | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
21123c72-aeba-5dde-9f77-016cb4e1467f | signoff | AUTHORITY HOLDPOINT
40c10db9-951b-5411-b1f8-17e3c1db6a88 | section | 6.0 Verification Testing
f9e43ea6-274c-538c-b93a-cbe7425c0516 | checkpoint | 6.01 - Cone Penetration Tests with Measurement of Porewater Pressure (Piezocone) on embankments constructed on soft ground.
25b83bab-2e63-58d2-8161-f74d2f3fad0b | note | Method/Description - Document Review
a526018d-a623-57d9-916c-77b4e4e84e3a | note | Test frequency - Following surcharge removal or as directed by the Geotechnical Designer
aed0e893-ae5a-5015-be33-fb306be96076 | note | Designer - H
f7cedd37-a9cb-5174-b18a-f0e0cb7926ad | note | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
110586ab-4c47-5749-8624-d8c8f2d77547 | signoff | AUTHORITY HOLDPOINT
a147d8f6-e10d-5f20-87e0-430eb54e3e3f | checkpoint | 6.02 - Geonor Shear Vane Test in Borehole
b5ba8aac-43bd-5d42-932b-787b8bca6b46 | note | Method/Description - Document Review
983d5752-c4d4-5df5-aae7-2aceeb77145c | note | Test frequency - Following surcharge removal or as directed by the Geotechnical Designer
cbf20790-1bc4-5707-a234-67dfa0e10846 | note | Designer - H
3edad595-afdc-5c62-aeac-a93461fb4435 | note | Verifying Records Checklists, Test and Supplier Certificates - To be agreed with Designer
362924a7-c48b-5e69-8ebc-ad5a75d17a6d | signoff | AUTHORITY HOLDPOINT
2c659a61-06a1-5e6d-b925-ae5c2f19e9d6 | section | 7.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
45524c2d-1de8-5e60-b52d-1f4484181dd2 | checkpoint | ITP Close-Out by
c556cb97-27a2-54d1-ac22-33c5add19a2b | note | Site Engineer/Project Engineer
9085754f-7919-5f99-aa9b-8b51a6ef85c9 | note | Zone Manager Approval
172aecee-c4ff-5342-b113-6a7fea964577 | note | Construction Manager Approval
1a4a79be-3d44-55df-a6f3-39ee885349f4 | note | Quality Manager Approval
3aa16109-4f17-5b44-a99b-ce5b19258f75 | date | Date:
1dc2c9d0-048a-5501-9488-936d3248a797 | signoff | SIGNATURE
6ba86b3b-cbb7-5b3c-8caa-8d226740f20f | checklist | SYS - ITP - 011 - Fill 15 & 16 |  | ITP - 011 - Fill 15 & 16
69ce9b50-1ebc-5d31-8f34-23a4d34fa275 | section | 1.1.0 Pre-construction Approvals
c6325e1f-98cf-5dd9-a024-c2741f8830c3 | checkpoint | 1.1.1 - Construction Environmental Management Plan
50034a9b-c7fd-5d4a-ac48-4a40acfd5153 | note | Method/Description - Document Review
ca266398-4518-5357-8549-a06a9b788e3f | note | Test frequency - Prior to work starting
f0e3afb8-6790-5be9-a0f8-80f3ec578b99 | note | Contractor - H
ba562c65-bc6c-522d-9f17-2f2b27639032 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CEMP
ee7771bc-2366-56f9-836d-696e37f5e599 | checkpoint | 1.1.2 - Construction Work Plan
07bf01a9-825c-5fdc-b175-9ae5c8ca892f | note | Method/Description - Document Review
9b7eeef0-c1e4-56e5-b431-7adfa97d42a0 | note | Test frequency - Prior to personal starting
35ee3d69-2c98-5c1e-85f0-9f0593f4aa04 | note | Contractor - H
ae769efa-75b8-536c-860e-dbb95892bf82 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
80997794-398e-58e2-88f5-b742e9843f56 | checkpoint | 1.1.3 - IANZ accredited testing organisation
dc14c63e-01e6-5479-9e93-4f506f8ac28d | note | Method/Description - Document Review
be91758d-b187-54a6-9a01-4dc6ce1f1c07 | note | Test frequency - Once prior to works commencing
4eb99b6d-d70c-571b-b090-cec6be83195e | note | Contractor - H
67fdb9b4-4c51-5187-b60f-def6158133b7 | note | Designer - H
4b926d1e-7dc3-59f3-a856-b730cdafc0c1 | note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
1b40a37a-e607-5a69-894d-892e8bd1f5d4 | signoff | AUTHORITY HOLDPOINT
1506fbf7-5b48-517d-a6d7-cb5c453622a3 | checkpoint | 1.1.4 - IFC's specification
2450ca51-e036-508c-b9f4-8d0a3dbd04a8 | note | Method/Description - Document Review
ecf481fe-aa10-5f6c-9eeb-33e0dc2a64a3 | note | Test frequency - Once prior to works commencing
20b4c479-3a6d-5812-9a25-7374d89f6fdb | note | Contractor - H
9f9cade3-9e8b-5b6d-834e-672f2279b41e | note | Designer - H
86591545-de2f-5cef-8092-31f351edb218 | note | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
2358ac4e-bff1-5d5e-8f51-59f40a42db53 | signoff | AUTHORITY HOLDPOINT
66467056-0c6d-5a0c-8857-462d47f00167 | checkpoint | 1.1.5 - IFC drawings
d8ddcaa6-3582-5415-81c3-661c617f6746 | note | Method/Description - Document Review
83b2c398-5712-59c6-a5db-35bfd54ccb56 | note | Test frequency - Once prior to works commencing
5c4b541e-c631-5927-992e-7794c26099b2 | note | Contractor - H
3bcfe335-1b32-5b01-a8c3-d3124621f671 | note | Designer - H
e7cf6945-0b86-53c6-a8bd-15cd5969fe82 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
9f8f9341-c120-5c71-b92d-67279bb7414d | signoff | AUTHORITY HOLDPOINT
316bbdcc-8b33-5a80-808c-5b370f7f4360 | checkpoint | 1.1.6 - Approved earthworks model
dbdd446d-910f-5404-aff5-101f91ddd9e3 | note | Method/Description - Document Review
a52bbb2b-cdd1-5db8-9599-2bb2aff2ebe5 | note | Test frequency - Every new Earthworks Model and prior to work commencing
3604447a-d645-5d16-85c1-4d0ce474b5bf | note | Contractor - H
da4ad63a-38af-5b42-8c77-10e66b0f0fb6 | note | Designer - H
6d2e6e99-3707-508d-a97d-0d75889b5c9a | note | Verifying Records Checklists, Test and Supplier Certificates - This PCP Signed
cda43a17-cf1a-5b2c-ae43-dc8d2fdf0ccb | signoff | AUTHORITY HOLDPOINT
19d8b93b-c4a4-55e7-ad84-fcfed6a60769 | checkpoint | 1.1.7 - Approval of stockpile location
1b3a81d4-0e09-5121-9c26-788f157b3581 | note | Method/Description - Document Review & Approval
326eba61-a9dc-5712-b9ca-9966dc847b73 | note | Test frequency - Prior to works commencing
b25e1244-930e-50ab-bb58-0e00d83a8336 | note | Contractor - H
0fe42e9c-25ef-5976-a855-5eb2a06e11c0 | note | Verifying Records Checklists, Test and Supplier Certificates - This PCP Signed
724843d0-fcb5-5464-bdfa-4148b5a2ce77 | signoff | AUTHORITY HOLDPOINT
40ac7040-23b3-5151-b100-bc666aea5ad7 | section | 1.2.0 Material Compliance
a1238f1d-a91f-504e-994d-e554accc72cb | checkpoint | 1.2.1 - Structural fill
5fc7058d-46da-5dfd-a86d-1732f318088c | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2 Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4 Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8
cc0df67d-b45e-5269-b280-818b498dd30f | note | Test frequency - 1 test per 20,000m³
caf36ebc-9909-584e-aef0-edd566e89c93 | note | Contractor - H
cec78310-376b-52e9-b854-ce279b2cbb61 | note | Designer - H
06e6a241-3136-5004-8427-a080f041cd13 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
57f696ae-0fa0-54e5-8594-35630edd6b1a | signoff | AUTHORITY HOLDPOINT
f76c7613-4e9a-59f0-8ac5-e29309a6bd99 | checkpoint | 1.2.2 - Drainage blanket and AP 7
6e842e6a-54ff-59d3-9470-fb4a5205080a | note | Method/Description - NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer Laboratory Triaxial Hydraulic Conductivity - ASTM D5084 – 16a
45ecceae-e84d-57d2-a88e-f8bdab0ad1ff | note | Test frequency - PSD - 3 no. tests per source and 1 test per 1000m3 Hydraulic conductivity - 3 no. tests per source
1f04baf1-07ca-5358-88c2-91c150c5d2bf | note | Contractor - H
0a900ba6-1f79-5556-9fcd-ecd98196d97d | note | Designer - H
f92a7750-3e4e-5d0a-a3a9-a900b540ce28 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
7d666602-7962-52dd-9c9b-071dd7a07e31 | signoff | AUTHORITY HOLDPOINT
c0efaaf7-f4e4-5afb-b6b5-5becf2f21833 | checkpoint | 1.2.3 - GAP 65
9c740a6e-8cdb-52a6-9d62-8e429ce97fd9 | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.3
67480ea2-8248-598c-823e-7344fffeb339 | note | • NZS 4402 Supplement No 1:1998 - Test 3.8.1 Determination of the particle size distribution Standard method by wet sieving
be8cc692-0330-558a-b852-0ea7a4214757 | note | • Large shear box (min 3 normal stresses) - BS 1377 Part 7: 1990. Methods of tests for Soils for civil engineering purposes – Part 7 : Shear strength tests (total stress).Test 5 – Determination of shear strength by direct shear (large shear box apparatus)
e6bea317-9c5a-5276-8c06-2e25199693e4 | note | Test frequency - Determination of the dry density/water content - 3 tests per source.
c694db45-500d-57b6-90c3-0997b8a422df | note | • PSD - 3 no. tests per source + 1 test per 2,000m3.
75054765-b58d-5321-b86b-3576953a5afa | note | • Permeability, Large shear box (min 3 normal stresses) - 3 no. tests per source
bd06ccbb-640f-559d-9286-017191331ada | note | Contractor - H
9bb7105e-96e5-5b5b-b5a9-c3e8c81a4c45 | note | Designer - W
c5bcb335-c9c1-5f34-bdff-091d90a12925 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
91de1951-4552-50a8-8b6d-89dffc792541 | checkpoint | 1.2.4 - GAP 65
b95347ff-aa0e-5115-af84-f66859e6c3bd | note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
c1f243d8-d504-571f-8662-93d4b1b08273 | note | Test frequency - 3 no. tests per source and 1 test per 2000m3
1c4c2757-5579-5847-82e5-8f21a5255178 | note | Contractor - H
8ef58d5b-1336-52d3-91e5-f42d49851d85 | note | Designer - W
5609d593-aac0-5012-8424-f895ca3aa213 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
61091160-50f7-5108-8cbe-c665a30e8ac7 | checkpoint | 1.2.5 - Cement stabilised structural fill
23fe0fbd-c79a-5fd2-bfc0-a2888cef20ea | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
ef52621c-cc35-5389-9836-fc2ac990b949 | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
76bde9e1-5a97-5375-98cf-727ab48a46aa | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
a4fae4c5-76c9-5f65-bc55-8e3b5b2f4a2b | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
b9c041f6-1aa6-539d-87ac-4f9364055105 | note | • Atterberg limit - 1 test per source and 1 test per 500 m3
85a13705-1cdb-5924-9a3a-f225b9fabdd2 | note | • UCS - 3 no. tests per source at adopted cement ratio.
17d9408c-e7c0-5a2d-90b9-7d0912274a11 | note | Contractor - H
e93eefa6-9f30-5c6d-9395-ef2bea0b7640 | note | Designer - W
bf1b304c-f40d-58ad-a6cf-d83763cf48e7 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
2e35b49a-2d9d-59fa-b7b4-d467015e88c4 | checkpoint | 1.2.6 - MSE Fill
c924383a-bf1e-57a6-97ab-b7327c09ef88 | note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
4bf57aed-417b-5982-8772-317488d061c6 | note | Test frequency - 3 no. tests per source and 1 test per 2500m3
4a95af0c-5716-5bf3-8137-06135e0403f7 | note | Contractor - H
86686b7e-b0c1-5e3b-8575-9804afd8440f | note | Designer - W
b83b7c0a-9874-5bbc-89d6-b929b0828073 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
c4ea4217-0ca9-5320-ae9c-f4a7996a939b | checkpoint | 1.2.8 - Cement stabilised GAP 65
ce1a64af-ba5d-5af2-9c4a-bd52d9c04c5d | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
d390698d-822c-582c-b0f0-2c1a57a3b314 | note | • NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving
e42c1b44-e183-5f1d-b8ec-594f650831e0 | note | • NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer
7312d13e-7a47-59fc-810b-63332e2a420a | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
3f5d2f30-e252-5ec0-b102-00e15489ebf4 | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
9f298b74-ab69-52d8-9b49-094ec559f3fb | note | • PSD - 3 no. tests per source + 1 test per 2,000 m3
11a054a6-eb72-57a0-ade8-885820346df2 | note | • UCS - 3 no. tests per source at adopted cement ratio.
89b7c534-a19b-5331-8ec4-61780cdf09ef | note | Contractor - H
3a63962c-0f91-5111-9c75-5e5db315b837 | note | Designer - W
e6a54885-9a41-586d-aec2-37bc361566cd | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
0aacd5c2-02bb-5e46-82b4-75d8e4af789c | checkpoint | 1.2.9 - Cement stabilised structural fill
18e0ecc2-c1bc-551e-bcaa-8d117f7d90a8 | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
cb2d3c33-fe66-59c7-8030-55cae4ed270c | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
cc499b43-ada5-5ad4-bca0-c6b366795ae8 | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
7ad62184-4e33-5913-96c7-b00e32c77454 | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
38fc5ab4-9f54-5a28-af9f-177185621f89 | note | • Atterberg limit - 1 test per source and 1 test per 500 m3
ec1130bd-8224-55f4-9350-82adb52f6f9d | note | • UCS - 3 no. tests per source at adopted cement ratio.
13d5fa02-5f05-565f-86a0-855e0391301b | note | Contractor - H
1369ebd8-0b5c-55a7-b8d6-c01be1dee74e | note | Designer - W
8364c7e9-8278-51d6-aee3-b445fcc3f905 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
2cb6f306-2e70-5654-8402-8b2ec9e52277 | section | 1.3.0 Geosynthetics, geogrid and basal reinforcement - Pre-construction
a0d1b4c5-5949-5558-8250-7684a084cf68 | checkpoint | 1.3.1 - Product name Name and address of producer/supplier Manufacturer’s compliance certificate
dfc6d86c-a7d0-549d-8103-ebfbc43d72b9 | note | Method/Description - Document Review
3f49e66f-27b3-5db3-b4c7-01ae780c9357 | note | Test frequency - Check each lot (1 roll)
3dcf9eaf-134d-5b8b-b37c-d452438c3c81 | note | Contractor - H
6a00fbbb-96b0-571a-844c-dc0fdbfc4520 | note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
b8261911-8ced-51ae-8ad1-71ec10996ee5 | checkpoint | 1.3.2 - Tensile strength (machine direction) - geogrid and basal reinforcement
6b312682-20dd-5521-a652-4a804adb6c19 | note | Method/Description - Document Review
27d5b2fa-0b8c-5a08-970c-9d355b1461ca | note | Test frequency - 1 test per production batch
90077b3b-9ade-5198-aea3-b92e7a44febe | note | Contractor - H
9fe05ba0-e3d1-5689-abd2-9f043b9dcff1 | note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
b4649fe9-a20a-5953-8fd0-6c614ee5b97b | checkpoint | 1.3.3 - Visual inspection - separation geotextiles, basal reinforcement
7edba1c7-cfc6-5c26-9ac6-8a370dbd5f8f | note | Method/Description - To inspect geotextile and basal reinforement is the proper type and no tears, rips or other signs of deterioration.
70b3561c-9dae-5efe-ad2e-218ddbe437cb | note | Test frequency - Check each lot (1 roll)
dc30d6c0-16d2-52b2-a254-58e7f99e486e | note | Contractor - H
cff40156-97da-5a03-b246-2ecb3e6845b5 | note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
1a6ab162-84a3-5713-bd08-b7d0fc7fd420 | checkpoint | 1.3.4 - Visual inspection - geogrids
a6fa02d3-5d52-5402-a62a-291db157f256 | note | Method/Description - To inspect geogrid is the proper type and no tears, rips or other signs of deterioration.
7af6b0af-0b4b-52e4-9c62-24c8b4e50d74 | note | Test frequency - Check each lot (1 roll)
f9a1cdca-dba7-50cf-9e52-bbd393bc9711 | note | Contractor - H
de95b5aa-14ff-5c6f-95ba-fd9685ca48ad | note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
d65f2e5c-a857-5839-a24b-993bea45ce2f | section | 1.4.0 Monitoring - Pre-construction
42702933-7cc6-5ba0-b870-39eda8f6d009 | checkpoint | 1.4.1 - Monitoring prior to preload
4e4ad618-ec23-5ca0-ab5e-a1237938ffd1 | note | Method/Description - Baseline readings
057ae6a7-fec6-5698-85ae-f7f142d42112 | note | Test frequency - Settlement marker, extensometer, profilometer, and lateral deformation markers - 1 month before construction start. 2 consistent readings (24 hrs apart) post installation and one immediately prior to filling Vibrating wire piezometer - 1 month
c5f36bfe-9cf2-546e-bad0-d56637147e4c | note | Contractor - H
1b6b515d-d125-5456-9c97-3c1e434b5a2c | note | Designer - H
096e062b-f92d-5bff-bb7c-915e2808986d | note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary - confirming baseline readings satisfactory
62a168bf-14f7-5bcb-ae11-291e4b8c17b8 | signoff | AUTHORITY HOLDPOINT
cf067a8d-e9b1-5966-8add-fb54234eef7d | section | 2.1.0 Pre-filling
58543979-2b9b-5921-8d5b-0c34906f420b | checkpoint | 2.1.1 - Set out extents of fill and check against design
1056ca91-1289-58de-922b-0e500e9fcfff | note | Method/Description - Survey/visual
7b79e7d6-a31a-5931-bd63-9a1dd80f8e9e | note | Test frequency - Prior to Commencement
50ac7331-e74c-5514-97e2-9cab71b1f8e2 | note | Contractor - I.R
438590e0-ed48-5b3d-add6-e2963b4df405 | checkpoint | 2.1.2 - Vegetation Clearance
e3e61131-c40d-5470-a93c-090e828e4830 | note | Method/Description - Survey/visual
40e89c54-9b20-5897-855a-227d098f02fc | note | Test frequency - Fill area foot print
610d68e9-9738-5b5c-920f-9ab0b99e6e3f | note | Contractor - I
40ee3f69-74ac-54fe-8a49-a9c419d5bec0 | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
6ae270b1-2292-5f67-9b4e-bf082c0a5d4e | checkpoint | 2.1.3 - Any area that requires ground improvements must be completed as per Ground improvements ITP prior to fill operations
0c7fa32b-93be-5b2c-86b8-e0c3a56c0203 | note | Method/Description - Document Review
4832ef5e-f47d-59e9-9a4c-bda04d23df25 | note | Test frequency - Prior to Filling
dc11d2b9-4407-54a9-88b9-33f592567cbb | note | Contractor - I
862245e6-f218-5a61-bb79-c5bfceec4f89 | checkpoint | 2.1.4 - Designer witness of in-situ subgrade prior to filling
ac514d07-ddf0-592a-9153-4b5f546ab61d | note | Method/Description - Visual inspection
41dcbadf-ec3e-5ec3-84e6-400a3e26dc92 | note | Test frequency - Prior to Filling
a9e77516-a4c9-5340-aee7-d28fb19d4c46 | note | Contractor - I
7ac43eb5-b116-58fd-9178-36a0750aa2a8 | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
e1215e41-225a-5d6b-b773-fa60c65c633d | signoff | AUTHORITY HOLDPOINT
9544fc50-a083-526d-a563-9ec7a24959fb | checkpoint | 2.1.5 - General Undercuts
3480f777-a904-56eb-b9a4-d79f2b8c6219 | note | Method/Description - Visual inspection
06520e0f-6a06-5bd0-a4d5-4a8b37a31a13 | note | Test frequency - Prior to Filling
1f3264c8-20f1-5c43-ab5f-d35d7b96716e | note | Contractor - I
ab67a8df-28ab-5ae8-896b-013dd1bc9f9a | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
70202bbd-c12a-58c1-8344-9ef760ec6ead | checkpoint | 2.1.6 - Required undercuts for basal reinforcement installation
ee8adac9-fea8-542c-a789-b01a47493bca | note | Method/Description - Visual inspection
c662db2d-fab3-5b38-b749-9e849f6ea002 | note | Test frequency - Prior to Filling
84f5833c-b83f-58ea-bc82-75e82a408384 | note | Contractor - I
6f3e9b22-78ae-5763-b926-430f662340d3 | signoff | AUTHORITY HOLDPOINT
260c5884-acfb-5f8f-b8b0-bf35f1a7392a | checkpoint | 2.1.7 - Basal reinforcement installation
bf44088c-6a88-5529-a4cd-fa2d06cccbba | note | Method/Description - Visual inspection of directional placement, panel length, laps, and damage
0a5f93b0-2ea9-5639-a053-77137316c762 | note | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
c2db837e-4a44-5d64-9d6e-7e5e937c4872 | note | Contractor - I
f8c44445-6c82-55aa-96fa-0de241f02e15 | signoff | AUTHORITY HOLDPOINT
a6fb49d7-acf8-5f1b-ba57-15cc1e5a84d6 | checkpoint | 2.1.8 - Drainage blanket installation
eed9ab96-9869-5901-9c98-73d791d28672 | note | Method/Description - Visual inspection
0dd722de-cdb6-58d0-b1f1-8c1fb2be2a69 | note | Test frequency - Prior to filling, and every 100m2 of geotextile installed.
17596efd-2352-5432-9700-9e4d831de1d3 | note | Contractor - I
fd0f6409-f3be-58b9-aaa7-79259a6aa1ac | signoff | AUTHORITY HOLDPOINT
72d9decb-4e4b-5ba1-9f0e-7853deac0d90 | checkpoint | 2.1.9 - Construction of wick drains
eed9ab96-9869-5901-9c98-73d791d28672 | note | Method/Description - Visual inspection and subcontractor record review
0dd722de-cdb6-58d0-b1f1-8c1fb2be2a69 | note | Test frequency - During wick drain construction
17596efd-2352-5432-9700-9e4d831de1d3 | note | Contractor - I
6cd7e87c-a2bd-5455-ae74-ad01f88c9c21 | note | Designer - W
7a4c5c42-e10c-5dfe-b933-747f38f45850 | note | Verifying Records Checklists, Test and Supplier Certificates - Wick drain check list
075a395e-5b9e-5fa4-914a-7b13d0564ca7 | checkpoint | 2.1.10 - Sub soil drainage
42ccfbf3-d7c8-5861-8695-87ef965970d0 | note | Method/Description - Inspection
3f6da756-e5f2-56f8-b4f6-cb3a297f7a5e | note | Test frequency - During subsoil construction
4e5a0339-543f-5332-92ca-06f701caa96a | note | Contractor - I
c42fb20e-057b-5948-a395-7a9c068ca1f4 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
3afa5f76-2a6d-5f28-9ab5-e2c4fe8297d6 | checkpoint | 2.1.11 - Monitoring Equipment
6b9bea36-81df-5467-b603-75cead2f7917 | note | Method/Description - Survey/ data logging
bfccd6c5-e006-5bd0-915b-9f1becba6486 | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
abf886e1-f802-519f-a7f1-802dca3eb53d | note | Contractor - R
0454222b-e3bc-5f84-823b-bacf51f4567f | note | Verifying Records Checklists, Test and Supplier Certificates - Drill logs
f5ed585a-3cba-525c-9dc6-89488bcc7c81 | section | 2.2.0 Fill Construction
ca8d15bd-63b2-5c11-9d8f-b2ab8edfad49 | checkpoint | 2.2.1 - Filling operations
1e4eee05-2b8b-5f7e-a4ad-75a8996d96ca | note | Method/Description - Visual inspection
0d9b7c2e-1f76-5e9b-9b34-987cbad8a792 | note | Test frequency - Daily
f5b59f25-1b02-5c93-abd6-bc4790a820d3 | note | Contractor - W
10a7a72d-399a-50e4-912a-938f130c7865 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
c6c48250-3625-5f48-8d72-509cfed59c1c | checkpoint | 2.2.2 - Filling operations
590f413c-bc5c-501f-9230-21d41c7b9ae8 | note | Method/Description - Survey/visual
f09d59de-6754-51dc-bec3-c047c0a6951d | note | Test frequency - Daily
1580519a-7ac8-5084-9aa6-a7d0bf1036bf | note | Contractor - W
23fa558f-48fd-518e-bad3-d13dc474fb25 | note | Verifying Records Checklists, Test and Supplier Certificates - test report
6703af28-977b-5cf8-9f2e-106b78778eb0 | checkpoint | 2.2.3 - Installation of Separation Geotextiles and Basal Reinforcement
fe14da24-958a-5b46-9de0-6ea0dfc8194d | note | Method/Description - Checklist for directional placement, tensioning, laps, spacing, damage
5b0cc25b-0198-57a4-96b8-f7aedf5e4bdc | note | Test frequency - 1 checklist peer 100m2 of geosynthetic installed
3b5133b0-010c-5881-a1e8-5c20acdf6578 | note | Contractor - I
31c10d01-6a27-5b09-ba92-7d533d7d96e2 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
67fa0f67-96ef-5f19-ad08-3d77ea125216 | checkpoint | 2.2.4 - Insitu fill testing
fe14da24-958a-5b46-9de0-6ea0dfc8194d | note | Method/Description - In situ moisture content and density
5b0cc25b-0198-57a4-96b8-f7aedf5e4bdc | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length (approx 1 per 3000 m3) ; 1 test per lift per 50m length for top 1m of fill to subgrade level
3b5133b0-010c-5881-a1e8-5c20acdf6578 | note | • Buttress fill - 1 test per 200m length, approx 1 per 6000 m3
31c10d01-6a27-5b09-ba92-7d533d7d96e2 | note | • GAP65 - 4 tests per lift per structure
b95fa105-1813-5254-82fa-76d19ad6a362 | note | • Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
5eb78135-4bbc-52f3-a53a-94582587602c | note | • Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
1da394e1-1f8b-57d8-9229-00c507273604 | note | Contractor - W
2d842370-226b-5726-93ec-9ad07c0c106c | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
21161ec4-b2cb-56bd-b97f-5dd17aa2d85d | checkpoint | 2.2.5 - insitu fill testing
cc647bff-19fc-50e3-8464-a62cdaa5f4e2 | note | Method/Description - Plateau Test
50ab74b6-3db2-5da6-be8c-0764f24d0f39 | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone
a669c3db-1caf-5be6-9e9a-fcf790db4faa | note | Contractor - W
cc7eae38-0c01-5b0f-86f1-5127d4ebc492 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
cbc38db0-5d27-5cb8-a99b-eecad01c06aa | checkpoint | 2.2.6 - Pavement Subgrade Fill Testing
cc647bff-19fc-50e3-8464-a62cdaa5f4e2 | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
50ab74b6-3db2-5da6-be8c-0764f24d0f39 | note | Test frequency - Surcharged Fills - 1 test at subgrade formation level per 50m length, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth
a669c3db-1caf-5be6-9e9a-fcf790db4faa | note | Contractor - W
cc7eae38-0c01-5b0f-86f1-5127d4ebc492 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
284a15fc-5f1e-5461-802b-39846fca04f0 | checkpoint | 2.2.7 - Pavement Subgrade Fill Testing
b2390827-462b-5793-91ae-2865fccef62b | note | Method/Description - Scala Penetrometer Surcharged Fills
6fc16cd9-d17f-57f9-b8e8-b0591bcaa905 | note | Test frequency - 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width
16b66314-a0aa-57d3-a05d-894fe995c16f | note | Contractor - W
664b35cc-d550-5ee2-b9fe-db2b478a84e0 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
90f82bbc-7c77-5080-9894-3fee24b9e688 | checkpoint | 2.2.8 - Pavement Subgrade Fill Testing
01e3215c-e556-534b-a474-d5fa358c39d1 | note | Method/Description - Benkelman beam and FWD Testing
453fb531-f452-5b5b-9aed-aa2e53ca6026 | note | Test frequency - Surcharged Fills - At subgrade formation level 10m interval in each wheel path
a572348a-90b7-5565-ab36-52514901a76c | note | • Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
3134ec51-bfe1-5848-aab8-c6d362e75a81 | note | Contractor - W
0f8e517d-537c-5544-a591-34539a8f0986 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
4efa10f0-7afe-53e1-b597-18591b6c7850 | checkpoint | 2.2.9 - Pavement Subgrade Fill Testing
24a5717e-2919-5200-998b-997057ae1e1a | note | Method/Description - Laboratory Soaked CBR
1e4936b9-f357-57ff-b0c0-d98c2efc11b2 | note | Test frequency - Surcharged Fills and Cut Fill Transitions - 1 Test per 5000m2 at subgrade formation level
faf65416-3d56-58f3-85c1-015bebae8f29 | note | Contractor - W
8c6a3b80-1ba7-5bc3-81e0-d7bf5fda7642 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
83fe715c-0c21-59e5-8e43-2a4cad5f184b | checkpoint | 2.2.10 - Confirm testing requirements are meet for insitu fill
af89f5a8-465b-5698-adec-10be03ae82a0 | note | Method/Description - Summarise, interpret and review test records
865041c7-878d-543a-846a-bbbbf75a23d5 | note | Test frequency - Every test result
a1854082-b9a5-599f-8a19-6a14e0b975c2 | note | Contractor - H
45e89e15-d49c-5fc0-a970-04f92ecdbf1e | note | Designer - H
8d8677ca-8b07-5302-b8b4-773fb9064aaf | note | Verifying Records Checklists, Test and Supplier Certificates - Review of testing records
8388a423-c359-55bc-9eff-1b899a325e81 | signoff | AUTHORITY HOLDPOINT
4641fb01-25ca-50ad-9142-2fea76a7350e | checkpoint | 2.2.11 - Failed test result and remedial approval
978410f7-d492-5c3f-8469-f4a587881556 | note | Method/Description - Review and approval of remedial action
da02a4e1-161d-5232-9191-1a3866fed6a4 | note | Test frequency - Every failed test and prior to remedial works
33cf084f-b57d-5e9f-bae4-3d31aa60290c | note | Contractor - H
eb9c6464-4c79-5082-b888-caa806c04c9e | note | Designer - H
bf673edb-be0e-5d76-a7be-9092fea4c24e | signoff | AUTHORITY HOLDPOINT
7f89079d-cda4-55b2-ab50-1a8db2ace849 | checkpoint | 2.2.12 - Insitu Fill Testing
82d4cdc0-3ec4-590f-bc86-5f7ca1bf3219 | note | Method/Description - Undrained shear Strength
22c5d558-a834-51b9-8b4a-934507e56f7f | note | Test frequency - Structural fill - 1 test per layer per 1000m2
2e832840-edc7-5ff5-9a03-7ef3dc05c5a3 | note | • Buttress Fill - 1 Test per layer per 2000m2
eece1da6-06bd-53e9-b2c9-cbb2a26f5e7c | note | • Cement Stabilised Structural Fill - 1 test per layer per 500m2
e8ee7147-d185-53a8-a85a-441af5ae2501 | note | Contractor - W
1cdec2cd-06d6-5f86-8dbc-cbc21614f28f | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
abf3d6d2-8f49-501e-8763-a456ac66b5f2 | section | 2.3.0 Preload/Surcharge (for embankments requiring preload)
6deb424e-254c-50ae-892e-99dec8122407 | checkpoint | 2.3.1 - Visual inspection for rate of filling
10c4545e-de25-5a5c-a168-4f21293bd73f | note | Method/Description - Inspection of fill height, rate of filling of 200mm/day (1m per week)
4f07bd8e-166d-5735-a1d8-267d811adfb3 | note | Test frequency - To be monitored daily
7806a283-7d1f-5d25-bb18-147fa620e32f | note | Contractor - H
065fbfb0-056f-5dfa-a5f8-32eff8f25091 | note | Designer - W
00e58ff8-9766-5514-9579-9d193dae66b4 | checkpoint | 2.3.2 - After 1m of fill placement. Await approval from Designer before placing more fill.
f2efcc47-ad20-52d1-9262-78af7d76a26f | note | Method/Description - Review data and TARP levels before releasing HOLD.
818092fa-e6cf-50c9-beae-ce0f8b8ff080 | note | Test frequency - Before releasing hold periods and allowing filling to continue.
366a83f9-ed1d-59b6-a51d-d91de90b554d | note | Contractor - H
d1f0ba82-7efe-5dcb-b6fc-1fbdf8798d13 | note | Designer - H
970d389c-1bce-51c8-8bd4-a427b9b4d60e | note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary
1a38b1ec-504f-57af-b33c-55650cd60378 | signoff | AUTHORITY HOLDPOINT
ba21e5c0-002b-581c-a9a2-df988f0b76ae | checkpoint | 2.3.3 - Removal of preload/surcharge
426f1f25-f038-5105-ae0b-f9faff0a44e5 | note | Method/Description - Assessment of monitoring and instrumentation data
d822bd21-2701-5001-9dd5-d8f220626730 | note | Test frequency - After completion of proposed hold period
5e007f41-66e9-542d-aa89-517a5c49edca | note | Contractor - H
e6c88f6a-d0ac-54a6-8221-9f476f4bd4ac | note | Designer - H
876481c0-bb68-5bb8-8241-0b258305c146 | signoff | AUTHORITY HOLDPOINT
5d38b1b1-f66a-5279-a5d4-cfbcba80db16 | section | 2.4.0 Monitoring
21607b28-2d45-5c79-8c1e-c9d831eb80c9 | checkpoint | 2.4.1 - During earth filling/preloading/surcharging
0508c0c1-3b68-5298-ab26-971a6c8cdd4d | note | Method/Description - Monitoring during earth filling/preloading/surcharging
ac6e85aa-d9b7-56a1-b2d4-9ed493d69c5e | note | Test frequency - Plate settlement marker, extensometer, profilometer, water standpipe, and lateral deformation marker- twice weekly Vibrating wire piezometer - hourly reading via data logger, twice weekly download
7b43fb96-5a3d-5665-861f-a1c7fd890290 | note | Contractor - W
ea56ba06-57cd-5c61-9b21-b229ce4daedf | checkpoint | 2.4.2 - During preload or surcharge hold period
ec8a779d-8d2d-594b-907c-c8f6dd8e0c8a | note | Method/Description - Monitoring during preloading or surcharge hold period
d60d1926-e190-5341-9c8b-a189abfec7ad | note | Test frequency - Plate settlement marker, extensometer and profilometer, and lateral deformation marker - twice weekly for the first month then weekly. Vibrating wire piezometer - hourly reading via data logger, twice weekly download
678f212b-8a42-5868-a84c-12b6fbed5944 | note | Contractor - W
0cf7ff11-e900-53fd-bf72-eb63a2e335fb | checkpoint | 2.4.3 - At surcharge removal or hold period release
1c573b88-3078-5933-91db-1c442ee4743d | note | Method/Description - Monitoring at surcharge removal or hold period release
4c9e8f91-f39a-572f-a85a-6505d660fd59 | note | Test frequency - Plate settlement marker, extensometer and profilometer, lateral deformation marker, and vibrating wire piezometer - one reading 24 hours prior and one reading 24 hours following.
7a325fb4-0492-5d84-bdd5-f0cbfe83eff1 | note | Contractor - W
28f0a228-5fb7-5aaf-bb29-794b3586bca9 | section | 2.5.0 Monitoring reports
8b606181-c983-5bca-88dc-b467817ced37 | checkpoint | 2.5.1 - Preliminary inspection/monitoring report
b08d460d-bc6d-5fba-b22b-ad6393e8bc26 | note | Method/Description - Summary of site inspection / observation / measurement
16ce8cc1-eecb-5edc-ae6b-8e98181bffa8 | note | Test frequency - Within one working day of site inspection/observation/measurement
2967dff5-eddc-54d8-926c-341b575369c9 | note | Contractor - W
7f047d64-3aed-5f16-821e-f32443e70d74 | checkpoint | 2.5.2 - Inspection/ monitoring report
9f48fe2d-8360-5dda-a43f-e4871c95e452 | note | Report - Full and certified results
3dfc2134-58ee-5b80-88dd-5c8590d4f4a6 | note | Frequency/timing - Within five working days of reading the particular instrument
4e48e42a-eaec-50aa-90db-eb341fc3afc4 | note | Owner - Construction Team and Geotechnical Technician
8b2b65f7-137a-56db-b113-5b69bccfff7b | note | Distribution - Geotechnical Engineer, Geotechnical Lead
c7e4d0ae-e975-5d2e-b7f3-b9458e127e4c | checkpoint | 2.5.3 - Pre surcharge removal report
ff8beb86-d12f-5560-8246-a1c80f7c0678 | note | Report - Comparison between monitored results and baseline design predictions in both table and graphical format. Provide approval to remove surcharge.
a7d4b419-c260-5cf8-96f5-a4e0b22aa619 | note | Frequency/timing - Prior to surcharge removal at each fill
e60d8ccf-98e9-5478-985a-87c124c23c05 | note | Owner - Geotechnical Engineer (with Geotechnical Lead approval)
6a7e8fcd-a899-5703-8f66-c8f396c9dd6e | note | Distribution - Design Manager, Construction Manager
d5545795-84a2-5564-99ac-44165c0761fb | section | 3.0 Post Construction
c421ac5b-2341-54ac-9eef-7f76b03d37ee | checkpoint | 3.2 - Survey As-builts
2fedca43-8a17-5e2c-8f13-e2bc11e82da5 | note | Test frequency - During construction and at end
7a91f791-ee73-5afa-887c-4012cc9ad184 | note | Contractor - H
0a1fe3ec-d554-5e9e-95f3-5bb6abd1c5b3 | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
f942a45e-241e-5b37-8e44-9028309ca493 | checkpoint | 3.3 - As-builts
44be87e5-1442-522d-b981-49cf755d70e8 | note | Method/Description - Mark up of construction drawings to reflect completed works
e272a1b2-9225-56cb-abe5-1ebc1f609d07 | note | Test frequency - End of Construction or after completion of preload/surcharge works
9fbcfdc8-e32a-57f1-bcbb-9c289c69fb02 | note | Contractor - H
f055874e-0151-5cc8-96d8-693015353207 | note | Designer - H
ad52bbbe-934e-5c68-8a9a-9aca1591f155 | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
a7e79338-2b18-506b-bce6-2cb742cbfcd9 | signoff | AUTHORITY HOLDPOINT
8919eff8-fed3-572c-bcf7-d24e7712e7ba | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
45524c2d-1de8-5e60-b52d-1f4484181dd2 | checkpoint | ITP Close-Out by
37d3795c-51da-5d7f-ad97-0fb503cf9c4f | note | Site Engineer/Project Engineer
7726aa8f-f137-5131-9ccb-a0d7cb3915d0 | note | Zone Manager Approval
9ee3c4da-5bab-5d55-ba41-2d8efd8d318b | note | Construction Manager Approval
c4b083ec-831a-54d2-ad43-5c7405c973ff | note | Quality Manager Approval
8093829e-d2ee-5a87-9383-b08bc5ebef17 | date | Date:
1dc2c9d0-048a-5501-9488-936d3248a797 | signoff | SIGNATURE
d332392e-726a-59e5-b8db-28b0b7978937 | checklist | SYS - ITP - 012 - Concrete Culvert | itp | ITP - 012 - Concrete Culvert
42f478fc-2189-5924-ba07-4baaf8f6299c | section | 1.1.0 Pre-construction approvals
c6325e1f-98cf-5dd9-a024-c2741f8830c3 | checkpoint | 1.1.1 - Construction Environmental Management Plan
9228b49e-5aee-50d3-942b-513a1e401c62 | note | Method/Description - Document Review
5377f383-17ff-587f-8f81-1473fcf043e6 | note | Test frequency - Prior to work starting
ec45cb7e-6dfa-5859-baa1-f3d73975ea0a | note | Contractor - H
75e814f9-98ac-5a60-b5b6-2b847c137ed4 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed CEMP
ee7771bc-2366-56f9-836d-696e37f5e599 | checkpoint | 1.1.2 - Construction Work Plan
87ecf765-4293-5159-912e-f58d4aa9e29c | note | Method/Description - Document Review
43582105-9874-562e-a056-f5fef5f7bebe | note | Test frequency - Prior to work starting
577042e6-c79f-572f-a20c-2060ec37af0f | note | Contractor - H
5c2d71bc-4f66-5599-8f1f-c89960790661 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
80997794-398e-58e2-88f5-b742e9843f56 | checkpoint | 1.1.3 - IANZ accredited testing organisation
d73622e4-339e-57f0-8976-0951e2f36dba | note | Method/Description - Document Review
0cfa570d-3e93-5252-968e-96862152a449 | note | Test frequency - Once prior to works commencing
b5ef69a8-7b63-5c04-a0db-11432dc931b5 | note | Contractor - H
57277e7f-aec3-5eaa-ba65-bfc85d2bf0ee | note | Designer - H
49551789-7e21-5026-b6bf-2296c8af16ad | note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
c01bda50-5337-52d8-a035-bce8c22e8ba1 | signoff | HOLDPOINT
1506fbf7-5b48-517d-a6d7-cb5c453622a3 | checkpoint | 1.1.4 - IFC's specification
a2b1b20e-abef-5ee8-bf13-ba4a3c21c1ad | note | Method/Description - Document Review
f5842c77-6e5a-5e98-aeec-edf052fa72a2 | note | Test frequency - Once prior to works commencing
a7b08a26-79f9-585e-9f62-84ec09d1c8c0 | note | Contractor - H
da4d491c-8d62-5680-9df1-96017b9bf004 | note | Designer - H
fb143926-042d-58fc-8ca4-eec66f248683 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC specifications or Written approval from PAB
e9f68c7e-1fda-53e7-8a67-e45a02bd974e | signoff | HOLDPOINT
66467056-0c6d-5a0c-8857-462d47f00167 | checkpoint | 1.1.5 - IFC drawings
d02bfaf1-7299-5414-b0e0-98744319620b | note | Method/Description - Document Review
fec2408c-f0cd-5a7f-a5b7-0b1e81716e06 | note | Test frequency - Once prior to works commencing
f9724dbf-bbef-5a78-a688-caa65e6b1b06 | note | Contractor - H
f09a0e65-2f7a-594b-aee0-d5908c89cdd7 | note | Designer - H
25fe20b3-1c16-5164-820f-b435da814784 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
5570fc79-df84-53b5-b250-4000c5782617 | signoff | HOLDPOINT
edd8ec75-09d1-5a78-addc-e4f573ae83d2 | checkpoint | 1.1.6 - Approved Drainage Strings
859362a7-67dc-5889-b3ca-caf93ee2434c | note | Method/Description - Document Review
50b400a9-6b28-55ac-bcf7-162f72351b1f | note | Test frequency - Every new Drainage Line and prior to work commencing
7219ff0f-4965-5490-b4b6-c12ceb794f6a | note | Contractor - H
86b0c31e-7352-5b3d-9ad9-97b67ae08f6c | note | Designer - H
49771ed7-1726-5648-b0a6-189e97078026 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Cover Form
4e59ff90-65fc-56e4-a9fe-b41aa13006df | signoff | HOLDPOINT
19d8b93b-c4a4-55e7-ad84-fcfed6a60769 | checkpoint | 1.1.7 - Approval of stockpile location
642f99c1-08c7-506b-8db2-2883f207768e | note | Method/Description - Document Review & Approval
d546ad01-1270-5ac6-a636-f549e73d0c2b | note | Test frequency - Prior to works commencing
37a316ed-bb20-5d4e-a168-6bf6c2b76503 | note | Contractor - H
78dd2113-9c68-5c3b-8803-a60c3627460d | note | Designer - R
62701554-698e-5a31-9c47-9144c3604c8f | note | Verifying Records Checklists, Test and Supplier Certificates - Written approval from DSR
0f3f7c86-5e36-5d1b-a6d0-ea9aff9da0d5 | section | 1.2.0 Material compliance
8e814b7f-c3eb-5bf4-99ab-b89915cd8e9f | checkpoint | 1.2.1 - Materials - pipes and fittings
52bd9155-494f-50d7-9d15-f147933cb9e2 | note | Method/Description - Confirm pipe diameter, class and jointing type as shown on the drawings and that pipes are in correct and good condition.
8f9fee52-df73-5037-ae6e-15486c792166 | note | Test frequency - Each delivery to site
0bbd4002-a9a9-5e67-95ad-5336d271823e | note | Contractor - H
d45cc9dd-3a9c-5658-8ee3-f4f279645b18 | note | Designer - W
b3a4b655-16ee-5511-9857-d63a707641ea | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check Sheet
5cb1d0fe-bcbb-5f6c-ae8d-3e3b4d1bff9c | checkpoint | 1.2.2 - Materials – pipes and pre-cast units (wingwalls)
cc85ecff-a0a9-5dff-9f0d-62f3ed39471f | note | Method/Description - Specification compliance – manufacturer’s certificate to TNZ F/3 for pipe and pre-cast units
fb6948fc-a24a-5291-ba8d-40f8b19a9977 | note | Test frequency - Each delivery to site
36a9fc4a-073f-5fb2-b911-50585553b5ad | note | Contractor - H
16b99f2f-7550-5378-9ea1-c0e18cdd3938 | note | Designer - W
a8b26609-a72c-5441-8fea-d0a3727e055e | note | Verifying Records Checklists, Test and Supplier Certificates - Compliance Cettifcates
f6d7d14f-8d72-5b98-9707-4650fa278a2c | checkpoint | 1.2.3 - Materials – Grading for Bedding, Haunch and Sides Zones AP20
6127b00d-50de-50be-92d7-9842234e7627 | note | Method/Description - NZS 4407 Test 3.8.1 (or similar approved) Determination of the particle size distribution Standard method by wet sieving
21e84d09-0dd6-5311-b066-688534eeca4b | note | Test frequency - 2 per 400m3, 3 per 400-1500m3, 4 per 1500-4000m3 and for over 4000m3, 1 additional test per 1000 m3
97cbce36-4cb4-5ede-8b72-da68dbed02b2 | note | Contractor - H
cc179de9-a7a0-51e4-9176-705d7e1bf48a | note | Designer - W
a002bb78-6be2-584f-bf16-fab19d6b0b3b | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
fdb353fb-0c17-5c05-8674-d0e2369af3c0 | checkpoint | 1.2.4 - Materials – Testing for Bedding, Haunch and Sides Zones AP20
86342b20-ceb0-5782-9c67-c639fa47c4a5 | note | Method/Description - Determination of the linear shrinkage NZS 4402.2.6, Determination of the Weathering Index NZS 4407.3.11, Determination of the Crushing Resistance NZS 4407.3.10
be977e92-5547-5fe0-9598-a70a11a6f493 | note | Test frequency - 2 per source then 1 per 1000 m3
9bbea42a-4985-5447-908b-4be23dfb7261 | note | Contractor - H
ff97a6ad-39fc-54d3-aabe-d8225f1a9a24 | note | Designer - W
de9a1911-a267-57cb-91b1-39f1b813891e | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
0efafa97-346c-5759-b662-65b500d8d701 | checkpoint | 1.2.5 - Materials – Compaction Curves Bedding, Haunch and Sides Zones AP20
65f1536e-47d5-5d9f-8ba7-43e351273f6e | note | Method/Description - Establish a relationship between MDD and DI (density index) to determine the target MDD (NZS 4402.4.2.1 for the minimum dry density and NZS4402.4.2.2 for the maximum dry density).
2cd7c8dd-710e-5143-9509-543b9368f5c6 | note | Test frequency - 3 no. tests per source with minimum 5 points
1dcc800b-9f9b-54b4-8b5d-162fe72c0b8f | note | Contractor - H
6a1f3567-b35c-5172-9d6e-8edf6b5b96b6 | note | Designer - W
8cd22a33-3a32-512c-bf5b-3748f591d44a | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
71fb3631-7e34-5985-adc9-4b2503ba35a6 | checkpoint | 1.2.6 - Materials - Grading GAP 65
83436569-fa71-5144-aa61-2d89e282a663 | note | Method/Description - NZS 4407 Test 3.8.1 (or similar approved) Determination of the particle size distribution Standard method by wet sieving
7bc3ed3a-3ca9-5c2d-8836-200c464ab9a1 | note | Test frequency - 2 per 400m3, 3 per 400-1500m3, 4 per 1500-4000m3 and for over 4000m3, 1 additional test per 1000 m3
8582ab00-843f-5371-aa75-07b417e65dd8 | note | Contractor - H
4203cd20-24ce-53a7-8d67-07d728e562cf | note | Designer - W
efc084eb-7a7a-5c1d-b8bd-15648d90c3a1 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Reports
f9887d87-f9b6-549d-a938-52adc269b655 | checkpoint | 1.2.7 - Materials - Testing GAP 65
25d5cdf5-53b6-5069-84f3-df1fea371e38 | note | Method/Description - Determination of the Weathering Index NZS 4407.3.11, Determination of the Crushing Resistance NZS 4407.3.10
8b0e5de7-e311-520a-bdcd-31fa19e427c1 | note | Test frequency - 2 per source then 1 per 1000 m3
339a17bb-ac56-58dd-a213-d1b3beff7630 | note | Contractor - H
ef21b36e-4f63-56e5-bfe9-ffc1742911d7 | note | Designer - W
ea842e33-c074-55d0-a5a1-08194f2d3d06 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Reports
30927859-c459-5c65-aa59-fb764ad677fc | checkpoint | 1.2.8 - Materials – Compaction Curves GAP 65
bc5f7429-197c-5f43-806c-a083bff36ec1 | note | Method/Description - Establish the optimum moisture content and minimum and maximum dry density. NZS4402 Supplement No 1:1988 - Test 4.1.1 or similar approved
b5443b02-cb36-54f0-9d3f-a5b2b509e24f | note | Test frequency - 3 no. tests per source with minimum 5 points
398afac6-63d5-5dc6-b7aa-7df26a13e6ec | note | Contractor - H
2a123bd7-d6e7-58ef-85bc-ac1f93042350 | note | Designer - W
e353a401-6dad-5093-9c44-f3e09c2dc04c | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
7624046b-faba-553b-8b48-cb4f37d6fa18 | checkpoint | 1.2.9 - Materials - Structural Fill and for Overlay Zones
cd4baa4b-91f6-5c0a-ace9-cd6ee27b175b | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2, Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4, Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8
a6a8d166-d53c-573f-881f-05defcc1407c | note | Test frequency - 1 test per 20,000m3
86b62a4d-06ff-5f12-ba8b-67ba02bd1470 | note | Contractor - H
0c0daa9c-346a-540f-8493-22ce36bc0266 | note | Designer - W
078c2dc3-2c7c-51db-a567-9c6a6ae74c88 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
d20b64aa-0a76-53c1-b68c-1341121a0906 | checkpoint | 1.2.10 - Material - Rip Rap - Grading
8fedcc53-0875-509b-8b60-6a5c450f37ab | note | Method/Description - NZS 4407 Test 3.8.1 (or similar approved) Determination of the particle size distribution Standard method by wet sieving
f8e2b0f3-9dc2-55d4-a121-8319ba8be70e | note | Test frequency - 1 per source then 1 per 500 m3
7d87816f-8a30-5fc6-b191-8cfe4b067382 | note | Contractor - H
4c70234c-da14-5be1-9585-3a68fe8d4284 | note | Designer - W
04c98a3e-da02-5b42-85c7-7a839f249836 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
511f1f7e-09e7-5f71-a86b-d6695894df84 | checkpoint | 1.2.11 - Material - Rip Rap
f29bbd4a-58c3-518b-bfa2-dd9bb2369659 | note | Method/Description - Determination of: Weathering Index Coarse Aggregate dry density NZS4407.3.11, Crushing Resistance of Coarse Aggregate NZS4407.3.10, Solid Density of Aggregate NZS4407.3.7.1 & 2, Point Load Strength ASTM D5731, UCS Rock AS4133.4.2.2
579e6197-b2f2-51a9-9cb6-349506b7c731 | note | Test frequency - 1 per source then 1 per 1000 m3
650c2dc0-f9a1-5372-894f-2f502109c62f | note | Contractor - H
ec637ec8-7e7c-56b7-a74a-8fb29f7243b7 | note | Designer - W
cf22aa9f-e7dd-56ac-ae42-3228ffeae010 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
7776722d-c74f-534d-951e-10aa78343830 | section | 1.3.0 Geosynthetics
97d64c28-aeb6-5fd1-b959-6a3a6a5701c7 | checkpoint | 1.3.3 - Visual inspection - geotextiles
0db1dd08-cf25-5a83-98fb-b78beabf6e34 | note | Method/Description - To inspect geotextile and is the proper type and no tears, rips or other signs of deterioration.
a4c984cd-ae01-5139-99e9-e5b98c37dd16 | note | Test frequency - Check each lot (1 roll)
268892fb-2c5d-5ce1-ad2d-f8e82d79373f | note | Contractor - H
88b4001b-385e-57ac-9181-fece7ee10919 | note | Designer - W
3b6dabf8-b6a7-5b7e-a02f-ab02d1ccc8ae | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checklist
d7c755dd-0b57-5bdc-bbe9-9270429921e2 | checkpoint | 1.3.4 - Geotextiles
2ff86310-02b0-5683-be3b-65387d1ae0e0 | note | Method/Description - Specification compliance – manufacturer’s certificate to TNZ F/7 2003
85c3a159-0f78-536a-971c-759c0364cb62 | note | Test frequency - Check each lot (1 roll)
0c3c90a2-c72c-5b90-a571-de290875c9ae | note | Contractor - H
6261776d-24d8-543f-a2b8-6d3a56fd1e4d | note | Designer - W
ad6c9d91-dcfe-5123-9922-d9c2d3e1687e | note | Verifying Records Checklists, Test and Supplier Certificates - Manufactures Certifcate
4c0dc328-3b88-5f08-b329-45e2cf194f3a | section | 2.1.0 Trench Excavation
f986fadd-ceae-50ae-8ad8-b02d3b3a73e8 | checkpoint | 2.1.1 - Trench Subgrade
847e7178-d71f-5f9a-8147-da80203f137c | note | Method/Description - Testing trench foundation material to assess is undercut is required. Scala penetrometer test as per NZS4402.6.5.2 for non-cohesive materials. The CBR value of the subgrade soils shall also be measured using the in-situ CBR test in accordance with NZS4402 Test 6.1.3.
45a647cb-092a-5069-a13c-23fbaee0f119 | note | Test frequency - 2 nos. scala penetrometer tests / 5m of trench, 1 per ancillary structure
70b28c97-0316-5492-9fda-120649e4d15d | note | Contractor - W
f9b21d77-9275-5be5-bc34-7bbdfc68b456 | note | Designer - W
72bc675b-d854-517d-8eb5-e36777048a7d | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
eb50ab69-1329-59cf-a234-f44f19866d30 | checkpoint | 2.1.2 - Trench Benching
ea4b4f01-db21-5042-aa47-a6bffcb6519a | note | Method/Description - 1.5m benches to be constructed strating from rock (pap) top
e3e0e14b-b1f3-5841-838e-ff78e88bb891 | note | Test frequency - Daily
85cc4c53-0690-5d9f-8dda-8c730a8a3309 | note | Contractor - H
6945ba66-2aef-5448-b240-0f6c8238fe9d | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check List
50816fdf-3a18-5603-b151-5a929acd38e6 | section | 2.2.0 Pipe Bedding and Construction
105a0377-f680-585a-8f43-0393b04334fd | checkpoint | 2.2.1 - Construction of embedment side zones using AP20
3a7ba378-3987-5b74-8f07-b83588c52669 | note | Method/Description - Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991;
33deb3de-4a1a-5a03-8e66-8127f4ea16af | note | Test frequency - Two test “sets” per layer, 10m evenly spaced intervals on combined lifts upto 300mm lift
919547bb-70d0-5ccf-b4dd-321aeb76e91c | note | Contractor - W
0b9d354a-383a-59b4-bd63-18093e708e72 | note | Designer - W
d1570523-4240-5e8c-8472-5d3a389c01d6 | note | Lab - I
ba0ecf47-244f-5440-b923-0f52e5fd3c52 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
75f1d9d2-90be-5906-b1d5-437f0bb9dfd3 | checkpoint | 2.2.2 - Construction of Overlay Zone
69b3b9a8-f078-5dbb-9f5e-9c813035422f | note | Method/Description - Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991; Undrained shear Strength
9e012799-ff14-5a55-aefa-01c479d91ba7 | note | Test frequency - 1no NDM and 1no Shear Vane Test per 20m max canters at 300mm lifts
a1c7c260-c6b0-5a2c-9435-7ca233679ef8 | note | Contractor - W
943df5af-0820-5d7d-9e21-bdb41665cadb | note | Designer - W
37d8da41-ddd1-5515-888a-c20a8228259f | note | Lab - I
fe7b455b-e6bb-5d65-a5ed-1aa67681411c | note | Verifying Records Checklists, Test and Supplier Certificates - NDM Test Report
da31c029-6072-53a1-a4b7-22c4aa43839b | checkpoint | 2.2.3 - Construction of pipe
5495e333-1841-5d58-a491-9d43276c9772 | note | Method/Description - Visual test prior to backfill above the side zones – line and level, correct installation, and joints are all sealed.
2c330310-90ff-58e2-966d-39f47fe9b707 | note | Test frequency - Review every 10m and witness every 25m
63264f0b-8b4c-562c-8ba5-74f0d41f691f | note | Contractor - W
150709ef-07d4-5761-94ab-46be48debe81 | note | Designer - W
2cb52ef5-085e-528a-ab3b-fd0f482a608d | note | Lab - I
a9ac0eb5-2063-5928-815d-ac0a351654aa | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
f5fa687b-8e4f-5725-9c87-97b706549725 | checkpoint | 2.2.4 - Construction of Wingwalls
63e31e78-1cb6-5685-a317-de149d6ba04a | note | Method/Description - Wingwalls shall be constructed on a compacted, 150 mm layer of AP65 granular material. Jointing between the connecting pipe and the back of the wingwall shall be completed using mass concrete.
23794daf-fd71-5587-ae40-508d5f86f8fb | note | ○ Visual inspection of joints between pipe and wingwall
b3f0c1c6-cede-5fe4-8db2-a2f7618ad84f | note | Test frequency - Each Wingwall
a64fac22-c168-52a8-8e9c-17a8ca99a408 | note | Contractor - W
95dcca66-7830-5bcc-8e0b-c1fa1340f6df | note | Designer - W
a7c398a7-c4e2-55e8-89f5-9fbbcb7152a9 | note | Lab - I
e71736b2-6383-5e48-8937-ae2a8056a9bf | note | Verifying Records Checklists, Test and Supplier Certificates - Test report, Onsite Check sheet
a50d0e9f-e834-599b-8523-b84375fdd90f | checkpoint | 2.2.5 - Construction of Antiseep Collars
4c99c008-fdb2-5621-8d69-e78e5f9ee706 | note | Method/Description - Antiseep collars to be embedded 200mm horizontally into side of trench and 400mm below base of trench. To be located every second pipe joint. The collars shall be constructed using 25 MPa concrete.
85ddf569-907e-56ec-8b62-49a94a82b8c8 | note | Test frequency - Each Anti Seep Collar
60bb4a34-1198-5817-a955-75899b32e8f7 | note | Contractor - W
dc501a93-a067-500b-b7b2-b712ae7708fd | note | Designer - H
6e4341db-cdb0-5dfb-b7ec-d0d4d9996949 | note | Verifying Records Checklists, Test and Supplier Certificates - DSR Inspection (Pre-Pour), Pre-Pour Check sheet, Concrete Dockets, Concrete Test results
6cde02ed-5070-566a-b966-0872f46a6950 | signoff | AUTHORITY HOLDPOINT
582cd8b8-8363-549d-9259-a765ac8c6e8b | checkpoint | 2.2.6 - Construction of Cut Off Toes
427d8625-88da-5823-8de8-4f5aadec412b | note | Method/Description - Cut off Toe to be embedded 1m (or note 4) from top of wingwall base, to be constructed as per IFC Drawings
ca58d884-f8f0-5b9d-9796-e3ee82da142a | note | Test frequency - Cut Off Toe
1d881238-7e12-5496-aa65-5a99f5277924 | note | Contractor - W
d1641998-47dd-5bb3-9217-e0d77c23c526 | note | Designer - H
a122cb44-bda1-5576-86aa-cd11a610b441 | note | Verifying Records Checklists, Test and Supplier Certificates - Pre-Pour Check sheet, Detail Sheets
d14e1df5-6882-5afd-a62c-c939f4ca19f3 | signoff | AUTHORITY HOLDPOINT
594c0178-f298-52f4-9f5b-7c9b1e5b64e5 | checkpoint | 2.2.7 - Construction of Inlet/Outlet Channels
45ed5101-68a7-5e22-a22f-f5825168438d | note | Method/Description - DSR to inspect geotextiles before rip - rap is laid. Max drop heights to be adhered to when placing rip-rap
5afe2323-d6f6-5caf-b559-8b73dba33b0e | note | Test frequency - Each Channels
c0b813fb-a9aa-5f37-aae5-84685b21bd6e | note | Contractor - W
1e47230d-026c-5f7d-9395-bc17239f19f5 | note | Designer - W
3086fc60-1d3c-57a8-a396-5bfc16171ca0 | note | Verifying Records Checklists, Test and Supplier Certificates - Geotextile Installation Check Sheet
c512f035-a60f-5265-aa88-74075cc49bc6 | checkpoint | 2.2.8 - Fish Passage
a09e9033-37fe-59f4-805b-6df53e475682 | note | Method/Description - 25% embedment depth with meandering low flow path from void filled riprap. Spat ropes for CU-17
5661c784-7c55-55e6-963d-25c98bc02011 | note | Test frequency - Review every 10m and witness every 25m
3abb2b58-3dab-5492-85a0-92faafcb0ecc | note | Contractor - W
58acd012-3564-52bb-8c5f-829e197eeb19 | note | Designer - W
b3639ecc-1436-532c-98be-e037658ce66b | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check sheet
37038c88-37a8-5007-ba3d-45bc5b4228f4 | checkpoint | 2.2.9 - Construction of Safety Rail
3e635c4d-68d4-5c4e-ad17-6fdfcc89400f | note | Method/Description - Constructed as per IFC Drawings
eeccdb52-2237-5e3e-a86f-4cd66649a4c6 | note | Test frequency - Each Fence
4cd7c820-cb60-52e5-ba17-3960a61db922 | note | Contractor - W
f527a4c2-cae9-57f6-a5a6-84009edc69f3 | note | Designer - W
94535d2b-004f-5af0-8369-14420763c9a4 | note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check sheet
d5545795-84a2-5564-99ac-44165c0761fb | section | 3.0 Post Construction
be98c092-01d5-5b90-971c-8c4da0244e2b | checkpoint | 3.1 - Survey/as-builts
40494747-1472-5bb5-97a8-aec6c59a584d | note | Method/Description - As built survey of coordinates and invert levels, structures, and pipe ends
d0bc6e8a-5d57-5205-96ec-3b694ce97faf | note | Test frequency - Every 25m
b7b8a638-6e8e-54a2-a65d-1745e26dfbf9 | note | Contractor - H
dce60108-fd2f-58a4-a4b9-29f1c2f24a17 | note | Designer - R
56259f04-79c5-52f0-aeac-f4d4376e7aa7 | note | Verifying Records Checklists, Test and Supplier Certificates - As-Built
cbc3445c-ac90-550f-9e82-af6420eeb789 | checkpoint | 3.2 - Post Construction CCTV inspection
95f0d49c-e324-5e35-baf4-fa86f7683f68 | note | Method/Description - Check conformance with the specification and assess the asset condition post construction
643a8dbb-4725-5eca-8ad5-5559c1234b0a | note | Test frequency - To be completed following pipe construction but prior to spat rope installation
45a53d30-beb9-5f86-9463-33c05271ac0e | note | Contractor - H
9fa72698-7372-5ff0-bf78-8761ee087785 | note | Designer - R
ad14c004-5c03-5329-98e8-cd1f97967c30 | note | Verifying Records Checklists, Test and Supplier Certificates - CCTV log Report as per the standard
8919eff8-fed3-572c-bcf7-d24e7712e7ba | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
45524c2d-1de8-5e60-b52d-1f4484181dd2 | checkpoint | ITP Close-Out by
a57f4b42-7ec8-5415-9f65-ce1d2e335413 | note | Site Engineer/Project Engineer
ff8f41d9-1fe9-5988-adb9-7e759afebebf | note | Zone Manager Approval
b1b07624-6b73-5228-a07f-2293c17788af | note | Construction Manager Approval
0e4133ec-0e60-5fd8-b55d-a9be9b10ab3d | note | Quality Manager Approval
5750c7ec-09a8-5539-9a20-022691aefd0c | date | Date:
1dc2c9d0-048a-5501-9488-936d3248a797 | signoff | SIGNATURE
c8a256c3-1bba-57f6-8a4f-89e7f5a9d404 | checklist | SYS - ITP - Fill 12 For Season 2023/2024. |  | ITP - Fill 12 For Season 2023/2024.
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
c9e7969a-5007-57ec-ba14-7e88241a4737 | checkpoint | 1.01 - CWP
1fd7bc15-7b75-56ee-90ea-64d2ed7cd0fa | note | Method/Description - Document Review
2d6fe952-cf71-5bfc-9670-82288734cf09 | note | Test frequency - Prior to personal starting
edeb92b5-8427-55c7-a8c3-c6d9907e3017 | note | Contractor - H
3d72a513-8b7c-5811-9207-becb8381f6b0 | note | Verifying Records - Signed off CWP
5c6d3d2d-8b90-5b45-ac77-8cb3e4b937f4 | checkpoint | 1.02 - Design
8c4b0047-156c-586f-8f33-0259491ef1fb | note | Method/Description - Document Review
5d603b27-a348-586b-9d5d-4a9e16c405df | note | Test frequency - Prior to starting
58328657-106f-576e-bef9-66260f63f3bb | note | Contractor - H
94770155-8c54-523d-86d3-f5001fe94dac | note | Designer - H
230170c5-4b0d-5a1c-831d-aee8dcc0214b | note | Verifying Records - IFC drawings or Written approval from PAB
7bd1fe4b-029d-5a22-999a-91130e63165b | signoff | AUTHORITY HOLDPOINT
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
265e2a41-b6af-58cb-9aec-e70b81447852 | checkpoint | 2.01 - Structural fill
843a877e-afab-5723-b797-d1e3e4a6d016 | note | Method/Description - Determination of the dry density/water content, Atterberg limits, Triaxial (Single stage min. 3 samples)
1ef9ada4-cbd5-5c9f-8615-b75fcad5a5a7 | note | Test frequency - 1 test per 20,000m3
5e07418b-5d1e-525a-a70f-5f83018efce4 | note | Contractor - H
15750547-c9ba-5ba1-9d88-1a2406902a8e | note | Designer - H
79172de2-0ca6-53ba-a825-f50e292e216d | note | Verifying Records - Test Report
228a3ddf-c4be-5722-a7fb-9380f8859aa2 | signoff | AUTHORITY HOLDPOINT
2a735733-e33f-5a2c-8219-fba4a2eb7209 | checkpoint | 2.02 - Buttress Fill
72f577ab-2a72-5a15-ad9a-e191a2caf005 | note | Method/Description - Determination of the dry density/water content, Atterberg limits,
de4a0cb6-c889-55ba-8927-2ac74ed52b77 | note | Test frequency - 1 test per 20,000m3
68c11a0c-177b-5be6-93bf-517e2dfc875e | note | Contractor - H
961cda57-bca9-5b4a-955e-9a7dbb6bed30 | note | Designer - H
7a1bc3f8-bd1e-5d53-9c31-69881a980b0e | note | Verifying Records - Test Report
b005e003-bd07-5459-960e-8bc2ffe248ac | signoff | AUTHORITY HOLDPOINT
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
f80e3859-9837-5795-b26c-edce867f3449 | checkpoint | 3.01 - Set out extents of fill and check against design
54470988-20a7-588b-9eaa-7de92c883ade | note | Method/Description - Survey/visual
dbbcf320-807a-50e3-a052-c5f4f8daaca6 | note | Test frequency - Prior to Commencement
a3ca4369-038a-5267-ae01-95a64d991327 | note | Contractor - W
9a2366ea-dde1-5a1f-aa20-31976fcfcac4 | checkpoint | 3.02 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
4689b6f4-b066-5f1b-8240-8fcc4de99da1 | note | Method/Description - Survey/visual
997ac537-43b3-5192-9017-0bf3e3dcb597 | note | Test frequency - Prior to Commencement
d9ac4fbc-7600-56df-85a5-8ea200705489 | note | Contractor - W
b5cbf260-9166-51fa-99e7-82b481d6e014 | checkpoint | 3.03 - Vegetation Clearance
b4fb3a68-71ef-58da-8097-40b7a89c112a | note | Method/Description - Survey/visual
8970b38d-8b8a-5e49-9c38-d63fc8472797 | note | Test frequency - Fill area footprint
f6a103a5-5e83-54ad-a66a-0eff52520bbf | note | Contractor - H
b87f98d4-d11c-551d-81c7-8f4f29f9fedf | note | Designer - W
21e996d7-b1c6-5e55-bfcc-f4f44de77c3c | note | Verifying Records - Subgrade approval checksheet
968214fd-11f9-5702-8296-7a714958f524 | checkpoint | 3.04 - Designer witness of in-situ subgrade prior to filling
ba2f9358-a9a9-5881-bc01-18f984aee4f3 | note | Method/Description - Inspection
11f42312-c5e8-5541-9374-4f1594c9a91e | note | Test frequency - Prior to Filling
8a0edce7-145a-5525-b5b4-f396d248a2e9 | note | Contractor - H
36da4f01-26aa-5525-99f1-2d9554b96007 | note | Designer - W
62478400-b8e3-59d6-a6a1-8dcf7c77e368 | note | Verifying Records - Subgrade approval checksheet
9337de40-bb4e-5c4d-869b-d8f3bcf1a9cc | checkpoint | 3.05 - Undercuts
69ecde8d-3869-5cf5-ae08-76c8bd5d180a | note | Method/Description - Visual inspection
438a220f-e72c-56fb-9404-7451932cbae9 | note | Test frequency - Prior to Filling
bc6f60ed-4f21-5290-8116-2a8222b4d19d | note | Contractor - I
8d209e60-b20b-5233-9b84-a05bf17c9165 | note | Verifying Records - Subgrade approval checksheet
201333b3-3907-5aaf-a1a8-9a0136b59a29 | checkpoint | 3.06 - Subsoil Drainage
1a089570-6390-58b5-8b70-7e61af11ec2d | note | Method/Description - Inspection
1b9050a5-547b-527d-9c0b-c94f51eff89c | note | Test frequency - During subsoil construction
9e02960e-ab55-55c1-9b30-b7fca11a2b74 | note | Contractor - I
eb43c112-b2d0-56f7-882d-36705c85ffc3 | note | Designer - W
dbc35f7b-b8a8-52b7-a189-44533021e349 | note | Verifying Records - Sub soil drainage ITP,
bc1aa750-f038-51a9-8190-ade6b85cd655 | checkpoint | 3.07 - Monitoring Equipment
1ef14143-ffb9-517a-8f56-4a92d767339c | note | Method/Description - Survey/ data logging
de174a21-52f0-5099-bc2a-2fce93f54897 | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
988e2157-806d-5f8a-b89e-c6251768791b | note | Contractor - W
9a75421e-9f90-5e9f-93ee-665134a87991 | note | Designer - W
5e4495f7-1404-5969-92b4-0f14e57f6446 | note | Verifying Records - Drill logs
3a553daa-8f6a-5704-9183-3bb478bdeca4 | checkpoint | 3.08 - Filling operations
adbb1f75-98dc-556c-a631-3bc5b41ba1e0 | note | Method/Description - Visual inspection
66e1ae20-c616-5dc4-9692-bfd386ade1d1 | note | Test frequency - Daily
17d7b1e3-8e17-59c3-b4c2-f7bfadb16577 | note | Contractor - W
ec83abcf-a19b-5853-bcb4-61fa99665448 | checkpoint | 3.09 - Filling operations
ee8cacb4-bc0a-5ead-b3e9-8dd2e866d9f6 | note | Method/Description - Survey/visual
310c020a-61b0-587d-a195-8b4d2bc41a10 | note | Test frequency - Daily
10983cb4-a0f8-543a-84d5-dfe3867faf88 | note | Contractor - W
dd3aad50-bdbe-5682-bd2e-421f2703fd43 | checkpoint | 3.1 - insitu fill testing
69a46851-b372-5748-8d21-a101d637e99b | note | Method/Description - Plateau Test
8d5d5d55-7dbc-5e0a-b42b-4505a96aae12 | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone, Buttress Fill - 1 test per material type per earthworks zone
c350c99f-eccb-585b-82ac-03e070b715f7 | note | Contractor - W
7364e9ca-6681-5b8c-be6d-f877ddd2313d | note | Designer - R
a48bd035-17e9-5865-9115-15eb677f0492 | note | Verifying Records - Test report
fe966276-cf7e-5918-9f15-68fc2a7e5b6d | checkpoint | 3.11 - insitu fill testing
600dd621-0d81-50d0-80c4-9dc0f518b981 | note | Method/Description - In situ moisture content and density
0c1794d4-660b-55ea-acae-9466ec554854 | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length Buttress fill - 1 test per 200m length Average Subsoil Drainage Back fill - 1 test per 500m3 , Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
09464a21-4611-56a8-a5fe-3e0edf4ffdaa | note | Contractor - W
6a52ccdc-6010-5574-b132-a0d049b97e2d | note | Verifying Records - Test report
9e244908-a5e8-5361-88f6-bc38e3b257d2 | checkpoint | 3.12 - insitu fill testing
a0afe7b1-fee4-5fa3-9c71-8fbf8f5a5acf | note | Method/Description - Undrained shear Strength
af0fabf9-9e6b-5b60-adc5-e80a21430127 | note | Test frequency - Structural fill - 1 test per layer per 1000m2 Buttress Fill - 1 Test per layer per 2000m2 Cement Stabilised Structural Fill - 1 test per layer per 500m2
6c4d0280-0c7d-5097-98a7-f68560fc8028 | note | Contractor - W
fbe8a438-4bda-5e3c-9d73-322b30940467 | note | Verifying Records - test report
32bf1bf8-4b78-5538-a4b0-a25271cd10fc | checkpoint | 3.13 - Confirm testing requirements are met for insitu fill
5c909215-a304-562f-ba2e-1b17343aed8e | note | Method/Description - Document Review
02bc81e6-ca2b-5dc5-a474-4c20bd89a2c7 | note | Contractor - H
c69f231d-1c8d-5151-846b-45fe51c69acf | note | Designer - R
49638fac-20ae-5cd6-a1f4-ceed719c72c3 | note | Verifying Records - Review of testing records
8b69e985-c302-59b9-82d2-a52a38698c15 | checkpoint | 3.14 - Subgrade Fill Testing
f555f46b-d1e3-5003-8844-e622c6d88ac5 | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
b9934e02-df02-58e0-87fd-ee458ddd54ac | note | Test frequency - 1 test per 0.5m lift per 50m length for 1.0m subgrade depth
fd34ab6a-c392-52d6-9c5c-0fed575b1764 | note | Contractor - W
d86a7167-2b5a-5754-bb5f-f0e4f1a196b9 | note | Verifying Records - Test report
3ee45fde-032a-51c7-b9c3-5a2f343b79c1 | checkpoint | 3.17 - Subgrade Fill Testing
c9fb14e6-4cd2-5dc0-af5c-95b191f08475 | note | Method/Description - Benkelman beam or FWD Testing
c428f2d7-9aa5-5956-98a3-072d60654b87 | note | Test frequency - At three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
ec4011ac-576e-544f-b4aa-606496abe07b | note | Contractor - W
d2973614-4cc8-59bc-8d68-4022b26ad1d4 | note | Verifying Records - Test report
b1d90aa6-8720-532f-ac39-1f798f47992d | checkpoint | 3.18 - Subgrade Fill Testing
3e147788-ed35-54be-8ec5-a539d24bf29e | note | Method/Description - Laboratory Soaked CBR
0fc8e469-f22c-5704-89f9-d7fe018fb000 | note | Test frequency - 1 Test per 5000m2 at subgrade formation level
8931dde4-2398-509e-9f8e-52ed93d5f832 | note | Contractor - W
0fb58b69-8f60-5619-bacf-d43c590a3e70 | note | Verifying Records - Test report
261fd088-1d37-5bb5-8cd2-c96c245bd596 | checkpoint | 3.19 - Confirm testing requirements are meet for subgrade fill
09cf899d-703a-57b2-b32f-4d3da9cf3da4 | note | Method/Description - Document Review
ca9875f0-73ae-5e90-8de8-7302acc32331 | note | Test frequency - Completion of Filling
0cc662ce-b0e8-58c5-b821-6b286fa94e2d | note | Contractor - H
f2a108d2-b42a-5c4e-8639-6ba9e41a718c | note | Designer - R
b5536ccb-b6ba-5e9f-a442-cefb3e4a58ee | note | Verifying Records - Review of testing records
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
de153151-2496-515f-a86e-a71e4ea85abf | checkpoint | 4.01 - Monitoring Data
a7db3a4b-38db-57a6-b6e3-59634dff1edc | note | Method/Description - Data Recordings
2a085e1a-02b9-5208-940b-25fa6a85b2e1 | note | Test frequency - During construction and at end
3167efb4-0f87-5712-9e42-e14a688fc186 | note | Contractor - H
c842e8aa-996e-5622-a3a8-8af7e1d2ec92 | note | Verifying Records - monitoring Data tables
96b27424-f2a1-51a5-ba79-d8a2e76ef901 | checkpoint | 4.02 - Survey As-builts
36fe3d22-feb1-5dc2-9164-8b5f09094e1d | note | Method/Description - Survey As-built
52dd3e4e-8331-5648-bad5-815d78477912 | note | Test frequency - During construction and at end
5193b0a9-ec26-5a50-b6c1-11b49445bce8 | note | Contractor - H
1674725e-8610-5f4e-9cb6-85c094bf0c22 | note | Verifying Records - CAD files
5c0732e6-58ca-5568-815f-7eb40f0c0149 | checkpoint | 4.03 - As-builts
2454005a-a3a1-5a1e-8746-49dd0e0d6520 | note | Method/Description - Red Pen Mark up
96a442d1-51b2-58fb-8c6a-9faa90e5fc92 | note | Test frequency - End of Construction
464ca93d-6b25-544b-a8d5-12229c34574b | note | Contractor - H
e733f8c7-53c6-5be1-a3de-610e2867dd0c | note | Designer - H
c8c4f16c-a75c-5270-82f0-708815469c7c | note | Verifying Records - Red pen mark ups
da8801c3-a745-57ae-8ee9-97e0c79c7f28 | signoff | AUTHORITY HOLDPOINT
cefcef9d-53d6-4c93-b4f4-9d94350a9600 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
130d003e-15e4-4636-a9a7-b175f92d1bdf | checkpoint | ITP Close-Out by
c4577bd6-d6f9-502e-bc50-dda3d65d0743 | note | Site Engineer/Project Engineer
f380107c-d87f-5e54-9489-e1df87b2fcfc | note | Zone Manager Approval
f5a1c8e5-1331-5cfa-9772-4c5e24b10127 | note | Construction Manager Approval
ff845d6d-879d-53c9-b282-21d7994b0ebd | note | Quality Manager Approval
b598fd83-e66d-5fce-953a-0e612cd022ab | date | Date:
678dba56-63f5-47ef-82c5-b6e3c4bcf5b8 | signoff | SIGNATURE
78c2c92e-36d9-5895-8493-9ad0f06587a4 | checklist | SYS - ITP 004 Earthworks Cut |  | ITP 004 Earthworks Cut
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
b8036728-618f-5223-862b-4d5d9b7392e7 | checkpoint | 1.01 - Approved CWP
b9b05130-21d0-59f5-81b8-3a1a66ee3588 | note | Method/Description - Document Review
cca29099-c6de-57fd-ae2f-5ea7651289fd | note | Test frequency - Prior to personal starting
4905a6bb-47b9-5612-ae3f-f47e06a3b0f0 | note | Constructor - H
1f5798a0-6591-5954-918a-aee49800be2c | note | Verifying Records - signed off CWP
8bba7d2b-c99b-5bc4-a108-87b749bd8128 | checkpoint | 1.02 - IFC issued
24af5ac5-dc0f-5572-9f8f-f968599806a2 | note | Method/Description - Document Review
d029f256-64c1-5d38-8894-c6b955988ec4 | note | Test frequency - Prior to starting
9ccc7c7c-c593-53c9-9870-a2b85c4ac74e | note | Constructor - H
72f7fbe8-8bd4-59ac-ac7e-03030dbfa37b | note | Verifying Records - IFC drawings or written approval from PAB
c1036124-090c-538f-921f-e077596a4d48 | checkpoint | 1.03 - Approved SCWMP
0f4c9061-2d18-5631-8ae0-0ec860083288 | note | Method/Description - Document Review
a327f40c-0cc6-5dcc-a5dd-6af44d88cad3 | note | Test frequency - Once prior to works commencing
e23ce9b7-d559-5ade-84ab-75a9ecf1e255 | note | Constructor - H
3080528e-d0ce-5ac5-86cf-2503bbfaeec7 | note | Verifying Records - Approved SCWMP
431dec39-58e7-5089-ad02-f482ccba3585 | section | 2.0 During Construction
f6ede248-e8c1-545c-a833-6b2657cc9e14 | checkpoint | 2.01 - Set out extents
103bcb86-e5f6-5c01-af96-35bd1d9e7fee | note | Method/Description - Survey/visual
262daded-4c81-56e9-8f2d-3e49f5dff431 | note | Test frequency - Prior to Commencement
1ea47dec-8e81-5dcb-a913-446cacda69f8 | note | Constructor - H
deb203b7-5718-5616-9630-a1d5c9b53cb4 | note | Verifying Records - Earthworks Cut Checklist dsr reports
0ae64486-0c22-5720-9019-21e5033b47c2 | checkpoint | 2.02 - Verify Machine Control
1eb179e8-4c86-5fa2-9225-acc058072e50 | note | Method/Description - Survey/visual
ff8ab6ca-fe21-580e-91cd-305bc4ec1caa | note | Test frequency - Daily
0bd6ade8-f046-5723-bd0b-cff871f84ada | note | Constructor - W
81b1d103-1a86-5f80-98b9-ade368456739 | note | Verifying Records - Plant Pre Starts
cdc6721c-be76-5a77-a6e9-fb7d20e019f6 | checkpoint | 2.03 - Assess Crest detail
f3ac45c9-18de-5552-a055-bfe70ec804e4 | note | Method/Description - Hand augers/ slope assess
b75a31c8-d7b1-5a3f-9647-11984d4d8ef7 | note | Test frequency - Prior to Excavation
d2943094-13b2-5e7a-a39e-0717e6228ecc | note | Constructor - H
5cbe8ddb-a41b-53d1-8cde-c352d85b9596 | note | Designer - H
bafc3aed-08c4-5976-9598-1264d363e6e2 | note | Verifying Records - Earthworks Cut Checklist dsr reports
62ebec08-b5d3-543d-8d00-87f19d4c604c | signoff | HOLDPOINT
5c3c338c-b063-551e-b0b7-0e856fe79964 | checkpoint | 2.04.01 - Install crest detail: Soil Nailing
adac4e33-95b4-5458-9ce8-697f3b3b7dbc | note | Method/Description - Visual Inspection
d9512120-644e-57a0-b43a-c5e04cd770db | note | Test frequency - Prior to cutting rock slope
84f258ea-3834-54e0-8cbd-ed1f3850922c | note | Constructor - H
a3a10b54-2402-59ce-bb85-8f6c786ccc34 | note | Designer - H
8aa35759-d24a-5aaa-a711-b1cb733df60c | note | Verifying Records - Sub Contractor QA Records
8b97e7a6-81b9-50df-be58-21d6af314de7 | signoff | HOLDPOINT
f30a4918-4290-51f0-a1be-99450e886872 | checkpoint | 2.04.02 - Install crest detail: Erosion Matting
d57b4711-e40c-53cf-8d1b-f0876f8d9957 | note | Method/Description - Visual Inspection
95465785-0b13-5703-9136-61773491d56b | note | Test frequency - Prior to cutting rock slope
93f1b126-b28e-5388-a0bc-f4e064b993de | note | Constructor - H
c5badbe0-bac7-5e2b-93aa-25331a045951 | note | Designer - W
5778f670-eae3-5fd7-bc03-4203a0c7e7ca | note | Verifying Records - Sub Contractor QA Records
a7894671-f77a-5d3a-b48f-1542784fc7c0 | checkpoint | 2.05 - Cut Face inspection: Cut Face inspection
acfa0d9c-0bcd-515d-a750-0c97ef4b5f5a | note | Method/Description - Survey check by construction team, visual inspection by designer.
31f04f6c-d015-5817-98c6-d1fe5971b4ce | note | Test frequency - 100m2 or maximum 5m vertical cut
41ae2613-b497-5a9d-a029-654d7e2bd51d | note | Constructor - H
59fc9c46-102d-5bb7-a357-2a09a166aedf | note | Verifying Records - Earthworks Cut Checklist, Survey record, As-built
e71b20ad-af3e-5881-ae40-bfe327f63f04 | signoff | HOLDPOINT
934315ef-3c81-5654-a0e0-c67605217f9b | checkpoint | 2.06 - Cut Face inspection: Cut face material verification - Geo mapping
4d6bb129-d861-5f8e-81d3-dc1f94ac6fee | note | Method/Description - Geo inspection and face mapping
a8b16777-a627-5be9-9840-c87648cdc4cf | note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
f226a919-790e-56f6-8c3b-36bbcf89b915 | note | Constructor - H
056b5fad-0b37-52be-a52d-471442da127d | note | Designer - H
5b8b5c68-2bae-5e3c-824e-c2b2f5d84c39 | note | Verifying Records - Earthworks Cut Checklist dsr reports, And face map from geotechnical engineer/geologist
3aefa3ef-87ce-57ab-bc69-a63002c032ef | signoff | HOLDPOINT
9db09d53-bc11-59cb-adc2-7fb9c6a10f61 | checkpoint | 2.07 - Install Rock Drape: Set out drape anchorages
5183685a-f9a1-54de-b5a8-55d252383bd4 | note | Method/Description - Geo walk over
2265fabb-5f12-543f-974b-43bbd5ab3478 | note | Test frequency - Prior to drilling
8fb6da51-6d90-5d71-8c95-1facf5504a92 | note | Constructor - H
b3d8e1dc-497b-5d87-acbe-02ca013aa778 | note | Designer - H
0cdcf132-3e26-5085-8ea2-a1f512f388e8 | note | Verifying Records - Sub Contractor QA Records
7b3a43d4-ea6a-5ddb-b725-bed4c7b54432 | signoff | HOLDPOINT
47491151-84ff-54fa-8320-f77c5d526623 | checkpoint | 2.08 - Install Rock Drape: Install anchors
c5eb9fb5-a4ec-5c94-b7dc-4604772bf060 | note | Method/Description - Drill and grout records. Stressing records.
dfa0837c-37da-5a6d-8c65-32929a1f1296 | note | Test frequency - During construction and at end
6ae8403c-b05a-5a44-b2a3-25561d0b3959 | note | Constructor - H
8258a11a-e5cc-52de-97d0-f25ba8a92110 | note | Designer - H
ebacc7f3-1f60-5c72-8025-72696e0ca23a | note | Verifying Records - Sub Contractor QA Records. Calibration certificates for stressing equipment.
2acca676-cc5f-5b8c-984e-e398c66c2a65 | signoff | HOLDPOINT
48b7361f-fd28-52f3-8622-7a5ca66eb740 | checkpoint | 2.09 - Install Rock Drape: Install Drapes
fc21ffbb-bd96-598a-96b1-6db9e1946805 | note | Method/Description - Visual inspection
8072ffbf-0279-5439-9379-5d52e34ff66b | note | Test frequency - During construction and at end
de624760-9f81-522a-9b58-c0003f7f368e | note | Constructor - H
bdff8204-3322-5084-8aab-73333ca33573 | note | Designer - H
4cf2dc7d-1a23-5873-981a-c1c24b4001d4 | note | Verifying Records - Sub Contractor QA Records
72c006a3-13d5-503b-bbf0-c34024ba7575 | signoff | HOLDPOINT
21ddba91-27de-5694-bb2a-98f394afc87d | checkpoint | 2.1 - Install Rock Bolts
87b32ff1-a65e-5141-bc7f-05d8afa61fe4 | note | Method/Description - Drill and grout records. Stressing records.
c40dcf3d-f43c-5a07-92ef-f797e8f4187b | note | Test frequency - During construction and at end
2c83b556-60d1-58ed-ae76-55188c239b0f | note | Constructor - H
4d079ed6-1e69-5da2-ac1b-b1da20dea177 | note | Designer - H
9ee04451-2404-5d7e-90b8-340826f2ec8a | note | Verifying Records - Sub Contractor QA Records. Calibration certificates for stressing equipment.
aa407136-e50a-5459-ab59-b934fc5eb599 | signoff | HOLDPOINT
7b64d5a1-622f-557e-8925-2010edc9dfd3 | checkpoint | 2.11 - Catch Ditch Inspection
00e58ffe-037b-545d-bace-5b883e0647b3 | note | Method/Description - Visual inspection
750aae21-4e55-55ee-95d8-d2214481286c | note | Test frequency - During construction and at end
38c24efb-1c17-5bfc-8867-5830c39a3cdb | note | Constructor - W
1b2daf5e-43d3-523f-9929-d91a9a0cbfdc | note | Designer - H
49901b71-e92f-5910-92b8-f91214a6bb2b | note | Verifying Records - EarthworksCut Checklist
c5d3be53-a967-58fe-8fd5-67d36a5de4bc | signoff | HOLDPOINT
d5545795-84a2-5564-99ac-44165c0761fb | section | 3.0 Post Construction
447a125f-d49a-53d6-b7b4-33f92b5beae1 | checkpoint | 3.01 - Rock Fall Test
01881ecd-5f95-53d8-9234-8808dd9fbc0a | note | Method/Description - Visual inspection
f6e238b7-83bb-57db-8393-f9fd6e598922 | note | Test frequency - After catch ditch is formed at each rock cutting site
20517f6f-4dc0-53d7-b6cc-bda6897dc3a5 | note | Constructor - H
b50f0b20-1e92-5d53-b575-7fa220612f21 | note | Designer - H
c8176c17-9c21-5b7c-830f-603325d44830 | note | Verifying Records - Designer assessment Memo
d2f9c6be-4f78-59d7-bc8b-c894326e9ac4 | signoff | HOLDPOINT
4c3f9085-940f-5e68-a868-e06bbbc712b5 | checkpoint | 3.02 - Survey As-builts
96e8f962-2b54-5686-b51d-3c930ba3629b | note | Method/Description - Survey As-built
adec30b1-222c-5cca-9b84-a8fff78f3ce7 | note | Test frequency - During construction and at end
696c0ab2-add1-5162-a27c-a6be042143f9 | note | Constructor - H
d0445372-fb8a-58cc-a492-62a96ba38b50 | note | Verifying Records - Digital file
d53f93fd-7c54-5619-82d9-9c68b8b077b1 | checkpoint | 3.03 - Monitoring Data
a4a65e69-72d3-54bd-bff7-c79b0236a9e3 | note | Method/Description - Visual inspection and review of monitoring data review.
849a4e4b-61b2-5118-bf7b-39abb9f6c1c8 | note | Test frequency - End of construction
3bcde90b-3f05-5b5a-b4d3-04605f0478fa | note | Constructor - H
3e6bdc87-1ffa-51a4-b7e2-789510c68974 | note | Designer - H
5204e30e-6e3d-59f7-8aaa-6c8263b29352 | note | Verifying Records - Digital file
d5ad98fd-d977-5f94-8be6-225d9ad2ec7d | signoff | HOLDPOINT
82937e25-4885-5d7a-be8e-ea951f14bc73 | checkpoint | 3.04 - Red Line Mark Ups
ba02192f-3b0c-5b84-a1cd-58a1b7a4a369 | note | Method/Description - Red Pen Mark up
b040b799-4cd0-5bc0-984a-70a0dc98eace | note | Test frequency - End of construction
cdedf424-4590-5f49-a9f5-e4f800f21a12 | note | Constructor - H
8c2ed140-05e6-564e-84d1-1868fec32d9d | note | Designer - W
ed08f1da-48e6-5d19-83b3-e1012293eca4 | note | Verifying Records - Red Pen mark ups
8919eff8-fed3-572c-bcf7-d24e7712e7ba | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
45524c2d-1de8-5e60-b52d-1f4484181dd2 | checkpoint | ITP Close-Out by
8daf5f14-6013-5009-b236-3638f2c275a6 | note | Site Engineer/Project Engineer
8bd05865-687b-56e2-91f9-d1b0d8ddae3e | note | Zone Manager Approval
71e00a12-d4ba-542a-b192-34ec02325679 | note | Construction Manager Approval
1469c7f4-a2de-515e-be40-4a582d94c73a | note | Quality Manager Approval
7eb7055c-3586-51f9-9375-bb33d9b0c07a | date | Date:
1dc2c9d0-048a-5501-9488-936d3248a797 | signoff | SIGNATURE
b071e353-4214-5842-b772-a8958808af3f | checklist | SYS - ITP 006 - Drainage - Access Track and Stream Diversion PKS Installation |  | ITP 006 - Drainage - Access Track and Stream Diversion PKS Installation
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
25cb42ef-7d50-5dca-89f5-4c29a78ce685 | checkpoint | 1.01 - Confirm CWP Signed off
8bcca5d2-2976-5a23-b405-c6d60403e2c7 | note | Method/Description - Document Review
596fcf40-f136-57c5-b157-a2026b0750f5 | note | Test frequency - Prior to Work
914272b8-2591-57ba-8b32-66cbde1c092d | note | Contractor - H
ce7bd977-6308-5ba0-8caa-bcb8124f28fe | note | Hynds - H
5cd0f26c-3486-5983-a10b-64ebfe083bb7 | note | Client - H
a70b1538-7ab2-5367-b91b-fbad9a2c2b0b | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Copy of Method Statement
90528568-7dbb-505b-b32d-75da79ee0256 | signoff | AUTHORITY HOLDPOINT
5c8b235a-89c6-5bc2-95c3-af3747fcf89a | checkpoint | 1.02 - Confirm Compliance against Resource Consent & Management Plans
34056558-ffa0-5201-9cbe-64991ed1eee5 | note | Method/Description - Document Review
960eba53-f532-5268-8712-6315c1f919c3 | note | Test frequency - Prior to Work
476a2b2a-cca6-5fe4-9472-b248f2e1ecc0 | note | Contractor - H
5d933087-1e33-57c8-9f59-ea2d8a93b731 | note | Hynds - H
08ecf120-7547-5d3e-9034-0795223f7415 | note | Client - H
2c0d4747-0a14-50bd-9c2d-5f8abe5c4780 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Management Plans, Approved SCWMP and Approved CWP
80f44c70-59d0-5d07-bf6f-65b719d78da8 | signoff | AUTHORITY HOLDPOINT
5e649741-08e8-53d7-90e2-13e62ad83986 | checkpoint | 1.03 - Confirm Design is in place
3fa3020d-d5fa-595b-8997-cbc3df6ab9a2 | note | Method/Description - Document Review
b55513d7-aff4-5d1b-b59f-448213c77dd9 | note | Test frequency - Prior to Work
270616d9-4f18-5544-8286-f403e79e2939 | note | Contractor - H
ace7769b-523d-51fd-822e-b72ceeef6121 | note | Hynds - R
f29e2e19-05a2-5629-a09d-20cc11a5c036 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings
3e4ca7a6-fdcd-5bc0-9f74-9e85ab2206e0 | checkpoint | 1.04 - Complete Permit To Dig
af02e228-acc9-54cf-9a3e-36242cec0f72 | note | Method/Description - Document Production
1f54f34e-5794-5d1a-bd82-926f0c86727c | note | Test frequency - Prior to all Excavation works
6d47b75e-8b10-57e6-bbef-dc38a33cad7a | note | Contractor - H
6150d923-7e62-5da7-ba68-907c67f93212 | note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Dig Form
ed3b9c61-8190-5c6b-bc78-3deea876281e | checkpoint | 1.05 - Survey
9730b2b4-d46c-5e42-a1ae-692deef46d6e | note | Method/Description - Record inlet and outlet heights for the stream diversion. Mark out scope of works
4d07a43d-8960-5c0e-b316-015a3e30f74a | note | Test frequency - Prior to Work
5309efbf-ad8b-5a9a-99a7-38d6467979c8 | note | Contractor - H
152f6c24-ecfe-5867-8f14-ad95ef1b88f1 | note | Hynds - R
223ffcb4-c380-5273-b0c5-44d06cace32f | note | Verifying Records Checklists, Test and Supplier Certificates - Survey Heights, Survey Mark-out
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
276596e5-622f-540a-b5fb-f058d6208be7 | checkpoint | 2.01 - PKS pipe (1400mm, 900mm & 800mm)
b06cb1e0-db13-5f81-b7cc-421395cfedb4 | note | Method/Description - Document Review
2de5d1f6-0b15-552b-9ae9-c60845cc3631 | note | Test frequency - All PKS pipes
271ef182-0804-5ac6-a12d-4e5c7b25e43c | note | Contractor - R
1e0c9aea-6f5a-5eea-b0d1-05f17118606e | note | Lab - H
dc5630ab-1c5c-564d-88fd-b67809ac8e65 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Lab Tests
2b0c4440-9e92-590b-8648-3562a3bdd6ac | signoff | AUTHORITY HOLDPOINT
437e53b9-8816-57a5-8687-f2b95e8eadd2 | checkpoint | 2.02 - PKS pipe fittings
f932ecbc-b8ee-5dd0-9a4c-7c567961ab1a | note | Method/Description - Document Review
dfbe90df-f533-5e42-a64b-e3f461674ef4 | note | Test frequency - All Fittings
83fd9542-eb46-5a0c-b6a9-0b911ecdc1d5 | note | Contractor - R
c374d92e-68f5-52a4-97cd-cc5468747a9c | note | Lab - H
603d3e25-09ff-5064-8c8c-ee2ec0a80ccb | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Lab Tests
c5f6844e-e2c3-5736-b591-d9b8a313842e | signoff | AUTHORITY HOLDPOINT
f0fafa0a-7d8b-52d3-a270-8e95cd73cf98 | checkpoint | 2.03 - Subsoil Pipe
1e2c4e12-4456-54ca-98ce-23e9afca0bd4 | note | Method/Description - Ensure Pipes are ordered as per drawing
df6de802-7bb9-50a9-8aa6-8d422b96aba7 | note | Test frequency - All Subsoils
37113ea6-9d63-5b69-9d08-41fe777895f4 | note | Contractor - R, I
a0d873da-bb0f-51c7-8c75-c371e5c812a7 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
18fcaed8-c292-5c18-b5e2-81222a052df4 | checkpoint | 2.05 - Geotextile
6abcee02-d71e-5353-9406-568821dc632d | note | Method/Description - Document Review
232e368e-b197-5f21-8168-2b48ba57e51b | note | Test frequency - All Geotextiles
b11614e8-3f0a-56f2-86b2-de669b5e7fc2 | note | Contractor - R, I
7b82b63b-2b35-561f-940e-4592ea2aa393 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
1c4ee408-b787-5f05-9623-9c6acb31d725 | checkpoint | 2.06 - Drainage aggregate
df6c7a2a-83f2-5829-9495-8dd85be80236 | note | Method/Description - Laboratory Testing
cdaaf44a-989d-5b0f-ae69-7240c3d030b4 | note | Test frequency - Embedment material
f58b17e0-177b-551c-9062-be0282493020 | note | Contractor - R
c099be62-f1b1-54bc-9c86-bc290562861e | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Results, Crushing Resistance Test, Confirmation of Material acceptance from Designers
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
3212d783-a144-5989-a497-6dc108eb26ac | checkpoint | 3.01 - Trench for PKS
3977f772-33d4-57e6-90b8-2feb495543bd | note | Method/Description - Inspection
e8a5eb11-0157-5a7a-8fba-cdf5b9fdcb59 | note | Test frequency - Prior to BIDIM installation
0d032c5e-9f49-589e-b2cb-52b52f4b433f | note | Contractor - I
20752364-a489-58c8-bc4f-5a04546530b4 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
aa967d00-f53d-5a11-aac7-dac3cb7ed00a | checkpoint | 3.02 - Insitu subgrade (foundation) Compliance
a8c0c653-f9d9-5249-9319-bfd0314824ee | note | Method/Description - Inspection
d3ba65cc-f58a-5014-9287-8ada3d77f468 | note | Test frequency - Checksheet filled in for every 100m section of drainage
4c222a4a-3879-512c-b4f2-6f94eba25e25 | note | Contractor - I
70fbe8e1-f018-5077-8251-bae2e11936cb | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
a6f1c758-656b-5240-862b-c139a4e5de79 | checkpoint | 3.03 - Lay Geotextile (BIDIM A29)
ebe45091-9fd6-522b-a2be-340c1bc986f1 | note | Method/Description - Inspection
bead50f6-cbb5-5b7e-8a8e-80b8190fa3e1 | note | Test frequency - Checksheet filled in for every 100m section of drainage
84d60d6e-d840-5b67-bb17-03d3c2d37533 | note | Contractor - I
f2c15657-8d2f-5f98-98ec-3739dee09921 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
49eaf908-2e12-581f-a669-34aeaf41b1ee | checkpoint | 3.04 - Install Bedding Material
3052fcf5-adac-5953-94fe-08aee1b89c9a | note | Method/Description - Inspection
8aa7b042-497a-5f83-84fc-56f7c3d1d02c | note | Test frequency - Checksheet filled in for every 100m section of drainage
9067b1fc-854b-53f7-bc24-12544cbb1ada | note | Contractor - I
6f7a9cd3-1457-536c-84c2-a59272032605 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
58e93f70-4a80-5048-aca7-98b095e4b403 | checkpoint | 3.05 - Survey pick up location and heights
040d3231-b354-5c54-9ce1-8a3565693a52 | note | Method/Description - Survey pick up
fa1e1bdc-a7c8-51c8-b34b-c0d3cebcc5bf | note | Test frequency - Picked up location minimum every 100m
aefefd22-5e33-55cb-9e46-25743eaee2a0 | note | Contractor - H
02914537-456f-5a3a-9ef0-03e65e99b61b | note | Verifying Records Checklists, Test and Supplier Certificates - Survey record
20ab2a1c-5777-58bb-b116-74a612dcf678 | checkpoint | 3.06 - Install PKS pipe
abf8ce50-12bd-500e-aeb4-df6600783a89 | note | Method/Description - Inspection
244d6350-dbfb-57e3-9156-80d9806181ee | note | Test frequency - Checksheet filled in for every 100m section of drainage. Hynds inspection once at start of Works.
d6a34e46-217e-5e8e-9213-f8842cf24615 | note | Contractor - W, I
7e620971-3b53-5329-af4f-f37450836102 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
c9866cdc-da9a-5642-919e-bc2cee48d5bb | checkpoint | 3.07 - Install side support embedment material
440be4b5-d534-50ef-a6c7-4f0b0b8d06e6 | note | Method/Description - Inspection
879f454b-bd86-5b94-9a4b-775d230bda64 | note | Test frequency - Checksheet filled in for every 100m section of drainage
0ec9c69b-8080-55dc-b629-314ab5f88c15 | note | Contractor - I
b06f40dd-10f8-5f79-a209-6ebfc55208f4 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
a21bcbfa-81b7-53c2-bdc3-81d407ba28a0 | checkpoint | 3.08 - Install overlay embedment material
5daa1abf-1d51-5d22-8d25-b2778c9e14b2 | note | Method/Description - Inspection
950c6c35-8e94-5d5c-b0af-42f73473c9a3 | note | Test frequency - Checksheet filled in for every 100m section of drainage
a3f368f2-6f89-531e-af54-4dab17c427e8 | note | Contractor - I
b25648b8-be95-5d7a-9ead-06d5d13d43ad | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
3b075c01-8664-586a-af05-3b593bc393d7 | checkpoint | 3.09 - Wrap Geotextile
f880db3f-6fba-5897-a26e-fd6c967d1fd4 | note | Method/Description - Inspection
1121fef9-fb6a-55e0-adc3-52a93be20d8e | note | Test frequency - Checksheet filled in for every 100m section of drainage
6fb29771-c5bd-5ccd-8242-6062b1db58bd | note | Contractor - I
28e60a39-7acf-5806-b945-d43365d7222b | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
85910491-7d0d-55df-8a28-bc8442b458f3 | checkpoint | 3.10 - Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top
dbd0b7a1-a2be-5ec2-b340-53cdc03d5b30 | note | Method/Description - Inspection
a81c3316-cd58-54b0-9aca-a135186dd12e | note | Test frequency - Checksheet filled in for every 100m section of drainage
f748059f-174f-5691-9e36-6d688ef30e5c | note | Contractor - I
5100807d-70d9-515d-94c7-ce73b075e195 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
768d3ea8-4aa7-5499-b4df-1095b7adf573 | checkpoint | 3.11 - Spat Rope installation
26fb15df-8f1c-5fc2-9927-977c0216bfd3 | note | Method/Description - Inspection
f389ccce-38c8-5466-a680-6cef979a2879 | note | Test frequency - Checksheet filled in for every 100m section of drainage
a3039d5f-16f3-5594-96cd-ad67855d4841 | note | Contractor - I
a32cb2d9-99d4-54bd-9179-a784e4a84c0c | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
5b2bf91d-9fc6-51c5-8e1e-5861949c524a | checkpoint | 3.12 - Construct inlet and Outlet structures
0debb97a-37cf-5e40-91c1-af9269a59654 | note | Method/Description - Inspection
96c1baf3-ef5a-5846-9dab-4d01f267ad65 | note | Contractor - I
a831b8a8-7715-514c-b650-4b7b6359cbc0 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
c815dfd0-5dcc-5cc4-9c68-7c8d5d947fd0 | checkpoint | 4.01 - Install culvert screen to catch debris
4ab8e6dd-0aab-5add-b907-365591572736 | note | Method/Description - Inspection
799d5670-42e5-56fe-abe7-2f3c64b5f83e | note | Test frequency - N/A
fee25ee8-e98b-522e-bb8c-9cd932df95ad | note | Contractor - I
5b8df720-9ca7-5ae8-a81d-997056d6c93b | checkpoint | 4.02 - Provide Maintenance and Inspection Report/As Built
d1d19c64-3d49-5249-b158-ed8c6fe54809 | note | Method/Description - Maintenance and Inspection Report Completed
d71fd21d-0ecc-5b3a-a2c5-bb49a68bac7f | note | Test frequency - All Temporary culverts
79b5c7e6-7a1a-52ef-9bcd-2c261e157190 | note | Contractor - I
ddbff481-7bcf-56e2-802d-cec814301f0d | note | Hynds - R
10203b48-48b9-5a03-b653-dfd45f5dc6ea | note | Verifying Records Checklists, Test and Supplier Certificates - Maintenance and Inspection Report including As Built Plan & Photographs
e4682236-23b4-4423-a017-c85f91186ff0 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
709ae6a2-5203-4b94-b61e-eeec4b5f5d01 | checkpoint | ITP Close-Out by
6092af0d-34d8-5cb7-832a-92c39bd8bec3 | note | Site Engineer/Project Engineer
5d071146-e630-5827-a9f1-cebf39cb5f8e | note | Zone Manager Approval
6689418b-e9c7-5f81-a815-04d383c345c1 | note | Construction Manager Approval
89648402-2784-5c0b-8411-8b606ea65cec | note | Quality Manager Approval
6ab5c8c7-19ad-5112-b570-6a6f759ea3a9 | date | Date:
95696420-dfde-4589-82df-3d2323e75c32 | signoff | SIGNATURE
9f2048db-5d6d-599e-93ac-9673bd2bfd6e | checklist | SYS - ITP-003 – Subsoil Drainage Install For Season 2023/2024 | itp | ITP-003 – Subsoil Drainage Install For Season 2023/2024
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
840d7178-b03e-537c-b111-82e872a14b9c | checkpoint | 1.01 - Confirm Method Statement Signed off
411bd5c4-b550-5426-8642-6e9d38cedd5a | note | Method/Description - Document Review
f6ff0115-1f4c-5d65-84e0-4a72c28bf9ca | note | Test frequency - Prior to Work, Once
b9764723-8ab4-5c67-9161-c65c2a44bca2 | note | Contractor - H
a3fc211d-6b84-5b39-a13a-b983ebbf904c | note | Designer - H
7e6343fc-ee4e-526f-9ad7-299d1c34eb9b | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Copy of Method Statement
42bc0245-639c-57f9-9f09-8f12305c24ce | signoff | AUTHORITY HOLDPOINT
5c8b235a-89c6-5bc2-95c3-af3747fcf89a | checkpoint | 1.02 - Confirm Compliance against Resource Consent & Management Plans
420fd7b7-423b-5959-993b-c73d42531c56 | note | Method/Description - Document Review
c0e5bc45-3814-5ff4-8b3b-a565b622cff6 | note | Test frequency - Prior to Work, Once
8bc82449-2207-5d7a-96f3-793f9ca06ac7 | note | Contractor - H
ee6e2cd8-d98a-5e50-8c59-1804da061700 | note | Designer - H
d9d381ec-bfa8-5bee-899c-969666ee4ecb | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Management Plans, Approved SCWMP and Approved CWP
80f44c70-59d0-5d07-bf6f-65b719d78da8 | signoff | AUTHORITY HOLDPOINT
a7abe052-25a4-5b64-9ac8-d2d5e962d5e3 | checkpoint | 1.03 - Confirm IFC Design is in place
5cbb18ad-918d-5405-baf8-81fe5da2b49a | note | Method/Description - Document Review
44f5de07-bec1-5e35-9c1d-3dbfd9464002 | note | Test frequency - Prior to Work, Once
3e53d722-fa25-56af-a398-678a5682fc0e | note | Designer - H
52e4814e-6fe0-54f8-8f1f-0538178473a1 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings Issued
124b501d-73e4-53df-a8f5-6b9175b379e6 | signoff | AUTHORITY HOLDPOINT
3e4ca7a6-fdcd-5bc0-9f74-9e85ab2206e0 | checkpoint | 1.04 - Complete Permit To Dig
6c102f09-b37e-5afb-9f26-f77c2b9aaf0b | note | Method/Description - Document Production
7fa5eb99-b91d-5ad4-a556-531062f8850e | note | Test frequency - All Excavation works
e699e163-c0cf-5681-8f18-b79553cb4f80 | note | Contractor - H
22edda1f-88cd-53b8-aea5-1fcfe52e7623 | note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Dig Form
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
e86f10e9-8b19-553f-804e-38c741e160bf | checkpoint | 2.01 - Order Subsoil Pipes
af305bec-6dca-5765-b4f2-db988afa71b5 | note | Method/Description - Ensure Pipes are ordered as per drawing
58b89afa-b730-5c29-8e64-326ba59444aa | note | Test frequency - All Subsoils
aaf13ecc-db2a-5c90-b8f9-81bdf5689aee | note | Contractor - R, I
4c61e2ae-16c6-515a-ae67-2009a7fad8cd | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Material Complaince Certifcate/Data Sheets, Material Delivery Inspection Checksheet
c73d4d38-f592-5050-beca-bb24f088b3c2 | checkpoint | 2.02 - Order Geotextile Material
89d6f497-7bfc-594c-8eb7-f5bf197f03de | note | Method/Description - Document Review
ed503d8c-d3ee-56a7-95a4-7d45becbd6f0 | note | Test frequency - All Geotextiles
6dab2856-732b-5149-bb06-32b809f5eebd | note | Contractor - R, I
f6b1b5ff-c92c-5653-ab33-115f67ed0fb4 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
d741fc1d-dd82-5c6d-887a-c3e4e41fe079 | checkpoint | 2.04 - Order Subsoil Drainage Backfill Material
622bff40-4a90-54e1-ac66-8edb6738428f | note | Method/Description - Laboratory Testing
c03b408a-b9c9-5dde-a71e-959b63c50f10 | note | Test frequency - All Material
6e3b59f8-2e8a-5963-b6e3-3d0ed4beccf3 | note | Contractor - R
fffe0c0f-4766-5f30-bcb7-3d94a3257e7b | note | Designer - H
06f57223-d4a2-5114-841e-5138808b0dbf | note | Lab - R
31c62d6a-1468-5b2c-a597-e96682946414 | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Results, Permeability Test Results, Crushing Resistance Test, RFI - Confirmation of Material acceptance from Designers
6ab3c3a9-4260-5c59-9e2e-57263c4a3e85 | signoff | AUTHORITY HOLDPOINT
3e07f1f2-f893-5997-ab8c-2f8ebbc67b8c | checkpoint | 2.05 - Order FarmBoss Pipes (Temporary Drainage)
30bbcc20-5408-5d2e-bbb9-6a5cc69851f3 | note | Method/Description - Document Review, Material Delivery Inspection
097d041c-1f47-517b-ba4d-56ce9da6c904 | note | Test frequency - All Pipe
54e4c6d4-86dc-5dc4-8573-38697687ca70 | note | Contractor - R, I
b2774fba-4484-5c97-9af9-b270674f6e74 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Docket, Material Delivery Inspection Checksheet
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
3e503167-dfec-5627-8b25-d5091f7b1f38 | checkpoint | 3.01 - Clearing and Stripping of Area
54a0b372-b788-5f8c-8fd7-89a9b8adf917 | note | Note: Fill 12 and 13 are exempt from Organic Waste Clearing and Stripping when >5m from finished ground level
7eba61e1-a678-5b88-9a49-d2db0087350f | note | Method/Description - Removal of Organic Material
bdb87169-5d7d-5d33-8552-99ef9253825d | note | Test frequency - All areas. Subsoil Checklist completed for every independent section and minimum 100m length.
8d14f524-c053-58df-8c51-56f43d393668 | note | Contractor - I
cce81a3b-409a-51fc-9e95-83e31b1880d2 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual Inspection
d731f851-5a53-5724-9682-975128810a16 | checkpoint | 3.02 - Inspection and Confirmation of Foundation Subbase (Designer shall be notified 24 hours prior)
f3036a5d-b13c-5a63-88a3-3ad0e220544f | note | Note: Fill 12 and 13 are exempt from Organic Waste Clearing and Stripping when >5m from finished ground level
73ba8bc8-6bab-599d-880a-2e0ac03881d2 | note | Method/Description - Visual
c5c8c29f-0e83-5d1a-bd36-890b925bcb8a | note | Test frequency - All new areas opened. Subsoil Checklist completed for every independent section and minimum 100m length.
12b260a7-1688-5966-a01b-82021a9ef5d8 | note | Contractor - I
908813d1-8520-5971-8f63-9195c1247d12 | note | Verifying Records Checklists, Test and Supplier Certificates - Designer Site Report Issued, Visual inspection
3ffb03be-3168-5ad5-a602-7618f3bca33c | checkpoint | 3.02 - Formation Level Inspection
f3036a5d-b13c-5a63-88a3-3ad0e220544f | note | Method/Description - Visual
73ba8bc8-6bab-599d-880a-2e0ac03881d2 | note | Test frequency - At formation level before installing the geotextile. First section of pipe and then once every 50 m of pipe laid.
c5c8c29f-0e83-5d1a-bd36-890b925bcb8a | note | Contractor - H
12b260a7-1688-5966-a01b-82021a9ef5d8 | note | Designer - H
908813d1-8520-5971-8f63-9195c1247d12 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
264dba25-731d-5ed7-a78b-a7a629fa9437 | signoff | AUTHORITY HOLDPOINT
a6f1c758-656b-5240-862b-c139a4e5de79 | checkpoint | 3.03 - Lay Geotextile (BIDIM A29)
b0109de6-b404-5c76-83d0-ee683c2dfc73 | note | Method/Description - Inspection
8a80bde1-54b6-543b-b6c2-cda6cba54adf | note | Test frequency - All BIDIM. Subsoil Checklist completed for every independent section and minimum 100m length.
24ab384e-d96a-5aee-8fd9-df1dbc3afed3 | note | Contractor - H
ebdc72b7-9bbb-5a3d-a0bd-4a4bcb2818a5 | note | Designer - R
21353ae2-3c95-5f46-a40e-3f9a08d0b24a | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
64925617-a85a-5a43-bba0-7650792c7468 | checkpoint | 3.04 - Install Bedding Material for Subsoil
b1b5b860-f0e8-59d4-8346-be74e228a313 | note | Method/Description - Inspection
1932a309-a32e-55fc-93d9-935909f265bb | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
b5aa431b-d802-58d1-9bbb-f308f7575c4f | note | Contractor - I
9d45cff1-e3db-556c-af76-eccfe60a67a3 | note | Designer - R
a401c1cf-1d25-578f-a88d-dddeb91d97c4 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
48dfe27e-ff7a-521b-bae5-f5f55a05dd96 | checkpoint | 3.05 - Install Main Gully Subsoil
d93d3077-04f3-546b-b3be-ac4b4e79bcd9 | note | Method/Description - Inspection
674c2c76-db0e-5354-9d19-d1bba290b267 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
70ae588f-5643-5ac0-b22f-66abfa02029d | note | Contractor - I
6726ff69-0b15-5532-9c98-d9bc9e2801b3 | note | Designer - I
def36970-6afd-5238-9837-484c1143cf7b | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
90d6e7a1-cbd8-5795-bbe8-f63561ce30fc | checkpoint | 3.06 - Install 450mm FarmBoss (temporary Additional Drainage)
8b8f3e16-dd01-5675-92a4-435fab8755d0 | note | Method/Description - Inspection
8fbebcb2-31f7-5f10-b82e-ddee47f53f77 | note | Test frequency - All FarmBoss. Subsoil Checklist completed for every independent section and minimum 100m length.
6dfe1a21-1962-5a75-b326-ae092497b44c | note | Contractor - I
aed160f8-f5ac-58c1-a9fd-a2328f4a380a | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
4a8e29a9-6a51-5d0b-a0ba-a0530485b2f3 | checkpoint | 3.07 - Install Backfill Material
b4e7f7da-0ff1-5759-9d07-6a0864cfeec3 | note | Method/Description - Inspection
4b40a2a4-a5b6-5991-bf26-b9638cf60226 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
95d1b2f7-f730-57c0-9193-1e90daff09ff | note | Contractor - I
a058d4fd-902f-543e-a36c-8526c32e317e | note | Designer - R
41c9c328-47f6-593f-8583-164ac40798a2 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
c04adb27-0b59-522b-aa33-a966e3353cf0 | checkpoint | 3.08 - Install Vertical Subsoils and Connections
70d540f5-3674-5eb4-9939-8a266b433505 | note | Method/Description - Inspection
3025783b-2ad7-52b3-b7d8-46663eff93c3 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
593fd4d7-8d4c-5b1a-854f-d31948c4321e | note | Contractor - I
b0b52af5-2717-5265-adcb-6f49bfc656a4 | note | Designer - R
026816eb-1786-5f1e-961b-799c1ca2c9aa | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
a91430d2-3995-5e25-9013-6a3786f37df3 | checkpoint | 3.09 - Install Additional Vertical Subsoils
f73c7e64-4c1d-577d-8897-de04a5088be1 | note | Method/Description - Inspection
b698bbae-bbee-51e0-a8d4-9e6765faddd9 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
4bbb6a7d-4a4e-55e4-a0cd-1800f317b7d1 | note | Contractor - I
e6260eb6-b8f2-5558-8c53-26626c1ca0a2 | note | Designer - R
da5d75ec-f13e-5505-ba75-0d4508d09075 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs, As built, Formal correspondence
e938a91e-74a1-5e8d-a2f9-7fc1fe37cb86 | checkpoint | 3.10 - Wrap Geotextile
b951fc49-e9bb-5569-a949-395e600ee30a | note | Method/Description - Inspection
1c01c10c-9fa7-58ab-8b6b-3fb8505c1baa | note | Test frequency - All Geotextiles. Subsoil Checklist completed for every independent section and minimum 100m length.
8a4e6575-67ed-5e13-9a2a-850167260611 | note | Contractor - I
e073d395-68ca-51a8-8020-9c1788f97bb9 | note | Designer - R
f54484f6-89d0-5be0-90bd-3c34df2a0802 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
fae5e183-4e7a-5bc3-a094-f921f788ef4c | checkpoint | 3.11 - Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top
14bcfb28-8ee2-59d4-98f6-b3db43730e62 | note | Method/Description - Inspection
1860d7b7-3a54-5c3c-85ba-ecb2572989b9 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
dfea8ab4-fa9e-50fa-b290-3ce40295a690 | note | Contractor - I
d31434ef-14ff-5ac1-8c82-8d3cddfb7331 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
f761d223-9345-5a5d-b40f-3a06946049ac | checkpoint | 3.12 - Construct Outlet structures
5339cc5e-3443-5fec-bdd4-21e0f10d5a58 | note | Method/Description - Inspection
668a31e4-9a76-5145-8e78-0956646d97a8 | note | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
78b9c36b-690c-5484-b0a6-77e3f0dc8fcc | note | Contractor - I
d6830253-1bb1-55e1-9676-884360d4f7bc | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
d2ef6b17-bd1e-5c35-a60f-ec686fb1ab1f | checkpoint | 4.01 - Completion of works
f02a4548-7e0b-51e6-a9f6-074e47f3d4c0 | note | Method/Description - Inspection
5cd33b37-6710-54c6-ad63-77e8e0294792 | note | Test frequency - All Subsoils
a0972601-b0f8-5893-800a-3405c5695e7f | note | Contractor - I
a7e369d4-7517-5cb4-953c-c8ee47bd25ca | note | Designer - R
3d4b2ee6-962e-5c38-9871-4f195c3114c3 | note | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
5b8df720-9ca7-5ae8-a81d-997056d6c93b | checkpoint | 4.02 - Provide Maintenance and Inspection Report/As Built
cb221f93-58c1-52bc-8de9-adf7abe7dea6 | note | Method/Description - Maintenance and Inspection Report Completed
d7776e28-748f-5c55-bf04-2ececb274d93 | note | Test frequency - All Subsoils
d00a9801-7a1c-5d96-9a3b-1d01d832ceaf | note | Contractor - I
92feb325-2ac3-5e68-a22c-4ee3742ece37 | note | Designer - R
5ef0b631-7bc9-56bc-b929-46845b742467 | note | Verifying Records Checklists, Test and Supplier Certificates - As Built Plan, Redline markup
353fa8f9-a372-4f70-8cac-8919ec45c582 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
9189bcb7-1bd4-466a-9fb5-69ca5e088f53 | checkpoint | ITP Close-Out by
03896ce5-3e0e-5e2e-84d5-3fc1558c3698 | note | Site Engineer/Project Engineer
13039842-346e-5609-96be-4bc090843db5 | note | Zone Manager Approval
f75558db-2290-5935-a14a-046c74a85ba2 | note | Construction Manager Approval
0756a054-de42-5aab-85ee-990e722888e3 | note | Quality Manager Approval
2092d767-0cac-5956-8fa5-c74e414efdff | date | Date:
94df220f-3e9d-4c35-a02f-ea43180fe707 | signoff | SIGNATURE
cb50cf57-e5ab-5641-9e76-b97cf66b4fd1 | checklist | SYS - ITP-006 – Temporary PKS Culverts Installation For Season 2023/2024 |  | ITP-006 – Temporary PKS Culverts Installation For Season 2023/2024
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
25cb42ef-7d50-5dca-89f5-4c29a78ce685 | checkpoint | 1.01 - Confirm CWP Signed off
8bcca5d2-2976-5a23-b405-c6d60403e2c7 | note | Method/Description - Document Review
596fcf40-f136-57c5-b157-a2026b0750f5 | note | Test frequency - Prior to Work
914272b8-2591-57ba-8b32-66cbde1c092d | note | Contractor - H
ce7bd977-6308-5ba0-8caa-bcb8124f28fe | note | Hynds - H
5cd0f26c-3486-5983-a10b-64ebfe083bb7 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Copy of Method Statement
90528568-7dbb-505b-b32d-75da79ee0256 | signoff | AUTHORITY HOLDPOINT
5c8b235a-89c6-5bc2-95c3-af3747fcf89a | checkpoint | 1.02 - Confirm Compliance against Resource Consent & Management Plans
34056558-ffa0-5201-9cbe-64991ed1eee5 | note | Method/Description - Document Review
960eba53-f532-5268-8712-6315c1f919c3 | note | Test frequency - Prior to Work
476a2b2a-cca6-5fe4-9472-b248f2e1ecc0 | note | Contractor - H
5d933087-1e33-57c8-9f59-ea2d8a93b731 | note | Hynds - H
08ecf120-7547-5d3e-9034-0795223f7415 | note | Client - H
2c0d4747-0a14-50bd-9c2d-5f8abe5c4780 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed Management Plans, Approved SCWMP and Approved CWP
80f44c70-59d0-5d07-bf6f-65b719d78da8 | signoff | AUTHORITY HOLDPOINT
5e649741-08e8-53d7-90e2-13e62ad83986 | checkpoint | 1.03 - Confirm Design is in place
3fa3020d-d5fa-595b-8997-cbc3df6ab9a2 | note | Method/Description - Document Review
b55513d7-aff4-5d1b-b59f-448213c77dd9 | note | Test frequency - Prior to Work
270616d9-4f18-5544-8286-f403e79e2939 | note | Contractor - H
ace7769b-523d-51fd-822e-b72ceeef6121 | note | Hynds - R
f29e2e19-05a2-5629-a09d-20cc11a5c036 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings
3e4ca7a6-fdcd-5bc0-9f74-9e85ab2206e0 | checkpoint | 1.04 - Complete Permit To Dig
af02e228-acc9-54cf-9a3e-36242cec0f72 | note | Method/Description - Document Production
1f54f34e-5794-5d1a-bd82-926f0c86727c | note | Test frequency - Prior to all Excavation works
6d47b75e-8b10-57e6-bbef-dc38a33cad7a | note | Contractor - H
6150d923-7e62-5da7-ba68-907c67f93212 | note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Dig Form
ed3b9c61-8190-5c6b-bc78-3deea876281e | checkpoint | 1.05 - Survey
9730b2b4-d46c-5e42-a1ae-692deef46d6e | note | Method/Description - Record inlet and outlet heights for the stream diversion. Mark out scope of works
4d07a43d-8960-5c0e-b316-015a3e30f74a | note | Test frequency - Prior to Work
5309efbf-ad8b-5a9a-99a7-38d6467979c8 | note | Contractor - H
152f6c24-ecfe-5867-8f14-ad95ef1b88f1 | note | Hynds - R
223ffcb4-c380-5273-b0c5-44d06cace32f | note | Verifying Records Checklists, Test and Supplier Certificates - Survey Heights, Survey Mark-out
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
276596e5-622f-540a-b5fb-f058d6208be7 | checkpoint | 2.01 - PKS pipe (1400mm, 900mm & 800mm)
b06cb1e0-db13-5f81-b7cc-421395cfedb4 | note | Method/Description - Document Review
2de5d1f6-0b15-552b-9ae9-c60845cc3631 | note | Test frequency - All PKS pipes
271ef182-0804-5ac6-a12d-4e5c7b25e43c | note | Contractor - R
1e0c9aea-6f5a-5eea-b0d1-05f17118606e | note | Lab - H
dc5630ab-1c5c-564d-88fd-b67809ac8e65 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Lab Tests
2b0c4440-9e92-590b-8648-3562a3bdd6ac | signoff | AUTHORITY HOLDPOINT
437e53b9-8816-57a5-8687-f2b95e8eadd2 | checkpoint | 2.02 - PKS pipe fittings
f932ecbc-b8ee-5dd0-9a4c-7c567961ab1a | note | Method/Description - Document Review
dfbe90df-f533-5e42-a64b-e3f461674ef4 | note | Test frequency - All Fittings
83fd9542-eb46-5a0c-b6a9-0b911ecdc1d5 | note | Contractor - R
c374d92e-68f5-52a4-97cd-cc5468747a9c | note | Lab - H
603d3e25-09ff-5064-8c8c-ee2ec0a80ccb | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Lab Tests
c5f6844e-e2c3-5736-b591-d9b8a313842e | signoff | AUTHORITY HOLDPOINT
f0fafa0a-7d8b-52d3-a270-8e95cd73cf98 | checkpoint | 2.03 - Subsoil Pipe
1e2c4e12-4456-54ca-98ce-23e9afca0bd4 | note | Method/Description - Ensure Pipes are ordered as per drawing
df6de802-7bb9-50a9-8aa6-8d422b96aba7 | note | Test frequency - All Subsoils
37113ea6-9d63-5b69-9d08-41fe777895f4 | note | Contractor - R, I
a0d873da-bb0f-51c7-8c75-c371e5c812a7 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
18fcaed8-c292-5c18-b5e2-81222a052df4 | checkpoint | 2.05 - Geotextile
6abcee02-d71e-5353-9406-568821dc632d | note | Method/Description - Document Review
232e368e-b197-5f21-8168-2b48ba57e51b | note | Test frequency - All Geotextiles
b11614e8-3f0a-56f2-86b2-de669b5e7fc2 | note | Contractor - R, I
7b82b63b-2b35-561f-940e-4592ea2aa393 | note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
1c4ee408-b787-5f05-9623-9c6acb31d725 | checkpoint | 2.06 - Drainage aggregate
df6c7a2a-83f2-5829-9495-8dd85be80236 | note | Method/Description - Laboratory Testing
cdaaf44a-989d-5b0f-ae69-7240c3d030b4 | note | Test frequency - Embedment material
f58b17e0-177b-551c-9062-be0282493020 | note | Contractor - R
c099be62-f1b1-54bc-9c86-bc290562861e | note | Verifying Records Checklists, Test and Supplier Certificates - PSD Results, Crushing Resistance Test, Confirmation of Material acceptance from Designers
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
3212d783-a144-5989-a497-6dc108eb26ac | checkpoint | 3.01 - Trench for PKS
3977f772-33d4-57e6-90b8-2feb495543bd | note | Method/Description - Inspection
e8a5eb11-0157-5a7a-8fba-cdf5b9fdcb59 | note | Test frequency - Prior to BIDIM installation
0d032c5e-9f49-589e-b2cb-52b52f4b433f | note | Contractor - I
20752364-a489-58c8-bc4f-5a04546530b4 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
aa967d00-f53d-5a11-aac7-dac3cb7ed00a | checkpoint | 3.02 - Insitu subgrade (foundation) Compliance
a8c0c653-f9d9-5249-9319-bfd0314824ee | note | Method/Description - Inspection
d3ba65cc-f58a-5014-9287-8ada3d77f468 | note | Test frequency - Checksheet filled in for every 100m section of drainage
4c222a4a-3879-512c-b4f2-6f94eba25e25 | note | Contractor - I
70fbe8e1-f018-5077-8251-bae2e11936cb | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
a6f1c758-656b-5240-862b-c139a4e5de79 | checkpoint | 3.03 - Lay Geotextile (BIDIM A29)
ebe45091-9fd6-522b-a2be-340c1bc986f1 | note | Method/Description - Inspection
bead50f6-cbb5-5b7e-8a8e-80b8190fa3e1 | note | Test frequency - Checksheet filled in for every 100m section of drainage
84d60d6e-d840-5b67-bb17-03d3c2d37533 | note | Contractor - I
f2c15657-8d2f-5f98-98ec-3739dee09921 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
49eaf908-2e12-581f-a669-34aeaf41b1ee | checkpoint | 3.04 - Install Bedding Material
3052fcf5-adac-5953-94fe-08aee1b89c9a | note | Method/Description - Inspection
8aa7b042-497a-5f83-84fc-56f7c3d1d02c | note | Test frequency - Checksheet filled in for every 100m section of drainage
9067b1fc-854b-53f7-bc24-12544cbb1ada | note | Contractor - I
6f7a9cd3-1457-536c-84c2-a59272032605 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
58e93f70-4a80-5048-aca7-98b095e4b403 | checkpoint | 3.05 - Survey pick up location and heights
040d3231-b354-5c54-9ce1-8a3565693a52 | note | Method/Description - Survey pick up
fa1e1bdc-a7c8-51c8-b34b-c0d3cebcc5bf | note | Test frequency - Picked up location minimum every 100m
aefefd22-5e33-55cb-9e46-25743eaee2a0 | note | Contractor - H
02914537-456f-5a3a-9ef0-03e65e99b61b | note | Verifying Records Checklists, Test and Supplier Certificates - Survey record
20ab2a1c-5777-58bb-b116-74a612dcf678 | checkpoint | 3.06 - Install PKS pipe
abf8ce50-12bd-500e-aeb4-df6600783a89 | note | Method/Description - Inspection
244d6350-dbfb-57e3-9156-80d9806181ee | note | Test frequency - Checksheet filled in for every 100m section of drainage. Hynds inspection once at start of Works.
d6a34e46-217e-5e8e-9213-f8842cf24615 | note | Contractor - W, I
7e620971-3b53-5329-af4f-f37450836102 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
c9866cdc-da9a-5642-919e-bc2cee48d5bb | checkpoint | 3.07 - Install side support embedment material
440be4b5-d534-50ef-a6c7-4f0b0b8d06e6 | note | Method/Description - Inspection
879f454b-bd86-5b94-9a4b-775d230bda64 | note | Test frequency - Checksheet filled in for every 100m section of drainage
0ec9c69b-8080-55dc-b629-314ab5f88c15 | note | Contractor - I
b06f40dd-10f8-5f79-a209-6ebfc55208f4 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
a21bcbfa-81b7-53c2-bdc3-81d407ba28a0 | checkpoint | 3.08 - Install overlay embedment material
5daa1abf-1d51-5d22-8d25-b2778c9e14b2 | note | Method/Description - Inspection
950c6c35-8e94-5d5c-b0af-42f73473c9a3 | note | Test frequency - Checksheet filled in for every 100m section of drainage
a3f368f2-6f89-531e-af54-4dab17c427e8 | note | Contractor - I
b25648b8-be95-5d7a-9ead-06d5d13d43ad | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
3b075c01-8664-586a-af05-3b593bc393d7 | checkpoint | 3.09 - Wrap Geotextile
f880db3f-6fba-5897-a26e-fd6c967d1fd4 | note | Method/Description - Inspection
1121fef9-fb6a-55e0-adc3-52a93be20d8e | note | Test frequency - Checksheet filled in for every 100m section of drainage
6fb29771-c5bd-5ccd-8242-6062b1db58bd | note | Contractor - I
28e60a39-7acf-5806-b945-d43365d7222b | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
85910491-7d0d-55df-8a28-bc8442b458f3 | checkpoint | 3.10 - Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top
dbd0b7a1-a2be-5ec2-b340-53cdc03d5b30 | note | Method/Description - Inspection
a81c3316-cd58-54b0-9aca-a135186dd12e | note | Test frequency - Checksheet filled in for every 100m section of drainage
f748059f-174f-5691-9e36-6d688ef30e5c | note | Contractor - I
5100807d-70d9-515d-94c7-ce73b075e195 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
768d3ea8-4aa7-5499-b4df-1095b7adf573 | checkpoint | 3.11 - Spat Rope installation
26fb15df-8f1c-5fc2-9927-977c0216bfd3 | note | Method/Description - Inspection
f389ccce-38c8-5466-a680-6cef979a2879 | note | Test frequency - Checksheet filled in for every 100m section of drainage
a3039d5f-16f3-5594-96cd-ad67855d4841 | note | Contractor - I
a32cb2d9-99d4-54bd-9179-a784e4a84c0c | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
5b2bf91d-9fc6-51c5-8e1e-5861949c524a | checkpoint | 3.12 - Construct inlet and Outlet structures
0debb97a-37cf-5e40-91c1-af9269a59654 | note | Method/Description - Inspection
96c1baf3-ef5a-5846-9dab-4d01f267ad65 | note | Contractor - I
a831b8a8-7715-514c-b650-4b7b6359cbc0 | note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
c815dfd0-5dcc-5cc4-9c68-7c8d5d947fd0 | checkpoint | 4.01 - Install culvert screen to catch debris
4ab8e6dd-0aab-5add-b907-365591572736 | note | Method/Description - Inspection
799d5670-42e5-56fe-abe7-2f3c64b5f83e | note | Test frequency - N/A
fee25ee8-e98b-522e-bb8c-9cd932df95ad | note | Contractor - I
5b8df720-9ca7-5ae8-a81d-997056d6c93b | checkpoint | 4.02 - Provide Maintenance and Inspection Report/As Built
d1d19c64-3d49-5249-b158-ed8c6fe54809 | note | Method/Description - Maintenance and Inspection Report Completed
d71fd21d-0ecc-5b3a-a2c5-bb49a68bac7f | note | Test frequency - All Temporary culverts
79b5c7e6-7a1a-52ef-9bcd-2c261e157190 | note | Contractor - I
ddbff481-7bcf-56e2-802d-cec814301f0d | note | Hynds - R
10203b48-48b9-5a03-b653-dfd45f5dc6ea | note | Verifying Records Checklists, Test and Supplier Certificates - Maintenance and Inspection Report including As Built Plan & Photographs
74c1dd7f-58c1-4631-a79f-ecfae99e5886 | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
b27613f6-a434-4df8-85e9-c0e7f3a1ff18 | checkpoint | ITP Close-Out by
b3145aaa-6aca-5ac8-b536-1ee8815eb5b5 | note | Site Engineer/Project Engineer
5a2ac00b-0e94-5039-8c8d-01407c841783 | note | Zone Manager Approval
b9c70988-a0ec-5e06-b0ee-e4f54c320a49 | note | Construction Manager Approval
df7b2ea3-0f62-5f06-a7c0-13f5f2425a99 | note | Quality Manager Approval
ae22d57e-20f8-541c-a512-8a21c3ba2f6b | date | Date:
d3d8b125-7309-4082-9adc-b0c125ee92f6 | signoff | SIGNATURE
f0a4552b-deb1-5731-b34e-6c882e186bfe | checklist | SYS - ITP-013– Earthworks Fill |  | ITP-013– Earthworks Fill
e631fd1c-c7ec-5455-943c-2624fae3e7e6 | section | 1.0 Pre-Construction
c9e7969a-5007-57ec-ba14-7e88241a4737 | checkpoint | 1.01 - CWP
1fd7bc15-7b75-56ee-90ea-64d2ed7cd0fa | note | Method/Description - Document Review
2d6fe952-cf71-5bfc-9670-82288734cf09 | note | Test frequency - Prior to personal starting
edeb92b5-8427-55c7-a8c3-c6d9907e3017 | note | Contractor - H
3d72a513-8b7c-5811-9207-becb8381f6b0 | note | Verifying Records - Signed off CWP
5c6d3d2d-8b90-5b45-ac77-8cb3e4b937f4 | checkpoint | 1.02 - Design
8c4b0047-156c-586f-8f33-0259491ef1fb | note | Method/Description - Document Review
5d603b27-a348-586b-9d5d-4a9e16c405df | note | Test frequency - Prior to starting
58328657-106f-576e-bef9-66260f63f3bb | note | Contractor - H
94770155-8c54-523d-86d3-f5001fe94dac | note | Designer - H
230170c5-4b0d-5a1c-831d-aee8dcc0214b | note | Verifying Records - IFC drawings or Written approval from PAB
7bd1fe4b-029d-5a22-999a-91130e63165b | signoff | AUTHORITY HOLDPOINT
c2b681ed-cd09-5ba2-a8e4-282d9a28f5e2 | section | 2.0 Material Compliance
265e2a41-b6af-58cb-9aec-e70b81447852 | checkpoint | 2.01 - Structural fill
843a877e-afab-5723-b797-d1e3e4a6d016 | note | Method/Description - Determination of the dry density/water content, Atterberg limits, Triaxial (Single stage min. 3 samples)
1ef9ada4-cbd5-5c9f-8615-b75fcad5a5a7 | note | Test frequency - 1 test per 20,000m3
5e07418b-5d1e-525a-a70f-5f83018efce4 | note | Contractor - H
15750547-c9ba-5ba1-9d88-1a2406902a8e | note | Designer - H
79172de2-0ca6-53ba-a825-f50e292e216d | note | Verifying Records - Test Report
228a3ddf-c4be-5722-a7fb-9380f8859aa2 | signoff | AUTHORITY HOLDPOINT
2a735733-e33f-5a2c-8219-fba4a2eb7209 | checkpoint | 2.02 - Buttress Fill
72f577ab-2a72-5a15-ad9a-e191a2caf005 | note | Method/Description - Determination of the dry density/water content, Atterberg limits,
de4a0cb6-c889-55ba-8927-2ac74ed52b77 | note | Test frequency - 1 test per 20,000m3
68c11a0c-177b-5be6-93bf-517e2dfc875e | note | Contractor - H
961cda57-bca9-5b4a-955e-9a7dbb6bed30 | note | Designer - H
7a1bc3f8-bd1e-5d53-9c31-69881a980b0e | note | Verifying Records - Test Report
b005e003-bd07-5459-960e-8bc2ffe248ac | signoff | AUTHORITY HOLDPOINT
ead2ebe7-31b9-55f7-9bbc-38374699115e | section | 3.0 During Construction
f80e3859-9837-5795-b26c-edce867f3449 | checkpoint | 3.01 - Set out extents of fill and check against design
54470988-20a7-588b-9eaa-7de92c883ade | note | Method/Description - Survey/visual
dbbcf320-807a-50e3-a052-c5f4f8daaca6 | note | Test frequency - Prior to Commencement
a3ca4369-038a-5267-ae01-95a64d991327 | note | Contractor - W
9a2366ea-dde1-5a1f-aa20-31976fcfcac4 | checkpoint | 3.02 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
4689b6f4-b066-5f1b-8240-8fcc4de99da1 | note | Method/Description - Survey/visual
997ac537-43b3-5192-9017-0bf3e3dcb597 | note | Test frequency - Prior to Commencement
d9ac4fbc-7600-56df-85a5-8ea200705489 | note | Contractor - W
b5cbf260-9166-51fa-99e7-82b481d6e014 | checkpoint | 3.03 - Vegetation Clearance
b4fb3a68-71ef-58da-8097-40b7a89c112a | note | Method/Description - Survey/visual
8970b38d-8b8a-5e49-9c38-d63fc8472797 | note | Test frequency - Fill area footprint
f6a103a5-5e83-54ad-a66a-0eff52520bbf | note | Contractor - H
b87f98d4-d11c-551d-81c7-8f4f29f9fedf | note | Designer - H
21e996d7-b1c6-5e55-bfcc-f4f44de77c3c | note | Verifying Records - Subgrade approval checksheet
16cf1c01-ca69-5bf9-ad8a-9de1531a47fa | signoff | AUTHORITY HOLDPOINT
968214fd-11f9-5702-8296-7a714958f524 | checkpoint | 3.04 - Designer witness of in-situ subgrade prior to filling
ba2f9358-a9a9-5881-bc01-18f984aee4f3 | note | Method/Description - Inspection
11f42312-c5e8-5541-9374-4f1594c9a91e | note | Test frequency - Prior to Filling
8a0edce7-145a-5525-b5b4-f396d248a2e9 | note | Contractor - H
36da4f01-26aa-5525-99f1-2d9554b96007 | note | Designer - H
62478400-b8e3-59d6-a6a1-8dcf7c77e368 | note | Verifying Records - Subgrade approval checksheet
0df5fe88-5f22-57d6-b8f0-47988d704f9b | signoff | AUTHORITY HOLDPOINT
9337de40-bb4e-5c4d-869b-d8f3bcf1a9cc | checkpoint | 3.05 - Undercuts
69ecde8d-3869-5cf5-ae08-76c8bd5d180a | note | Method/Description - Visual inspection
438a220f-e72c-56fb-9404-7451932cbae9 | note | Test frequency - Prior to Filling
bc6f60ed-4f21-5290-8116-2a8222b4d19d | note | Contractor - I
8d209e60-b20b-5233-9b84-a05bf17c9165 | note | Verifying Records - Subgrade approval checksheet
201333b3-3907-5aaf-a1a8-9a0136b59a29 | checkpoint | 3.06 - Subsoil Drainage
1a089570-6390-58b5-8b70-7e61af11ec2d | note | Method/Description - Inspection
1b9050a5-547b-527d-9c0b-c94f51eff89c | note | Test frequency - During subsoil construction
9e02960e-ab55-55c1-9b30-b7fca11a2b74 | note | Contractor - I
eb43c112-b2d0-56f7-882d-36705c85ffc3 | note | Designer - I
dbc35f7b-b8a8-52b7-a189-44533021e349 | note | Verifying Records - Sub soil drainage ITP,
bc1aa750-f038-51a9-8190-ade6b85cd655 | checkpoint | 3.07 - Monitoring Equipment
1ef14143-ffb9-517a-8f56-4a92d767339c | note | Method/Description - Survey/ data logging
de174a21-52f0-5099-bc2a-2fce93f54897 | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
988e2157-806d-5f8a-b89e-c6251768791b | note | Contractor - W
9a75421e-9f90-5e9f-93ee-665134a87991 | note | Designer - W
5e4495f7-1404-5969-92b4-0f14e57f6446 | note | Verifying Records - Drill logs
3a553daa-8f6a-5704-9183-3bb478bdeca4 | checkpoint | 3.08 - Filling operations
adbb1f75-98dc-556c-a631-3bc5b41ba1e0 | note | Method/Description - Visual inspection
66e1ae20-c616-5dc4-9692-bfd386ade1d1 | note | Test frequency - Daily
17d7b1e3-8e17-59c3-b4c2-f7bfadb16577 | note | Contractor - W
ec83abcf-a19b-5853-bcb4-61fa99665448 | checkpoint | 3.09 - Filling operations
ee8cacb4-bc0a-5ead-b3e9-8dd2e866d9f6 | note | Method/Description - Survey/visual
310c020a-61b0-587d-a195-8b4d2bc41a10 | note | Test frequency - Daily
10983cb4-a0f8-543a-84d5-dfe3867faf88 | note | Contractor - W
dd3aad50-bdbe-5682-bd2e-421f2703fd43 | checkpoint | 3.1 - insitu fill testing
69a46851-b372-5748-8d21-a101d637e99b | note | Method/Description - Plateau Test
8d5d5d55-7dbc-5e0a-b42b-4505a96aae12 | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone, Buttress Fill - 1 test per material type per earthworks zone
c350c99f-eccb-585b-82ac-03e070b715f7 | note | Contractor - W
7364e9ca-6681-5b8c-be6d-f877ddd2313d | note | Designer - R
a48bd035-17e9-5865-9115-15eb677f0492 | note | Verifying Records - Test report
fe966276-cf7e-5918-9f15-68fc2a7e5b6d | checkpoint | 3.11 - insitu fill testing
600dd621-0d81-50d0-80c4-9dc0f518b981 | note | Method/Description - In situ moisture content and density
0c1794d4-660b-55ea-acae-9466ec554854 | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length Buttress fill - 1 test per 200m length Average Subsoil Drainage Back fill - 1 test per 500m3 , Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
09464a21-4611-56a8-a5fe-3e0edf4ffdaa | note | Contractor - W
6a52ccdc-6010-5574-b132-a0d049b97e2d | note | Verifying Records - Test report
9e244908-a5e8-5361-88f6-bc38e3b257d2 | checkpoint | 3.12 - insitu fill testing
a0afe7b1-fee4-5fa3-9c71-8fbf8f5a5acf | note | Method/Description - Undrained shear Strength
af0fabf9-9e6b-5b60-adc5-e80a21430127 | note | Test frequency - Structural fill - 1 test per layer per 1000m2 Buttress Fill - 1 Test per layer per 2000m2 Cement Stabilised Structural Fill - 1 test per layer per 500m2
6c4d0280-0c7d-5097-98a7-f68560fc8028 | note | Contractor - W
fbe8a438-4bda-5e3c-9d73-322b30940467 | note | Verifying Records - test report
32bf1bf8-4b78-5538-a4b0-a25271cd10fc | checkpoint | 3.13 - Confirm testing requirements are met for insitu fill
5c909215-a304-562f-ba2e-1b17343aed8e | note | Method/Description - Document Review
02bc81e6-ca2b-5dc5-a474-4c20bd89a2c7 | note | Contractor - H
c69f231d-1c8d-5151-846b-45fe51c69acf | note | Designer - R
49638fac-20ae-5cd6-a1f4-ceed719c72c3 | note | Verifying Records - Review of testing records
8b69e985-c302-59b9-82d2-a52a38698c15 | checkpoint | 3.14 - Subgrade Fill Testing
f555f46b-d1e3-5003-8844-e622c6d88ac5 | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
b9934e02-df02-58e0-87fd-ee458ddd54ac | note | Test frequency - 1 test per 0.5m lift per 50m length for 1.0m subgrade depth
fd34ab6a-c392-52d6-9c5c-0fed575b1764 | note | Contractor - W
d86a7167-2b5a-5754-bb5f-f0e4f1a196b9 | note | Verifying Records - Test report
3ee45fde-032a-51c7-b9c3-5a2f343b79c1 | checkpoint | 3.17 - Subgrade Fill Testing
c9fb14e6-4cd2-5dc0-af5c-95b191f08475 | note | Method/Description - Benkelman beam or FWD Testing
c428f2d7-9aa5-5956-98a3-072d60654b87 | note | Test frequency - At three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
ec4011ac-576e-544f-b4aa-606496abe07b | note | Contractor - W
d2973614-4cc8-59bc-8d68-4022b26ad1d4 | note | Verifying Records - Test report
b1d90aa6-8720-532f-ac39-1f798f47992d | checkpoint | 3.18 - Subgrade Fill Testing
3e147788-ed35-54be-8ec5-a539d24bf29e | note | Method/Description - Laboratory Soaked CBR
0fc8e469-f22c-5704-89f9-d7fe018fb000 | note | Test frequency - 1 Test per 5000m2 at subgrade formation level
8931dde4-2398-509e-9f8e-52ed93d5f832 | note | Contractor - W
0fb58b69-8f60-5619-bacf-d43c590a3e70 | note | Verifying Records - Test report
261fd088-1d37-5bb5-8cd2-c96c245bd596 | checkpoint | 3.19 - Confirm testing requirements are meet for subgrade fill
09cf899d-703a-57b2-b32f-4d3da9cf3da4 | note | Method/Description - Document Review
ca9875f0-73ae-5e90-8de8-7302acc32331 | note | Test frequency - Completion of Filling
0cc662ce-b0e8-58c5-b821-6b286fa94e2d | note | Contractor - H
f2a108d2-b42a-5c4e-8639-6ba9e41a718c | note | Designer - R
b5536ccb-b6ba-5e9f-a442-cefb3e4a58ee | note | Verifying Records - Review of testing records
bf6eb456-e3ba-56cc-aae9-ed26fb0d4aad | section | 4.0 Post Construction
de153151-2496-515f-a86e-a71e4ea85abf | checkpoint | 4.01 - Monitoring Data
a7db3a4b-38db-57a6-b6e3-59634dff1edc | note | Method/Description - Data Recordings
2a085e1a-02b9-5208-940b-25fa6a85b2e1 | note | Test frequency - During construction and at end
3167efb4-0f87-5712-9e42-e14a688fc186 | note | Contractor - H
c842e8aa-996e-5622-a3a8-8af7e1d2ec92 | note | Verifying Records - monitoring Data tables
96b27424-f2a1-51a5-ba79-d8a2e76ef901 | checkpoint | 4.02 - Survey As-builts
36fe3d22-feb1-5dc2-9164-8b5f09094e1d | note | Method/Description - Survey As-built
52dd3e4e-8331-5648-bad5-815d78477912 | note | Test frequency - During construction and at end
5193b0a9-ec26-5a50-b6c1-11b49445bce8 | note | Contractor - H
1674725e-8610-5f4e-9cb6-85c094bf0c22 | note | Verifying Records - CAD files
5c0732e6-58ca-5568-815f-7eb40f0c0149 | checkpoint | 4.03 - As-builts
2454005a-a3a1-5a1e-8746-49dd0e0d6520 | note | Method/Description - Red Pen Mark up
96a442d1-51b2-58fb-8c6a-9faa90e5fc92 | note | Test frequency - End of Construction
464ca93d-6b25-544b-a8d5-12229c34574b | note | Contractor - H
e733f8c7-53c6-5be1-a3de-610e2867dd0c | note | Designer - H
c8c4f16c-a75c-5270-82f0-708815469c7c | note | Verifying Records - Red pen mark ups
da8801c3-a745-57ae-8ee9-97e0c79c7f28 | signoff | AUTHORITY HOLDPOINT
bbb6b99e-b0e9-4ffd-8477-ec3f3f9a73cc | section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
1e66d1cc-278f-4b3a-9f71-3a46c1d7ab01 | checkpoint | ITP Close-Out by
09034d67-6d0c-5002-8a20-e4a05a4a91d2 | note | Site Engineer/Project Engineer
a5e89064-7993-5de8-b7b1-9f6be03ca519 | note | Zone Manager Approval
03d41ca2-8062-58c1-9f94-6708f0dde44f | note | Construction Manager Approval
dd01a371-0fe2-5939-8390-150d3a5db453 | note | Quality Manager Approval
652e4a78-71b6-56ad-8339-ade7f20f98fc | date | Date:
92b3d86b-5be5-4ea9-b8c6-f918beef5497 | signoff | SIGNATURE
0a558841-40e7-56fc-99a6-9d6d1ea300be | checklist | SYS - Z07-EWK-ITP-011-LOT-001 - Fill 15 & 16 | itp | Z07-EWK-ITP-011-LOT-001 - Fill 15 & 16
69ce9b50-1ebc-5d31-8f34-23a4d34fa275 | section | 1.1.0 Pre-construction Approvals
c6325e1f-98cf-5dd9-a024-c2741f8830c3 | checkpoint | 1.1.1 - Construction Environmental Management Plan
50034a9b-c7fd-5d4a-ac48-4a40acfd5153 | note | Method/Description - Document Review
ca266398-4518-5357-8549-a06a9b788e3f | note | Test frequency - Prior to work starting
f0e3afb8-6790-5be9-a0f8-80f3ec578b99 | note | Contractor - H
ba562c65-bc6c-522d-9f17-2f2b27639032 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CEMP
ee7771bc-2366-56f9-836d-696e37f5e599 | checkpoint | 1.1.2 - Construction Work Plan
07bf01a9-825c-5fdc-b175-9ae5c8ca892f | note | Method/Description - Document Review
9b7eeef0-c1e4-56e5-b431-7adfa97d42a0 | note | Test frequency - Prior to personal starting
35ee3d69-2c98-5c1e-85f0-9f0593f4aa04 | note | Contractor - H
ae769efa-75b8-536c-860e-dbb95892bf82 | note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
80997794-398e-58e2-88f5-b742e9843f56 | checkpoint | 1.1.3 - IANZ accredited testing organisation
dc14c63e-01e6-5479-9e93-4f506f8ac28d | note | Method/Description - Document Review
be91758d-b187-54a6-9a01-4dc6ce1f1c07 | note | Test frequency - Once prior to works commencing
4eb99b6d-d70c-571b-b090-cec6be83195e | note | Contractor - H
67fdb9b4-4c51-5187-b60f-def6158133b7 | note | Designer - H
4b926d1e-7dc3-59f3-a856-b730cdafc0c1 | note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
1b40a37a-e607-5a69-894d-892e8bd1f5d4 | signoff | AUTHORITY HOLDPOINT
1506fbf7-5b48-517d-a6d7-cb5c453622a3 | checkpoint | 1.1.4 - IFC's specification
2450ca51-e036-508c-b9f4-8d0a3dbd04a8 | note | Method/Description - Document Review
ecf481fe-aa10-5f6c-9eeb-33e0dc2a64a3 | note | Test frequency - Once prior to works commencing
20b4c479-3a6d-5812-9a25-7374d89f6fdb | note | Contractor - H
9f9cade3-9e8b-5b6d-834e-672f2279b41e | note | Designer - H
86591545-de2f-5cef-8092-31f351edb218 | note | Verifying Records Checklists, Test and Supplier Certificates - IFCspecifications or Written approval from PAB
2358ac4e-bff1-5d5e-8f51-59f40a42db53 | signoff | AUTHORITY HOLDPOINT
66467056-0c6d-5a0c-8857-462d47f00167 | checkpoint | 1.1.5 - IFC drawings
d8ddcaa6-3582-5415-81c3-661c617f6746 | note | Method/Description - Document Review
83b2c398-5712-59c6-a5db-35bfd54ccb56 | note | Test frequency - Once prior to works commencing
5c4b541e-c631-5927-992e-7794c26099b2 | note | Contractor - H
3bcfe335-1b32-5b01-a8c3-d3124621f671 | note | Designer - H
e7cf6945-0b86-53c6-a8bd-15cd5969fe82 | note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
9f8f9341-c120-5c71-b92d-67279bb7414d | signoff | AUTHORITY HOLDPOINT
316bbdcc-8b33-5a80-808c-5b370f7f4360 | checkpoint | 1.1.6 - Approved earthworks model
dbdd446d-910f-5404-aff5-101f91ddd9e3 | note | Method/Description - Document Review
a52bbb2b-cdd1-5db8-9599-2bb2aff2ebe5 | note | Test frequency - Every new Earthworks Model and prior to work commencing
3604447a-d645-5d16-85c1-4d0ce474b5bf | note | Contractor - H
da4ad63a-38af-5b42-8c77-10e66b0f0fb6 | note | Designer - H
6d2e6e99-3707-508d-a97d-0d75889b5c9a | note | Verifying Records Checklists, Test and Supplier Certificates - ?
cda43a17-cf1a-5b2c-ae43-dc8d2fdf0ccb | signoff | AUTHORITY HOLDPOINT
19d8b93b-c4a4-55e7-ad84-fcfed6a60769 | checkpoint | 1.1.7 - Approval of stockpile location
1b3a81d4-0e09-5121-9c26-788f157b3581 | note | Method/Description - Document Review & Approval
326eba61-a9dc-5712-b9ca-9966dc847b73 | note | Test frequency - Prior to works commencing
b25e1244-930e-50ab-bb58-0e00d83a8336 | note | Contractor - H
0fe42e9c-25ef-5976-a855-5eb2a06e11c0 | note | Designer - H
d6e67424-952f-5384-bec9-25ef44e9b841 | note | Verifying Records Checklists, Test and Supplier Certificates - ?
724843d0-fcb5-5464-bdfa-4148b5a2ce77 | signoff | AUTHORITY HOLDPOINT
40ac7040-23b3-5151-b100-bc666aea5ad7 | section | 1.2.0 Material Compliance
a1238f1d-a91f-504e-994d-e554accc72cb | checkpoint | 1.2.1 - Structural fill
5fc7058d-46da-5dfd-a86d-1732f318088c | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
cc0df67d-b45e-5269-b280-818b498dd30f | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
caf36ebc-9909-584e-aef0-edd566e89c93 | note | • Triaxial (Single stage min. 3 samples) - BS 1377 Part 8: 1990. Methods of tests for Soils for civil engineering purposes – Test 7 or Test 8
cec78310-376b-52e9-b854-ce279b2cbb61 | note | Test frequency - 1 test per 20,000m³
06e6a241-3136-5004-8427-a080f041cd13 | note | Contractor - H
617c7773-2781-5469-bfc5-843c1ba862da | note | Designer - W
d698a9e7-51a5-5ed3-bdf9-c793b6b02760 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
57f696ae-0fa0-54e5-8594-35630edd6b1a | signoff | AUTHORITY HOLDPOINT
4375cfa0-b14d-59a0-a47d-b583f3b063a4 | checkpoint | 1.2.2 - Buttress Fill
6e842e6a-54ff-59d3-9470-fb4a5205080a | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
45ecceae-e84d-57d2-a88e-f8bdab0ad1ff | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
1f04baf1-07ca-5358-88c2-91c150c5d2bf | note | Test frequency - 1 test per 20,000m3
0a900ba6-1f79-5556-9fcd-ecd98196d97d | note | Contractor - H
f92a7750-3e4e-5d0a-a3a9-a900b540ce28 | note | Designer - W
670aa45d-4889-5e43-b84a-e1249e99e5d2 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
c0efaaf7-f4e4-5afb-b6b5-5becf2f21833 | checkpoint | 1.2.3 - GAP 65
9c740a6e-8cdb-52a6-9d62-8e429ce97fd9 | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.3
67480ea2-8248-598c-823e-7344fffeb339 | note | • NZS 4402 Supplement No 1:1998 - Test 3.8.1 Determination of the particle size distribution Standard method by wet sieving
be8cc692-0330-558a-b852-0ea7a4214757 | note | • Large shear box (min 3 normal stresses) - BS 1377 Part 7: 1990. Methods of tests for Soils for civil engineering purposes – Part 7 : Shear strength tests (total stress).Test 5 – Determination of shear strength by direct shear (large shear box apparatus)
e6bea317-9c5a-5276-8c06-2e25199693e4 | note | Test frequency - Determination of the dry density/water content - 3 tests per source.
c694db45-500d-57b6-90c3-0997b8a422df | note | • PSD - 3 no. tests per source + 1 test per 2,000m3.
75054765-b58d-5321-b86b-3576953a5afa | note | • Permeability, Large shear box (min 3 normal stresses) - 3 no. tests per source
bd06ccbb-640f-559d-9286-017191331ada | note | Contractor - H
9bb7105e-96e5-5b5b-b5a9-c3e8c81a4c45 | note | Designer - W
c5bcb335-c9c1-5f34-bdff-091d90a12925 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
91de1951-4552-50a8-8b6d-89dffc792541 | checkpoint | 1.2.4 - GAP 65
b95347ff-aa0e-5115-af84-f66859e6c3bd | note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
c1f243d8-d504-571f-8662-93d4b1b08273 | note | Test frequency - 3 no. tests per source and 1 test per 2000m3
1c4c2757-5579-5847-82e5-8f21a5255178 | note | Contractor - H
8ef58d5b-1336-52d3-91e5-f42d49851d85 | note | Designer - W
5609d593-aac0-5012-8424-f895ca3aa213 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
61091160-50f7-5108-8cbe-c665a30e8ac7 | checkpoint | 1.2.5 - Cement stabilised structural fill
23fe0fbd-c79a-5fd2-bfc0-a2888cef20ea | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
ef52621c-cc35-5389-9836-fc2ac990b949 | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
76bde9e1-5a97-5375-98cf-727ab48a46aa | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
a4fae4c5-76c9-5f65-bc55-8e3b5b2f4a2b | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
b9c041f6-1aa6-539d-87ac-4f9364055105 | note | • Atterberg limit - 1 test per source and 1 test per 500 m3
85a13705-1cdb-5924-9a3a-f225b9fabdd2 | note | • UCS - 3 no. tests per source at adopted cement ratio.
17d9408c-e7c0-5a2d-90b9-7d0912274a11 | note | Contractor - H
e93eefa6-9f30-5c6d-9395-ef2bea0b7640 | note | Designer - W
bf1b304c-f40d-58ad-a6cf-d83763cf48e7 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
2e35b49a-2d9d-59fa-b7b4-d467015e88c4 | checkpoint | 1.2.6 - MSE Fill
c924383a-bf1e-57a6-97ab-b7327c09ef88 | note | Method/Description - PH, Chloride ion content, sulphate content, electrical resistivity, organic content. Refer to The Reinforced Earth Company technical specification (TAINZ-TS-0100; Table 2)
4bf57aed-417b-5982-8772-317488d061c6 | note | Test frequency - 3 no. tests per source and 1 test per 2500m3
4a95af0c-5716-5bf3-8137-06135e0403f7 | note | Contractor - H
86686b7e-b0c1-5e3b-8575-9804afd8440f | note | Designer - W
b83b7c0a-9874-5bbc-89d6-b929b0828073 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
c4ea4217-0ca9-5320-ae9c-f4a7996a939b | checkpoint | 1.2.8 - Cement stabilised GAP 65
ce1a64af-ba5d-5af2-9c4a-bd52d9c04c5d | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
d390698d-822c-582c-b0f0-2c1a57a3b314 | note | • NZS 4402 Supplement No 1:1998 - Test 2.8.1 Determination of the particle size distribution Standard method by wet sieving
e42c1b44-e183-5f1d-b8ec-594f650831e0 | note | • NZS 4402 Supplement No 1:1998 - Test 2.8.3 Determination of the particle size distribution Standard method by hydrometer
7312d13e-7a47-59fc-810b-63332e2a420a | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
3f5d2f30-e252-5ec0-b102-00e15489ebf4 | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
9f298b74-ab69-52d8-9b49-094ec559f3fb | note | • PSD - 3 no. tests per source + 1 test per 2,000 m3
11a054a6-eb72-57a0-ade8-885820346df2 | note | • UCS - 3 no. tests per source at adopted cement ratio.
89b7c534-a19b-5331-8ec4-61780cdf09ef | note | Contractor - H
3a63962c-0f91-5111-9c75-5e5db315b837 | note | Designer - W
e6a54885-9a41-586d-aec2-37bc361566cd | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
0aacd5c2-02bb-5e46-82b4-75d8e4af789c | checkpoint | 1.2.9 - Cement stabilised structural fill
18e0ecc2-c1bc-551e-bcaa-8d117f7d90a8 | note | Method/Description - Determination of the dry density & OMC determination - NZS 4402:Supplement No 1:1998, Test 4.1.2
cb2d3c33-fe66-59c7-8030-55cae4ed270c | note | • Atterberg limits - NZS 4402:Supplement No 1:1998, Test 2.2, 2.3 & 2.4
cc499b43-ada5-5ad4-bca0-c6b366795ae8 | note | • Unconfined compressive strength test - NZS 4402 Supplement No 1:1998 Test 6.3.1.
7ad62184-4e33-5913-96c7-b00e32c77454 | note | Test frequency - Determination of the dry density/water content - 3 nos. tests per source
38fc5ab4-9f54-5a28-af9f-177185621f89 | note | • Atterberg limit - 1 test per source and 1 test per 500 m3
ec1130bd-8224-55f4-9350-82adb52f6f9d | note | • UCS - 3 no. tests per source at adopted cement ratio.
13d5fa02-5f05-565f-86a0-855e0391301b | note | Contractor - H
1369ebd8-0b5c-55a7-b8d6-c01be1dee74e | note | Designer - W
8364c7e9-8278-51d6-aee3-b445fcc3f905 | note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
2cb6f306-2e70-5654-8402-8b2ec9e52277 | section | 1.3.0 Geosynthetics, geogrid and basal reinforcement - Pre-construction
a0d1b4c5-5949-5558-8250-7684a084cf68 | checkpoint | 1.3.1 - Product name Name and address of producer/supplier Manufacturer’s compliance certificate
dfc6d86c-a7d0-549d-8103-ebfbc43d72b9 | note | Method/Description - Document Review
3f49e66f-27b3-5db3-b4c7-01ae780c9357 | note | Test frequency - Check each lot (1 roll)
3dcf9eaf-134d-5b8b-b37c-d452438c3c81 | note | Contractor - H
6a00fbbb-96b0-571a-844c-dc0fdbfc4520 | note | Designer - W
977b0cb2-fab5-597f-ad3d-fcb59fcf2fa1 | note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
b8261911-8ced-51ae-8ad1-71ec10996ee5 | checkpoint | 1.3.2 - Tensile strength (machine direction) - geogrid and basal reinforcement
6b312682-20dd-5521-a652-4a804adb6c19 | note | Method/Description - Document Review
27d5b2fa-0b8c-5a08-970c-9d355b1461ca | note | Test frequency - 1 test per production batch
90077b3b-9ade-5198-aea3-b92e7a44febe | note | Contractor - H
9fe05ba0-e3d1-5689-abd2-9f043b9dcff1 | note | Designer - W
5acde8d0-aa95-5250-bfab-031799620b49 | note | Verifying Records Checklists, Test and Supplier Certificates - Lab test cert
b4649fe9-a20a-5953-8fd0-6c614ee5b97b | checkpoint | 1.3.3 - Visual inspection - separation geotextiles, basal reinforcement
7edba1c7-cfc6-5c26-9ac6-8a370dbd5f8f | note | Method/Description - To inspect geotextile and basal reinforement is the proper type and no tears, rips or other signs of deterioration.
70b3561c-9dae-5efe-ad2e-218ddbe437cb | note | Test frequency - Check each lot (1 roll)
dc30d6c0-16d2-52b2-a254-58e7f99e486e | note | Contractor - H
cff40156-97da-5a03-b246-2ecb3e6845b5 | note | Designer - W
b2445143-698f-575b-9370-ce13a1387c07 | note | Verifying Records Checklists, Test and Supplier Certificates - Approval checklist
1a6ab162-84a3-5713-bd08-b7d0fc7fd420 | checkpoint | 1.3.4 - Visual inspection - geogrids
a6fa02d3-5d52-5402-a62a-291db157f256 | note | Method/Description - To inspect geogrid is the proper type and no tears, rips or other signs of deterioration.
7af6b0af-0b4b-52e4-9c62-24c8b4e50d74 | note | Test frequency - Check each lot (1 roll)
f9a1cdca-dba7-50cf-9e52-bbd393bc9711 | note | Contractor - H
de95b5aa-14ff-5c6f-95ba-fd9685ca48ad | note | Designer - W
d8e9db36-8fb2-50b3-aea1-8439359b718f | note | Verifying Records Checklists, Test and Supplier Certificates - Approval checklist
d65f2e5c-a857-5839-a24b-993bea45ce2f | section | 1.4.0 Monitoring - Pre-construction
42702933-7cc6-5ba0-b870-39eda8f6d009 | checkpoint | 1.4.1 - Monitoring prior to preload
4e4ad618-ec23-5ca0-ab5e-a1237938ffd1 | note | Method/Description - Baseline readings
057ae6a7-fec6-5698-85ae-f7f142d42112 | note | Test frequency - Settlement marker, extensometer, profilometer, and lateral deformation markers - 1 month before construction start. 2 consistent readings (24 hrs apart) post installation and one immediately prior to filling Vibrating wire piezometer - 1 month
c5f36bfe-9cf2-546e-bad0-d56637147e4c | note | Contractor - H
1b6b515d-d125-5456-9c97-3c1e434b5a2c | note | Designer - H
096e062b-f92d-5bff-bb7c-915e2808986d | note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary - confirming baseline readings satisfactory
62a168bf-14f7-5bcb-ae11-291e4b8c17b8 | signoff | AUTHORITY HOLDPOINT
cf067a8d-e9b1-5966-8add-fb54234eef7d | section | 2.1.0 Pre-filling
58543979-2b9b-5921-8d5b-0c34906f420b | checkpoint | 2.1.1 - Set out extents of fill and check against design
1056ca91-1289-58de-922b-0e500e9fcfff | note | Method/Description - Survey/visual
7b79e7d6-a31a-5931-bd63-9a1dd80f8e9e | note | Test frequency - Prior to Commencement
50ac7331-e74c-5514-97e2-9cab71b1f8e2 | note | Contractor - W
438590e0-ed48-5b3d-add6-e2963b4df405 | checkpoint | 2.1.2 - Vegetation Clearance
e3e61131-c40d-5470-a93c-090e828e4830 | note | Method/Description - Survey/visual
40e89c54-9b20-5897-855a-227d098f02fc | note | Test frequency - Fill area foot print
610d68e9-9738-5b5c-920f-9ab0b99e6e3f | note | Contractor - H
40ee3f69-74ac-54fe-8a49-a9c419d5bec0 | note | Designer - W
5f2ced3b-2e57-58bb-b07b-88b49adfa8c7 | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet Designer site report (where advise given)
862245e6-f218-5a61-bb79-c5bfceec4f89 | checkpoint | 2.1.4 - Designer witness of in-situ subgrade prior to filling
0c7fa32b-93be-5b2c-86b8-e0c3a56c0203 | note | Method/Description - Visual inspection
4832ef5e-f47d-59e9-9a4c-bda04d23df25 | note | Test frequency - Prior to Filling
dc11d2b9-4407-54a9-88b9-33f592567cbb | note | Contractor - H
29e6c598-5b25-5aa2-beeb-530dd25eac36 | note | Designer - H
bf8b4fed-9c9b-52b3-b994-a42be9f71a1b | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
e1215e41-225a-5d6b-b773-fa60c65c633d | signoff | AUTHORITY HOLDPOINT
9544fc50-a083-526d-a563-9ec7a24959fb | checkpoint | 2.1.5 - General Undercuts
ac514d07-ddf0-592a-9153-4b5f546ab61d | note | Method/Description - Visual inspection
41dcbadf-ec3e-5ec3-84e6-400a3e26dc92 | note | Test frequency - Prior to Filling
a9e77516-a4c9-5340-aee7-d28fb19d4c46 | note | Contractor - I
7ac43eb5-b116-58fd-9178-36a0750aa2a8 | note | Designer - I
f0c579ef-ad83-53bc-97fc-53c6d8a96f31 | note | Verifying Records Checklists, Test and Supplier Certificates - Subgrade approval checksheet
70202bbd-c12a-58c1-8344-9ef760ec6ead | checkpoint | 2.1.6 - Required undercuts for basal reinforcement installation
3480f777-a904-56eb-b9a4-d79f2b8c6219 | note | Method/Description - Visual inspection
06520e0f-6a06-5bd0-a4d5-4a8b37a31a13 | note | Test frequency - Prior to Filling
1f3264c8-20f1-5c43-ab5f-d35d7b96716e | note | Contractor - H
ab67a8df-28ab-5ae8-896b-013dd1bc9f9a | note | Designer - H
6f3e9b22-78ae-5763-b926-430f662340d3 | signoff | AUTHORITY HOLDPOINT
260c5884-acfb-5f8f-b8b0-bf35f1a7392a | checkpoint | 2.1.7 - Basal reinforcement installation
ee8adac9-fea8-542c-a789-b01a47493bca | note | Method/Description - Visual inspection of directional placement, panel length, laps, and damage
c662db2d-fab3-5b38-b749-9e849f6ea002 | note | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
84f5833c-b83f-58ea-bc82-75e82a408384 | note | Contractor - H
5067dfdf-d82a-54b2-8fc7-a37183507390 | note | Designer - H
f8c44445-6c82-55aa-96fa-0de241f02e15 | signoff | AUTHORITY HOLDPOINT
a6fb49d7-acf8-5f1b-ba57-15cc1e5a84d6 | checkpoint | 2.1.8 - Drainage blanket installation
bf44088c-6a88-5529-a4cd-fa2d06cccbba | note | Method/Description - Visual inspection
0a5f93b0-2ea9-5639-a053-77137316c762 | note | Test frequency - Prior to filling, and every 100m2 of geotextile installed.
c2db837e-4a44-5d64-9d6e-7e5e937c4872 | note | Contractor - H
f0c2daf9-4a2e-5221-a69f-8912915cd473 | note | Designer - H
fd0f6409-f3be-58b9-aaa7-79259a6aa1ac | signoff | AUTHORITY HOLDPOINT
72d9decb-4e4b-5ba1-9f0e-7853deac0d90 | checkpoint | 2.1.9 - Construction of wick drains
eed9ab96-9869-5901-9c98-73d791d28672 | note | Method/Description - Visual inspection and subcontractor record review
0dd722de-cdb6-58d0-b1f1-8c1fb2be2a69 | note | Test frequency - During wick drain construction
17596efd-2352-5432-9700-9e4d831de1d3 | note | Contractor - I
6cd7e87c-a2bd-5455-ae74-ad01f88c9c21 | note | Designer - W
7a4c5c42-e10c-5dfe-b933-747f38f45850 | note | Verifying Records Checklists, Test and Supplier Certificates - Wick drain check list
075a395e-5b9e-5fa4-914a-7b13d0564ca7 | checkpoint | 2.1.10 - Sub soil drainage
42ccfbf3-d7c8-5861-8695-87ef965970d0 | note | Method/Description - Inspection
3f6da756-e5f2-56f8-b4f6-cb3a297f7a5e | note | Test frequency - During subsoil construction
4e5a0339-543f-5332-92ca-06f701caa96a | note | Contractor - I
c42fb20e-057b-5948-a395-7a9c068ca1f4 | note | Designer - I
74c8065b-cd85-5891-a6fc-9f12d70d5128 | note | Verifying Records Checklists, Test and Supplier Certificates - Sub soil drainage ITP,
3afa5f76-2a6d-5f28-9ab5-e2c4fe8297d6 | checkpoint | 2.1.11 - Monitoring Equipment
6b9bea36-81df-5467-b603-75cead2f7917 | note | Method/Description - Survey/ data logging
bfccd6c5-e006-5bd0-915b-9f1becba6486 | note | Test frequency - As outlined in MMA-DES-GEO-E1-SKT-4077
abf886e1-f802-519f-a7f1-802dca3eb53d | note | Contractor - W
0454222b-e3bc-5f84-823b-bacf51f4567f | note | Verifying Records Checklists, Test and Supplier Certificates - Drill logs
f5ed585a-3cba-525c-9dc6-89488bcc7c81 | section | 2.2.0 Fill Construction
ca8d15bd-63b2-5c11-9d8f-b2ab8edfad49 | checkpoint | 2.2.1 - Filling operations
1e4eee05-2b8b-5f7e-a4ad-75a8996d96ca | note | Method/Description - Visual inspection
0d9b7c2e-1f76-5e9b-9b34-987cbad8a792 | note | Test frequency - Daily
f5b59f25-1b02-5c93-abd6-bc4790a820d3 | note | Contractor - W
10a7a72d-399a-50e4-912a-938f130c7865 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
c6c48250-3625-5f48-8d72-509cfed59c1c | checkpoint | 2.2.2 - Filling operations
590f413c-bc5c-501f-9230-21d41c7b9ae8 | note | Method/Description - Survey/visual
f09d59de-6754-51dc-bec3-c047c0a6951d | note | Test frequency - Daily
1580519a-7ac8-5084-9aa6-a7d0bf1036bf | note | Contractor - W
23fa558f-48fd-518e-bad3-d13dc474fb25 | note | Verifying Records Checklists, Test and Supplier Certificates - test report
854030b8-6c68-56b3-b5d6-595a65916d36 | checkpoint | 2.2.3 - Insitu fill testing
ec20bb4c-a3d2-5065-a7fc-ccbb753ba82b | note | Method/Description - Plateau Test
a453c1a3-24d7-5eaf-8a06-5ac243dbeb4b | note | Test frequency - Structural Fill - 1 test per material type per earthworks zone,
124fbdf9-52dc-5ff3-84c6-6fc5cf11502c | note | • Buttress Fill - 1 test per material type per earthworks zone
f0c0fca8-2726-598a-beed-31f8461f1af3 | note | • GAP65 - 1 test per material type per structure / location
d4efdf89-480c-5aa7-80a1-444e361aed7b | note | • Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location
ee686f5a-7f8d-5631-bbf4-a4cc05909ece | note | Contractor - W
61833c91-188c-5c25-8c44-70fec08dc8a5 | note | Designer - W
f4b6f81b-bb5a-5bb0-850c-0cc72ba47c9d | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
67fa0f67-96ef-5f19-ad08-3d77ea125216 | checkpoint | 2.2.4 - Insitu fill testing
fe14da24-958a-5b46-9de0-6ea0dfc8194d | note | Method/Description - In situ moisture content and density
5b0cc25b-0198-57a4-96b8-f7aedf5e4bdc | note | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length (approx 1 per 3000 m3) ; 1 test per lift per 50m length for top 1m of fill to subgrade level
3b5133b0-010c-5881-a1e8-5c20acdf6578 | note | • Buttress fill - 1 test per 200m length, approx 1 per 6000 m3
31c10d01-6a27-5b09-ba92-7d533d7d96e2 | note | • GAP65 - 4 tests per lift per structure
b95fa105-1813-5254-82fa-76d19ad6a362 | note | • Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure
5eb78135-4bbc-52f3-a53a-94582587602c | note | • Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length
1da394e1-1f8b-57d8-9229-00c507273604 | note | Contractor - W
2d842370-226b-5726-93ec-9ad07c0c106c | note | Designer - R
052d651a-6597-5ca1-a7b2-12188636fab2 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
0900f54e-be40-59d0-8c13-6db2d40791b3 | checkpoint | 2.2.5 - Insitu fill testing
ffe420a6-fa5e-5bd3-b6a5-db05ea076886 | note | Method/Description - Undrained shear Strength
12f930a3-afd3-5cd4-a47a-aaf3eb346a33 | note | Test frequency - Structural fill - 1 test per layer per 1000m2
d25a3467-ec32-5c9d-a55e-383c0a71567c | note | • Buttress Fill - 1 Test per layer per 2000m2
1635b668-6837-5e3d-a324-fad5ee830c8b | note | • Cement Stabilised Structural Fill - 1 test per layer per 500m2
283ac3a3-2e88-5042-82a5-6988c1b4c8e9 | note | Contractor - W
ae593c0e-dadc-56ce-a786-a4cf8aa09216 | note | Designer - R
703e8fbb-92b2-557c-9f05-380b2439272a | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
cbc38db0-5d27-5cb8-a99b-eecad01c06aa | checkpoint | 2.2.6 - Pavement Subgrade Fill Testing
cc647bff-19fc-50e3-8464-a62cdaa5f4e2 | note | Method/Description - in situ moisture content and density (and/ or air voids) testing of compacted fill material
50ab74b6-3db2-5da6-be8c-0764f24d0f39 | note | Test frequency - Surcharged Fills - 1 test at subgrade formation level per 50m length, Cut Fill Transitions - 1 Test per 0.5m lift per 50m length for 1.0m subgrade depth
a669c3db-1caf-5be6-9e9a-fcf790db4faa | note | Contractor - W
cc7eae38-0c01-5b0f-86f1-5127d4ebc492 | note | Designer - R
bc577fb3-7c22-5f3d-aa96-cb1fedcbbdad | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
284a15fc-5f1e-5461-802b-39846fca04f0 | checkpoint | 2.2.7 - Pavement Subgrade Fill Testing
b2390827-462b-5793-91ae-2865fccef62b | note | Method/Description - Scala Penetrometer Surcharged Fills
6fc16cd9-d17f-57f9-b8e8-b0591bcaa905 | note | Test frequency - 435mm above Subgrade formation level to 1.5m depth. 3 tests per 20m chainage evenly across formation pavement width
16b66314-a0aa-57d3-a05d-894fe995c16f | note | Contractor - W
664b35cc-d550-5ee2-b9fe-db2b478a84e0 | note | Designer - R
65d32115-8f52-592a-88a8-b6ad84eec55e | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
90f82bbc-7c77-5080-9894-3fee24b9e688 | checkpoint | 2.2.8 - Pavement Subgrade Fill Testing
01e3215c-e556-534b-a474-d5fa358c39d1 | note | Method/Description - Benkelman beam and FWD Testing
453fb531-f452-5b5b-9aed-aa2e53ca6026 | note | Test frequency - Surcharged Fills - At subgrade formation level 10m interval in each wheel path
a572348a-90b7-5565-ab36-52514901a76c | note | • Cut Fill Transitions - at three heights: 1.0m, 0.5m and 0m below subgrade formation level 10m interval in each wheel path
3134ec51-bfe1-5848-aab8-c6d362e75a81 | note | Contractor - W
0f8e517d-537c-5544-a591-34539a8f0986 | note | Designer - R
79a00819-98d5-5246-ae99-7eb67a88926c | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
4efa10f0-7afe-53e1-b597-18591b6c7850 | checkpoint | 2.2.9 - Pavement Subgrade Fill Testing
24a5717e-2919-5200-998b-997057ae1e1a | note | Method/Description - Laboratory Soaked CBR
1e4936b9-f357-57ff-b0c0-d98c2efc11b2 | note | Test frequency - Surcharged Fills and Cut Fill Transitions - 1 Test per 5000m2 at subgrade formation level
faf65416-3d56-58f3-85c1-015bebae8f29 | note | Contractor - W
8c6a3b80-1ba7-5bc3-81e0-d7bf5fda7642 | note | Designer - R
06f4e76b-e9c6-50ed-a167-d8eae77752f0 | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
83fe715c-0c21-59e5-8e43-2a4cad5f184b | checkpoint | 2.2.10 - Confirm testing requirements are meet for insitu fill
af89f5a8-465b-5698-adec-10be03ae82a0 | note | Method/Description - Summarise, interpret and review test records
865041c7-878d-543a-846a-bbbbf75a23d5 | note | Test frequency - Every test result
a1854082-b9a5-599f-8a19-6a14e0b975c2 | note | Contractor - H
45e89e15-d49c-5fc0-a970-04f92ecdbf1e | note | Designer - H
8d8677ca-8b07-5302-b8b4-773fb9064aaf | note | Verifying Records Checklists, Test and Supplier Certificates - Review of testing records
8388a423-c359-55bc-9eff-1b899a325e81 | signoff | AUTHORITY HOLDPOINT
4641fb01-25ca-50ad-9142-2fea76a7350e | checkpoint | 2.2.11 - Failed test result and remedial approval
978410f7-d492-5c3f-8469-f4a587881556 | note | Method/Description - Review and approval of remedial action
da02a4e1-161d-5232-9191-1a3866fed6a4 | note | Test frequency - Every failed test and prior to remedial works
33cf084f-b57d-5e9f-bae4-3d31aa60290c | note | Contractor - H
eb9c6464-4c79-5082-b888-caa806c04c9e | note | Designer - H
bf673edb-be0e-5d76-a7be-9092fea4c24e | signoff | AUTHORITY HOLDPOINT
7f89079d-cda4-55b2-ab50-1a8db2ace849 | checkpoint | 2.2.12 - Insitu Fill Testing
82d4cdc0-3ec4-590f-bc86-5f7ca1bf3219 | note | Method/Description - Undrained shear Strength
22c5d558-a834-51b9-8b4a-934507e56f7f | note | Test frequency - Structural fill - 1 test per layer per 1000m2
2e832840-edc7-5ff5-9a03-7ef3dc05c5a3 | note | • Buttress Fill - 1 Test per layer per 2000m2
eece1da6-06bd-53e9-b2c9-cbb2a26f5e7c | note | • Cement Stabilised Structural Fill - 1 test per layer per 500m2
e8ee7147-d185-53a8-a85a-441af5ae2501 | note | Contractor - W
1cdec2cd-06d6-5f86-8dbc-cbc21614f28f | note | Verifying Records Checklists, Test and Supplier Certificates - Test report
abf3d6d2-8f49-501e-8763-a456ac66b5f2 | section | 2.3.0 Preload/Surcharge (for embankments requiring preload)
6deb424e-254c-50ae-892e-99dec8122407 | checkpoint | 2.3.1 - Visual inspection for rate of filling
10c4545e-de25-5a5c-a168-4f21293bd73f | note | Method/Description - Inspection of fill height, rate of filling of 200mm/day (1m per week)
4f07bd8e-166d-5735-a1d8-267d811adfb3 | note | Test frequency - To be monitored daily
7806a283-7d1f-5d25-bb18-147fa620e32f | note | Contractor - H
065fbfb0-056f-5dfa-a5f8-32eff8f25091 | note | Designer - W
00e58ff8-9766-5514-9579-9d193dae66b4 | checkpoint | 2.3.2 - After 1m of fill placement. Await approval from Designer before placing more fill.
f2efcc47-ad20-52d1-9262-78af7d76a26f | note | Method/Description - Review data and TARP levels before releasing HOLD.
818092fa-e6cf-50c9-beae-ce0f8b8ff080 | note | Test frequency - Before releasing hold periods and allowing filling to continue.
366a83f9-ed1d-59b6-a51d-d91de90b554d | note | Contractor - H
d1f0ba82-7efe-5dcb-b6fc-1fbdf8798d13 | note | Designer - H
970d389c-1bce-51c8-8bd4-a427b9b4d60e | note | Verifying Records Checklists, Test and Supplier Certificates - Designer site diary
1a38b1ec-504f-57af-b33c-55650cd60378 | signoff | AUTHORITY HOLDPOINT
ba21e5c0-002b-581c-a9a2-df988f0b76ae | checkpoint | 2.3.3 - Removal of preload/surcharge
426f1f25-f038-5105-ae0b-f9faff0a44e5 | note | Method/Description - Assessment of monitoring and instrumentation data
d822bd21-2701-5001-9dd5-d8f220626730 | note | Test frequency - After completion of proposed hold period
5e007f41-66e9-542d-aa89-517a5c49edca | note | Contractor - H
e6c88f6a-d0ac-54a6-8221-9f476f4bd4ac | note | Designer - H
876481c0-bb68-5bb8-8241-0b258305c146 | signoff | AUTHORITY HOLDPOINT
5d38b1b1-f66a-5279-a5d4-cfbcba80db16 | section | 2.4.0 Monitoring
21607b28-2d45-5c79-8c1e-c9d831eb80c9 | checkpoint | 2.4.1 - During earth filling/preloading/surcharging
0508c0c1-3b68-5298-ab26-971a6c8cdd4d | note | Method/Description - Monitoring during earth filling/preloading/surcharging
ac6e85aa-d9b7-56a1-b2d4-9ed493d69c5e | note | Test frequency - Plate settlement marker, extensometer, profilometer, water standpipe, and lateral deformation marker- twice weekly Vibrating wire piezometer - hourly reading via data logger, twice weekly download
7b43fb96-5a3d-5665-861f-a1c7fd890290 | note | Contractor - W
ea56ba06-57cd-5c61-9b21-b229ce4daedf | checkpoint | 2.4.2 - During preload or surcharge hold period
ec8a779d-8d2d-594b-907c-c8f6dd8e0c8a | note | Method/Description - Monitoring during preloading or surcharge hold period
d60d1926-e190-5341-9c8b-a189abfec7ad | note | Test frequency - Plate settlement marker, extensometer and profilometer, and lateral deformation marker - twice weekly for the first month then weekly. Vibrating wire piezometer - hourly reading via data logger, twice weekly download
678f212b-8a42-5868-a84c-12b6fbed5944 | note | Contractor - W
0cf7ff11-e900-53fd-bf72-eb63a2e335fb | checkpoint | 2.4.3 - At surcharge removal or hold period release
1c573b88-3078-5933-91db-1c442ee4743d | note | Method/Description - Monitoring at surcharge removal or hold period release
4c9e8f91-f39a-572f-a85a-6505d660fd59 | note | Test frequency - Plate settlement marker, extensometer and profilometer, lateral deformation marker, and vibrating wire piezometer - one reading 24 hours prior and one reading 24 hours following.
7a325fb4-0492-5d84-bdd5-f0cbfe83eff1 | note | Contractor - W
28f0a228-5fb7-5aaf-bb29-794b3586bca9 | section | 2.5.0 Monitoring reports
8b606181-c983-5bca-88dc-b467817ced37 | checkpoint | 2.5.1 - Preliminary inspection/monitoring report
b08d460d-bc6d-5fba-b22b-ad6393e8bc26 | note | Method/Description - Summary of site inspection / observation / measurement
16ce8cc1-eecb-5edc-ae6b-8e98181bffa8 | note | Test frequency - Within one working day of site inspection/observation/measurement
2967dff5-eddc-54d8-926c-341b575369c9 | note | Contractor - W
7f047d64-3aed-5f16-821e-f32443e70d74 | checkpoint | 2.5.2 - Inspection/ monitoring report
9f48fe2d-8360-5dda-a43f-e4871c95e452 | note | Report - Full and certified results
3dfc2134-58ee-5b80-88dd-5c8590d4f4a6 | note | Frequency/timing - Within five working days of reading the particular instrument
4e48e42a-eaec-50aa-90db-eb341fc3afc4 | note | Owner - Construction Team and Geotechnical Technician
8b2b65f7-137a-56db-b113-5b69bccfff7b | note | Distribution - Geotechnical Engineer, Geotechnical Lead
c7e4d0ae-e975-5d2e-b7f3-b9458e127e4c | checkpoint | 2.5.3 - Pre surcharge removal report
ff8beb86-d12f-5560-8246-a1c80f7c0678 | note | Report - Comparison between monitored results and baseline design predictions in both table and graphical format. Provide approval to remove surcharge.
a7d4b419-c260-5cf8-96f5-a4e0b22aa619 | note | Frequency/timing - Prior to surcharge removal at each fill
e60d8ccf-98e9-5478-985a-87c124c23c05 | note | Owner - Geotechnical Engineer (with Geotechnical Lead approval)
6a7e8fcd-a899-5703-8f66-c8f396c9dd6e | note | Distribution - Design Manager, Construction Manager
d5545795-84a2-5564-99ac-44165c0761fb | section | 3.0 Post Construction
c421ac5b-2341-54ac-9eef-7f76b03d37ee | checkpoint | 3.2 - Survey As-builts
5da60d60-bdd0-5bfe-b0e7-868735364dd0 | note | Test frequency - During construction and at end
2b08a453-1ed5-568f-9545-ce3745e7ef82 | note | Contractor - H
cff27b27-0d6d-53c6-8a51-7394f8cc638a | note | Verifying Records Checklists, Test and Supplier Certificates - CAD files
f942a45e-241e-5b37-8e44-9028309ca493 | checkpoint | 3.3 - As-builts
8d12136b-99b7-56a6-b8e8-423c4f932c01 | note | Method/Description - Mark up of construction drawings to reflect completed works
b5546a51-57d1-5cf1-9ae4-55734aedefc3 | note | Test frequency - End of Construction or after completion of preload/surcharge works
79a814d3-c269-50a3-8459-acaec7673abd | note | Contractor - H
3dd1ce46-19e3-55b4-9cd6-a7d70d14373c | note | Designer - H
4110ec92-8b1c-5466-a377-9bccbb7254f0 | note | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
a7e79338-2b18-506b-bce6-2cb742cbfcd9 | signoff | AUTHORITY HOLDPOINT
8919eff8-fed3-572c-bcf7-d24e7712e7ba | section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
45524c2d-1de8-5e60-b52d-1f4484181dd2 | checkpoint | ITP Close-Out by
37d3795c-51da-5d7f-ad97-0fb503cf9c4f | note | Site Engineer/Project Engineer
7726aa8f-f137-5131-9ccb-a0d7cb3915d0 | note | Zone Manager Approval
9ee3c4da-5bab-5d55-ba41-2d8efd8d318b | note | Construction Manager Approval
c4b083ec-831a-54d2-ad43-5c7405c973ff | note | Quality Manager Approval
8093829e-d2ee-5a87-9383-b08bc5ebef17 | date | Date:
1dc2c9d0-048a-5501-9488-936d3248a797 | signoff | SIGNATURE