## Fill 14 ITP
Inspection and Test Plan Te Ara o Te Ata MMA-QA-ITP-Z07-EW-GE004 MSE Wall 4
| This ITP has been prepared by |  |  | Reviewed by Quality Manager |  |  | Reviewed by CPS |  |  | Approved by Construction Manager
Rev # | Name | Signature | Date | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 01 | Libby Whyte | LW | 2025-02-07 |  |  |  | Dave Averill | DA | 2025-02-21
Rev 02
Rev 03
Rev 04
ITP NO: MMA-QA-ITP-Z07-EW-FL014 |  | Project: Te Ara o Te Ata | [5 empty] | Method Statement Ref:
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Structural Fill | [7 empty] | Area Location / Work Breakdown: Zone 7 (Fill 14)
Item | Construction Step or Material |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Responsible |  |  |  | Verifying Records Checklists, Test and Supplier Certificates
[5 empty] | Method/ Description | Test frequency |  | Conformance Criteria | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.01 | CWP |  |  |  | Document Review | Prior to personal starting |  | Ensure all crew members are briefed on the CWP | H |  |  |  | Signed off CWP
1.02 | IFC's specification |  | MMA-GES-GEO-E1-SPC-3859 MMA-DES-GEO-E1-SPC-8804 |  | Document Review | Prior to works commencing |  | Obtain copy of the earthworks specifications | H | H |  |  | IFC Technical Specifications
1.03 | IFC drawings |  | IFC drawings |  | Document Review | Prior to works commencing |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB | H | H |  |  | IFC Drawings upload into InEight
1.04 | Approved earthworks model |  |  |  | Document Review | Every new Earthworks Model and prior to work commencing |  | Designer to confirm and approve models to be loaded on the equipment | H | H |  |  | Earthworks model approval
1.05 | Approval of stockpile location |  | MMA-DES-GEO-E1-SPC-3859 |  | Document Review & Approval | Prior to works commencing |  | Approved stockpile location | H | H |  |  | RFI of Approval of stockpile location
2.0 Material Compliance
2.01 | Determination of the dry density/water content relationship (Heavy Compaction) for Structural Fill Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 & 7.2 |  | NZS 4402:1986, Test 4.1.2 | 1 Per 2,500m3 (Structural Fill) |  | N/A | H | R |  | I | MDD Test Report
2.02 | Atterberg limits test for Structural Fill Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 & 7.2 |  | NZS 4402:1986, Test 2.2, 2.3 & 2.4 | 1 Per 2,500m3 (Structural Fill) |  | Liquid Limit less than 50% | H | R |  | I | Test Report
2.03 | Subsoil Drainage Backfill |  | MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 & 7.2 |  | NZS 4402:1986, Test 2.8 | Source Approval 3 no. tests + 1 test per 500m3 |  | Crushing Resistance - <10% fines passing 2.36mm | H | R |  |  | Material Compliance Certificate
2.04 | Subsoil Drainage Backfill |  | MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 & 7.2 |  | Constant Head Permeability of Aggregate: LAP2 | Source Approval 3 no. tests |  | Permeability - >/= 1x10^-4 m/s | H | R |  |  | Material Compliance Certificate
2.05 | High Strength Geo Grid |  | MMA-DES-GEO-E1-SPC-3859 Clause 4.17 |  | Designer Approval | Once Prior to commence |  | Use the Specific high strength Geotextiles as per IFC Drawings, RFI to be submitted to designers for use of alternative | H | R |  |  | Material Compliance Certificate
2.06 | Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 4.1.2 | Source approval 3 no. tests |  | Report Only | H | R |  | I | MDD Test Report
2.07 | Particle size distribution (PSD) Test for GAP 65 material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 2.8 | Source approval 3 no. tests then every 2000m3. |  |  | H | H |  | I | PSD Test Report
2.08 | Permeability test for GAP 65 material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | ASTM D5084 - 16a | Source approval 3 no. tests |  | > 5x10-5 m/s | H | H |  | I | Permeability Test Report
2.09 | Visual inspection - separation geotextiles, basal reinforcement |  | MMA-DES-GEO-E1-SPC-3859 |  | To inspect geotextile and basal reinforcement is the proper type and no tears, rips or other signs of deterioration. | Check each lot (1 roll) |  | Report Only | H | H |  |  | Material Delivery Inspection Checklist
3.0 During Construction
3.1 Pre-filling
3.1.1 | Set out extents of fill and check against design |  |  |  | Survey/visual | Prior to Commencement |  | Consistency with Construction Drawings | W
3.1.2 | Ensure GPS plant have the correct model set up in machine and that a datum is available for checking |  |  |  | Survey/visual | Prior to Commencement |  | Consistency with Construction Drawings | W
3.1.3 | Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots. |  | MMA-DES-GEO-E1-SPC-3859 Clause 6.3 |  | Survey/visual | Immediately prior to earthworks beginning in all Fill areas |  | Construction team shall coordinate with the Designer ahead of and during clearing and stripping operations to determine the stripping depth. | H | H |  |  | Daily Site Report by Design Site Representative
3.1.4 | Designer witness of in-situ subgrade prior to filling |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 |  | Inspection | 100% subgrade inspection |  | Before fill is placed in any area, the Constructor shall notify the Designer that the fill foundation has been stripped and drained, and is ready for the Designer’s inspection and approval. | H | H |  |  | Daily Site Report by Design Site Representative
3.1.5 | MSE Wall Undercut Inspection |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | Visual inspection | 100% of works area |  | • Where shown on the drawings. • The Designer will specify the depth of the undercut in materials. • The Constructor shall treat any excavated undercut material as landscape fill or unsuitable. Inspection to cover the benching into the exisiting ground around the undercut. | H | H |  |  | Daily Site Report by Design Site Representative
3.2 Fill construction
3.2.1 | Basal reinforcement installation |  | IFC drawings and MMA-DES-GEO-E1-SPC-3859 |  | Visual inspection of directional placement, panel length, laps, and damage | During basal reinforcement installation and every 100m² of geotextile installed. |  | Ensure geogrid used is the correct type, undamaged, and directional placement, tensioning, laps, and spacing are correct | H | H |  |  | Geotextile Installation Checksheet
3.2.2 | Subsoil Drainage Backfill |  | MMA-DES-GEO-E1-SPC-3859 Section 9 |  | Visual inspection | Prior to Backfilling |  | Subsoils drains to be checked that they are being installed as per the earthworks specification and drawings | H | H |  |  | Subsoil Installation Checklist
3.2.7 | insitu fill testing-Plateau Test |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | Plateau Test | Structural Fill - 1 test per material type per fill MSE Fill - 1 test per material type per fill |  | Reviewed by designer | W | R |  | I | Test report
3.2.8 | insitu fill testing-In situ moisture content and density |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | In situ moisture content and density | Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057 MSE Fill - 1 test per 1 m lift per 100m length GAP 65 - 4 tests per 1 m lift per 100m length |  | Structural Fill - average > 95% MDD All tests > 92%, GAP65 - Average > 98% MDD All tests > 95%, MSE Fill - Average > 95% MDD All tests > 25%, | W | R |  | I | Test report
3.2.9 | insitu fill testing- Strength |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | Scala penetrometer | Scala Structural fill - 1 test per layer per 100m MSE Fill - 1 Test per layer per 100m | Structural fill - 1 test per layer per 1000m2 Average > 150kPa all tests > 120kPa Buttress Fill - 1 Test per layer per 2000m2 Average > 120kPa all tests > 80kPa Cement Stabilised Structural Fill - 1 test per layer per 500m2 Average > 150kPa all tests > 120kPa | MSE Fill - The number of blows per 100mm to drive the scala penetrometer from a depth of 100 to 1000mm below the fill surface shall not be less than 5 Structural fill - The number of blows per 100mm to drive the scala penetrometer from a depth of 100 to 1000mm below the fill surface shall not be less than 5 | W | R |  | I | test report
4.0 Post Construction
4.01 | Survey As-builts |  |  |  | Survey As-built | During construction and at end |  | Ensure all features and buried items are captured. | H |  |  |  | CAD files
4.02 | As-builts |  |  |  | Red Pen Mark up | End of Construction |  | All variances captured | H | H |  |  | Red pen mark ups
Note on G22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MSE fill, so 1 test per 2,500m3
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Only need to do liquid limit as per revised specification. Reply: To do liquid limit you need to do atterbergs
Note on G23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is MSE fill, so 1 test per 2,500 m3
Note on I23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Liquid Limit less than 50%
Note on I24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add conformance criteria into here from Table 4-2 of specification
Note on I25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add conformance criteria into here from Table 4-2 of specification
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this the geogrid? Reply: Changed the title
Note on A38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to have witness point for benching into existing ground on each side of MSE wall. Reply: It is covered in the undercut hold point I think, I will change the wording a touch
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Also obviously need to ensure that it is undamaged Reply: Added
Note on I41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Probably not much use here since there will be a small volume of fill placed. Also any plateau test wont be fully representative due to variabilities with MSE embankment filling (i.e. geogrid placement and assuming will need to use light weight compaction equipment until you can fit a roller in there). Suggest we do a semi plateau test, i.e. spread and compact up first layer, then get testing completed as per CPSA-051 compaction test template Reply: We can workshop this onsite but sounds good.