## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - MSE Wall 4 | itp |  |  |  |  | ITP - MSE Wall 4 Rev 1
section | 1.0 Pre-Construction
checkpoint | 1.01 - CWP
label | Method/Description - Document Review
label | Test frequency - Prior to personal starting
label | Conformance Criteria - Ensure all crew members are briefed on the CWP
label | Constructor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.02 - IFC's specification
label | Specifications and Standards - MMA-GES-GEO-E1-SPC-3859, MMA-DES-GEO-E1-SPC-8804
label | Method/Description - Document Review
label | Test frequency - Prior to works commencing
label | Conformance Criteria - Obtain copy of the earthworks specifications
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC Technical Specifications
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - IFC drawings
label | Specifications and Standards - IFC drawings
label | Method/Description - Document Review
label | Test frequency - Prior to works commencing
label | Conformance Criteria - Ensure all drawings are approved and of the latest revision, or written approval from PAB
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings upload into InEight
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.04 - Approved earthworks model
label | Method/Description - Document Review
label | Test frequency - Every new Earthworks Model and prior to work commencing
label | Conformance Criteria - Designer to confirm and approve models to be loaded on the equipment
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Earthworks model approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.05 - Approval of stockpile location
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859
label | Method/Description - Document Review & Approval
label | Test frequency - Prior to works commencing
label | Conformance Criteria - Approved stockpile location
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - RFI of Approval of stockpile location
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Material Compliance
checkpoint | 2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural Fill Material
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 & 7.2
label | Method/Description - NZS 4402:1986, Test 4.1.2
label | Test frequency - 1 Per 2,500m3 (Structural Fill)
label | Conformance Criteria - N/A
label | Constructor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint | 2.02 - Atterberg limits test for Structural Fill Material
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 & 7.2
label | Method/Description - NZS 4402:1986, Test 2.2, 2.3 & 2.4
label | Test frequency - 1 Per 2,500m3 (Structural Fill)
label | Conformance Criteria - Liquid Limit less than 50%
label | Constructor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 2.03 - Subsoil Drainage Backfill
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 & 7.2
label | Method/Description - NZS 4402:1986, Test 2.8
label | Test frequency - Source Approval 3 no. tests + 1 test per 500m3
label | Conformance Criteria - Crushing Resistance - <10% fines passing 2.36mm
label | Constructor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
checkpoint | 2.04 - Subsoil Drainage Backfill
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 & 7.2
label | Method/Description - Constant Head Permeability of Aggregate: LAP2
label | Test frequency - Source Approval 3 no. tests
label | Conformance Criteria - Permeability - >/= 1x10^-4 m/s
label | Constructor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
checkpoint | 2.05 - High Strength Geo Grid
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 4.17
label | Method/Description - Designer Approval
label | Test frequency - Once Prior to commence
label | Conformance Criteria - Use the Specific high strength Geotextiles as per IFC Drawings, RFI to be submitted to designers for use of alternative
label | Constructor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
checkpoint | 2.06 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2
label | Method/Description - NZS 4402:1986, Test 4.1.2
label | Test frequency - Source approval 3 no. tests
label | Conformance Criteria - Report Only
label | Constructor - H
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
checkpoint | 2.07 - Particle size distribution (PSD) Test for GAP 65 material
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2
label | Method/Description - NZS 4402:1986, Test 2.8
label | Test frequency - Source approval 3 no. tests then every 2000m3.
label | Constructor - H
label | Designer - H
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.08 - Permeability test for GAP 65 material
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2
label | Method/Description - ASTM D5084 - 16a
label | Test frequency - Source approval 3 no. tests
label | Conformance Criteria - > 5x10-5 m/s
label | Constructor - H
label | Designer - H
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.09 - Visual inspection - separation geotextiles, basal reinforcement
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859
label | Method/Description - To inspect geotextile and basal reinforcement is the proper type and no tears, rips or other signs of deterioration.
label | Test frequency - Check each lot (1 roll)
label | Conformance Criteria - Report Only
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Material Delivery Inspection Checklist
holdpoint | AUTHORITY HOLDPOINT
section | 3.1 Pre-filling
checkpoint | 3.1.1 - Set out extents of fill and check against design
label | Method/Description - Survey/visual
label | Test frequency - Prior to Commencement
label | Conformance Criteria - Consistency with Construction Drawings
label | Constructor - W
checkpoint | 3.1.2 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
label | Method/Description - Survey/visual
label | Test frequency - Prior to Commencement
label | Conformance Criteria - Consistency with Construction Drawings
label | Constructor - W
checkpoint | 3.1.3 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots.
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 6.3
label | Method/Description - Survey/visual
label | Test frequency - Immediately prior to earthworks beginning in all Fill areas
label | Conformance Criteria - Construction team shall coordinate with the Designer ahead of and during clearing and stripping operations to determine the stripping depth.
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.4 - Designer witness of in-situ subgrade prior to filling
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.2
label | Method/Description - Inspection
label | Test frequency - 100% subgrade inspection
label | Conformance Criteria - Before fill is placed in any area, the Constructor shall notify the Designer that the fill foundation has been stripped and drained, and is ready for the Designer’s inspection and approval.
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.5 - MSE Wall Undercut Inspection
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3
label | Method/Description - Visual inspection
label | Test frequency - 100% of works area
label | Conformance Criteria - Where shown on the drawings.
label | ○ The Designer will specify the depth of the undercut in materials.
label | ○ The Constructor shall treat any excavated undercut material as landscape fill or unsuitable.
label | ○ Inspection to cover the benching into the exisiting ground around the undercut.
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
holdpoint | AUTHORITY HOLDPOINT
section | 3.2 Fill construction
checkpoint | 3.2.1 - Basal reinforcement installation
label | Specifications and Standards - IFC drawings and MMA-DES-GEO-E1-SPC-3859
label | Method/Description - Visual inspection of directional placement, panel length, laps, and damage
label | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
label | Conformance Criteria - Ensure geogrid used is the correct type, undamaged, and directional placement, tensioning, laps, and spacing are correct
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Geotextile Installation Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Subsoil Drainage Backfill
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Section 9
label | Method/Description - Visual inspection
label | Test frequency - Prior to Backfilling
label | Conformance Criteria - Subsoils drains to be checked that they are being installed as per the earthworks specification and drawings
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Installation Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - insitu fill testing-Plateau Test
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3
label | Method/Description - Plateau Test
label | Test frequency - Structural Fill - 1 test per material type per fill
label | ○ MSE Fill - 1 test per material type per fill
label | Conformance Criteria - Reviewed by designer
label | Constructor - W
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 3.2.8 - insitu fill testing-In situ moisture content and density
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3
label | Method/Description - In situ moisture content and density
label | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057
label | ○ MSE Fill - 1 test per 1 m lift per 100m length
label | ○ GAP 65 - 4 tests per 1 m lift per 100m length
label | Conformance Criteria - Structural Fill - average > 95% MDD All tests > 92%,
label | ○ GAP65 - Average > 98% MDD All tests > 95%,
label | ○ MSE Fill - Average > 95% MDD All tests > 25%,
label | Constructor - W
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 3.2.9 - insitu fill testing- Strength
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3
label | Method/Description - Scala penetrometer
label | Test frequency - Scala
label | ○ Structural fill - 1 test per layer per 100m
label | ○ MSE Fill - 1 Test per layer per 100m
label | Conformance Criteria - MSE Fill - The number of blows per 100mm to drive the scala penetrometer from a depth of 100 to 1000mm below the fill surface shall not be less than 5
label | ○ Structural fill - The number of blows per 100mm to drive the scala penetrometer from a depth of 100 to 1000mm below the fill surface shall not be less than 5
label | Constructor - W
label | Designer - R
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - test report
section | 4.0 Post Construction
checkpoint | 4.01 - Survey As-builts
label | Method/Description - Survey As-built
label | Test frequency - During construction and at end
label | Conformance Criteria - Ensure all features and buried items are captured.
label | Constructor - H
label | Verifying Records Checklists, Test and Supplier Certificates - CAD files
checkpoint | 4.02 - As-builts
label | Method/Description - Red Pen Mark up
label | Test frequency - End of Construction
label | Conformance Criteria - All variances captured
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups
holdpoint | AUTHORITY HOLDPOINT
section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
signoff | SIGNATURE