## Master List Templates
Id | Type | Name | Values | Prompting Name
8c253716-b068-4463-864a-a3ae084d0e6b | checklist | Add Site Visit Checklist |  | Site Visit Date:
4729aca8-cc4e-4c3b-9d0d-a415b9052b42 | checkpoint | Details entered
c3a4ba6a-1e39-5d18-880b-bcdc67943f1e | textbox | Site visit performed by
4c7c7e47-fb8f-57a7-b263-468dc7b66dfc | textbox | Site visit completed with / attendees
ab920d2f-11ad-511e-b608-b814391e07d9 | textbox | Description of area
2ebdfd27-7e28-4565-8eee-4f24e4f57fca | checkpoint | Photos taken
83fe08c2-8d6e-434f-bf70-eb85b3f4bb73 | checkpoint | General observations and comments
4394ccfc-826d-4325-b3ea-75b1f92f751f | checklist | Add Variation |  | Variation Details -
5812f9c1-031f-4ef4-8377-40218f3be5b5 | checkpoint | Variation Details Approved
a1dcf207-c630-5a69-87a0-3ffad882385e | textbox | Reference/Drawing/Instruction Number
e72912a4-382e-5a1d-b596-ca10ca275739 | textbox | Variation Area
b09de357-4c7d-5c81-b481-e02733600b27 | textbox | Materials & labour breakdown
42639ab8-ba44-4321-b193-ffa3b389b783 | signoff | Request Variation Acknowledgement
5720f4c5-8810-49b3-8227-164f7f441f37 | checkpoint | Variation Completed
743190f8-163d-40f9-995b-87adf468e9f5 | signoff | Request Variation Signoff
2aa2a7ed-2364-4deb-ba20-22d94b115844 | checklist | Document Attach |  | Document:
12c8ad85-0133-4af1-948a-ad327307b0f9 | checkpoint | Document Attached

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
facba851-a294-4134-a819-2e70cb0549a8 | checklist | Chiller Roof Small Plinth Variations |  | Chiller Roof Small Plinth Variations
50022278-2ee5-4a4e-baef-1fe59f9e46bb | section | Details
96183990-47c2-4323-a1c1-c90d6684eea0 | checkpoint | Substrate acceptable
25d41d97-f3ae-45b0-afd2-9fa1c6f7272f | checkpoint | Membrane applied over grouted surface
19cd2d5d-52c0-5e9a-ae27-91c183deaf7b | note | Photo required
323c40b3-791f-442b-9f36-2d0fcc0b24ed | checklist | Chiller Roof Square Plate Variation |  | Chiller Roof Square Plate Variation
a17bee81-16d8-41ed-89ab-b43bac77c998 | section | Details
d6eed782-700e-437a-95c4-914485f6c3f8 | checkpoint | Substrate cleaned
15fd5464-6c24-4a01-b003-8c03c700544d | checkpoint | Customs flashings installed
f3b84007-0896-400a-afa1-18a26787c95c | checkpoint | Primer applied
7bd900f0-56e4-5281-8e90-590eaee22216 | note | Photo required
e8a1d5e0-9320-4450-8fea-c55f35e3773d | checkpoint | Pourable sealant applied
bd114b98-a37c-5a4e-8062-61dd46a488d2 | note | Photo required
cead1e0a-a12a-4988-89bb-8771eebe4b90 | checklist | Enviroclad Plinth sections |  | Enviroclad Plinth sections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c7932c22-0315-4929-9592-251b8d06f16b | checkpoint | Plinth number
73335a54-9601-4ac5-a4a3-e56767dea305 | checkpoint | Substrate as per manufactures specs
d9e612df-49e8-4501-b840-a01605ee5429 | checkpoint | Application of adhesive to substrate and membrane
3cecc75f-a14b-410d-83f0-33cc9220fe8c | checkpoint | Enviroclad application to manufactures specs
03bfb535-6a45-4d16-86d2-4b7a50368136 | checkpoint | Laps heat wielded
1070ad15-74ef-4ee0-8e08-5d51283e382c | checkpoint | Corners detailed
ed00f9d9-31f2-4604-aed1-d615b88b6eeb | checkpoint | Marked up drawing showing Plinth location
3a751906-e398-4d99-87be-c9a3397336d7 | checklist | Enviroclad TPO Flat sections |  | Enviroclad TPO Flat sections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
fef0e9ba-e359-4eeb-b032-6131eea2798d | checkpoint | Substrate as per manufactures specs
5d05bc08-d07b-4d93-9c25-b469e9ba601b | checkpoint | Application of adhesive to substrate and membrane
22d2db09-b7ce-4b14-a1da-862be61edcec | checkpoint | Enviroclad application to manufactures specs
bda41a4b-96d4-43ac-ad07-6dde550cd834 | checkpoint | Laps heat wielded
f6256d36-d097-4da7-bb63-8b770b6f2a1d | checkpoint | Corners detailed
3d6f07f1-b554-4699-acbd-5daad17776be | checkpoint | Marked up drawing for area of work
ebbf4570-3b98-4dce-9516-39b9ad978444 | checklist | Perimeter Terminations |  | Perimeter Terminations
3d1c4512-dc45-4ce4-973d-4fa915499d4c | section | Details
6bd4fd19-b607-43f8-91b5-dfd20f586886 | checkpoint | Substrate acceptable
ee25fe6c-b9b3-4ec0-8186-c9140940d8bf | checkpoint | Membrane applied to downturn
7c0f5b40-2a19-55e8-b229-6e57ba4aff68 | note | Photo required
d4644fa7-31ea-4b8b-b1a0-a323ee84c52d | checkpoint | Termination bar/ drip edge applied
f788b9a0-99fd-5a3e-85a6-fb4b97201c60 | note | Photo required
e92af795-b34d-42d2-bf8f-b6fda57b9e63 | checklist | Protection board installation |  | Protection board installation
7e853b3d-a527-4c2a-85c1-6f66d21ff005 | section | Details
4bdf04c9-ba22-4715-9cb3-d217698e0d0d | checkpoint | Surface clean and free from debris
963df5d2-8980-4173-9abf-8671f4ca6ea4 | checkpoint | Protection board laid
842155fb-f827-4079-be3c-1a8b12905e51 | checkpoint | Penetrations and laps sealed
439a64f6-bad5-42ad-8c16-6ddfa7a12d64 | checklist | Threaded rod penetrations |  | Threaded rod penetrations
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
231f12f5-d7e0-45a5-bf57-a79c57c981af | checkpoint | Clean surface with Membrane cleaner
c0695052-7420-4f17-a037-19901b135864 | checkpoint | Fix PVC to substrate with sealant
497c4728-61a4-4b0f-8a28-aec91df573e7 | checkpoint | Apply membrane to PVC
f92947c8-4147-42ce-9f8c-9bb4c72e0f2c | checkpoint | Prime interior of PVC
184afe99-d21c-44d5-8dec-8ebd6415bfca | checkpoint | Pour in Viking pourable sealant