## Sheet1
1.01 | CWP |  | Document Review | Prior to personal starting |  | Ensure all crew members are briefed on the CWP | H |  |  | Signed off CWP | 1.01 - CWP | Specifications and Standards - | Method/Description - Document Review | Test frequency - Prior to personal starting | Conformance Criteria - Ensure all crew members are briefed on the CWP | Constructor - H | Designer - | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP | 1.01 - CWP
1.02 | IFC's specification | MMA-GES-GEO-E1-SPC-3859 MMA-DES-GEO-E1-SPC-8804 | Document Review | Prior to works commencing |  | Obtain copy of the earthworks specifications | H | H |  | IFC Technical Specifications | 1.02 - IFC's specification | Specifications and Standards - MMA-GES-GEO-E1-SPC-3859 MMA-DES-GEO-E1-SPC-8804 | Method/Description - Document Review | Test frequency - Prior to works commencing | Conformance Criteria - Obtain copy of the earthworks specifications | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - IFC Technical Specifications | Specifications and Standards -
1.03 | IFC drawings | IFC drawings | Document Review | Prior to works commencing |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB | H | H |  | IFC Drawings upload into InEight | 1.03 - IFC drawings | Specifications and Standards - IFC drawings | Method/Description - Document Review | Test frequency - Prior to works commencing | Conformance Criteria - Ensure all drawings are approved and of the latest revision, or written approval from PAB | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings upload into InEight | Method/Description - Document Review
1.04 | Approved earthworks model |  | Document Review | Every new Earthworks Model and prior to work commencing |  | Designer to confirm and approve models to be loaded on the equipment | H | H |  | Earthworks model approval | 1.04 - Approved earthworks model | Specifications and Standards - | Method/Description - Document Review | Test frequency - Every new Earthworks Model and prior to work commencing | Conformance Criteria - Designer to confirm and approve models to be loaded on the equipment | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Earthworks model approval | Test frequency - Prior to personal starting
1.05 | Approval of stockpile location | MMA-DES-GEO-E1-SPC-3859 | Document Review CHAR(AMP) Approval | Prior to works commencing |  | Approved stockpile location | H | H |  | RFI of Approval of stockpile location | 1.05 - Approval of stockpile location | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 | Method/Description - Document Review CHAR(AMP) Approval | Test frequency - Prior to works commencing | Conformance Criteria - Approved stockpile location | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - RFI of Approval of stockpile location | Conformance Criteria - Ensure all crew members are briefed on the CWP
2.01 | Determination of the dry density/water content relationship (Heavy Compaction) for Structural Fill Material | MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2 | NZS 4402:1986, Test 4.1.2 | 1 Per 2,500m3 (Structural Fill) |  | N/A | H | R | I | MDD Test Report | 2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural Fill Material | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2 | Method/Description - NZS 4402:1986, Test 4.1.2 | Test frequency - 1 Per 2,500m3 (Structural Fill) | Conformance Criteria - N/A | Constructor - H | Designer - R | Client - | Lab - I | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report | Constructor - H
2.02 | Atterberg limits test for Structural Fill Material | MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2 | NZS 4402:1986, Test 2.2, 2.3 CHAR(AMP) 2.4 | 1 Per 2,500m3 (Structural Fill) |  | Liquid Limit less than 50% | H | R | I | Test Report | 2.02 - Atterberg limits test for Structural Fill Material | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2 | Method/Description - NZS 4402:1986, Test 2.2, 2.3 CHAR(AMP) 2.4 | Test frequency - 1 Per 2,500m3 (Structural Fill) | Conformance Criteria - Liquid Limit less than 50% | Constructor - H | Designer - R | Client - | Lab - I | Verifying Records Checklists, Test and Supplier Certificates - Test Report | Designer -
2.03 | Subsoil Drainage Backfill | MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2 | NZS 4402:1986, Test 2.8 | Source Approval 3 no. tests + 1 test per 500m3 |  | Crushing Resistance - CHAR(LESS)10% fines passing 2.36mm | H | R |  | Material Compliance Certificate | 2.03 - Subsoil Drainage Backfill | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2 | Method/Description - NZS 4402:1986, Test 2.8 | Test frequency - Source Approval 3 no. tests + 1 test per 500m3 | Conformance Criteria - Crushing Resistance - CHAR(LESS)10% fines passing 2.36mm | Constructor - H | Designer - R | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate | Client -
2.04 | Subsoil Drainage Backfill | MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2 | Constant Head Permeability of Aggregate: LAP2 | Source Approval 3 no. tests |  | Permeability - >/= 1x10^-4 m/s | H | R |  | Material Compliance Certificate | 2.04 - Subsoil Drainage Backfill | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2 | Method/Description - Constant Head Permeability of Aggregate: LAP2 | Test frequency - Source Approval 3 no. tests | Conformance Criteria - Permeability - >/= 1x10^-4 m/s | Constructor - H | Designer - R | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate | Lab -
2.05 | High Strength Geo Grid | MMA-DES-GEO-E1-SPC-3859 Clause 4.17 | Designer Approval | Once Prior to commence |  | Use the Specific high strength Geotextiles as per IFC Drawings, RFI to be submitted to designers for use of alternative | H | R |  | Material Compliance Certificate | 2.05 - High Strength Geo Grid | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 4.17 | Method/Description - Designer Approval | Test frequency - Once Prior to commence | Conformance Criteria - Use the Specific high strength Geotextiles as per IFC Drawings, RFI to be submitted to designers for use of alternative | Constructor - H | Designer - R | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
2.06 | Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 CHAR(AMP) 7.2 | NZS 4402:1986, Test 4.1.2 | Source approval 3 no. tests |  | Report Only | H | R | I | MDD Test Report | 2.06 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 CHAR(AMP) 7.2 | Method/Description - NZS 4402:1986, Test 4.1.2 | Test frequency - Source approval 3 no. tests | Conformance Criteria - Report Only | Constructor - H | Designer - R | Client - | Lab - I | Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report | 1.02 - IFC's specification
2.07 | Particle size distribution (PSD) Test for GAP 65 material | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 CHAR(AMP) 7.2 | NZS 4402:1986, Test 2.8 | Source approval 3 no. tests then every 2000m3. |  |  | H | H | I | PSD Test Report | 2.07 - Particle size distribution (PSD) Test for GAP 65 material | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 CHAR(AMP) 7.2 | Method/Description - NZS 4402:1986, Test 2.8 | Test frequency - Source approval 3 no. tests then every 2000m3. | Conformance Criteria - | Constructor - H | Designer - H | Client - | Lab - I | Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report | Specifications and Standards - MMA-GES-GEO-E1-SPC-3859 MMA-DES-GEO-E1-SPC-8804
2.08 | Permeability test for GAP 65 material | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 CHAR(AMP) 7.2 | ASTM D5084 - 16a | Source approval 3 no. tests |  | > 5x10-5 m/s | H | H | I | Permeability Test Report | 2.08 - Permeability test for GAP 65 material | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 CHAR(AMP) 7.2 | Method/Description - ASTM D5084 - 16a | Test frequency - Source approval 3 no. tests | Conformance Criteria - > 5x10-5 m/s | Constructor - H | Designer - H | Client - | Lab - I | Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report | Method/Description - Document Review
2.09 | Visual inspection - separation geotextiles, basal reinforcement | MMA-DES-GEO-E1-SPC-3859 | To inspect geotextile and basal reinforcement is the proper type and no tears, rips or other signs of deterioration. | Check each lot (1 roll) |  | Report Only | H | H |  | Material Delivery Inspection Checklist | 2.09 - Visual inspection - separation geotextiles, basal reinforcement | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 | Method/Description - To inspect geotextile and basal reinforcement is the proper type and no tears, rips or other signs of deterioration. | Test frequency - Check each lot (1 roll) | Conformance Criteria - Report Only | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Material Delivery Inspection Checklist | Test frequency - Prior to works commencing
3.1.1 | Set out extents of fill and check against design |  | Survey/visual | Prior to Commencement |  | Consistency with Construction Drawings | W |  |  |  | 3.1.1 - Set out extents of fill and check against design | Specifications and Standards - | Method/Description - Survey/visual | Test frequency - Prior to Commencement | Conformance Criteria - Consistency with Construction Drawings | Constructor - W | Designer - | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - | Conformance Criteria - Obtain copy of the earthworks specifications
3.1.2 | Ensure GPS plant have the correct model set up in machine and that a datum is available for checking |  | Survey/visual | Prior to Commencement |  | Consistency with Construction Drawings | W |  |  |  | 3.1.2 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking | Specifications and Standards - | Method/Description - Survey/visual | Test frequency - Prior to Commencement | Conformance Criteria - Consistency with Construction Drawings | Constructor - W | Designer - | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - | Constructor - H
3.1.3 | Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots. | MMA-DES-GEO-E1-SPC-3859 Clause 6.3 | Survey/visual | Immediately prior to earthworks beginning in all Fill areas |  | Construction team shall coordinate with the Designer ahead of and during clearing and stripping operations to determine the stripping depth. | H | H |  | Daily Site Report by Design Site Representative | 3.1.3 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots. | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 6.3 | Method/Description - Survey/visual | Test frequency - Immediately prior to earthworks beginning in all Fill areas | Conformance Criteria - Construction team shall coordinate with the Designer ahead of and during clearing and stripping operations to determine the stripping depth. | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative | Designer - H
3.1.4 | Designer witness of in-situ subgrade prior to filling | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 | Inspection | 100% subgrade inspection |  | Before fill is placed in any area, the Constructor shall notify the Designer that the fill foundation has been stripped and drained, and is ready for the Designer’s inspection and approval. | H | H |  | Daily Site Report by Design Site Representative | 3.1.4 - Designer witness of in-situ subgrade prior to filling | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.2 | Method/Description - Inspection | Test frequency - 100% subgrade inspection | Conformance Criteria - Before fill is placed in any area, the Constructor shall notify the Designer that the fill foundation has been stripped and drained, and is ready for the Designer’s inspection and approval. | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative | Client -
3.1.5 | MSE Wall Undercut Inspection | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 | Visual inspection | 100% of works area |  | • Where shown on the drawings. • The Designer will specify the depth of the undercut in materials. • The Constructor shall treat any excavated undercut material as landscape fill or unsuitable. Inspection to cover the benching into the exisiting ground around the undercut. | H | H |  | Daily Site Report by Design Site Representative | 3.1.5 - MSE Wall Undercut Inspection | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 | Method/Description - Visual inspection | Test frequency - 100% of works area | Conformance Criteria - • Where shown on the drawings. • The Designer will specify the depth of the undercut in materials. • The Constructor shall treat any excavated undercut material as landscape fill or unsuitable. Inspection to cover the benching into the exisiting ground around the undercut. | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative | Lab -
3.2.1 | Basal reinforcement installation | IFC drawings and MMA-DES-GEO-E1-SPC-3859 | Visual inspection of directional placement, panel length, laps, and damage | During basal reinforcement installation and every 100m² of geotextile installed. |  | Ensure geogrid used is the correct type, undamaged, and directional placement, tensioning, laps, and spacing are correct | H | H |  | Geotextile Installation Checksheet | 3.2.1 - Basal reinforcement installation | Specifications and Standards - IFC drawings and MMA-DES-GEO-E1-SPC-3859 | Method/Description - Visual inspection of directional placement, panel length, laps, and damage | Test frequency - During basal reinforcement installation and every 100m² of geotextile installed. | Conformance Criteria - Ensure geogrid used is the correct type, undamaged, and directional placement, tensioning, laps, and spacing are correct | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Geotextile Installation Checksheet | Verifying Records Checklists, Test and Supplier Certificates - IFC Technical Specifications
3.2.2 | Subsoil Drainage Backfill | MMA-DES-GEO-E1-SPC-3859 Section 9 | Visual inspection | Prior to Backfilling |  | Subsoils drains to be checked that they are being installed as per the earthworks specification and drawings | H | H |  | Subsoil Installation Checklist | 3.2.2 - Subsoil Drainage Backfill | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Section 9 | Method/Description - Visual inspection | Test frequency - Prior to Backfilling | Conformance Criteria - Subsoils drains to be checked that they are being installed as per the earthworks specification and drawings | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Installation Checklist | 1.03 - IFC drawings
3.2.7 | insitu fill testing-Plateau Test | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 | Plateau Test | Structural Fill - 1 test per material type per fill MSE Fill - 1 test per material type per fill |  | Reviewed by designer | W | R | I | Test report | 3.2.7 - insitu fill testing-Plateau Test | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 | Method/Description - Plateau Test | Test frequency - Structural Fill - 1 test per material type per fill MSE Fill - 1 test per material type per fill | Conformance Criteria - Reviewed by designer | Constructor - W | Designer - R | Client - | Lab - I | Verifying Records Checklists, Test and Supplier Certificates - Test report | Specifications and Standards - IFC drawings
3.2.8 | insitu fill testing-In situ moisture content and density | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 | In situ moisture content and density | Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057 MSE Fill - 1 test per 1 m lift per 100m length GAP 65 - 4 tests per 1 m lift per 100m length |  | Structural Fill - average > 95% MDD All tests > 92%, GAP65 - Average > 98% MDD All tests > 95%, MSE Fill - Average > 95% MDD All tests > 25%, | W | R | I | Test report | 3.2.8 - insitu fill testing-In situ moisture content and density | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 | Method/Description - In situ moisture content and density | Test frequency - Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057 MSE Fill - 1 test per 1 m lift per 100m length GAP 65 - 4 tests per 1 m lift per 100m length | Conformance Criteria - Structural Fill - average > 95% MDD All tests > 92%, GAP65 - Average > 98% MDD All tests > 95%, MSE Fill - Average > 95% MDD All tests > 25%, | Constructor - W | Designer - R | Client - | Lab - I | Verifying Records Checklists, Test and Supplier Certificates - Test report | Method/Description - Document Review
3.2.9 | insitu fill testing- Strength | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 | Scala penetrometer | Scala Structural fill - 1 test per layer per 100m MSE Fill - 1 Test per layer per 100m | Structural fill - 1 test per layer per 1000m2 Average > 150kPa all tests > 120kPa Buttress Fill - 1 Test per layer per 2000m2 Average > 120kPa all tests > 80kPa Cement Stabilised Structural Fill - 1 test per layer per 500m2 Average > 150kPa all tests > 120kPa | MSE Fill - The number of blows per 100mm to drive the scala penetrometer from a depth of 100 to 1000mm below the fill surface shall not be less than 5 Structural fill - The number of blows per 100mm to drive the scala penetrometer from a depth of 100 to 1000mm below the fill surface shall not be less than 5 | W | R | I | test report | 3.2.9 - insitu fill testing- Strength | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 | Method/Description - Scala penetrometer | Test frequency - Scala Structural fill - 1 test per layer per 100m MSE Fill - 1 Test per layer per 100m | Conformance Criteria - MSE Fill - The number of blows per 100mm to drive the scala penetrometer from a depth of 100 to 1000mm below the fill surface shall not be less than 5 Structural fill - The number of blows per 100mm to drive the scala penetrometer from a depth of 100 to 1000mm below the fill surface shall not be less than 5 | Constructor - W | Designer - R | Client - | Lab - I | Verifying Records Checklists, Test and Supplier Certificates - test report | Test frequency - Prior to works commencing
4.01 | Survey As-builts |  | Survey As-built | During construction and at end |  | Ensure all features and buried items are captured. | H |  |  | CAD files | 4.01 - Survey As-builts | Specifications and Standards - | Method/Description - Survey As-built | Test frequency - During construction and at end | Conformance Criteria - Ensure all features and buried items are captured. | Constructor - H | Designer - | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - CAD files | Conformance Criteria - Ensure all drawings are approved and of the latest revision, or written approval from PAB
4.02 | As-builts |  | Red Pen Mark up | End of Construction |  | All variances captured | H | H |  | Red pen mark ups | 4.02 - As-builts | Specifications and Standards - | Method/Description - Red Pen Mark up | Test frequency - End of Construction | Conformance Criteria - All variances captured | Constructor - H | Designer - H | Client - | Lab - | Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups | Constructor - H
Designer - H
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings upload into InEight
1.04 - Approved earthworks model
Specifications and Standards -
Method/Description - Document Review
Test frequency - Every new Earthworks Model and prior to work commencing
Conformance Criteria - Designer to confirm and approve models to be loaded on the equipment
Constructor - H
Designer - H
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Earthworks model approval
1.05 - Approval of stockpile location
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859
Method/Description - Document Review CHAR(AMP) Approval
Test frequency - Prior to works commencing
Conformance Criteria - Approved stockpile location
Constructor - H
Designer - H
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - RFI of Approval of stockpile location
2.01 - Determination of the dry density/water content relationship (Heavy Compaction) for Structural Fill Material
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2
Method/Description - NZS 4402:1986, Test 4.1.2
Test frequency - 1 Per 2,500m3 (Structural Fill)
Conformance Criteria - N/A
Constructor - H
Designer - R
Client -
Lab - I
Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
2.02 - Atterberg limits test for Structural Fill Material
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2
Method/Description - NZS 4402:1986, Test 2.2, 2.3 CHAR(AMP) 2.4
Test frequency - 1 Per 2,500m3 (Structural Fill)
Conformance Criteria - Liquid Limit less than 50%
Constructor - H
Designer - R
Client -
Lab - I
Verifying Records Checklists, Test and Supplier Certificates - Test Report
2.03 - Subsoil Drainage Backfill
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2
Method/Description - NZS 4402:1986, Test 2.8
Test frequency - Source Approval 3 no. tests + 1 test per 500m3
Conformance Criteria - Crushing Resistance - CHAR(LESS)10% fines passing 2.36mm
Constructor - H
Designer - R
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
2.04 - Subsoil Drainage Backfill
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.2, 7.1 CHAR(AMP) 7.2
Method/Description - Constant Head Permeability of Aggregate: LAP2
Test frequency - Source Approval 3 no. tests
Conformance Criteria - Permeability - >/= 1x10^-4 m/s
Constructor - H
Designer - R
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
2.05 - High Strength Geo Grid
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 4.17
Method/Description - Designer Approval
Test frequency - Once Prior to commence
Conformance Criteria - Use the Specific high strength Geotextiles as per IFC Drawings, RFI to be submitted to designers for use of alternative
Constructor - H
Designer - R
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Material Compliance Certificate
2.06 - Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 CHAR(AMP) 7.2
Method/Description - NZS 4402:1986, Test 4.1.2
Test frequency - Source approval 3 no. tests
Conformance Criteria - Report Only
Constructor - H
Designer - R
Client -
Lab - I
Verifying Records Checklists, Test and Supplier Certificates - MDD Test Report
2.07 - Particle size distribution (PSD) Test for GAP 65 material
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 CHAR(AMP) 7.2
Method/Description - NZS 4402:1986, Test 2.8
Test frequency - Source approval 3 no. tests then every 2000m3.
Conformance Criteria -
Constructor - H
Designer - H
Client -
Lab - I
Verifying Records Checklists, Test and Supplier Certificates - PSD Test Report
2.08 - Permeability test for GAP 65 material
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 CHAR(AMP) 7.2
Method/Description - ASTM D5084 - 16a
Test frequency - Source approval 3 no. tests
Conformance Criteria - > 5x10-5 m/s
Constructor - H
Designer - H
Client -
Lab - I
Verifying Records Checklists, Test and Supplier Certificates - Permeability Test Report
2.09 - Visual inspection - separation geotextiles, basal reinforcement
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859
Method/Description - To inspect geotextile and basal reinforcement is the proper type and no tears, rips or other signs of deterioration.
Test frequency - Check each lot (1 roll)
Conformance Criteria - Report Only
Constructor - H
Designer - H
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Material Delivery Inspection Checklist
3.1.1 - Set out extents of fill and check against design
Specifications and Standards -
Method/Description - Survey/visual
Test frequency - Prior to Commencement
Conformance Criteria - Consistency with Construction Drawings
Constructor - W
Designer -
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates -
3.1.2 - Ensure GPS plant have the correct model set up in machine and that a datum is available for checking
Specifications and Standards -
Method/Description - Survey/visual
Test frequency - Prior to Commencement
Conformance Criteria - Consistency with Construction Drawings
Constructor - W
Designer -
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates -
3.1.3 - Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots.
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 6.3
Method/Description - Survey/visual
Test frequency - Immediately prior to earthworks beginning in all Fill areas
Conformance Criteria - Construction team shall coordinate with the Designer ahead of and during clearing and stripping operations to determine the stripping depth.
Constructor - H
Designer - H
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
3.1.4 - Designer witness of in-situ subgrade prior to filling
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.2
Method/Description - Inspection
Test frequency - 100% subgrade inspection
Conformance Criteria - Before fill is placed in any area, the Constructor shall notify the Designer that the fill foundation has been stripped and drained, and is ready for the Designer’s inspection and approval.
Constructor - H
Designer - H
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
3.1.5 - MSE Wall Undercut Inspection
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3
Method/Description - Visual inspection
Test frequency - 100% of works area
Conformance Criteria - • Where shown on the drawings. • The Designer will specify the depth of the undercut in materials. • The Constructor shall treat any excavated undercut material as landscape fill or unsuitable. Inspection to cover the benching into the exisiting ground around the undercut.
Constructor - H
Designer - H
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Daily Site Report by Design Site Representative
3.2.1 - Basal reinforcement installation
Specifications and Standards - IFC drawings and MMA-DES-GEO-E1-SPC-3859
Method/Description - Visual inspection of directional placement, panel length, laps, and damage
Test frequency - During basal reinforcement installation and every 100m² of geotextile installed.
Conformance Criteria - Ensure geogrid used is the correct type, undamaged, and directional placement, tensioning, laps, and spacing are correct
Constructor - H
Designer - H
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Geotextile Installation Checksheet
3.2.2 - Subsoil Drainage Backfill
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Section 9
Method/Description - Visual inspection
Test frequency - Prior to Backfilling
Conformance Criteria - Subsoils drains to be checked that they are being installed as per the earthworks specification and drawings
Constructor - H
Designer - H
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Subsoil Installation Checklist
3.2.7 - insitu fill testing-Plateau Test
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3
Method/Description - Plateau Test
Test frequency - Structural Fill - 1 test per material type per fill MSE Fill - 1 test per material type per fill
Conformance Criteria - Reviewed by designer
Constructor - W
Designer - R
Client -
Lab - I
Verifying Records Checklists, Test and Supplier Certificates - Test report
3.2.8 - insitu fill testing-In situ moisture content and density
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3
Method/Description - In situ moisture content and density
Test frequency - Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057 MSE Fill - 1 test per 1 m lift per 100m length GAP 65 - 4 tests per 1 m lift per 100m length
Conformance Criteria - Structural Fill - average > 95% MDD All tests > 92%, GAP65 - Average > 98% MDD All tests > 95%, MSE Fill - Average > 95% MDD All tests > 25%,
Constructor - W
Designer - R
Client -
Lab - I
Verifying Records Checklists, Test and Supplier Certificates - Test report
3.2.9 - insitu fill testing- Strength
Specifications and Standards - MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3
Method/Description - Scala penetrometer
Test frequency - Scala Structural fill - 1 test per layer per 100m MSE Fill - 1 Test per layer per 100m
Conformance Criteria - MSE Fill - The number of blows per 100mm to drive the scala penetrometer from a depth of 100 to 1000mm below the fill surface shall not be less than 5 Structural fill - The number of blows per 100mm to drive the scala penetrometer from a depth of 100 to 1000mm below the fill surface shall not be less than 5
Constructor - W
Designer - R
Client -
Lab - I
Verifying Records Checklists, Test and Supplier Certificates - test report
4.01 - Survey As-builts
Specifications and Standards -
Method/Description - Survey As-built
Test frequency - During construction and at end
Conformance Criteria - Ensure all features and buried items are captured.
Constructor - H
Designer -
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - CAD files
4.02 - As-builts
Specifications and Standards -
Method/Description - Red Pen Mark up
Test frequency - End of Construction
Conformance Criteria - All variances captured
Constructor - H
Designer - H
Client -
Lab -
Verifying Records Checklists, Test and Supplier Certificates - Red pen mark ups